## C2011
Revision Date: Dec 22, 2011 | 2011 Planned Transmission Outages
* Highlight indicates new/changed
strikethrough denotes cancellation or rescheduling | [9 empty] | Preliminary Estimates
[10 empty] | Path 3 |  |  |  | Path 1
Equipment/ Circuit OOS | Purpose | CROW # (outage tracking number) | Start Date (yyyymmdd) | Start Time | End Date (yyyymmdd) | End time | Daily or Continuous (C/D) | Resource Impact | Load Impact | ING to Custer Limit N->S (MW) | BC to US Total N->S (MW) | Custer to ING Limit S->N (MW) | US to BC Total S->N (MW) | BC to AB Limit W->E (MW) | AB to BC Limit E->W (MW)
WSN 5D27, 5D37, 5RX7 and 5L13 | Disconnect maintenance | 1-102397 | 2011-02-01 | 8:00 | 2011-02-02 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
5L31 | Insulator repair | 1-102728 | 2011-02-02 | 8:00 | 2011-02-02 | 16:00 | C | Yes
KLY 2CB34, 2RX2 | PM | 1-102198 | 2011-02-02 | 8:00 | 2011-02-04 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
KLY 5RX5 | Repair of 5GDNR5, PM and doble testing of the reactor | 1-102197 | 2011-02-07 | 8:00 | 2011-02-11 | 16:00 | C
5L4 | Remove CT secondary wiring | 1-103391 | 2011-02-10 | 8:00 | 2011-02-10 | 22:00 | C | Yes
5L29 | Insulator repair | 3-19960 | 2011-02-11 | 8:00 | 2011-02-11 | 18:00 | C | Yes
GUI 5CX1 | Inspection | 1-103626 | 2011-02-17 | 8:00 | 2011-02-17 | 16:00 | C
TKW 5RX1 | Gas Relay Fault Investigation | 1-103894 | 2011-02-18 | 8:00 | 2011-02-18 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
KLY 5RX2 | Oil Sampling for brushing | 1-102774 | 2011-02-18 | 8:00 | 2011-02-18 | 16:00 | C
SEL 5CB1 | Inspection | 4-14862 | 2011-02-21 | 8:00 | 2011-02-25 | 16:00 | C
SEL T2, SEL 5CB3 | Complete paralleling of T2 and T3, start replacement of 5CB3 | 1-102998 | 2011-02-21 | 8:00 | 2011-03-04 | 16:00 | C
5L4 | 5CC4 replacement | 1-103782 | 2011-02-24 | 8:00 | 2011-02-24 | 16:00 | C | Yes
5L4 | 5L4 PN upgrade | 1-103853 | 2011-02-24 | 8:00 | 2011-02-24 | 22:00 | C | Yes
5L52 & ING T4 | Install corona shields | 3-19765 | 2011-02-27 08:00 | 8:00 | 2011-02-27 08:00 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
5L71 | Protection Modification | 1-103905 | 2011-02-28 | 7:00 | 2011-03-07 | 0:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
5L52 & ING T4 | ING 5CB5 point on wave test | 1-99946 | 2011-02-28 08:00 | 8:00 | 2011-02-28 08:00 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
VIT 2CB14, T9 | CB replacements | 3-10540 | 2011-02-28 08:00 | 8:00 | 2011-03-18 | 16:00 | C
ING 5MB1, 5CB9, 5CB4, 5CB8 | Create TLC station side 5CB9; replace 5CB9 | 1-97825 | 2011-03-01 | 8:00 | 2011-03-03 | 16:00 | C
DMR SVC | Annual maintenance | 3-11369 | 2011-03-01 | 8:00 | 2011-03-08 | 16:00 | C
ACK 2B8, T2, 2CB9 | 2CB9 time testing | 1-102388 | 2011-03-02 | 8:00 | 2011-03-02 | 16:00 | C | Yes
ING 5B9, 5L81, 5CB9, 5CB10 | Create TLC line side 5CB9; replacement 5CB9 | 1-97824 | 2011-03-04 | 8:00 | 2011-03-06 | 16:00 | C |  |  | 1000 | 1400 | 2000 | 2000
SEL 5CB3 | Continue replacement of 5CB3 | 1-103003 | 2011-03-04 | 8:00 | 2011-03-25 | 16:00 | C
5L41 | Inspection | 4-014548 | 2011-03-07 | 8:00 | 2011-03-10 | 16:00 | C |  |  | 1700 | 2100 | 2000 | 2000
ING 5CB9 | Replace | 1-97827 | 2011-03-07 | 8:00 | 2011-05-09 | 16:00 | C
5L76 | Space Damper Inspection | 1-104631 | 2011-03-11 | 9:00 | 2011-03-011 | 16:00 | C | [6 empty] | 850 | 700
2L77 | install 4 D-Tower Deadends | 1-102782 | 2011-03-14 | 8:00 | 2011-03-27 | 16:00 | C | Yes
5L91, ACK 5B3 5D44 5RX4 | Inspection | 1-102369 | 2011-03-15 | 8:00 | 2011-03-16 | 16:00 | C | [6 empty] | 560 | 500
5L71 | Protection Modification | 1-103905 | 2011-03-15 | 7:00 | 2011-03-22 | 0:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
5L76 | Space Damper Replacement | 1-105387 | 2011-03-18 | 8:00 | 2011-03-18 | 16:00 | C | [6 empty] | 850 | 700
5L72 | MCA testing and reconfiguration | 3-21005 | 2011-03-19 | 5:00 | 2011-03-20 | 20:00 | C |  |  | 1000 | 1400 | 2000 | 2000 | 850 | 400
5L3 | Disconnect maintenance | 1-105371 | 2011-03-21 | 8:00 | 2011-03-21 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
NIC 5MB1 (5D1CB2,5D1CB3,5D1CB1) | Inspection | 1-102856 | 2011-03-21 | 8:00 | 2011-03-22 | 16:00 | C | Yes
5L92 | Replace Flex drop from SEL 5CB3 to SEL 5D2CB3 | 1-105391 | 2011-03-22 | 8:00 | 2011-03-22 | 14:00 | C | [6 empty] | 110 | 300
MSA 5RX2, 5L31 out of service for switching | Protection maintenance | 1-105535 | 2011-03-23 | 8:00 | 2011-03-23 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
NIC 5MB2 (5D1CB8,5D1CB4,5D1CB5) | Inspection | 1-102864 | 2011-03-23 | 8:00 | 2011-03-24 | 16:00 | C | Yes
5L51 | BPA request to wok on spacer replacement | 3-20444 | 2011-03-23 | 7:00 | 2011-03-26 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
ACK 5RX7 | Gas relay removal and non-electrical testing | 1-105280 | 2011-03-24 | 8:00 | 2011-03-24 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
NIC 5MB2 (5D1CB6,5D1CB7) | Inspection | 1-102865 | 2011-03-25 | 8:00 | 2011-03-26 | 16:00 | C | Yes
NIC 5MB3 (5D2CB23,5D2CB22,5D2CB21) | Inspection | 1-102873 | 2011-03-27 | 8:00 | 2011-03-28 | 16:00 | C | Yes
5L52 | BPA request to wok on spacer replacement | 3-20445 | 2011-03-27 | 7:00 | 2011-03-31 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
BRT T4 | 3D2CB6 maintenance | 1-105361 | 2011-03-28 | 10:00 | 2011-03-28 | 16:00 | C | Yes
BRT T4 | 12VTT4 replacement | 1-103717 | 2011-03-28 | 16:00 | 2011-03-30 | 11:45 | C | Yes
GMS 5CB5 | F12 Maintenance Cycle | 1-102332 | 2011-03-28 | 8:00 | 2011-04-05 | 16:00 | C
SEL 5CB4 | Replacement | 1-103005 | 2011-03-28 | 8:00 | 2011-04-29 | 16:00 | C
KLY 5RX2 | Bushing Sampling | 1-105715 | 2011-03-29 | 8:00 | 2011-03-29 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
2L19 | Structure replacements | 1-102879 | 2011-03-30 | 8:00 | 2011-03-31 | 16:00 | C
2L90 | Structure replacements | 1-102881 | 2011-04-01 | 8:00 | 2011-04-15 | 16:00 | C | Yes
NIC 5MB1 & 5MB2 & T3 (5D19) | Insp | 1-102862 | 2011-04-03 | 8:00 | 2011-04-03 | 16:00 | C | Yes
WSN 5RX3 | routine testing of auto-isolate and gas relay + non-electrical trip testing to be carried out | 1-101944 | 2011-04-04 | 8:00 | 2011-04-04 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
NIC 5CB1 | PVIN, PVRP | 1-102852 | 2011-04-04 | 8:00 | 2011-04-04 | 16:00 | C
KLY 5B7 &5L87 | 5D36 Insp | 4-014486 | 2011-04-04 | 8:00 | 2011-04-04 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
NIC 5L71, 5B14 (5DCB44,5D24) | Inspection | 4-014451 | 2011-04-04 | 8:00 | 2011-04-05 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
NIC 5L87,5B11,5CB1,5CB11 (5D22,5D1CB11,5D2CB1) | Inspection | 4-014485 | 2011-04-04 | 8:00 | 2011-04-05 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
NIC 5CB11 | Inspection | 1-102872 | 2011-04-04 | 8:00 | 2011-04-06 | 16:00 | C
ING T5 | To doble test T5 and bushing samples | 1-102566 | 2011-04-04 | 8:00 | 2011-04-07 | 16:00 | C
MLS 5CX1 | Platform and Doble work | 1-102033 | 2011-04-04 | 8:00 | 2011-04-08 | 16:00 | C
WSN 5RX3 | WSN 5RX3 | 1-102287 | 2011-04-04 | 8:00 | 2011-04-08 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
GUI 5L87, 5CX1 (5D1,5D2,5BP1) | Inspection | 4-014483 | 2011-04-04 | 8:00 | 2011-04-08 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
ALZ T2 | Insp/Doble/LTC | 1-102783 | 2011-04-04 | 8:00 | 2011-04-08 | 16:00 | C
KLY SC2 | SC2 MNRI | 4-014771 | 2011-04-04 | 8:00 | 2011-04-10 | 16:00 | C
5L71 | Replace flashed insulators | 4-014450 | 2011-04-04 | 8:00 | 2011-04-14 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
2L294 (NYL - AAL) | Replace insulators | 1-102835 | 2011-04-04 | 8:00 | 2011-04-15 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000 | 250 | 500
HVDC Pole 1 & 2 | Preventive maintenance | 1-104727 | 2011-04-04 | 8:00 | 2011-05-13 | 16:00 | C
HVDC Pole 1 & 2 | Preventive maintenance | 1-104727 | 2011-04-04 | 8:00 | 2011-05-13 | 16:00 | C
NIC PN-5CB11 | 43.15-100-4 COND | 1-102925 | 2011-04-05 | 8:00 | 2011-04-05 | 16:00 | C
GMS 5CB1 BFPN | F12 Maintenance Cycle | 1-102333 | 2011-04-06 | 8:00 | 2011-04-06 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
ACK 5RX8 | SF6 Pressure Switch Change | 1-102886 | 2011-04-06 | 8:00 | 2011-04-06 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
MSA T2 & MSA 12RX2 | Inspection and Doble test | 1-102567 | 2011-04-06 | 9:00 | 2011-04-10 | 17:00 | C |  |  | 2000 | 2400 | 2000 | 2000
NIC PN-T5 | 43.03-004-4 COLT CAL,OP,LOAD,TRIP | 4-014788 | 2011-04-08 | 8:00 | 2011-04-08 | 16:00 | C
2L253 | ACK 2CL253 INSP | 4-014874 | 2011-04-10 | 8:00 | 2011-04-10 | 16:00 | C |  | Yes
2L253 | REV 2GD1CB2 INSP | 4-014874 | 2011-04-10 | 8:00 | 2011-04-10 | 16:00 | C |  | Yes
WSN 5RX7 | routine testing of auto-isolate and gas relay + non-electrical trip testing to be carried out | 1-101945 | 2011-04-11 | 8:00 | 2011-04-11 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
KLY PN-5CB1 | 43.15-100-4 COND | 1-102914 | 2011-04-11 | 8:00 | 2011-04-11 | 16:00 | C
NIC PN-5CB14 | 43.15-015-4 COND | 4-014798 | 2011-04-11 | 8:00 | 2011-04-11 | 16:00 | C
GUI 5CX1 (5GD1&2) | Inspection | 1-102850 | 2011-04-11 | 8:00 | 2011-04-12 | 16:00 | C
ACK 5MB1, 5RX7, 5CX1 | ACK 5D1CB1 A INSP | 1-102892 | 2011-04-11 | 8:00 | 2011-04-12 | 16:00 | D |  |  | 2000 | 2400
ACK 5MB1, 5RX7, 5CX1 | ACK 5D1CB5 A INSP | 1-102892 | 2011-04-11 | 8:00 | 2011-04-12 | 16:00 | D |  |  | 2000 | 2400
ACK 5MB1, 5RX7, 5CX1 | ACK 5D1CB9 INSP | 1-102892 | 2011-04-11 | 8:00 | 2011-04-12 | 16:00 | D |  |  | 2000 | 2400
5L71 | Insulator replacements | 4-014452 | 2011-04-11 | 8:00 | 2011-04-14 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
MSA T1 & 12RX1 | Inspection and Doble test | 1-102568 | 2011-04-11 | 8:00 | 2011-04-15 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
GUI 5CX1 | MNRI | 1-102847 | 2011-04-11 | 8:00 | 2011-04-15 | 16:00 | C
KLY SC2 | SC2 Insp Hydrogen Gas Analyzer | 4-014772 | 2011-04-11 | 11:00 | 2011-04-15 | 16:00 | C
KLY PN-5CB11 | 43.15-100-4 COND | 1-102916 | 2011-04-12 | 8:00 | 2011-04-12 | 16:00 | C
NIC PN-5CB4 | 43.15-015-4 COND | 4-014792 | 2011-04-12 | 8:00 | 2011-04-12 | 16:00 | C
ALZ T3 | Insp/Doble/LTC | 1-102789 | 2011-04-12 | 8:00 | 2011-04-15 | 16:00 | C
KLY PN-5CB13 | 43.15-100-4 COND | 1-102918 | 2011-04-13 | 8:00 | 2011-04-13 | 16:00 | C
ACK 5RX4 | ACK 5CTRX4 DOBL | 1-102894 | 2011-04-13 | 8:00 | 2011-04-14 | 16:00 | C |  |  | 2000 | 2400
ACK 5RX4 | ACK 5CTRX4 INSP | 1-102894 | 2011-04-13 | 8:00 | 2011-04-14 | 16:00 | D |  |  | 2000 | 2400
ACK 5RX4 | ACK 5RX4 A DOBL | 1-102894 | 2011-04-13 | 8:00 | 2011-04-14 | 16:00 | D |  |  | 2000 | 2400
KLY PN-5CB3 | 43.15-100-4 COND | 1-102919 | 2011-04-14 | 8:00 | 2011-04-14 | 16:00 | C
5L92 and SEL T2 | 5CB3 system integration test | 2-064764 | 2011-04-14 | 21:00 | 2011-04-15 | 0:59 | C | [6 empty] | 110 | 300
NIC 5MB3 & 5MB4 & T2 (5D20) | Inspection | 1-102863 | 2011-04-17 | 8:00 | 2011-04-17 | 16:00 | C | Yes
NTL T3 | LTC overhaul | 2-65017 | 2011-04-17 | 12:00 | 2011-04-22 | 15:00 | C
KDS T1 | protection upgrade. Auto-isolate and gas relay + non-electrical trip testing to be carried out | 1-102350 | 2011-04-18 | 8:00 | 2011-04-18 | 12:00 | C
NIC PN-5CB12 | 43.15-015-4 COND | 1-102926 | 2011-04-18 | 8:00 | 2011-04-18 | 16:00 | C
NIC PN-T6 | 43.03-004-4 COLT CAL,OP,LOAD,TRIP | 4-014787 | 2011-04-18 | 8:00 | 2011-04-18 | 16:00 | C
NIC 5L82, 5B22 (5D28,5D48) | Inspection | 1-102857 | 2011-04-18 | 8:00 | 2011-04-19 | 16:00 | C |  |  | 1700 | 2100 | 2000 | 2000
NIC 5L72, 5B13 (5DCB43,5D23) | Inspection | 4-014454 | 2011-04-18 | 8:00 | 2011-04-19 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
REV 2B2, T8 | REV 2D1CB3 INSP | 4-014875 | 2011-04-18 | 8:00 | 2011-04-20 | 16:00 | C
REV 2B2, T8 | REV 2D2CB2 INSP | 4-014875 | 2011-04-18 | 8:00 | 2011-04-20 | 16:00 | C
REV 2B2, T8 | REV 2D8 INSP | 4-014875 | 2011-04-18 | 8:00 | 2011-04-20 | 16:00 | C
REV 2B2, T8 | REV 2GD1CB3 INSP | 4-014875 | 2011-04-18 | 8:00 | 2011-04-20 | 16:00 | C
REV 2B2, T8 | REV 2GD2CB2 INSP | 4-014875 | 2011-04-18 | 8:00 | 2011-04-20 | 16:00 | C
REV 2B2, T8 | REV 2GD8 INSP | 4-014875 | 2011-04-18 | 8:00 | 2011-04-20 | 16:00 | C
ACK 2B10 T3 | ACK 2D1CB11 INSP | 1-102886 | 2011-04-18 | 8:00 | 2011-04-20 | 16:00 | C
ACK 2B10 T3 | ACK 2D2CB10 INSP | 1-102886 | 2011-04-18 | 8:00 | 2011-04-20 | 16:00 | D
ACK 2B10 T3 | ACK 2D3 INSP | 1-102886 | 2011-04-18 | 8:00 | 2011-04-20 | 16:00 | D
ACK 2B10 T3 | ACK 2GD1CB11 INSP | 1-102886 | 2011-04-18 | 8:00 | 2011-04-20 | 16:00 | D
NIC T2, 2CB11, T6 | Doble Tests | 1-102869 | 2011-04-18 | 8:00 | 2011-04-21 | 8:00 | C
NIC 5RX8 | Insp, Doble Tests | 1-102875 | 2011-04-18 | 8:00 | 2011-04-21 | 16:00 | C |  |  | 2000 | 2400
PCN 5CB2 | F12 Maintenance Cycle | 1-102335 | 2011-04-18 | 8:00 | 2011-04-22 | 16:00 | C
KLY SC2 | S2-2 Insp Pneumatic isolating switch | 4-014773 | 2011-04-18 | 10:00 | 2011-04-22 | 16:00 | C
5L72 | Replace flashed insulators | 4-014453 | 2011-04-18 | 8:00 | 2011-04-28 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
2L294 (AAL - CBK) | Replace insulators | 1-102837 | 2011-04-18 | 8:00 | 2011-04-28 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000 | 250 | 500
KDS T3 | protection upgrade. Auto-isolate and gas relay + non-electrical trip testing to be carried out | 1-102351 | 2011-04-19 | 8:00 | 2011-04-19 | 12:00 | C
KLY 5RX2 | Bushing Sampling | 1-105715 | 2011-04-19 | 8:00 | 2011-04-19 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
NIC PN-5CB22 | 43.15-015-4 COND | 4-014795 | 2011-04-19 | 8:00 | 2011-04-19 | 16:00 | C
SEL T4 | Maintenace | 2-064921 | 2011-04-19 | 7:00 | 2011-04-19 | 18:00 | C
2L86 | Structure replacements | 1-102880 | 2011-04-19 | 8:00 | 2011-04-21 | 16:00 | C
KDS T4 | protection upgrade. Auto-isolate and gas relay + non-electrical trip testing to be carried out | 1-102352 | 2011-04-20 | 8:00 | 2011-04-20 | 12:00 | C
TSC 1-165 Mvar | Inspection DMR SVC | 1-102569 | 2011-04-20 | 8:00 | 2011-04-20 | 16:00 | C
5L72 | Insulator replacements | 4-014455 | 2011-04-20 | 8:00 | 2011-04-20 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
NIC PN-5CB13 | 43.15-015-4 COND | 4-014799 | 2011-04-20 | 8:00 | 2011-04-20 | 16:00 | C
NIC 5RX3 (5CB43) | Inspection | 1-102860 | 2011-04-20 | 8:00 | 2011-04-21 | 16:00 | C |  |  | 2000 | 2400
TSR 1 - 77.2 Mvar | Inspection DMR SVC | 1-102570 | 2011-04-21 | 8:00 | 2011-04-21 | 16:00 | C
NIC T2, 2CB11, T6 | 1D2CB15, 1D6 Maintenace | 1-102869 | 2011-04-21 | 8:00 | 2011-04-21 | 16:00 | C
NIC PN-5CB3 | 43.15-015-4 COND | 4-014793 | 2011-04-21 | 8:00 | 2011-04-21 | 16:00 | C
GUI PN-5CX1 | Laser Power Supply Replacement | 4-014786 | 2011-04-21 | 8:00 | 2011-04-22 | 16:00 | C
TSR 2 - 19.3 Mvar | Inspection DMR SVC | 1-102571 | 2011-04-22 | 8:00 | 2011-04-22 | 16:00 | C
2L92 | SVA 2D21 | 4-014765 | 2011-04-22 | 8:00 | 2011-04-22 | 16:00 | C
TSR 3 - 38.6 Mvar | Inspection DMR SVC | 1-102572 | 2011-04-23 | 8:00 | 2011-04-23 | 16:00 | C
NIC PN-5CB18 | 43.15-015-4 COND | 4-014796 | 2011-04-25 | 8:00 | 2011-04-25 | 16:00 | C
NIC PN-T3 | 43.03-004-4 COLT CAL,OP,LOAD,TRIP | 4-014789 | 2011-04-25 | 8:00 | 2011-04-25 | 16:00 | C
BRT 3B2 &3B3 3L14 &3L16 | 3D2CB3 Insp | 4-014522 | 2011-04-25 | 8:00 | 2011-04-25 | 16:00 | C | Yes
NIC 5L81, 5B28 (5D30,5D50) | Inspection | 4-014487 | 2011-04-25 | 8:00 | 2011-04-26 | 16:00 | C |  |  | 1700 | 2100 | 2000 | 2000
MDN 5B3, 5L45, 5CB3, 5CB4 | Create TLC line side 5CB4; replacement 5CB4 | 4-014617 | 2011-04-25 | 8:00 | 2011-04-27 | 16:00 | C | Yes
REV 2B5, T7 | REV 2D1CB1 INSP | 4-014876 | 2011-04-25 | 8:00 | 2011-04-27 | 16:00 | C
REV 2B5, T7 | REV 2D2CB3 INSP | 4-014876 | 2011-04-25 | 8:00 | 2011-04-27 | 16:00 | C
REV 2B5, T7 | REV 2D7 INSP | 4-014876 | 2011-04-25 | 8:00 | 2011-04-27 | 16:00 | C
REV 2B5, T7 | REV 2GD1CB1 INSP | 4-014876 | 2011-04-25 | 8:00 | 2011-04-27 | 16:00 | C
REV 2B5, T7 | REV 2GD2CB1 INSP | 4-014876 | 2011-04-25 | 8:00 | 2011-04-27 | 16:00 | C
REV 2B5, T7 | REV 2GD2CB3 INSP | 4-014876 | 2011-04-25 | 8:00 | 2011-04-27 | 16:00 | C
REV 2B5, T7 | REV 2GD7 INSP | 4-014876 | 2011-04-25 | 8:00 | 2011-04-27 | 16:00 | C
NTL T4 | LTC overhaul | 2-65018 | 2011-04-25 | 12:00 | 2011-04-29 | 15:00 | C
NTL T4 | LTC overhaul | 2-06018 | 2011-04-25 | 12:00 | 2011-04-29 | 15:00 | C
NIC PN-5CB28 | 43.15-015-4 COND | 4-014794 | 2011-04-26 | 8:00 | 2011-04-26 | 16:00 | C
NIC T3 | Inspection | 1-102874 | 2011-04-26 | 8:00 | 2011-04-29 | 16:00 | C
MLS 5CX2 | routine testing | 1-101942 | 2011-04-26 | 8:00 | 2011-05-06 | 16:00 | C
MLS 5CX2 | Platform and Doble work. | 1-102039 | 2011-04-26 | 8:00 | 2011-05-06 | 16:00 | C
MLS 5CX2 | routine testing | 1-101942 | 2011-04-26 | 8:00 | 2011-05-06 | 16:00 | C
MLS 5CX2 | Platform and Doble work. | 1-102039 | 2011-04-26 | 8:00 | 2011-05-06 | 16:00 | C
KLY SC2 | major maintenance | 2-065252 | 2011-04-26 | 16:00 | 2011-06-30 | 16:00 | C
KLY SC2 | major maintenance | 2-065252 | 2011-04-26 | 16:00 | 2011-06-30 | 16:00 | C
KLY SC2 | major maintenance | 2-065252 | 2011-04-26 | 16:00 | 2011-06-30 | 16:00 | C
CKY5CT3 (D) | 5CB3 | 4-014618 | 2011-04-27 | 8:00 | 2011-04-27 | 16:00 | C
CHP 5CX1 | Major Inspection | 4-014602 | 2011-04-28 | 8:00 | 2011-05-03 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
GLN T11 | GLN T11 replacement | 1-102997 | 2011-04-28 | 9:00 | 2011-05-09 | 17:00 | C
5L71, MCA 5MB2 | MCA GIS upgrade | 2-065442 | 2011-05-01 | 12:30 | 2011-05-12 | 21:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
TKW T2 SYPN | T2 | 1-102988 | 2011-05-02 | 8:00 | 2011-05-02 | 14:00 | C
DC1L2 | Replace broken insulators | 4-014603 | 2011-05-02 | 8:00 | 2011-05-02 | 16:00 | C
NIC 5CB15 | PVIN, PVRP | 1-102853 | 2011-05-02 | 8:00 | 2011-05-02 | 16:00 | C
TKW T4 SYPN | T4 | 1-102989 | 2011-05-02 | 14:00 | 2011-05-02 | 20:00 | C
2L86 | Structure replacements | 1-102880 | 2011-05-02 | 8:00 | 2011-05-04 | 16:00 | C
2L294 (AAL Tap) | Replace structure 43/9 | 1-102841 | 2011-05-02 | 8:00 | 2011-05-04 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000 | 250 | 500
ACK 2B10 T3 | ACK 2D1CB11 INSP | 1-102886 | 2011-05-02 | 8:00 | 2011-05-04 | 16:00 | C | Yes
ACK 2B10 T3 | ACK 2D2CB10 INSP | 1-102886 | 2011-05-02 | 8:00 | 2011-05-04 | 16:00 | D
ACK 2B10 T3 | ACK 2D3 INSP | 1-102886 | 2011-05-02 | 8:00 | 2011-05-04 | 16:00 | D
ACK 2B10 T3 | ACK 2GD1CB11 INSP | 1-102886 | 2011-05-02 | 8:00 | 2011-05-04 | 16:00 | D
ACK 2B10 T3 | ACK 2GD2CB10 INSP | 1-102886 | 2011-05-02 | 8:00 | 2011-05-04 | 16:00 | D
2L45 | to install new GIS breaker 2CB6 at SPG - to make up the bus cut and restore 2B5 | 1-102784 | 2011-05-02 | 8:00 | 2011-05-04 | 16:00 | C
PCN 5CB1 | F12 Maintenance Cycle | 1-102334 | 2011-05-02 | 8:00 | 2011-05-06 | 16:00 | C
5L41 | Insulator/marker ball replacements | 4-014523 | 2011-05-02 | 8:00 | 2011-05-06 | 16:00 | C |  |  | 1700 | 2100 | 2000 | 2000
WSN 5RX3 | Inspection | 1-102287 | 2011-05-02 | 9:00 | 2011-05-06 | 17:00 | C |  |  | 2000 | 2400 | 2000 | 2000
2L94 | Poles, Timbers and Insul. | 2-064683 | 2011-05-02 | 9:00 | 2011-05-12 | 19:00 | C
Pole 1 & 2 | Insulator washing | 4-014604 | 2011-05-02 | 8:00 | 2011-05-13 | 16:00 | C
SKA T1 | SKA Transformer Protection upgrade | 1-102990 | 2011-05-02 | 8:00 | 2011-05-15 | 16:00 | C | Yes
SEL 5CB8 | Replacement | 4-014821 | 2011-05-02 | 8:00 | 2011-06-24 | 16:00 | C
SEL 5CB9 | Replacement | 4-014821 | 2011-05-02 | 8:00 | 2011-06-24 | 16:00 | C
TKW 12RX3 SYPN | 12RX3 | 1-102986 | 2011-05-03 | 8:00 | 2011-05-03 | 14:00 | C
NIC 5CB15 | Inspection | 1-102868 | 2011-05-03 | 8:00 | 2011-05-03 | 16:00 | C
5L41, CBN 5D21 | Disconnect inspection | 4-014606 | 2011-05-04 | 8:00 | 2011-05-04 | 16:00 | C |  |  | 1700 | 2100 | 2000 | 2000
5L41, CBN 5D1CB8 | Disconnect inspection | 4-014601 | 2011-05-05 | 8:00 | 2011-05-05 | 16:00 | C |  |  | 1700 | 2100 | 2000 | 2000
5L41, CBN 5D2CB1 | Disconnect inspection | 4-014608 | 2011-05-06 | 8:00 | 2011-05-06 | 16:00 | C |  |  | 1700 | 2100 | 2000 | 2000
ACK 2B8 T2 | ACK 2D1CB9 INSP | 1-102887 | 2011-05-09 | 8:00 | 2011-05-11 | 16:00 | C | Yes
ACK 2B8 T2 | ACK 2D2 INSP | 1-102887 | 2011-05-09 | 8:00 | 2011-05-11 | 16:00 | D
ACK 2B8 T2 | ACK 2D2CB8 INSP | 1-102887 | 2011-05-09 | 8:00 | 2011-05-11 | 16:00 | D
ACK 2B8 T2 | ACK 2GD1CB9 INSP | 1-102887 | 2011-05-09 | 8:00 | 2011-05-11 | 16:00 | D
ACK 2B8 T2 | ACK 2GD2 INSP | 1-102887 | 2011-05-09 | 8:00 | 2011-05-11 | 16:00 | D
ACK 2B8 T2 | ACK 2GD2CB8 INSP | 1-102887 | 2011-05-09 | 8:00 | 2011-05-11 | 16:00 | D
ACK 2B8 T2 | ACK 2GD3 INSP | 1-102887 | 2011-05-09 | 8:00 | 2011-05-11 | 16:00 | D
ACK 2B8 T2 | ACK 2GDB10 INSP | 1-102887 | 2011-05-09 | 8:00 | 2011-05-11 | 16:00 | D
ACK 2B8 T2 | ACK 2GDB8 INSP | 1-102887 | 2011-05-09 | 8:00 | 2011-05-11 | 16:00 | D
ING 2CX2, 2RX2 | For 2CX2, 2D26, 2D30 Inspections | 1-102594 | 2011-05-09 | 8:00 | 2011-05-12 | 16:00 | C
CKY5D2CB21,22,23 (I) |  | 1-102746 | 2011-05-09 | 8:00 | 2011-05-011 | 16:00 | C
5L81, ING 5B9, 5CB9,5CB10 | Restore TLC line side 5CB9 | 1-97828 | 2011-05-10 | 8:00 | 2011-05-12 | 16:00 | C |  |  | 1000 | 1400 | 2000 | 2000
ACK T2, ACK 2B8 | Inspection | 4-014758 | 2011-05-10 | 8:00 | 2011-05-12 | 16:00 | C
5L81 | Insulator replacements | 4-014488 | 2011-05-10 | 8:00 | 2011-05-12 | 16:00 | C |  |  | 1000 | 1400 | 2000 | 2000
AMC 5CX1 | Elec and CPC insp's | 4-014594 | 2011-05-10 | 8:00 | 2011-05-14 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
GLN T11 | GLN T11 replacement | 1-102997 | 2011-05-10 | 9:00 | 2011-05-20 | 17:00 | C
KDS 5CB1 | trip test breaker and all associated protections | 1-102348 | 2011-05-11 | 8:00 | 2011-05-11 | 9:00 | C
KDS 5CB3 | trip test breaker and all associated protections | 1-102349 | 2011-05-11 | 10:00 | 2011-05-11 | 11:00 | C
WSN 5RX6 | WSN 5RX6 | 1-102289 | 2011-05-11 | 8:00 | 2011-05-13 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
5L71, 5L72 | MCA plant outage | 2-065446 | 2011-05-12 | 20:30 | 2011-05-15 | 21:00 | C | Yes | Yes | 2000 | 2400 | 2000 | 2000
5L72 | MCA GIS upgrade | 2-065914 | 2011-05-12 | 21:00 | 2011-07-31 | 8:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
5L72 | MCA GIS upgrade | 2-065914 | 2011-05-12 | 21:00 | 2011-07-31 | 8:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
5L72 | MCA GIS upgrade | 2-065914 | 2011-05-12 | 21:00 | 2011-08-05 | 0:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
5L72 | MCA GIS upgrade | 2-065914 | 2011-05-12 | 21:00 | 2011-08-05 | 0:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
5L72 | MCA GIS upgrade | 2-065914 | 2011-05-12 | 21:00 | 2011-09-23 | 8:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
WSN 5CB36 (5RX6) | trip test breaker and all associated protections | 1-102776 | 2011-05-13 | 9:00 | 2011-05-13 | 10:00 | C
ING 5MB1, 5CB4,5CB8,5CB9 | Restore TLC station side 5CB9 | 1-97831 | 2011-05-13 | 4:30 | 2011-05-16 | 21:00 | C
ING 2CX11, 2RX1 | For 2CX11, 2D22, 2D24 Inspections | 1-102595 | 2011-05-13 | 8:00 | 2011-05-17 | 16:00 | D
MLS 5CX3 | Majors on bank. | 1-105573 | 2011-05-13 | 8:00 | 2011-05-31 | 16:00 | C
2L240 | ACK 2CL240 INSP | 1-102882 | 2011-05-16 | 8:00 | 2011-05-16 | 16:00 | D
ACK 2MB2 | ACK 2D1CB8 INSP | 1-102889 | 2011-05-16 | 8:00 | 2011-05-18 | 16:00 | C
ACK 2MB2 | ACK 2D24 INSP | 1-102889 | 2011-05-16 | 8:00 | 2011-05-18 | 16:00 | D
ACK 2MB2 | ACK 2D2CB14 INSP | 1-102889 | 2011-05-16 | 8:00 | 2011-05-18 | 16:00 | D
ACK 2MB2 | ACK 2GD1CB8 INSP | 1-102889 | 2011-05-16 | 8:00 | 2011-05-18 | 16:00 | D
ACK 2MB2 | ACK 2GD1MB2 INSP | 1-102889 | 2011-05-16 | 8:00 | 2011-05-18 | 16:00 | D
ACK 2MB2 | ACK 2GD2CB14 INSP | 1-102889 | 2011-05-16 | 8:00 | 2011-05-18 | 16:00 | D
ACK 2MB2 | ACK 2GD3MB2 INSP | 1-102889 | 2011-05-16 | 8:00 | 2011-05-18 | 16:00 | D
ALZ 2L78/2B2/2B3/T4/T3 | Inspection | 1-102787 | 2011-05-16 | 8:00 | 2011-05-18 | 16:00 | C | Yes
PCN 5CB5 | F12 Maintenance Cycle | 1-102336 | 2011-05-16 | 8:00 | 2011-05-20 | 16:00 | C
2L293 | Replace structures | 1-102834 | 2011-05-16 | 8:00 | 2011-05-20 | 16:00 | C | Yes | [5 empty] | 560 | 600
KDY 5CX2 | routine testing | 2-064595 | 2011-05-16 | 8:00 | 2011-05-27 | 16:00 | C
2L95 | Poles, Timbers and Insul. | 2-065002 | 2011-05-16 | 9:00 | 2011-05-27 | 16:00 | C
SKA T2 | SKA Transformer Protection upgrade | 1-102991 | 2011-05-16 | 8:00 | 2011-05-27 | 16:00 | C | Yes
5L81 | Point on wave test | 2-64484 | 2011-05-17 | 8:00 | 2011-05-17 | 16:00 | C |  |  | 1000 | 1400 | 2000 | 2000
CKY5D1CB1,2,3 (I) | 5MB1 | 1-102596 | 2011-05-17 | 8:00 | 2011-05-19 | 16:00 | C
KI2 12RX1 | PN maintenance | 1-102599 | 2011-05-18 | 8:00 | 2011-05-18 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
MDN 2B14,2CX1,2XC2,2RX1 | MDN 2CX1, 2D11, 2D12 INSP, MDN 2RX1 DOBLE | 1-102600 | 2011-05-18 | 8:00 | 2011-05-19 | 16:00 | C
ING T2, ING 2B6 |  | 1-102598 | 2011-05-18 | 8:00 | 2011-05-22 | 16:00 | C
5L51, ING T4, ING 5CB3, ING 5MB2 | To complete warrantee work 5CB3 (painting, rupture discs replacement) | 3-19353 | 2011-05-18 | 4:30 | 2011-05-23 | 21:00 | C |  |  | 1400 | 1800 | 1400 | 1800
KI2 12RX3 | For 12CB3 Inspection and doble | 1-102601 | 2011-05-19 | 8:00 | 2011-05-20 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
KI2 12RX3, T3 | PN maintenance | 1-102602 | 2011-05-19 | 8:00 | 2011-05-20 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
ACK 5RX4 | ACK 5CTRX4 DOBL | 1-102894 | 2011-05-19 | 8:00 | 2011-05-20 | 16:00 | C |  |  | 2000 | 2400
ACK 5RX4 | ACK 5CTRX4 INSP | 1-102894 | 2011-05-19 | 8:00 | 2011-05-20 | 16:00 | D |  |  | 2000 | 2400
ACK 5RX4 | ACK 5RX4 A DOBL | 1-102894 | 2011-05-19 | 8:00 | 2011-05-20 | 16:00 | D |  |  | 2000 | 2400
ALZ T3 | Insp/Doble/LTC | 1-102789 | 2011-05-19 | 8:00 | 2011-05-21 | 16:00 | C
ACK 5CB8 | ACK 5CT8 A DOBL | 1-102891 | 2011-05-23 | 8:00 | 2011-05-25 | 16:00 | C
ACK 5CB8 | ACK 5CT8 A INSP | 1-102891 | 2011-05-23 | 8:00 | 2011-05-25 | 16:00 | D
PCN 5CB3 | F12 Maintenance Cycle | 1-102337 | 2011-05-23 | 8:00 | 2011-05-27 | 16:00 | C
ING 5CB6 | Replace | 1-97837 | 2011-05-23 | 8:00 | 2011-07-28 | 16:00 | C
ING 5CB6 | Replace | 1-97837 | 2011-05-23 | 8:00 | 2011-09-22 | 16:00 | C
ACK 5MB1, 5RX7, 5CX1 | ACK 5D1CB1 A INSP | 1-102892 | 2011-05-24 | 8:00 | 2011-05-25 | 16:00 | D |  |  | 2000 | 2400 | 2000 | 2000
ACK 5MB1, 5RX7, 5CX1 | ACK 5D1CB5 A INSP | 1-102892 | 2011-05-24 | 8:00 | 2011-05-25 | 16:00 | D |  |  | 2000 | 2400 | 2000 | 2000
ACK 5MB1, 5RX7, 5CX1 | ACK 5D1CB9 INSP | 1-102892 | 2011-05-24 | 8:00 | 2011-05-25 | 16:00 | D |  |  | 2000 | 2400 | 2000 | 2000
5L52, ING 5B5,5CB5,5CB6 | Create TLC line side 5CB6; replacement 5CB6 | 1-97832 | 2011-05-24 | 4:30 | 2011-05-26 | 21:00 | C |  |  | 2650 | 3050 | 1500 | 1900
5L7 | WSN 5DCB36,5CC6 | 1-102282 | 2011-05-24 | 8:00 | 2011-05-30 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
ACK 2CB8 | ACK 2CB8 Inspection | 1-102888 | 2011-05-26 | 8:00 | 2011-05-27 | 16:00 | C
2L4 & 2L56 | Raising of structures 4/1 and 4/2 | 1-102788 | 2011-05-26 | 8:00 | 2011-05-29 | 16:00 | C
VNT T1 | VNT 2D1 INSP | 4-014877 | 2011-05-27 | 8:00 | 2011-05-27 | 16:00 | C
ING T2 | SYPN maintenance | 1-102597 | 2011-05-27 | 4:30 | 2011-05-29 | 21:00 | C
ING T2,5B6,5CB6,5CB7 | Create TLC Station side 5CB6; replace 5CB6 | 1-97835 | 2011-05-27 | 4:30 | 2011-05-29 | 21:00 | C
MDN 5CT3, MDN 5CB3 | MDN 5CT3 DOBLE/OIL SAMPLE | 4-014681 | 2011-05-28 | 8:00 | 2011-05-30 | 16:00 | C
5L45, MDN 5B3, 5CB3, 5CB4 | Create TLC line side 5CB4; replacement 5CB4 | 4-014617 | 2011-05-28 | 6:00 | 2011-05-30 | 20:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
MDN 5CB4 | Replace | 1-102604 | 2011-05-28 | 8:00 | 2011-08-13 | 16:00 | C
MDN 5CB4 | Replace | 1-102604 | 2011-05-28 | 8:00 | 2011-09-24 | 16:00 | C
5L92 | 5CB4 Replacement | 2-066489 | 2011-05-29 | 8:00 | 2011-05-29 | 16:00 | C | [6 empty] | 110 | 300
BPA Annual RAS Test PACI | RAS Test Pacific AC Intertie | 3-20638 | 2011-05-30 | 7:00 | 2011-03-06 | 21:00 | Time Window | Yes
PCN 5CB5 BFPN | F12 Maintenance Cycle | 1-102338 | 2011-05-30 | 8:00 | 2011-05-30 | 16:00 | C
CCB5CC21/22/23 1SS21/22/23 |  | 1-102605 | 2011-05-30 | 8:00 | 2011-05-30 | 16:00 | C
5L29 | Terminal washing | 2-66284 | 2011-05-30 | 8:00 | 2011-06-02 | 16:00 | C | Yes
5L29 | Terminal washing | 2-66284 | 2011-05-30 | 8:00 | 2011-06-02 | 16:00 | C | Yes
2L255 | ACK 2D1CB12 INSP | 1-102883 | 2011-05-30 | 8:00 | 2011-06-02 | 16:00 | C
2L255 | ACK 2D26 INSP | 1-102883 | 2011-05-30 | 8:00 | 2011-06-02 | 16:00 | D
2L255 | ACK 2D2CB11 INSP | 1-102883 | 2011-05-30 | 8:00 | 2011-06-02 | 16:00 | D
2L255 | ACK 2GD1CB12 INSP | 1-102883 | 2011-05-30 | 8:00 | 2011-06-02 | 16:00 | D
2L255 | ACK 2GD26 INSP | 1-102883 | 2011-05-30 | 8:00 | 2011-06-02 | 16:00 | D
2L255 | ACK 2GD2CB11 INSP | 1-102883 | 2011-05-30 | 8:00 | 2011-06-02 | 16:00 | D
2L255 | ACK 2GDB11 INSP | 1-102883 | 2011-05-30 | 8:00 | 2011-06-02 | 16:00 | D
2L255 | ACK 2CL255 INSP | 1-102883 | 2011-05-30 | 8:00 | 2011-06-02 | 16:00 | D
MSA5CB3 |  | 1-102606 | 2011-05-30 | 8:00 | 2011-06-03 | 16:00 | C
MSA5CB3 |  | 1-102606 | 2011-05-30 | 8:00 | 2011-06-03 | 16:00 | C
5L29 | Insulator washing | 4-014620 | 2011-05-30 | 8:00 | 2011-06-05 | 16:00 | C | Yes
2L255 | Replace decayed structures | 1-102829 | 2011-05-30 | 8:00 | 2011-06-17 | 16:00 | C
2L255 | Replace decayed structures | 1-102829 | 2011-05-30 | 8:00 | 2011-06-17 | 16:00 | C
CKY5CB21 (D,I), CKY5CT21 | 5CB21 | 4-014623 | 2011-05-30 08:00 | 8:00 | 2011-06-04 08:00 | 16:00 | C
CKY5CB21 (D,I), CKY5CT21 | 5CB21 | 4-014623 | 2011-05-30 08:00 | 8:00 | 2011-06-04 08:00 | 16:00 | C
WSN 5RX 2 | 5CB32 Control Routine Test | 2-066487 | 2011-05-31 | 9:00 | 2011-05-31 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
2L293 | Replace structures | 1-102834 | 2011-06-01 | 8:00 | 2011-06-02 | 16:00 | C | [6 empty] | 560 | 600
ING T4 | SYPN maintenance | 1-102607 | 2011-06-01 | 8:00 | 2011-06-03 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
NIC 5RX11 (5CB51) | Inspection | 1-102871 | 2011-06-01 | 8:00 | 2011-06-03 | 16:00 | D |  |  | 2000 | 2400
5L98 | Repair damaged conductor | 4-014501 | 2011-06-01 | 8:00 | 2011-06-28 | 16:00 | C | Yes |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
KDS 5L7 Gen Shed | Allow 5L7 SY PN to be connected and tested. | 1-101946 | 2011-06-02 | 8:00 | 2011-06-02 | 16:00 | C | Yes
2L19 | Structure replacements | 1-102879 | 2011-06-02 | 8:00 | 2011-06-03 | 16:00 | C
5L71, 5L72 | Closure of MCA 5D4 | 2-066933 | 2011-06-04 | 8:00 | 2011-06-04 | 10:30 | C | Yes | Yes | 2000 | 2400 | 2000 | 2000
5L29 | Replace flashed insulators / terminal washing | 2-065050 | 2011-06-05 | 8:00 | 2011-06-11 | 16:00 | C | Yes
WSN 5CB11 | trip test breaker and all associated protections | 1-102302 | 2011-06-06 | 8:00 | 2011-06-06 | 9:00 | C
WSN 5CB1 | trip test breaker and all associated protections | 1-102303 | 2011-06-06 | 9:00 | 2011-06-06 | 10:00 | C
5L29-5B14-DMR 5DCB52 | 5DCB2 5CVT3 Inspection | 4-014650 | 2011-06-06 | 8:00 | 2011-06-06 | 16:00 | C | Yes
WSN 12RX1 | routine testing of auto-isolate and gas relay + non-electrical trip testing to be carried out | 1-102316 | 2011-06-06 | 13:00 | 2011-06-06 | 17:00 | C
NIC 5MB1 (5D1CB2,5D1CB3,5D1CB1) | Inspection | 1-102856 | 2011-06-06 | 8:00 | 2011-06-07 | 16:00 | C
NIC 5L72, 5B13 (5DCB43,5D23) | Inspection | 4-014454 | 2011-06-06 | 8:00 | 2011-06-07 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
CBN T1 | Insp/Doble | 1-102637 | 2011-06-06 | 8:00 | 2011-06-09 | 16:00 | C
DMR 5RX2 | Inspection | 4-014622 | 2011-06-06 | 8:00 | 2011-06-10 | 16:00 | C
5L42 | Line Rating Restoration | 4-014824 | 2011-06-06 | 8:00 | 2011-06-17 | 16:00 | C | Yes |  | 1300 | 1700 | 2000 | 2000
2L294 (AAL-CBK) | FBC Switch Replacement | 3-021105 | 2011-06-06 | 8:00 | 2011-06-17 | 16:00 | C | [6 empty] | 400 | 500
2L294 (AAL-CBK) | Insulator replacements | 1-102837 | 2011-06-06 | 9:00 | 2011-06-17 | 17:00 | C | [6 empty] | 400 | 500
GMS RAS | Replace RAS system and controllers at GMS | 1-101787 | 2011-06-06 | 8:00 | 2011-06-30 | 16:00 |  | Yes
5L72 | Replace flashed insulators | 4-014453 | 2011-06-06 | 8:00 | 2011-09-23 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
WSN 5RX1 (5L61) | routine testing of auto-isolate and gas relay + non-electrical trip testing to be carried out | 1-101943 | 2011-06-07 | 8:00 | 2011-06-07 | 12:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
GLN STN SYNC | station synchronizer scheme | 1-102973 | 2011-06-07 | 8:00 | 2011-06-07 | 16:00 | C
5L61 | WSN 5D21,5D31,5CC1,5D2CB1,5D1CB11, *5RX1 | 1-102285 | 2011-06-07 | 8:00 | 2011-06-08 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
DMR5RX3 | Inspection | 4-014646 | 2011-06-07 | 8:00 | 2011-06-08 | 16:00 | C
5L29 | Terminal washing | 2-066285 | 2011-06-07 | 8:00 | 2011-06-09 | 16:00 | C | Yes
5L30, CKY 5D25 | 1-105667 | 1-105667 | 2011-06-07 08:00 | 8:00 | 2011-06-07 08:00 | 16:00 | C | Yes
CKY5CB31 (D) | 5RX1 | 1-102609 | 2011-06-08 | 8:00 | 2011-06-08 | 16:00 | C
5L72 | Insulator replacements | 4-014455 | 2011-06-08 | 8:00 | 2011-06-08 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
NIC 5MB2 (5D1CB8,5D1CB4,5D1CB5) | Inspection | 1-102864 | 2011-06-08 | 8:00 | 2011-06-09 | 16:00 | C
KLY 5CB5 | 5CB5 Insp | 4-014769 | 2011-06-08 | 13:00 | 2011-06-10 | 16:00 | C
TKW 5RX1 (5L63) | routine testing | 1-102136 | 2011-06-09 | 8:00 | 2011-06-09 | 12:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
CKY5CT2 (D) | 5CB2 | 1-102610 | 2011-06-09 | 8:00 | 2011-06-09 | 16:00 | C
DMR 5RX4 | Inspection | 4-014647 | 2011-06-09 | 8:00 | 2011-06-10 | 16:00 | C
DMR SVC | Replace Thyristor | 2-067169 | 2011-06-10 | 8:00 | 2011-06-10 | 16:00 | C |  |  | 2000 | 2400
5L31 | Insulator washing | 2-065053 | 2011-06-12 | 8:00 | 2011-06-17 | 16:00 | C | Yes
5L29 | Terminal washing | 2-66286 | 2011-06-13 | 8:00 | 2011-06-14 | 16:00 | C | Yes
DMR 5CB51 -5RX1 | 5CB51 Incorrect close/open indication | 4-014649 | 2011-06-13 | 8:00 | 2011-06-14 | 16:00 | C
NIC 5MB2 (5D1CB6,5D1CB7) | Inspection | 1-102865 | 2011-06-13 | 8:00 | 2011-06-14 | 16:00 | C
CRK 5CX1 | 5CX1 | 1-102611 | 2011-06-13 | 8:00 | 2011-06-17 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
2L99 | Transmission Structures | 1-102322 | 2011-06-13 | 8:00 | 2011-06-17 | 20:00 | D | Yes
2L99 | Transmission Structures | 1-102321 | 2011-06-13 | 8:00 | 2011-06-18 | 20:00 | D | Yes
MIN 2CB3 BFPN | 2CB3 | 1-102977 | 2011-06-14 | 8:00 | 2011-06-14 | 9:00 | C
2L99 | Inspection SKA 2VT1 | 1-102698 | 2011-06-14 | 8:00 | 2011-06-14 | 16:00 | C | Yes
2L99 | Inspection MIN 2CVT2 | 1-102699 | 2011-06-15 | 8:00 | 2011-06-15 | 16:00 | C | Yes
5L31 | Pothead washing | 2-066287 | 2011-06-15 | 8:00 | 2011-06-16 | 16:00 | C | Yes
NIC 5MB3 (5D2CB23,5D2CB22,5D2CB21) | Inspection | 1-102873 | 2011-06-15 | 8:00 | 2011-06-16 | 16:00 | C
KLY 5CB15 | 5CB15 Insp | 4-014770 | 2011-06-15 | 9:00 | 2011-06-17 | 16:00 | C
GLN 5D2CB2 | Inspection | 1-102353 | 2011-06-16 | 8:00 | 2011-06-17 | 16:00 | C
5L42 | Re-contouring | 2-64481 | 2011-06-17 | 8:00 | 2001-06-30 | 16:00 | C |  |  | 1300 | 1700 | 2000 | 2000
DMR SVC | Replace Thyristor | 2-067497 | 2011-06-17 | 8:00 | 2011-06-17 | 16:00 | C |  |  | 2000 | 2400
5L71, 5L72 | Disconnect Switching | 2-067122 | 2011-06-17 | 19:00 | 2011-06-17 | 19:30 | C | Yes | Yes | 2000 | 2400 | 2000 | 2000
5L71 | Re-establish Bus Cut | 2-067121 | 2011-06-17 | 19:00 | 2011-06-20 | 19:30 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
MIN STN SYNC | station synchronizer scheme | 1-102980 | 2011-06-19 | 8:00 | 2011-06-19 | 16:00 | C
GLN T4 AI | T4 | 1-102975 | 2011-06-20 | 8:00 | 2011-06-20 | 14:00 | C
5L63 | Inspection SKA 5VT2 | 1-102700 | 2011-06-20 | 8:00 | 2011-06-20 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
TKW 5RX1 (5L63) | Gas relay repairs | 1-102701 | 2011-06-20 | 8:00 | 2011-06-20 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
CCB5CC24/25/26 1SS24/25/26 | Inspection | 1-102614 | 2011-06-20 | 8:00 | 2011-06-20 | 16:00 | C
SKA STN SYNC | station synchronizer scheme | 1-102985 | 2011-06-20 | 8:00 | 2011-06-20 | 16:00 | C
5L71, 5L72 | Disconnect Switching | 2-067125 | 2011-06-20 | 19:00 | 2011-06-20 | 19:30 | C | Yes | YEs | 2000 | 2400 | 2000 | 2000
NIC 5MB4 (5D2CB25,5D2CB26,5D2CB27) | Inspection | 1-102877 | 2011-06-20 | 8:00 | 2011-06-21 | 16:00 | C
KLY 5CB17 | 5CB17 Insp | 4-014777 | 2011-06-20 | 8:00 | 2011-06-23 | 16:00 | C
GLN T2 ABC | Inspection | 1-102356 | 2011-06-20 | 8:00 | 2011-06-24 | 16:00 | C
2L256 | ACK 2D1CB10 INSP | 1-102885 | 2011-06-20 | 8:00 | 2011-06-24 | 16:00 | C
2L256 | ACK 2D25 INSP | 1-102885 | 2011-06-20 | 8:00 | 2011-06-24 | 16:00 | D
2L256 | ACK 2D2CB9 INSP | 1-102885 | 2011-06-20 | 8:00 | 2011-06-24 | 16:00 | D
2L256 | ACK 2GD1CB10 INSP | 1-102885 | 2011-06-20 | 8:00 | 2011-06-24 | 16:00 | D
2L256 | ACK 2GD25 INSP | 1-102885 | 2011-06-20 | 8:00 | 2011-06-24 | 16:00 | D
2L256 | ACK 2GD2CB9 INSP | 1-102885 | 2011-06-20 | 8:00 | 2011-06-24 | 16:00 | D
2L256 | ACK 2GDB9 INSP | 1-102885 | 2011-06-20 | 8:00 | 2011-06-24 | 16:00 | D
2L256 | ACK 2CL256 INSP | 1-102885 | 2011-06-20 | 8:00 | 2011-06-24 | 16:00 | D
2L256 | VNT 2D21 INSP | 1-102885 | 2011-06-20 | 8:00 | 2011-06-24 | 16:00 | D
2L256 | Replace decayed structures | 1-102830 | 2011-06-20 | 8:00 | 2011-07-08 | 16:00 | C
2L256 | Replace decayed structures | 1-102830 | 2011-06-20 | 8:00 | 2011-07-08 | 16:00 | C
CKY5CT23 (D) | 5CB23 | 1-102615 | 2011-06-20 08:00 | 8:00 | 2011-06-20 08:00 | 16:00 | C
CKY5CB23 (D,I) | 5CB23 | 4-014651 | 2011-06-20 08:00 | 8:00 | 2011-06-23 17:00 | 16:00 | C
2L294 | Switching | 3-021106 | 2011-06-21 | 8:00 | 2011-06-21 | 9:00 | C | [6 empty] | 100 | 500
SKA T2 | Maintenance | 2-064368 | 2011-06-21 | 9:00 | 2011-06-30 | 16:00 | C
2L294 (NLY-AAL) | FBC Switch Replacement | 3-021106 | 2011-06-21 | 8:00 | 2011-07-01 | 16:00 | C | [6 empty] | 350 | 500
2L294 (NLY-AAL) | Insulator replacements | 1-102835 | 2011-06-21 | 8:00 | 2011-07-01 | 16:00 | C | [6 empty] | 350 | 500
2L294 (NLY-AAL) | FBC Switch Replacement | 3-021106 | 2011-06-21 | 8:00 | 2011-07-01 | 16:00 | C | [6 empty] | 350 | 500
2L294 (NLY-AAL) | Insulator replacements | 1-102835 | 2011-06-21 | 8:00 | 2011-07-01 | 16:00 | C | [6 empty] | 350 | 500
5L31 | Pothead washing | 2-066288 | 2011-06-22 | 8:00 | 2011-06-23 | 16:00 | C | Yes
NIC 5MB4 (5D2CB24,5D2CB28) | Inspection | 1-102878 | 2011-06-22 | 8:00 | 2011-06-23 | 16:00 | C
DMR 5RX6 | Inspection | 1-102618 | 2011-06-23 | 8:00 | 2011-06-25 | 16:00 | C
KLY 5CB17 | 5CB17 doble | 4-014778 | 2011-06-24 | 8:00 | 2011-06-24 | 16:00 | C
5L71, 5L72 | Open MCA 5D4 | 2-066935 | 2011-06-26 | 12:00 | 2011-06-26 | 12:30 | C | Yes | YEs | 2000 | 2400 | 2000 | 2000
DMR 5DCB55 - 5L31- 5MB1 | 5DCB55 5CVT4 Inspection | 1-102758 | 2011-06-27 | 8:00 | 2011-06-29 | 16:00 | C | Yes
KLY 5CB7 | 5CB7 Insp | 4-014779 | 2011-06-27 | 8:00 | 2011-06-29 | 16:00 | C
5L42 | KLY disconnect replacement | 2-066084 | 2011-06-27 | 8:00 | 2011-06-29 | 16:00 | C | Yes |  | 1300 | 1700 | 2000 | 2000
ACK 5CB8 | ACK 5CT8 A DOBL | 1-102891 | 2011-06-27 | 8:00 | 2011-06-29 | 16:00 | C
ACK 5CB8 | ACK 5CT8 A INSP | 1-102891 | 2011-06-27 | 8:00 | 2011-06-29 | 16:00 | D
SEL 5CB5 | Replacement | 4-014822 | 2011-06-27 | 8:00 | 2011-08-19 | 16:00 | C
SEL 5CB11 | Replacement | 4-014822 | 2011-06-27 | 8:00 | 2011-08-19 | 16:00 | C
SEL 5CB5 | Replacement | 4-014822 | 2011-06-27 | 8:00 | 2011-08-19 | 16:00 | C
SEL 5CB11 | Replacement | 4-014822 | 2011-06-27 | 8:00 | 2011-08-19 | 16:00 | C
SEL 5CB5 | Replacement | 4-014822 | 2011-06-27 | 8:00 | 2011-09-09 | 16:00 | C
SEL 5CB11 | Replacement | 4-014822 | 2011-06-27 | 8:00 | 2011-09-09 | 16:00 | C
SEL 5CB5 | Replacement | 4-014822 | 2011-06-27 | 8:00 | 2011-09-09 | 16:00 | C
SEL 5CB11 | Replacement | 4-014822 | 2011-06-27 | 8:00 | 2011-09-09 | 16:00 | C
GLN 5RX5 SYPN | 5RX5 | 1-102972 | 2011-06-28 | 8:00 | 2011-06-28 | 14:00 | C |  |  | 2000 | 2400 | 2000 | 2000
5L62 | Inspection TKW 5D26 | 1-102704 | 2011-06-28 | 8:00 | 2011-06-28 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
TKW STN SYNC | station synchronizer scheme | 1-102987 | 2011-06-28 | 8:00 | 2011-06-28 | 16:00 | C
5L31 | Pothead washing | 2-066289 | 2011-06-28 | 8:00 | 2011-06-30 | 16:00 | C | Yes
GLN 5RX5 ABCN (5L62) | Inspection | 1-102354 | 2011-06-28 | 8:00 | 2011-07-01 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
GLN 5RX5 ABCN (5L62) | Inspection | 1-102354 | 2011-06-28 | 8:00 | 2011-07-01 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
DMR 5RX8 | Replace core ground resistor | 4-014825 | 2011-06-30 | 8:00 | 2011-06-30 | 16:00 | C
KLY 5CB7 | 5CB7 doble | 4-014780 | 2011-06-30 | 8:00 | 2011-06-30 | 16:00 | C
5L44 (forced outage) | Repair tower near water crossing | 8-67755 | 2011-06-30 | 17:52 | 2011-09-10 | 19:46 | C |  |  | 1800 | 2200 | 1500 | 1900
5L44 (forced outage) | Repair tower near water crossing | 8-67755 | 2011-06-30 | 17:52 | 2011-09-15 | 16:00 | C |  |  | 1800 | 2200 | 1500 | 1900
5L44 (forced outage) | Repair tower near water crossing | 8-67755 | 2011-06-30 | 17:52 | 2011-10-31 | 16:00 | C |  |  | 1800 | 2200 | 1500 | 1900
5L12 | Spacer Dampers | 1-101949 | 2011-07-03 | 9:00 | 2011-07-16 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
WSN 5CB15 | trip test breaker and all associated protections | 1-102304 | 2011-07-04 | 8:00 | 2011-07-04 | 9:00 | C
MIN 2CB1 BFPN | 2CB1 | 1-102976 | 2011-07-04 | 8:00 | 2011-07-04 | 9:00 | C
WSN 5CB5 | trip test breaker and all associated protections | 1-102307 | 2011-07-04 | 9:00 | 2011-07-04 | 10:00 | C
MIN 2CB5 BFPN | 2CB5 | 1-102978 | 2011-07-04 | 9:00 | 2011-07-04 | 10:00 | C
MIN 2D2 BFPN | 2D2 & T2 | 1-102979 | 2011-07-04 | 10:00 | 2011-07-04 | 11:00 | C
5L2 | WSN 5CC4 | 1-102281 | 2011-07-04 | 8:00 | 2011-07-04 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
2L103 | Inspection MIN 2CVT1 | 1-102798 | 2011-07-04 | 8:00 | 2011-07-04 | 16:00 | C | Yes
5L3 | Insul badly flashed | 1-101940 | 2011-07-04 | 9:00 | 2011-07-04 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
WSN 5RX4 | WSN 5RX4 | 1-102288 | 2011-07-04 | 8:00 | 2011-07-06 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
2L129 | VITR remedial work | 4-016809 | 2011-07-04 | 8:00 | 2011-07-08 | 16:00 | C
2L129 English Bluff (EBT) X Maracaib (MBO) |  | 1-102742 | 2011-07-04 | 8:00 | 2011-07-08 | 16:00 | C
5L12 | Arc Horn Project | 1-101785 | 2011-07-04 | 8:00 | 2011-08-05 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
1L275 | Replace structure | 4-014873 | 2011-07-05 | 8:00 | 2011-07-07 | 16:00 | C | [6 empty] | 850 | 700
1L275 | NTL 1CB1 Replacement | 8-067689 | 2011-07-06 | 8:00 | 2011-08-02 | 15:00 | C | [6 empty] | 850 | 700
NTL 1CB1 | Replacement | 4-014967 | 2011-07-06 | 16:00 | 2011-08-02 | 15:00 | C | [6 empty] | 850 | 700
1L275 | NTL 1CB1 Replacement | 8-067689 | 2011-07-06 | 8:00 | 2011-08-02 | 15:00 | C | [6 empty] | 850 | 700
NTL 1CB1 | Replacement | 4-014967 | 2011-07-06 | 16:00 | 2011-08-02 | 15:00 | C | [6 empty] | 850 | 700
WSN 5B14 | WSN 5D2CB16 | 1-102286 | 2011-07-07 | 8:00 | 2011-07-08 | 16:00 | C
KLY T4 | Re-establish bus cut for SC2 | 2-067002 | 2011-07-07 | 3:00 | 2011-07-09 | 3:00 | C
KLY PN-T1 (12RX1) | 43.03-009-4 COLT CAL,OP,LOAD,TRIP | 1-102924 | 2011-07-08 | 8:00 | 2011-07-08 | 16:00 | C |  |  | 2000 | 2400
5L12 | Insulator replacements | 1-101948 | 2011-07-11 | 9:00 | 2011-07-12 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
KLY 5RX1 | 5CB31 Insp | 4-014774 | 2011-07-11 | 8:00 | 2011-07-13 | 16:00 | D |  |  | 2000 | 2400
5L1 | Arc Horn Project | 1-101707 | 2011-07-11 | 9:00 | 2011-07-20 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
KDY 5CX1, 5L1 | KDY Inpsectioin | 8-067808 | 2011-07-11 | 9:00 | 2011-07-20 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
5L12 | Disconnects 5BP2 and 5D22@5D32 inspections for all. | 1-102040 | 2011-07-11 | 9:00 | 2011-07-22 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
KLY 5B12 | 5D2CB11 Re-align | 4-014776 | 2011-07-12 | 8:00 | 2011-07-12 | 16:00 | C | Yes
KLY PN-5RX1 | 43.04-003-4 COLT CAL,OP,LOAD,TRIP | 1-102920 | 2011-07-14 | 8:00 | 2011-07-14 | 16:00 | C |  |  | 2000 | 2400
KLY 5RX1 | 5CB31 doble | 4-014775 | 2011-07-14 | 8:00 | 2011-07-14 | 16:00 | D |  |  | 2000 | 2400
KLY 5RX3, 5B3, 5L12 | 5D23 Insp | 1-101951 | 2011-07-14 | 8:00 | 2011-07-14 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
NIC 5MB4 | Equipnment Inspection | 1-102877 | 2011-07-14 | 8:00 | 2011-07-15 | 16:00 | C | Yes
KLY PN-5RX3 | 43.04-003-4 COLT CAL,OP,LOAD,TRIP | 1-102922 | 2011-07-15 | 8:00 | 2011-07-15 | 16:00 | C |  |  | 2000 | 2400
ING 2CX31 | For 2CX31 Inspection | 1-102620 | 2011-07-18 | 8:00 | 2011-07-19 | 16:00 | C | Yes
5L98 | 5D31 and 5DCB51 Inspections, 5RX11 Qualitrol upgrades | 2-066613 | 2011-07-18 | 8:00 | 2011-07-21 | 16:00 | C | Yes |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
5L98 | Damage Conductor Repair | 4-014501 | 2011-07-18 | 8:00 | 2011-07-27 | 16:00 | C | Yes |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
2L101 | Line Rating Restoration | 1-102708 | 2011-07-18 | 8:00 | 2011-07-29 | 20:00 | D | Yes
2L101 | Inspection RUP 2D28 & 2D3 | 1-102705 | 2011-07-18 | 8:00 | 2011-07-29 | 20:00 | C | Yes
2L101 | Inspection SKA 2VT5 | 1-102707 | 2011-07-18 | 8:00 | 2011-07-29 | 20:00 | C | Yes
NIC 5MB2 | Equipnment Inspection | 1-102865 | 2011-07-19 | 8:00 | 2011-07-20 | 16:00 | C | Yes
5L1 | WSN 5DCB21 5CC2 Inspection | 1-102280 | 2011-07-19 | 8:00 | 2011-07-20 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
KLY 5RX6 | 5RX6 Insp | 4-014781 | 2011-07-19 | 8:00 | 2011-07-22 | 16:00 | D |  |  | 2000 | 2400
2L101 | Transmission Structures | 1-102323 | 2011-07-19 | 8:00 | 2011-07-22 | 20:00 | D | Yes
RUP STN SYNC | station synchronizer scheme | 1-102982 | 2011-07-20 | 8:00 | 2011-07-20 | 16:00 | C
ING 2CX32 | For 2CX32 Inspection | 1-102621 | 2011-07-20 | 8:00 | 2011-07-21 | 16:00 | C
KLY 5RX6 | 5D36 doble | 4-014782 | 2011-07-21 | 8:00 | 2011-07-21 | 16:00 | C |  |  | 2000 | 2400
5L12, WSN 5B4 | WSN 5D25,5CC5 | 1-102283 | 2011-07-21 | 8:00 | 2011-07-22 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
MDN 5CT7, MDN 5CB7 | MDN 5CT7 OIL SAMPLE | 1-102633 | 2011-07-22 | 8:00 | 2011-07-22 | 16:00 | C
KLY PN-5RX4 | 43.04-003-4 COLT CAL,OP,LOAD,TRIP | 1-102923 | 2011-07-22 | 8:00 | 2011-07-22 | 16:00 | C |  |  | 2000 | 2400
KLY 2RX2 | 2RX2 Insp | 4-014767 | 2011-07-25 | 15:00 | 2011-07-27 | 16:00 | D |  |  | 2000 | 2400
SKA T2 | Test and Work | 2-067699 | 2011-07-25 | 8:00 | 2011-07-29 | 16:00 | C | Yes
KLY 2RX2 | Maintenance | 2-066069 | 2011-07-25 | 8:00 | 2011-07-29 | 16:00 | D |  |  | 2000 | 2400
5L91 | CB Replacement | 3-024951 | 2011-07-26 | 8:00 | 2011-07-26 | 16:00 | C | Yes |  | 2850 | 3150 | 2000 | 2000 | 560 | 500
5L2 | Arc Horn Project | 1-101782 | 2011-07-26 | 9:00 | 2011-08-05 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
5L96 | CB Replacement | 3-024952 | 2011-07-27 | 8:00 | 2011-07-27 | 16:00 | C | Yes |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
KLY 2RX2 | 2RX2 doble | 4-014768 | 2011-07-28 | 16:00 | 2011-07-28 | 16:00 | D |  |  | 2000 | 2400
KLY PN-5RX2 | 43.04-003-4 COLT CAL,OP,LOAD,TRIP | 1-102921 | 2011-07-29 | 8:00 | 2011-07-29 | 16:00 | C |  |  | 2000 | 2400
1L274 (NTL - 1D1L274) | Replace structures and insulators | 4-014869 | 2011-08-01 | 8:00 | 2011-08-05 | 16:00 | C
5L29 | to replace Oil Pumping Station at NCT | 4-014236 | 2011-08-01 | 8:00 | 2011-08-09 | 16:00 | C | Yes
SKA T2 | Test and Work | 2-064368 | 2011-08-02 | 8:00 | 2011-08-05 | 16:00 | C | Yes
5L98 | Damage Conductor Repair | 4-014501 | 2011-08-02 | 10:00 | 2011-08-12 | 16:00 | C | Yes |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
5L2 | Arc Horn Project | 1-101782 | 2011-08-02 | 9:00 | 2011-08-12 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
5L52, ING 5B5,5CB5,5CB6 | Restore TLC line side 5CB6 | 1-97882 | 2011-08-04 | 4:30 | 2011-08-06 | 21:00 | C |  |  | 2650 | 3050 | 1500 | 1900
5L98 | Insulator replacements | 4-14504 | 2011-08-05 | 10:00 | 2011-08-05 | 17:00 | C | Yes |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
1L274 (1D2L274 - EFT) | Replace structures and insulators | 4-014870 | 2011-08-06 | 8:00 | 2011-08-20 | 16:00 | C
5L40 and ING 5MB1 | Restore TLC station side 5CB6 (LOA) | 2-67384 | 2011-08-08 | 4:30 | 2011-08-08 | 13:00 | C |  |  | 1700 | 2100 | 1400 | 1800
ING T2, 5B6,5CB6,5CB7 | Restore TLC station side 5CB6 | 1-97884 | 2011-08-08 | 4:30 | 2011-08-09 | 21:00 | C
5L98, NIC 5B25, 5RX11 | Disconnect Insepction | 2-066613 | 2011-08-08 | 8:00 | 2011-08-11 | 16:00 | C | Yes |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
SKA T4 | SKA Transformer Protection upgrade | 1-102993 | 2011-08-08 | 8:00 | 2011-08-14 | 16:00 | C
1L44 | Line Rating Upgrade - Clowhom | 4-14209 | 2011-08-08 | 8:00 | 2011-09-23 | 16:00 | C | Yes
1L44 | Line Rating Upgrade - Clowhom | 4-14209 | 2011-08-08 | 8:00 | 2011-09-23 | 16:00 | C | Yes
2L101 | Inspection RUP 2D28 & 2D3 | 1-102705 | 2011-08-09 | 8:00 | 2011-08-09 | 20:00 | C | Yes
2L101 | Inspection SKA 2VT5 | 1-102707 | 2011-08-09 | 8:00 | 2011-08-09 | 20:00 | C | Yes
2L101 | Transmission Structures | 1-102323 | 2011-08-09 | 8:00 | 2011-08-12 | 20:00 | D | Yes
5L52 & ING T2 one at a time | Point on wave test ING 5CB6 | 2-64487 | 2011-08-10 | 8:00 | 2011-08-10 | 8:00 | C |  |  | 2650 | 3050 | 1500 | 1900
5L31 | to replace Oil Pumping Station at NCT | 4-014237 | 2011-08-10 | 8:00 | 2011-08-18 | 16:00 | C | Yes
ING 5CB8 | Replace | 1-97891 | 2011-08-10 | 8:00 | 2011-10-20 | 16:00 | C
ING 5CB8 | Replace | 1-97891 | 2011-08-10 | 8:00 | 2011-10-20 | 16:00 | C
5L45 | Restore TLC line side 5CB4 | 4-014617 | 2011-08-11 | 8:00 | 2011-08-13 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
ING 5MB1,5CB4,5CB8,5CB9 | Create TLC station side 5CB8 | 1-97889 | 2011-08-11 | 4:30 | 2011-08-13 | 21:00 | C |  |  | 2000 | 2400 | 2000 | 2000
5L82, MDN 5B7, MDN 5CB8 | MDN 5D1CB8, 5D24 INSP | 1-102634 | 2011-08-14 | 8:00 | 2011-08-16 | 16:00 | C |  |  | 1200 | 1600 | 2000 | 2000
5L82, MDN 5B7, 5CB7, 5CB8 | Create TLC line side 5CB8; replacement 5CB8 | 1-102630 | 2011-08-14 | 6:00 | 2011-08-16 | 20:00 | C |  |  | 1200 | 1600 | 2000 | 2000
MDN 5CB8 | Replace | 1-102635 | 2011-08-14 | 8:00 | 2011-10-29 | 16:00 | C
MDN 5CB8 | Replace | 1-102635 | 2011-08-14 | 8:00 | 2011-10-29 | 16:00 | C
MDN 5CB8 | Replace | 1-102635 | 2011-08-14 | 8:00 | 2011-10-29 | 16:00 | C
ING 5CB8 | Breaker controls testing by CPC | 1-102627 | 2011-08-15 | 8:00 | 2011-08-15 | 16:00 | C
2L101 | Line Rating Restoration | 1-102708 | 2011-08-15 | 8:00 | 2011-08-19 | 20:00 | D | Yes
SKA T5 | SKA Transformer Protection upgrade | 1-102994 | 2011-08-15 | 8:00 | 2011-08-21 | 16:00 | C
5L91 | Insulator replacements (Return Weekend) | 4-014493 | 2011-08-16 | 8:00 | 2011-09-01 | 16:00 | C | Yes |  | 2850 | 3150 | 2000 | 2000 | 560 | 500
5L91 | Insulator replacements (Return Weekend) | 4-014493 | 2011-08-16 | 8:00 | 2011-09-02 | 16:00 | C | Yes |  | 2850 | 3150 | 2000 | 2000 | 560 | 500
5L40, CBN 5D22 | Inspection | 2-067368 | 2011-08-17 | 8:00 | 2011-08-19 | 16:00 | C |  |  | 1700 | 2100 | 2000 | 2000
5L40 & ING 5B7 | Establish bus cut for | 1-97887 | 2011-08-17 | 4:30 | 2011-08-19 | 21:00 | C |  |  | 1700 | 2100 | 2000 | 2000
VAS 5RX1 | gas relay testing - PM | 4-014759 | 2011-08-19 | 8:00 | 2011-08-19 | 16:00 | C
5L71 | PD Test | 8-69233 | 2011-08-19 | 23:00 | 2011-08-21 | 23:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
ING 5CB8 | Replace | 1-97891 | 2011-08-20 | 8:00 | 2011-10-24 | 16:00 | C
1L274 (1D4L274 - BCK) | Replace structures | 4-014871 | 2011-08-21 | 8:00 | 2011-08-25 | 16:00 | C
VAS 5CB22 | PM on breaker control | 4-014760 | 2011-08-22 | 8:00 | 2011-08-22 | 16:00 | C
SKA T6 | SKA Transformer Protection upgrade | 1-102995 | 2011-08-22 | 8:00 | 2011-08-28 | 16:00 | C
KDY 5CX3 | routine testing | 1-101941 | 2011-08-22 | 8:00 | 0211-09-23 | 16:00 | C
KDY 5CX3 | routine testing | 1-101941 | 2011-08-22 | 8:00 | 0211-09-23 | 16:00 | C
VAS 5CB14 | PM on breaker control | 4-014761 | 2011-08-23 | 8:00 | 2011-08-23 | 16:00 | C
VAS 5CB13 | PM on breaker control | 4-014762 | 2011-08-24 | 8:00 | 2011-08-24 | 16:00 | C
NIC 5CB25 | Inspection | 1-102866 | 2011-08-25 | 8:00 | 2011-08-27 | 16:00 | C
NIC 5CB25 | PVIN, PVRP | 1-102854 | 2011-08-26 | 8:00 | 2011-08-26 | 16:00 | C
1L274 (BCK - POC) | Replace structures | 4-014872 | 2011-08-26 | 8:00 | 2011-09-09 | 16:00 | C
1L274 (BCK - POC) | Replace structures | 4-014872 | 2011-08-26 | 8:00 | 2011-09-09 | 16:00 | C
5L72 | MCA GIS upgrade | 8-69234 | 2011-08-27 | 7:00 | 2011-08-27 | 23:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
5L98 | Insulator replacements | 4-014504 | 2011-08-29 | 8:00 | 2011-08-29 | 16:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
5L98 | Repair conductor damage | 4-014505 | 2011-08-29 | 8:00 | 2011-08-29 | 16:00 | C | Yes |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
PCN 5CB1 | F12 Maintenance Cycle | 1-102334 | 2011-08-29 | 8:00 | 2011-08-30 | 16:00 | C
NIC 5L98,5B25 (5DCB51,5D31) | Inspection | 4-014503 | 2011-08-29 | 8:00 | 2011-08-30 | 16:00 | C | Yes |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
PCN 5CB2 | F12 Maintenance Cycle | 2-65723 | 2011-08-31 | 8:00 | 2011-09-01 | 16:00 | C
PCN 5CB2 | F12 Maintenance Cycle | 2-65723 | 2011-08-31 | 8:00 | 2011-09-01 | 16:00 | C
BRT 3B1 3L2 | 3D1CB1 Insp | 4-014784 | 2011-09-01 | 8:00 | 2011-09-01 | 16:00 | C | Yes
Ingledow AutoVar scheme | Upgrade | 2-66837 | 2011-09-01 | 8:00 | 2011-09-14 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
5L41 | Recontouring project | 2-66885 | 2011-09-02 | 7:00 | 2011-09-02 | 16:00 | C |  |  | 1700 | 2100 | 2000 | 2000
CBN T1 | PN upgrade at CBN on T1 and T2 | 4-14826 | 2011-09-05 | 8:00 | 2011-09-05 | 16:00 | C
2L295 | Replace insulators/timbers | 1-102843 | 2011-09-05 | 8:00 | 2011-09-07 | 16:00 | C | Yes
SEL T2 | Inspection | 4-014766 | 2011-09-05 | 8:00 | 2011-09-09 | 16:00 | C
CBN 5D2CB7 | Inspection | 1-102755 | 2011-09-06 | 8:00 | 2011-09-06 | 16:00 | C
NIC 5L79, 5B16 (5D26) | Inspection | 4-014461 | 2011-09-06 | 8:00 | 2011-09-06 | 16:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 850 | 700
5L79 | ACK 5D1CB2 INSP | 4-014460 | 2011-09-06 | 8:00 | 2011-09-06 | 16:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 850 | 700
PCN 5CB3 | F12 Maintenance Cycle | 1-102337 | 2011-09-06 | 8:00 | 2011-09-07 | 16:00 | C
NIC 5L71, 5B14 (5DCB44,5D24) | Inspection | 4-014451 | 2011-09-06 | 8:00 | 2011-09-09 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
5L71 | Replace flashed insulators | 4-014450 | 2011-09-06 | 10:00 | 2011-09-15 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
5L11 | Arc Horn Project | 1-101784 | 2011-09-06 | 8:00 | 2011-10-03 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
5L71 | GIS upgrade |  | 2011-09-06 | 8:00 | 2011-11-07 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
5L71 | GIS upgrade | 8-069235 | 2011-09-06 | 8:00 | 2011-11-07 | 23:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
CBN 5D1 | Inspection | 1-102638 | 2011-09-07 | 8:00 | 2011-09-07 | 16:00 | C
5L76 | Replace flashed insulators | 4-014456 | 2011-09-07 | 8:00 | 2011-09-07 | 16:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 850 | 700
NIC 5L76,5B15 (5D25) | Inspection | 4-014458 | 2011-09-07 | 8:00 | 2011-09-07 | 16:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 850 | 700
CBN 2D1 | Inspection | 1-102639 | 2011-09-08 | 8:00 | 2011-09-08 | 16:00 | C
5L96 | SEL CB Testing | 8-069028 | 2011-09-08 | 13:00 | 2011-09-08 | 17:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
SEL T1 | SEL CB Testing | 8-069028 | 2011-09-08 | 17:00 | 2011-09-08 | 19:00 | C
2L299 | Replace insulators/timbers | 1-102845 | 2011-09-08 | 8:00 | 2011-09-12 | 16:00 | C | Yes
5L91 | SEL CB Testing | 8-069028 | 2011-09-09 | 9:00 | 2011-09-09 | 13:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 560 | 500
CBN 5D2CB8 | Inspection | 1-102636 | 2011-09-09 | 8:00 | 2011-09-09 | 16:00 | C
1L274 Radial Operaion | Disconnect Repair | 8-069472 | 2011-09-09 | 8:00 | 2011-09-09 | 16:00 | C | Yes | [5 empty] | 850 | 700
SEL T4 | SEL CB Testing | 8-069028 | 2011-09-09 | 13:00 | 2011-09-09 | 17:00 | C
5L79 | ACK 5D2CB1 A INSP | 4-014459 | 2011-09-10 | 8:00 | 2011-09-10 | 16:00 | D |  |  | 2850 | 3150 | 2000 | 2000 | 850 | 700
BLW 2CB2 | trip test breaker and all associated protections | 1-102340 | 2011-09-12 | 8:00 | 2011-09-12 | 9:00 | C
WSN 2CB6 | trip test breaker and all associated protections | 1-102314 | 2011-09-12 | 8:00 | 2011-09-12 | 9:00 | C
WSN 2CB7 | trip test breaker and all associated protections | 1-102315 | 2011-09-12 | 10:00 | 2011-09-12 | 11:00 | C
CBN T2 | PN upgrade at CBN on T1 and T2 | 4-14827 | 2011-09-12 | 8:00 | 2011-09-12 | 16:00 | C
ACK 5CB10 | PM on breaker control | 4-014764 | 2011-09-12 | 8:00 | 2011-09-12 | 16:00 | C
2L96 | Poles, Timbers and Insul. | 1-102292 | 2011-09-12 | 8:00 | 2011-09-15 | 16:00 | C
CBN T2 | Insp/Doble | 1-102640 | 2011-09-12 | 8:00 | 2011-09-15 | 16:00 | C
2L113 | Replace insulators/timbers | 1-102831 | 2011-09-12 | 8:00 | 2011-09-16 | 17:00 | C | Yes
HMH 2CB1 | trip test breaker and all associated protections | 1-102344 | 2011-09-13 | 8:00 | 2011-09-13 | 9:00 | C
2L289 (CPC circuit) | Replace timbers | 1-102846 | 2011-09-13 | 8:00 | 2011-09-13 | 16:00 | C | Yes
ACK 5CB2 | PM on breaker control | 4-014764 | 2011-09-13 | 8:00 | 2011-09-13 | 16:00 | C
KLY 5B1, 5RX1, 5L11 | 5DCB31 Insp | 1-101950 | 2011-09-13 | 9:00 | 2011-09-13 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
HMH T1 | routine testing of auto-isolate and gas relay + non-electrical trip testing to be carried out | 1-102347 | 2011-09-13 | 13:00 | 2011-09-13 | 17:00 | C
5L11, WSN 5B4 | WSN 5D33,5CC3 | 1-102284 | 2011-09-13 | 8:00 | 2011-09-14 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
5L76 | Replace flashed insulators | 4-014456 | 2011-09-13 | 10:00 | 2011-09-14 | 16:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 850 | 700
5L1 | Arcing Horn Project | 3-021569 | 2011-09-13 | 9:00 | 2011-09-16 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
5L11 | Disconnects 5BP1 and 5D21@5D31 inspections for all. | 1-102034 | 2011-09-13 | 8:00 | 2011-09-23 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
2L78 | install 4 D-Tower Deadends | 1-102786 | 2011-09-13 | 8:00 | 2011-09-25 | 16:00 | C | Yes
ACK 5CB12 | PM on breaker control | 4-014764 | 2011-09-14 | 8:00 | 2011-09-14 | 16:00 | C
ACK 5CB12 | PM on breaker control | 4-014764 | 2011-09-15 | 8:00 | 2011-09-15 | 16:00 | C
2L97 | Poles, Timbers and Insul. | 1-102295 | 2011-09-16 | 8:00 | 2011-09-16 | 16:00 | C
WSN 2CB3 | WSN 2CT3 | 1-102319 | 2011-09-16 | 8:00 | 2011-09-16 | 16:00 | C
5L75 | Part of blackstart procedure at REV | 8-070552 | 2011-09-18 | 8:00 | 2011-09-18 | 18:00 | C | Yes |  | 2400 | 2800 | 200 | 200 | 850 | 700
WSN 5CB32 (5RX2) | trip test breaker and all associated protections | 1-102278 | 2011-09-19 | 9:00 | 2011-09-19 | 10:00 | C
HMH T2 | routine testing of auto-isolate and gas relay + non-electrical trip testing to be carried out | 1-102345 | 2011-09-19 | 8:00 | 2011-09-19 | 12:00 | C
5L40 and ING 5MB1 | Restore temporary line cut on 5B6 (for limits of approach) | 2-67384 | 2011-09-19 | 4:30 | 2011-09-19 | 13:00 | C |  |  | 1700 | 2100 | 1400 | 1800
5L11 | Insulator replacements | 1-101947 | 2011-09-19 | 8:00 | 2011-09-20 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
5L91 | Replace insulators | 4-014494 | 2011-09-19 | 8:00 | 2011-09-20 | 16:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 560 | 500
ING T2 & 5B6 | Restore temporary Line cut on 5B6 for 5CB6 replacement | 1-97884 | 2011-09-19 | 4:30 | 2011-09-20 | 21:00 | C
5L92 | Insulator replacements | 4-14495 | 2011-09-19 | 8:00 | 2011-09-22 | 16:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 110 | 300
5L92 | Insulator replacements | 4-14495 | 2011-09-19 | 8:00 | 2011-09-22 | 16:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 110 | 300
5L96 | Insulator replacements | 3-026963 | 2011-09-19 | 8:00 | 2011-09-23 | 16:00 | D |  |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
5L1 | Arcing Horn Project | 3-021569 | 2011-09-19 | 9:00 | 2011-09-23 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
2L101 | Transmission Structures and Disconnect Replacement | 1-102323 | 2011-09-19 | 8:30 | 2011-09-23 | 19:00 | D | Yes
5L71 | Insulator replacements | 4-014452 | 2011-09-19 | 8:00 | 2011-09-24 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
2L352 | Poles, Timbers and Insul. | 1-102296 | 2011-09-19 | 8:00 | 2011-09-29 | 16:00 | C
5L91 | Replace flashed insulators | 4-014493 | 2011-09-19 | 8:00 | 2011-09-30 | 16:00 | C | Yes |  | 2850 | 3150 | 2000 | 2000 | 560 | 500
5L52 & ING T2 one at a time | Point on wave test ING 5CB6 | 2-64487 | 2011-09-21 | 8:00 | 2011-09-21 | 16:00 | C |  |  | 2650 | 3050 | 1500 | 1900
5L45 & MDN 5B3 | Restore temporary line cut on 5B3 | 4-014617 | 2011-09-22 | 6:00 | 2011-09-24 | 20:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
2L112 | BPA to install new CCVT at BDY Terminal | 3-026350 | 2011-09-24 | 8:00 | 2011-09-24 | 14:00 | C |  |  | 2850 | 2850 | 2000 | 2000 | 560 | 600
5L45 & MDN 5CB4 | Point on Wave test MDN 5CB4 | 3-26138 | 2011-09-24 | 16:00 | 2011-09-24 | 21:00 | C |  |  | 2000 | 2400 | 2000 | 2000
5L1 | WSN 5DCB32,5CC2 | 1-102280 | 2011-09-26 | 8:00 | 2011-09-26 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
2L101 | Transmission Structures and Disconnect Replacement | 8-068199 | 2011-09-26 | 8:30 | 2011-09-29 | 19:00 | D | Yes
PCN 5CB5 | F12 Maintenance Cycle | 1-102336 | 2011-09-29 | 8:00 | 2011-09-30 | 16:00 | C
KLY 5B7 &5L87 | Repair KLY 5D1CB7, 5D2CB7 and 5D27; inspect KLY 5D36, 5D1CB17, 5D2CB17 and 5CVT7. | 8-070544 | 2011-09-30 | 8:00 | 2011-10-03 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000 | 560 | 600
KLY 5B7 &5L87 | Repair KLY 5D1CB7, 5D2CB7 and 5D27; inspect KLY 5D36, 5D1CB17, 5D2CB17 and 5CVT7. | 8-070544 | 2011-09-30 | 8:00 | 2011-10-03 | 16:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000 | 560 | 600
5L94 | Altalink Microwave work | 3-027649 | 2011-10-01 | 8:00 | 2011-10-01 | 12:00 | C | [6 empty] | 0 | 0
ING 12RX4 | For 12RX4 Inspection | 1-102641 | 2011-10-03 | 8:00 | 2011-10-03 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
5L52 & ING T2 one at a time | Point on wave test ING 5CB6 | 2-64487 | 2011-10-03 | 8:00 | 2011-10-03 | 16:00 | C |  |  | 2650 | 3050 | 1500 | 1900
AMC 5CX2 | Elec and CPC insp's | 1-102629 | 2011-10-03 | 8:00 | 2011-10-07 | 16:00 | C
5L2 | Arcing Horn Project | 3-021570 | 2011-10-03 | 9:00 | 2011-10-07 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
ING 12RX5 | For 12RX5 Inspection | 1-102642 | 2011-10-04 | 8:00 | 2011-10-04 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
Ingledow AutoVar scheme | Upgrade | 2-66837 | 2011-10-05 | 8:00 | 2011-10-18 | 16:00 | C |  |  | 2000 | 2400 | 2000 | 2000
MDN 5CT1, MDN 5CB1 | MDN 5CT1 DOBLE/OIL SAMPLE | 1-102745 | 2011-10-07 | 8:00 | 2011-10-07 | 16:00 | C
5L2 | Arcing Horn Project | 3-026556 | 2011-10-11 | 9:00 | 2011-10-14 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
5L82 | Insulator replacements | 4-014490 | 2011-10-13 | 8:00 | 2011-10-14 | 16:00 | C |  |  | 1700 | 2100 | 2000 | 2000
VIT SC3 | Major overhual | 2-67525 | 2011-10-13 | 8:00 | 2011-12-15 | 15:00 | C
MDN 2RX1 | protection work | 8-71489 | 2011-10-14 | 7:00 | 2011-10-14 | 18:00 | C |  |  | 2000 | 2400 | 2000 | 2000
5L96 | CB Replacement | 8-071302 | 2011-10-17 | 8:00 | 2011-10-17 | 16:00 | C | [6 empty] | 560 | 450
5L96 | Replace insulators | 4-014500 | 2011-10-17 | 8:00 | 2011-10-28 | 16:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
5L96 | Replace flashed insulators | 4-014499 | 2011-10-17 | 8:00 | 2011-10-28 | 16:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
5L91 | CB Replacement | 8-071306 | 2011-10-18 | 8:00 | 2011-10-18 | 16:00 | C | Yes | [5 empty] | 560 | 500
1L274 Radial Operaion | Disconnect Repair | 8-071028 | 2011-10-20 | 8:00 | 2011-10-20 | 16:00 | C | Yes | [5 empty] | 850 | 700
ING 5CB7 | Breaker controls testing by CPC | 1-102626 | 2011-10-24 | 8:00 | 2011-10-24 | 16:00 | C
ING 5B7,5L40,5CB7,5CB8 | Restore TLC line side 5CB8 | 1-97892 | 2011-10-24 | 8:00 | 2011-10-26 | 16:00 | C |  |  | 1700 | 2100 | 2000 | 2000
5L2 | Arcing Horn Project | 8-071852 | 2011-10-24 | 9:00 | 2011-10-27 | 17:00 | D | Yes |  | 2000 | 2400 | 2000 | 2000
5L12 | Spacer Dampers | 3-021572 | 2011-10-24 | 9:00 | 2011-11-10 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
5L12 | Spacer Dampers | 3-021572 | 2011-10-24 | 9:00 | 2011-11-10 | 17:00 | C | Yes |  | 2000 | 2400 | 2000 | 2000
5L44 (Meridian-Ingledow 500 kV Line) | Install rupture disc covers and corona rings | 8-71768/8-71772 | 2011-10-26 | 8:00 | 2011-10-28 | 16:00 | C |  |  | 1700 | 2100 | 1500 | 1900
MDN 5B7, 5L82, 5CB7, 5CB8 | Restore TLC line side 5CB8 | 1-102643 | 2011-10-27 | 8:00 | 2011-10-29 | 16:00 | C |  |  | 1700 | 2100 | 2000 | 2000
ING 5MB1,5CB4,5CB8,5CB9 | Restore TLC station side 5CB8 | 1-97897 | 2011-10-27 | 8:00 | 2011-10-29 | 16:00 | C
ING 5CB11 | Breaker controls testing by CPC | 1-102743 | 2011-10-31 | 8:00 | 2011-10-31 | 16:00 | C
MDN 12RX31 and 12RX32 | Disconnect Repair | 8-71091 | 2011-10-31 | 8:00 | 2011-11-04 | 16:00 | C |  |  | 2000 | 2400
ING 5CB12 | Breaker controls testing by CPC | 1-102744 | 2011-11-01 | 8:00 | 2011-11-01 | 16:00 | C
ING 5CB4 | Breaker controls testing by CPC | 1-102760 | 2011-11-02 | 8:00 | 2011-11-02 | 16:00 | C
KI2 12RX3 | inspection | 8-72593 | 2011-11-03 | 8:00 | 2011-11-03 | 16:00 | C |  |  | 2000 | 2400
2L112 | RAS outage | 8-68976/8-68977 | 2011-11-07 | 10:00 | 2011-11-07 | 16:00 | C |  |  | 2850 | 2850 | 2000 | 2000 | 560 | 600
MDN 12RX32 and 12RX31 | disconnect replacement | 8-71091 | 2011-11-07 | 8:00 | 2011-11-11 | 16:00 | C |  |  | 2000 | 2400
5L72 | GIS upgrade | 8-70704 | 2011-11-08 | 8:00 | 2011-11-10 | 22:00 |  |  |  | 2400 | 2800 |  |  | 850 | 700
ACK 5RX7 | PCB Sampling | 8-73898 | 2011-11-17 | 8:00 | 2011-11-17 | 13:00 | C | Yes |  | 2000 | 2400
5L91, SEL T1 and SEL 5CB9 | CB Testing | 5-73899 | 2011-11-23 | 12:00 | 2011-11-23 | 16:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 560 | 500
5L92 | CB Testing | 8-74387 | 2011-11-23 | 22:00 | 2011-11-23 | 23:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 110 | 300
5L96, SEL T4 and SEL 5CB8 | CB Testing | 8-75197 | 2011-11-24 | 8:00 | 2011-11-24 | 16:00 | C |  |  | 2850 | 3150 | 2000 | 2000 | 560 | 450
ACK 5RX8 | PCB Sampling | 8-73901 | 2011-11-25 | 8:00 | 2011-11-25 | 16:00 | C | Yes |  | 2000 | 2400
MDN 2RX1 | CB repair | 8-74979 | 2011-11-28 | 9:00 | 2011-11-30 | 17:00 | C |  |  | 2000 | 2400
5L72 | Insulator Replacement | 8-74995 | 2011-11-29 | 9:00 | 2011-11-29 | 16:00 | C | Yes |  | 2400 | 2800 | 2000 | 2000 | 850 | 700
5L4 | PCN SYPN Upgrade | 8-73473 | 2011-12-01 | 8:00 | 2011-12-01 | 20:00 | C | Yes |  | 2850 | 3150
CHP 5CX1 | Station work | 8-75045 | 2011-12-06 | 8:00 | 2011-12-08 | 16:00 | C |  |  | 2000 | 2400
MDN 12RX32 and 12RX31 | disconnect replacement | 8-76251 | 2011-12-06 | 9:00 | 2011-12-09 | 17:00 | C |  |  | 2000 | 2400
WSN 5RX3 | Repair Oil Leak | 8-76353 | 2011-12-12 | 8:00 | 2011-12-16 | 16:00 | C |  |  | 2000 | 2400