## Annual Plan Extract TTC (BCHydr
Annual Plan Extract (1/24/2023 11:17:48 AM) Warning-This file must be downloaded as File Preview may not show the most recent planned outages
Outage # | Outage Status | AP Outage Title | Outage Purpose | Requested Equipment | Start Date (MM/DD/YYYY HH:MM:SS) | Complete Date (MM/DD/YYYY HH:MM:SS) | Recall Time (Hours) | Outage Type : Continuous /Daily | Path 3 (N->S) ING to CUS (MW) | Path 3 (N->S) BC to US (MW) | Path 3 (S->N)CUS to ING (MW) | Path 3 (S->N) US to BC (MW) | Path 1 BC AB (W->E) BC to AB (MW) | Path 1 (E->W) AB to BC (MW) | Resource Impact | Load Impact | Posted To Plan | Under Review AOP | Revision Date (MM/DD/YYYY HH:MM:SS)
8-00253033 | Implemented | BSY G2 forced out | Synchronous Condensor Forced OOS | BSY G2 | 2016-08-26 00:43 | 2023-03-31 21:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-15 09:51
8-00377962 | Completed | MCA 5RX3 Forced OOS | Forced Outage | MCA 5RX3 | 2019-03-31 11:45 | 2021-03-18 13:55 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-03-18 14:01
8-00430257 | Completed | KLY SC2 oos | Forced Outage | KLY SC2 | 2019-12-20 01:02 | 2021-04-30 12:21 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-30 12:21
8-00429269 | Cancelled | 1L246 OOS | station work | 1L246 | 2020-04-20 08:00 | 2021-05-08 16:00 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2020-04-15 08:08
8-00474722 | Cancelled | 5L71 & 5L72 parallel Operation W/O MCA line end reactors | 5RX3/5RX4 Forced outage Operating Plan | MCA 5RX3, MCA 5RX4 | 2020-09-05 08:00 | 2021-01-01 16:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | N | Y | 2020-08-27 13:05
8-00500872 | Completed | MCA 5RX4 OOS | Forced Outage | MCA 5RX4 | 2020-09-20 08:25 | 2022-10-03 21:25 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-03 21:26
8-00493276 | Cancelled | MCA 5RX4 Forced outage | Forced Outage | MCA 5RX4 | 2020-10-10 08:00 | 2022-04-05 16:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2020-10-05 10:20
8-00428434 | Completed | 1L274 out from BCK to POC | refurbishment | 1L274 (887L) | 2021-01-04 07:00 | 2021-02-04 15:44 | 6 | Continuous | [6 empty] | N | N | N | Y | 2021-02-04 15:44
8-00428473 | Cancelled | 1L201 OOS | station work | 1L201 | 2021-01-04 08:00 | 2021-01-15 08:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2020-11-09 08:04
8-00428405 | Completed | 1L201 OOS | End of life Structure and Timber Replacements | 1L201 | 2021-01-04 12:00 | 2021-01-15 10:49 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2021-01-15 10:49
8-00533482 | Proposed |  |  | WBK T3 | 2021-01-13 08:00 | 2021-01-14 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-01-07 20:07
8-00526189 | Completed | 5L92 OOS | Disconnect repair | CBK 5CB11, CBK 5CB13, 5L92 | 2021-01-16 08:00 | 2021-01-16 15:35 | 2 | Continuous |  |  |  |  | 110 | 300 | N | N | Y | Y | 2021-01-16 15:35
8-00428474 | Cancelled | 1L202 OOS | station work | 1L202 | 2021-01-18 08:00 | 2021-01-29 08:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2020-11-09 08:04
8-00478148 | Cancelled | 2L22 OOS | Replace end-of-life structures | 2L22 | 2021-01-18 08:00 | 2021-01-22 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2020-11-02 07:29
8-00428443 | Completed | 60L270 out from KBY | structure replacement | 60L270 | 2021-01-19 08:00 | 2021-01-26 13:37 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-01-26 13:38
8-00428406 | Completed | 1L202 OOS | End of life Structure and Timber Replacements | 1L202 | 2021-01-19 08:00 | 2021-01-29 16:14 | 5 | Return Weekends | [6 empty] | N | Y | N | Y | 2021-01-29 16:14
8-00427839 | Completed | 2L38 OOOS | MDN 2D2CB11 2D1CB12, 2D27 DS maint. | MDN 2B12, 2L38 | 2021-01-19 08:00 | 2021-01-20 14:55 | 3 | Continuous | [6 empty] | Y | N | Y | Y | 2021-01-21 12:18
8-00429282 | Completed | 2L93 OOS | disconnect work | 2L93, SVA T1, SVA 2B4, SVA 2B5, KLY 2B7 | 2021-01-19 08:00 | 2021-01-22 13:58 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-01-22 13:58
8-00526090 | Completed | BSY T8 OOS | 4B8 PYPN PM (NERC). BSY T28 PN PM. | BSY T8 | 2021-01-19 08:00 | 2021-01-22 14:20 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-22 14:20
8-00527498 | Completed | VIT SC3 OOS | SC3 data collection, measurements & pictures | VIT SC3 | 2021-01-22 08:00 | 2021-01-22 15:53 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-01-22 16:17
8-00527501 | Completed | VIT SC4 OOS | SC4 data collection, measurements & pictures | VIT SC4 | 2021-01-25 08:00 | 2021-01-25 15:25 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-01-25 15:25
8-00533989 | Completed | 1L101 out from BKB, BKB T1 OOS | BKB SSI OSYR & upgrade Sampling port | 1L101, BKB T1 | 2021-01-25 08:00 | 2021-01-25 14:47 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-25 14:47
8-00530793 | Completed | 2L90 OOS | Clearance deficiency on 34-4 to 34-5 | 2L90 | 2021-01-25 13:00 | 2021-01-31 12:24 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-01-31 12:24
8-00524545 | Completed | 1L109 out from VIT to PVO | VIT 1D1CB6 INSP, 1D2CB5 INSP, 1D25 INSP + MOTOR REPL. | VIT 1D1CB6, VIT 1D2CB5, VIT 1D25, 1L109 | 2021-01-26 08:00 | 2021-01-28 14:55 | 5 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-28 14:56
8-00260968 | Completed | BSY G3 OOS | Major Inspection | BSY T3, BSY G3 | 2021-01-29 06:00 | 2021-05-13 12:57 | 960 | Continuous | 2400 | 2800 |  |  |  |  | N | N | Y | Y | 2021-05-13 12:58
8-00522996 | Completed | BSY T7 OOS | required for LOA for work on T3 and T13 | BSY T7 | 2021-01-29 08:00 | 2021-05-07 10:57 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-13 06:26
8-00306089 | Cancelled | BSY Synchronous Condenser (G3) OOS | Inspection and Exciter Mtce | BSY G3 | 2021-02-01 07:00 | 2021-02-05 20:00 | 72 | Continuous | 2400 | 2800 |  |  |  |  | N | N | Y | Y | 2020-10-15 13:31
8-00438281 | Cancelled | CK5 5CB1, 5D2CB1, 5CT1 OOS | Inspections and Doble Test | CK5 5CB1 | 2021-02-01 08:00 | 2021-02-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-19 10:34
8-00495777 | Completed | CYP T2 OOS | PCB Bushing Replacement | CYP T2 | 2021-02-01 08:00 | 2021-04-01 17:16 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-01 17:16
8-00399798 | Completed | 5L72 OOS | For new MCA 5RX3 testing & commissioning | 5L72, MCA 5CB7, MCA 5CB9, MCA 5RX3 | 2021-02-01 22:00 | 2021-02-10 11:15 | 6 | Continuous | [6 empty] | Y | N | Y | Y | 2021-03-18 13:55
8-00529926 | Completed | 5L72 OOS | Replacement of Spacers and Marker Balls | 5L72 | 2021-02-02 10:00 | 2021-02-10 11:14 | 6 | Continuous | [6 empty] | Y | N | Y | Y | 2021-02-10 11:14
8-00543610 | Completed | 1L102, JHT 1B9 OOS | Repair drop between 1L102 and JHT 1D24. | 1L102, JHT 1B9 | 2021-02-05 08:00 | 2021-02-05 14:18 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-02-05 14:22
8-00438283 | Cancelled | CKY T6 OOS | Inspections, NON-ELE PN, PYPN | CKY T6 | 2021-02-09 08:00 | 2021-02-09 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-01-19 10:35
8-00533392 | Cancelled | 2L13 OOS | Circuit Refurbishment | 2L13 | 2021-02-10 08:00 | 2021-03-05 16:00 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-04 14:33
8-00537767 | Completed | 2L13 OOS | change out end of life structures on 2L13 inside the Capilano Watershed | 2L13 | 2021-02-10 08:00 | 2021-03-05 17:28 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-05 17:50
8-00430381 | Completed | JHT 1CB1 OOS | Rebuild | JHT 1CB1 | 2021-02-12 08:00 | 2021-03-03 13:42 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-03 13:59
8-00546134 | Approved | KMO band 7/8 OOS | RTA work | KMO BANK 7/8 | 2021-02-14 12:00 | 2021-02-28 11:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-16 09:44
8-00546812 | Completed | 5L72 OOS | marker ball replacement | 5L72 | 2021-02-16 08:00 | 2021-02-26 16:50 | 6 | Continuous | [6 empty] | Y | N | Y | Y | 2021-02-26 16:51
8-00438553 | Completed | 2L42, TIS 2CVT22 Outage | Inspections and Test | TIS 2CB3, TIS 2CB2, 2L42 | 2021-02-16 08:00 | 2021-02-20 16:36 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-02-20 16:37
8-00482322 | Completed | 60L43 and Ki2 T2 OOS | REPLACE 60DCB6, 60CB6, INSTALL 60SA24 | KI2 T2, 60L43, KI2 60B5 | 2021-02-16 10:00 | 2021-03-08 11:15 | 4 | Continuous | [6 empty] | N | Y | N | Y | 2021-03-08 11:15
8-00428444 | Completed | 60L283 Out from CBK | structure replacement | 60L283 | 2021-02-17 08:00 | 2021-02-17 13:25 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-02-17 13:25
8-00433610 | Cancelled | PAL T12, 1CB5 OOS | PAL T12 LTC INSP, NON-EL TRIPS | PAL 1CB5, PAL T12 | 2021-02-22 08:00 | 2021-02-24 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-03 09:39
8-00438290 | Cancelled | CK5 5MB2, 5CB21, 5CT21 OOS | Inspections and Doble Test | CK5 5CB21, CK5 5CB22, CK5 5CB23, CK5 5MB2 | 2021-02-22 08:00 | 2021-02-28 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-19 10:36
8-00523069 | Completed | 2L13 OOS | Structure replacement | 2L13 | 2021-02-22 08:00 | 2021-03-05 17:51 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-03-05 17:51
8-00519033 | Completed | 2L294 Out from NLY | Replace end-of-life structures and timbers. | 2L294 | 2021-02-22 08:00 | 2021-02-22 21:17 | 4 | Continuous |  |  |  |  | 850 | 500 | N | N | Y | Y | 2021-02-25 15:19
8-00549696 | Cancelled | 5L83 OOS | Emergency work: Repair damaged conductor on 5L83 structure 77-2 | 5L83 | 2021-02-22 09:00 | 2021-02-24 16:00 | 3 | Continuous | [6 empty] | Y | N | Y | Y | 2021-02-21 12:04
8-00430598 | Cancelled | JHT 1CT8 OOS | JHT 1CT 8 RBLD, prepare for removal | JHT 1CB8 | 2021-02-24 08:00 | 2021-02-24 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-04 09:22
8-00426685 | Completed | PIK 2CB15 OOS | PIK 2CB15 PVIN , work with power tech | PIK 2CB15 | 2021-02-24 08:00 | 2021-02-24 13:53 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-24 13:53
8-00430599 | Cancelled | JHT 1MB1, 1CB8 OOS | JHT 1CT 8 RBLD, remove from Crane | JHT 1CB8, JHT 1MB1 | 2021-02-25 08:00 | 2021-02-25 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-04 09:22
8-00430600 | Cancelled | JHT 1CT8 OOS | JHT 1CT 8 RBLD, rebuild | JHT 1CB8 | 2021-02-26 08:00 | 2021-03-04 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-04 09:23
8-00546568 | Completed | GMS 5RX2 oos | Top up Conservator Tanks | GMS 5RX2 | 2021-02-27 07:00 | 2021-02-27 15:44 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-02-27 15:44
8-00526397 | Completed | 1L105 OOS from DMR | Test energization of DMR 1CVT2 and 1CT2 | 1L105, DMR 1CB2 | 2021-02-27 08:00 | 2021-02-27 14:05 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-27 14:05
8-00433376 | Completed | PML T2 OOS | PML T2 TFR & LTC INSP | PML T2 | 2021-02-28 09:00 | 2021-03-16 11:24 | 24 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-16 11:24
8-00429795 | Cancelled | KDY 5CX3 oos | INSP/MNRI PN | KDY 5CX3 | 2021-03-01 08:00 | 2021-03-29 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-02-23 09:29
8-00420387 | Cancelled | BSY Synchronous Condenser (G3) OOS | Protection Upgrades | BSY G3 | 2021-03-01 08:00 | 2021-03-26 16:00 | 336 | Continuous | 2400 | 2800 |  |  |  |  | N | N | Y | Y | 2020-10-15 13:40
8-00427322 | Cancelled | 2L64 OOS | Q3 & Q4 Maintenance - Detailed | 2L64 | 2021-03-01 08:00 | 2021-03-05 16:00 | 2 | Return Evenings | [6 empty] | N | N | Y | Y | 2021-03-03 07:44
8-00501174 | Completed | 2L142 OOS | Detailed Inspection | GTP T14, 2L142 | 2021-03-01 08:00 | 2021-03-04 17:48 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-03-04 17:57
8-00427213 | Cancelled | 5L98 OOS | Disconnect Switch Inspections | NIC 5B15, NIC 5B25, NIC 5RX11, 5L98, VAS 5RX1, VAS 5B11 | 2021-03-02 08:00 | 2021-03-05 16:00 | 2 | Continuous |  |  |  |  | 560 | 450 | N | N | N | Y | 2021-01-13 15:37
8-00433388 | Cancelled | DMR 1CB16 | Inspection | DMR 1CB16 | 2021-03-02 08:00 | 2021-03-03 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2020-08-11 13:08
8-00437864 | Completed | VIT T9 and SC4 OOS | PCB Bushing Replacement Program | VIT SC4, VIT T9 | 2021-03-02 08:00 | 2021-04-16 18:06 | 120 | Continuous | [6 empty] | N | N | N | Y | 2021-04-16 23:42
8-00433622 | Completed | PAL 1CB10 OOS | PAL 1CB10 PVIN | PAL 1CB10 | 2021-03-02 09:00 | 2021-03-02 19:53 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-02 19:53
8-00430056 | Cancelled | 1L374 oos | Str Repl | 1L374 | 2021-03-03 08:00 | 2021-03-04 16:00 | 2 | Return Evenings | [6 empty] | N | N | N | Y | 2021-02-26 13:27
8-00433389 | Cancelled | DMR 1CB17 OOS | Inspection | DMR 1CB17 | 2021-03-04 08:00 | 2021-03-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2020-08-11 13:07
8-00430604 | Cancelled | JHT 1CT8 OOS | JHT 1CT 8 RBLD, test and commissioning | JHT 1CB8 | 2021-03-05 08:00 | 2021-03-11 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-04 09:23
8-00430605 | Cancelled | JHT 1MB1, 1CB8 OOS | JHT 1CT 8 RBLD, install with crane | JHT 1CB8, JHT 1MB1 | 2021-03-05 08:00 | 2021-03-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-04 09:23
8-00433387 | Cancelled | DMR SVC OOS | SVC, T8 1CB16 & 1CB17 INSP | DMR SVC | 2021-03-08 08:00 | 2021-03-12 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2020-03-13 15:43
8-00439115 | Cancelled | CBN 2CB5 OOS | COMPLETE INSP / DOBLE AND HYDRAULIC HOSES, CPC - BFPN | CBN 5CB8 | 2021-03-08 08:00 | 2021-03-18 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-05 09:34
8-00444290 | Completed | BSY 2CB6, 2CB7 OOS | BSY 2D3 inspection | BSY 2CB6, BSY 2CB7, BSY G3 | 2021-03-08 08:00 | 2021-03-27 11:12 | 48 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-07 09:39
8-00427315 | Cancelled | 2L51 OOS | Q3 & Q4 Maintenance - Overview | 2L51 | 2021-03-08 08:00 | 2021-03-09 16:00 | 2 | Return Evenings | [6 empty] | N | N | Y | Y | 2021-02-23 08:40
8-00426656 | Completed | 2L145 OOS | ESQ 2D22, 2D2, 2D2CB2, 2D1CB3 INSP | 2L145, ESQ 2D22, ESQ 2D2CB2, ESQ 2D1CB3, ESQ 2B2, ESQ 2CB3, ESQ 2D2, ESQ T2 | 2021-03-08 08:00 | 2021-03-09 18:55 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-03-12 15:13
8-00438289 | Completed | CK5 5MB1 OOS | Disconnect Repair and Mtce work | CK5 5MB1 | 2021-03-08 08:00 | 2021-03-14 18:39 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-30 03:30
8-00526161 | Proposed | 1L105 OOS | End of Life Structure Replacements | 1L105 | 2021-03-08 08:00 | 2021-03-11 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2020-12-11 15:01
8-00555865 | Completed | 2L295 OOS | PT replacement | 2L295, KCL 2CB5, KCL 2CB6 | 2021-03-08 08:00 | 2021-03-31 17:36 | 336 | Continuous | [6 empty] | N | N | N | Y | 2021-03-31 17:37
8-00539277 | Denied | 2L295 OOS | PT replacement | 2L295, KCL 2CB5, KCL 2CB6 | 2021-03-08 08:00 | 2021-03-26 16:00 | 336 | Continuous | [6 empty] | N | N | N | Y | 2021-03-04 15:54
8-00526901 | Completed | BRT T4 OOS | Maintenance work on BRT T4 | 2L19, BRT T4, BRT 3B5, BRT 2B4 | 2021-03-08 13:00 | 2021-03-11 14:47 | 3 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-03-27 03:30
8-00495812 | Completed | 60L22 and 60L21 Out from BR1, and BR1 T3/T30 OOS | BR1 OSP Stage 6D | BR1 60B1, 60L21, 60L22, BR1 T3, BR1 T30, BR1 60B2 | 2021-03-08 13:00 | 2021-03-11 18:47 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-06-15 16:32
8-00464149 | Completed | MCA 5RX4 OOS | Replacement Project of 5RX4 all phases | MCA 5RX4 | 2021-03-09 07:00 | 2022-10-03 21:25 | 12000 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-10-03 21:26
8-00552508 | Completed | 5L83 OOS | Replace broken spacers and unroll conductor bundle | 5L83 | 2021-03-09 08:00 | 2021-03-10 15:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-10 15:01
8-00485157 | Cancelled |  |  | ANN T2 | 2021-03-15 07:00 | 2021-04-06 16:00 | 6 | Continuous | [6 empty] | N | N | N | Y | 2021-01-27 11:27
8-00427317 | Cancelled | 2L53 OOS | Q3 & Q4 Maintenance - Overview | 2L53 | 2021-03-15 08:00 | 2021-03-19 16:00 | 2 | Return Evenings | [6 empty] | N | N | Y | Y | 2020-09-11 13:47
8-00523200 | Denied | 2L63, SYH T3 OOS | Replace ARN 2CVT14 | SYH T3, 2L63 | 2021-03-15 08:00 | 2021-03-22 08:00 | 24 | Continuous | [6 empty] | N | Y | N | Y | 2021-03-09 10:38
8-00451693 | Completed | 5L52 OOS | BPA Requested Outage (Insulator Replacvements) | 5L52 | 2021-03-16 07:00 | 2021-03-16 16:10 | 2 | Continuous | 2400 | 2800 | 1500 | 1900 |  |  | N | N | Y | Y | 2021-03-16 17:42
8-00483278 | Cancelled | 5L51 OOS | BPA Requested Outage (Insulator Replacvements) | 5L51 | 2021-03-17 07:00 | 2021-03-18 17:00 | 2 | Continuous | 2400 | 2800 | 1500 | 1900 |  |  | N | N | Y | Y | 2021-01-06 12:52
8-00560578 | Completed | SYA 5CX1 Forced OOS | Forced Outage | SYA 5CX1 | 2021-03-18 00:30 | 2021-07-26 12:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-26 12:02
8-00497257 | Completed | 2L9 & LYN T1 OOS | Replacement of LYN 2D1CB2 | LYN 2CB2, LYN T1, 2L9 | 2021-03-19 08:00 | 2021-03-29 15:32 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2021-03-29 15:32
8-00561437 | Completed | MCA 5RX3 Forced OOS | Forced Outage | MCA 5RX3 | 2021-03-19 10:18 | 2021-03-24 13:42 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-03-24 13:42
8-00455798 | Completed | AMC 5CX1 OOS | AMC PN upgrade project | AMC 5CX1 | 2021-03-22 07:00 | 2021-03-29 11:56 | 72 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-14 03:30
8-00509129 | Completed | 2L44 OOS | Overview Inspection. | 2L44 | 2021-03-22 08:00 | 2021-03-25 15:05 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-03-25 15:05
8-00523249 | Denied | 2L63, ARN 2CVT14 OOS | Test 2CVT14 | 2L63 | 2021-03-22 08:00 | 2021-03-26 16:00 | 24 | Continuous | [6 empty] | N | Y | N | Y | 2021-03-09 10:39
8-00554482 | Completed | 5L71 and 5L72 OOS | MCA Blackstart testing | 5L71, 5L72, 60L223 | 2021-03-27 09:00 | 2021-03-29 09:29 | 1 | Continuous | 2000 | 2400 |  |  |  |  | N | N | N | Y | 2021-03-29 09:30
8-00563024 | Completed | MCA LS3, 5B5 OOS | MCA LS3/5B5 OOS for listed equipment maintenance | MCA LS3, MCA 5B5 | 2021-03-28 21:00 | 2021-04-13 23:54 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-13 23:55
8-00432382 | Completed | MDN T3 OOS | LOA outage for T3 Firewall Installation | MDN 12RX31, MDN 12RX32, MDN T3 | 2021-03-29 07:00 | 2021-04-30 11:57 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-30 12:01
8-00451181 | Cancelled | 5L81 OOS | PN upgrade project | 5L81, ING 5CB9, ING 5CB10, NIC 5CB14, NIC 5CB24 | 2021-03-29 08:00 | 2021-04-02 16:00 | 2 | Continuous | 1950 | 2350 |  |  |  |  | N | N | N | Y | 2021-01-06 13:56
8-00451184 | Completed | 5L81 OOS | PN upgrade project | 5L81, ING 5CB9, ING 5CB10, AMC 5CX1, NIC 5CB14, NIC 5D30, NIC 5CB24 | 2021-03-29 08:00 | 2021-04-02 14:56 | 2 | Continuous | 1950 | 2350 |  |  |  |  | N | N | N | Y | 2021-04-02 21:43
8-00462485 | Cancelled | 5L81 OOS | PN upgrade project | 5L81 | 2021-03-29 08:00 | 2021-04-02 16:00 | 8 | Continuous | 1950 | 2350 |  |  |  |  | N | N | N | Y | 2021-03-25 10:35
8-00526996 | Completed | 60L1 OOS, COK 60CB1, 60CB8 OOS COK 60B1 OOS | COK 60D20, 60D1CB8, 60D1CB1 60VT1 Inspections | 60L1, COK 60B1 | 2021-03-29 08:00 | 2021-03-31 14:25 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-03-31 14:26
8-00538533 | Cancelled | 5L81 OOS | Install/terminate new 5CX1, 5D21, 5BP1, 5D31, 5BPCB1, 5CVT1 AC/DC control cables | 5L81, AMC 5D21 (3), AMC 5D31 (3) | 2021-03-29 08:00 | 2021-04-02 16:00 | 6 | Continuous | 1950 | 2350 |  |  |  |  | N | N | N | Y | 2021-03-25 10:36
8-00537471 | Completed | HWW 1MB4 OOS | 1D2CB12, 1D2CB17, 1CB12 INSP, CBCN | HWW 1D2CB12, HWW 1CB12, HWW 1MB4, HWW 1D2CB17 | 2021-03-29 08:00 | 2021-03-29 16:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-29 19:40
8-00480100 | Completed | 2L3 Out From HPN | Install new LED lights on all four corners of lattice work associated with 2B2 | HPN 2CB2, HPN 2CB3, 2L3, HPN 2B2 | 2021-03-30 07:30 | 2021-04-01 17:33 | 4 | Continuous | [6 empty] | Y | N | N | Y | 2021-04-01 17:33
8-00435473 | Cancelled | SEA T1 OOS | PCB Bushing Replacement Program | SEA T1 | 2021-03-30 08:00 | 2021-04-30 16:00 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-02 13:50
8-00525389 | Cancelled | ANN T3 OOS - DUPLICATE ENTRY IN AOP SPREADSHEET - USE 8-00525385 SEPT 21 - OCT 22 | PCB Bushing Replacement Program | ANN T3 | 2021-03-30 08:00 | 2021-04-30 17:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2020-12-16 14:16
8-00537472 | Completed | HWW 1MB3 OOS | 1D1CB17, 1D2CB4, 1D2CB5, 1CB4, 1CB5 INSP, CBCN | HWW 1D2CB5, HWW 1CB5, HWW 1D2CB4, HWW 1CB4, HWW 1D1CB17 | 2021-03-30 08:00 | 2021-04-01 12:57 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-01 12:57
8-00551052 | Cancelled | MCA LS1,5B9 OOS | Prepare for T3 Replacement project support | 5L71, MCA 5B9, MCA LS1 | 2021-03-30 22:00 | 2021-03-30 22:30 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-30 15:21
8-00562807 | Cancelled | 1L218 OOS from SAM 1D21 to END 1D22 | replace insulators on dead-end structure | 1L218 | 2021-03-31 09:00 | 2021-03-31 15:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-29 08:29
8-00506397 | Completed | 5L51 OOS | BPA outage | 5L51 | 2021-04-01 06:30 | 2021-04-01 12:54 | 2 | Continuous | 2400 | 2800 | 1500 | 1900 |  |  | N | N | Y | Y | 2021-04-01 13:02
8-00508929 | Cancelled | MCA LS2 | Demo of GIS Bus | MCA LS2 | 2021-04-02 20:00 | 2021-04-10 17:00 | 24 | Continuous | [6 empty] | Y | N | N | Y | 2021-02-22 15:53
8-00493912 | Completed | HPN 2B3, T4, T7 OOS | RE/RE HPN 2D4 | HPN T4, HPN 2B3, HPN T7 | 2021-04-06 07:00 | 2021-04-26 15:31 | 4 | Continuous | [6 empty] | N | Y | N | Y | 2021-04-26 15:32
8-00493914 | Completed | 60L76 OOS | RE/RE of HPN 2D4 | 60L76 | 2021-04-06 07:00 | 2021-04-08 15:11 | 3 | Continuous | [6 empty] | N | Y | N | Y | 2021-04-08 15:11
8-00525384 | Cancelled | BND T2 OOS | PCB Bushing Replacement Program | BND T2 | 2021-04-06 08:00 | 2021-05-14 17:00 | 120 | Continuous | [6 empty] | N | Y | N | Y | 2021-04-06 14:17
8-00525194 | Completed | ARN T9, 60D9, 60D2CB3 OOS | TX Insp/Doble/CPC non-eles | ARN T9 | 2021-04-06 08:00 | 2021-04-16 15:54 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-04-16 15:54
8-00525242 | Completed | 5L52 OOS | Disconnect Maintenanceof ING 5GD25 | ING 5CB5, ING 5CB6, ING 5B5, 5L52 | 2021-04-06 08:00 | 2021-04-08 10:50 | 2 | Continuous | 2400 | 2800 | 1500 | 1900 |  |  | N | N | Y | Y | 2021-04-08 10:52
8-00525246 | Completed | MDN 5CB3 OOS | CPC control testing | MDN 5CB3 | 2021-04-06 08:00 | 2021-04-07 16:11 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-07 16:11
8-00529424 | Denied | 2L340, SGB 2B6 oos | Repair Failed Aux Contact SGB 2CB12, 2VT12 | SGB 2B6, 2L340 | 2021-04-06 08:00 | 2021-04-07 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-03-31 17:47
8-00533472 | Completed | END T1 OOS | END T1 NON-ELE PM | END T1 | 2021-04-06 08:00 | 2021-04-06 14:47 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-06 14:47
8-00533387 | Completed | 1L209 Out from from STO to CHS | STO T1 non-ELE, 1D1 INSP | 1L209, STO T1 | 2021-04-06 08:00 | 2021-04-07 11:53 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-07 11:53
8-00549155 | Completed | CBK T3 OOS | CBK 12RX13 replacement | CBK T3 | 2021-04-06 08:00 | 2021-04-09 12:03 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-16 14:54
8-00537850 | Completed | HWW 1CB6 OOS | HWW 1CB6 CN | HWW 1CB6 | 2021-04-06 08:00 | 2021-04-06 14:18 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-06 14:19
8-00533624 | Cancelled | UHT 3B5, 3CB2 OOS | TIE IN NEW BTR IPP, PM INSPECTION, TRIP TESTING | UHT 3D1CB2, UHT 3CB2, UHT 3B5 | 2021-04-06 08:00 | 2021-04-09 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-31 10:14
8-00533625 | Cancelled | UHT 3CB31, 3RX1 OOS | PM INSPECTIONS, PY/SY PN, RX NON-ELE PN | UHT 3CB31, UHT 3RX1 | 2021-04-06 08:00 | 2021-04-09 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-31 11:45
8-00536169 | Cancelled | ALZ T4 OOS | PCB Bushing Replacement Program | ALZ T4 | 2021-04-06 08:00 | 2021-05-14 16:00 | 120 | Continuous | [6 empty] | N | Y | Y | Y | 2021-03-30 08:32
8-00537074 | Cancelled | DMR T4, 2CB26 OOS | PN-2CB26 CN | DMR 2CB26, DMR T4 | 2021-04-07 08:00 | 2021-04-07 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-30 09:46
8-00537474 | Cancelled | HWw 1CB12 OOS | INSP | HWW 1CB12 | 2021-04-07 08:00 | 2021-04-09 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-09 09:30
8-00540029 | Completed | SAY T2 OOS | SAY T2 Non-electrical protection testing | SAY T2 | 2021-04-07 08:00 | 2021-04-07 16:30 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-07 22:30
8-00531456 | Completed | PCA T1 oos | PCA T1 Non-Elec PN PM | PCA T1 | 2021-04-07 08:00 | 2021-04-07 15:19 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-07 15:19
8-00531457 | Completed | PCA T2 oos | PCA T2 Non-Elec PN PM | PCA T2 | 2021-04-08 08:00 | 2021-04-08 17:18 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-08 17:18
8-00533390 | Completed | 1L209 out from SAM to STO | STO T2 non-ELE, 1D2 INSP | 1L209, STO T2 | 2021-04-08 08:00 | 2021-04-09 12:02 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-09 12:02
8-00527454 | Completed | 60L43 OOS | Detailed Inspection & Oil Sample | SEA T2, 60L43 | 2021-04-08 08:00 | 2021-04-12 14:36 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-12 14:37
8-00537073 | Completed | 1L134, GLD 1Cb1, 1CB8 OOS | 1D1CB1,1D1CB8, INSP, PN 1CB8 BF | 1L134, GLD 1D1CB1, GLD 1D1CB8, GLD 1CB1, GLD 1CB8, GLD 1D21 | 2021-04-08 08:00 | 2021-04-09 13:04 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-09 13:04
8-00531458 | Completed | PCA T3 oos | PCA T3 Non-Elec PN PM | PCA T3 | 2021-04-09 08:00 | 2021-04-09 13:50 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-09 13:50
8-00536908 | Completed | KTG 2CB1/2CB2 OOS | KTG 2CB1 CN PM | KTG 2CB1 | 2021-04-12 07:00 | 2021-04-12 11:45 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-12 11:45
8-00536795 | Completed | CBK 2CB6 | CPC Protection testing | CBK 2CB6 | 2021-04-12 08:00 | 2021-04-12 16:26 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-12 16:26
8-00533626 | Cancelled | UHT 3CB34, 3RX4 OOS | PM INSPECTIONS, PY/SY PN, RX NON-ELE PN | UHT 3CB34, UHT 3RX4 | 2021-04-12 08:00 | 2021-04-16 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-09 12:53
8-00537837 | Completed | HWW 1CB3 OOS | INSP | HWW 1CB3 | 2021-04-12 08:00 | 2021-04-14 13:51 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-14 13:51
8-00539598 | Completed | WLT T3, 2B3 OOS | WLT INSULATOR DEFICIENCY | WLT 2B3, WLT T3 | 2021-04-12 08:00 | 2021-04-16 15:37 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-16 15:38
8-00531453 | Completed | BVY T10 | BVY-T10 NON-ELE PN | BVY T10 | 2021-04-12 08:00 | 2021-04-12 15:40 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-12 15:40
8-00531203 | Completed | SKA 2CB7 oos | SKA CB CT Insp | SKA 2CB7 | 2021-04-12 08:00 | 2021-04-16 11:53 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-16 11:53
8-00527025 | Completed | CSN 2CB2 OOS | 2CB2 Inspections & Dobles. Disconnect Inspections. 2CB3 CPC CN Testing | CSN 2CB2 | 2021-04-12 08:00 | 2021-04-26 14:43 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-26 14:43
8-00526997 | Completed | 60L18 OOS, COK 60CB2 OOS, COK 60CB1 OOS, COK 60B2 OOS | COK 60CB1 Inspection, COK 60D21, 60D2CB1, 60D1CB2, 60VT2 Inspections | COK 60B2, 60L18 | 2021-04-12 08:00 | 2021-04-16 15:59 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-16 15:59
8-00526047 | Completed | vnt t12 oos | pcb bushing replacement | VNT T12 | 2021-04-12 08:00 | 2021-05-21 14:54 | 24 | Continuous | [6 empty] | N | N | N | Y | 2021-05-21 15:03
8-00525247 | Completed | MDN 5CB4 OOS | CPC control testing | MDN 5CB4, MDN 5CB7, MDN 5CB6 | 2021-04-12 08:00 | 2021-04-14 16:23 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-14 16:24
8-00518747 | Completed | 2L33 OOS | Overview & Oil Sample | 2L33 | 2021-04-12 08:00 | 2021-04-14 09:18 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-14 09:21
8-00518610 | Completed | 1L246 OOS | life structure replacement | 1L246 | 2021-04-12 08:00 | 2021-04-23 17:27 | 4 | Continuous | [6 empty] | Y | N | N | Y | 2021-04-23 17:27
8-00462495 | Completed | NIC 5CB14 OOS | 5L81 SYPN Replacement | NIC 5CB14 | 2021-04-12 08:00 | 2021-04-16 14:53 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-19 11:07
8-00456652 | Completed | ING 5CB10 OOS | For 5L81 SYPN Replacement | ING 5CB10 | 2021-04-12 08:00 | 2021-04-14 09:30 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-14 10:00
8-00482064 | Cancelled |  |  | KI2 60CB1 | 2021-04-13 07:00 | 2021-05-03 17:00 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-04-13 13:08
8-00536909 | Completed | KTG 2CB3/2CB4 OOS | KTG 2CB3/2CB4 CN PM | KTG 2CB3 | 2021-04-13 07:00 | 2021-04-13 10:39 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-13 14:50
8-00531454 | Completed | BVY T11 oos | BVY T11 Non-Elec PN PM | BVY T11 | 2021-04-13 08:00 | 2021-04-13 12:14 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-13 12:14
8-00567413 | Completed | MCA switching - to return G5 back onto LS3 for voltage control | switching G5 to LS3 | 5L71, 5L72, MCA 5B6, 60L223, MCA LS1, MCA LS2, MCA LS3, MCA 5B5 | 2021-04-13 22:00 | 2021-04-13 23:54 | 1 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | N | Y | 2021-04-13 23:55
8-00536901 | Completed | 2L145 out from ESQ | Required due to ESQ 2CB3 OPEN for ESQ 2CB3 CN PM | ESQ 2CB3 | 2021-04-14 08:00 | 2021-04-14 13:21 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-04-14 13:22
8-00537468 | Completed | 1L116 out from DMR to LTZ | QLC 1D21,1D1CB3,1D1CB1 INSP;T1 NON-EL 1D1 CN 25CB1 BF PN; DMR 1D2CB11 INSP | 1L116, DMR 1D2CB1, QLC 1D1CB1, PVL T1, QLC T1, QLC 1D21 | 2021-04-14 08:00 | 2021-04-15 19:00 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-04-17 01:26
8-00531986 | Completed | FM2 T2 oos | FM2 T2 PCB Bushing Repl | FM2 T2 | 2021-04-14 14:00 | 2021-06-09 12:03 | 144 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-25 03:30
8-00508941 | Completed | 5L71 OOS | MCA switchgear rooftop project | 5L71 | 2021-04-15 07:00 | 2021-06-30 11:37 | 24 | Continuous | 2850 | 3150 | 2500 | 2500 | 850 | 1000 | Y | N | Y | Y | 2021-06-30 11:54
8-00456653 | Completed | ING 5CB9 OOS | 5L81 SYPN Replacement | ING 5CB9 | 2021-04-15 08:00 | 2021-04-21 15:57 | 8 | Continuous | [6 empty] | Y | N | N | Y | 2021-04-21 15:58
8-00531455 | Completed | CHF T10 oos | CHF T10 Non-Elec PN PM | CHF T10 | 2021-04-15 08:00 | 2021-04-15 16:53 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-15 16:54
8-00537848 | Completed | HWW 1CB4 OOS | INSP | HWW 1CB4 | 2021-04-15 08:00 | 2021-04-16 14:08 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-16 14:08
8-00536907 | Completed | HSY 2CB4 OOS | HSY 2CB4 CN PM | HSY 2CB4 | 2021-04-15 08:00 | 2021-04-15 12:33 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-15 12:34
8-00533495 | Completed | SAM T1 OOS | SAM T1 non-ELE PM | SAM T1 | 2021-04-15 08:00 | 2021-04-15 15:52 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-15 15:58
8-00537470 | Cancelled | 1L115 out from DMR to QLC, QLC T2 OOS | RETURN BUS CUT on 1B2 | 1L115, QLC T2 | 2021-04-16 08:00 | 2021-04-16 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-16 16:47
8-00538426 | Completed | VIT SC2 OOS | VIT SC2 Brushgear PM | VIT SC2 | 2021-04-19 08:00 | 2021-05-02 17:24 | 72 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-02 17:24
8-00539989 | Completed | 2L13 OOS | change out end of life structures inside the Capilano Watershed | 2L13 | 2021-04-19 08:00 | 2021-05-03 11:25 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-03 11:29
8-00540144 | Completed | MSA 1B2, 1B3 OOS | MSA 1D2CB2, 1D23, 1D1CB3, 1D2CB3, 1D8, 1D2CB4 Disconnect Maintenance | MSA 1CB4, MSA 1B2, MSA 1B3 | 2021-04-19 08:00 | 2021-04-22 16:29 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-22 16:29
8-00539756 | Completed | WLT 60CB12 OOS | WLT 60CB12 BFPN protection testing | WLT 60CB12 | 2021-04-19 08:00 | 2021-04-19 10:50 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-19 10:54
8-00534993 | Cancelled | MIN T3, 2B4 & 2B5 oos | LNG Project - Commission new T3 protection & Remove old SS2 | MIN T3, MIN 2B4, MIN 2B5 | 2021-04-19 08:00 | 2021-04-23 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-06 09:33
8-00535778 | Proposed | 60L390 out from FLS | FLS 60D1 Overhaul | 60L390 | 2021-04-19 08:00 | 2021-04-19 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-13 14:25
8-00531225 | Proposed | MIN 2CB5 OOS | CB PM | MIN 2CB5 | 2021-04-19 08:00 | 2021-04-19 12:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-30 14:44
8-00533386 | Proposed | 2L13 OOS | Circuit Refurbishment | 2L13 | 2021-04-19 08:00 | 2021-05-03 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-01-19 10:12
8-00525364 | Cancelled | ING T7 OOS | PCB Bushing Replacement Program | ING T7 | 2021-04-19 08:00 | 2021-05-14 16:00 | 120 | Continuous | [6 empty] | N | N | N | Y | 2021-04-12 13:30
8-00539757 | Completed | WLT 60CB13 OOS | WLT 60CB13 BFPN protection testing | WLT 60CB13 | 2021-04-19 11:00 | 2021-04-19 11:06 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-20 17:28
8-00525419 | Completed | 1L143 SOO to CLD | Radial Feed Circuit prioritized for JOR maintainance in F23. Helicopter & Good weather Required | 1L143 | 2021-04-20 05:00 | 2021-04-27 16:35 | 4 | Return Evenings | [6 empty] | N | N | N | Y | 2021-04-27 18:03
8-00525407 | Cancelled | CBN 2CVT5 OOS | EL Inspection | CBN T4, CBN T7, 2L79 | 2021-04-20 08:00 | 2021-04-22 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-02-19 10:30
8-00518749 | Completed | 2L64 OOS | Overview Cable inspections | 2L64 | 2021-04-20 08:00 | 2021-04-22 14:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-04-22 14:00
8-00525257 | Completed | MDN 5CB5 OOS | CPC control testing | MDN 5CB5 | 2021-04-20 08:00 | 2021-04-21 14:55 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-21 14:55
8-00533397 | Completed | DUG T1 OOS | DUG T1 NON-ELE PM | DUG 1CB1, DUG T1, DUG 1CB6 | 2021-04-20 08:00 | 2021-04-20 15:38 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-20 15:39
8-00531226 | Proposed | MIN T3 oos | MIN 2D3 PM | MIN T3 | 2021-04-20 08:00 | 2021-04-20 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-11 10:33
8-00526237 | Completed | CK5 5CB1 OOS | CB TRIP TESTING | CK5 5CB1 | 2021-04-20 08:00 | 2021-04-20 13:21 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-20 13:21
8-00527036 | Completed | MUR 2CB1 OOS | BFPN | MUR 2CB1 | 2021-04-20 08:00 | 2021-04-20 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-21 05:44
8-00529366 | Cancelled | GMS T13 oos | GMS DS and Transf PM | GMS T13 | 2021-04-20 08:00 | 2021-04-26 08:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2020-12-31 15:33
8-00539758 | Completed | WLT 60CB2 OOS | WLT 60CB2 BFPN | WLT 60CB2 | 2021-04-20 08:00 | 2021-04-20 11:03 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-20 12:41
8-00539759 | Completed | WLT 60CB3 | WLT 60CB3 BFPN | WLT 60CB3 | 2021-04-20 08:00 | 2021-04-20 13:13 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-20 14:03
8-00539760 | Completed | WLT 60CB4 OOS | WLT 60CB4 BFPN | WLT 60CB4 | 2021-04-20 08:00 | 2021-04-20 14:14 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-20 14:15
8-00540023 | Completed | 1L37, SAY 1CB5, 1CB6, 1D23 OOS | SAY 1D23, 1D1CB5, 1D2CB6 Inspection | SAY 1CB6, SAY 1CB5, 1L37 | 2021-04-20 08:00 | 2021-04-21 19:04 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-21 19:17
8-00537851 | Completed | HWW 1CB8 OOS | INSP | HWW 1CB8 | 2021-04-20 08:00 | 2021-04-20 10:47 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-20 11:35
8-00537079 | Completed | DMR 1CB5 OOS | PN-1CB5 CN | DMR 1CB5 | 2021-04-20 08:00 | 2021-04-20 11:39 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-20 17:27
8-00537082 | Completed | 1L119 out from DMR and DMR 1CB6 OOS | PN-1CB6 BFPN | 1L119, DMR 1CB6 | 2021-04-21 08:00 | 2021-04-21 15:55 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-21 15:56
8-00537849 | Completed | HWW 1CB5 OOS | INSP | HWW 1CB5 | 2021-04-21 08:00 | 2021-04-23 13:40 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-23 13:40
8-00527037 | Completed | MUR 2CB2 OOS | Control Testing | MUR 2CB2 | 2021-04-21 08:00 | 2021-04-21 15:11 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-21 15:12
8-00526254 | Completed | CK5 5CB21 OOS | CB TRIP TESTING | CK5 5CB21 | 2021-04-21 08:00 | 2021-04-21 09:17 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-21 09:17
8-00456655 | Completed | ING 5CB10 OOS | 5L81 SY PN replacement | ING 5CB10 | 2021-04-21 10:00 | 2021-04-22 15:56 | 8 | Continuous | [6 empty] | N | N | N | Y | 2021-04-22 15:56
8-00526256 | Completed | CK5 5CB3 OOS | CB TRIP TESTING | CK5 5CB3 | 2021-04-22 08:00 | 2021-04-22 16:15 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-22 16:15
8-00527467 | Proposed | 60L41 OOS | Detailed & Terminal Washing | 60L41 | 2021-04-22 08:00 | 2021-04-22 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2020-12-15 19:10
8-00533389 | Cancelled | 2L93 & SVA T1 OOS | SVA T1 inepsctions | 2L93, SVA 1D1, SVA 2D1, SVA T1 | 2021-04-22 08:00 | 2021-04-22 16:00 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-05-21 08:19
8-00537083 | Completed | DMR 1CB7 OOS | PN-1CB7 BFPN | DMR 1CB7 | 2021-04-22 08:00 | 2021-04-22 13:15 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-22 13:15
8-00568376 | Completed | AMC 5CX2 OOS | to place 5D22 and 5D32 in open position and test Auxiliary B contacts | AMC 5CX2, AMC 5D22 (3), AMC 5D32 (3) | 2021-04-22 08:00 | 2021-04-22 11:10 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-08 03:30
8-00573358 | Completed | 5L91 Forced OOS | End time is subject to change | 5L91 | 2021-04-23 07:48 | 2021-04-26 08:09 | 2 | Continuous | 2000 | 2400 |  |  | 560 | 500 | N | N | Y | Y | 2021-04-26 08:28
8-00567391 | Completed | 5L81 OOS | PN Upgrade Project | 5L81, ING 5CB9, ING 5CB10, AMC 5CX1, NIC 5CB14, NIC 5CB24 | 2021-04-26 07:00 | 2021-04-30 16:40 | 2 | Continuous | 1950 | 2350 |  |  |  |  | Y | N | Y | Y | 2021-05-11 11:50
8-00568475 | Completed | 5L81 OOS | 5L81 PN upgrade project | 5L81, ING 5CB9, ING 5CB10, AMC 5CX1, NIC 5CB14, NIC 5CB24 | 2021-04-26 08:00 | 2021-04-30 16:40 | 2 | Continuous | 1950 | 2350 |  |  |  |  | N | N | Y | Y | 2021-05-11 11:50
8-00537864 | Cancelled | HWW 1CB2 OOS | INSP | HWW 1CB2 | 2021-04-26 08:00 | 2021-04-28 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-25 16:06
8-00540024 | Cancelled | SAY T3, 2B5, 2D3 OOS | SAY 2D3, 2D2CB5, 2D2CB6 Inspection | SAY 2CB5, SAY 2CB6, SAY T3 | 2021-04-26 08:00 | 2021-04-28 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-28 09:30
8-00539785 | Completed | HSB T1, 12CB1 OOS | HSB T1 Inspection, Doble, 12CB1 protection testing, SS1 Inspection | HSB T1 | 2021-04-26 08:00 | 2021-05-13 17:26 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-29 03:30
8-00532949 | Denied | 1L37, MSA 1D22 OOS | MSA 1D22, 1D1CB5, 1D2CB6 Inspection | MSA 1CB5, MSA 1CB6, 1L37 | 2021-04-26 08:00 | 2021-04-28 16:00 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-04-21 11:38
8-00526998 | Completed | 60L17 OOS, COK 60CB2, COK 60CB3, COK 60B3 OOS | COK 60CB2 Inspection, COK 60D1CB3, 60D2CB2, 60VT3, 60D22 Inspection | COK 60CB2, COK 60CB3, 60L17, COK 60B3 | 2021-04-26 08:00 | 2021-04-29 15:39 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-29 15:39
8-00456657 | Cancelled | 5L81 OOS | 5L81 PN upgrade project | 5L81, ING 5CB9, ING 5CB10, AMC 5CX1, NIC 5CB14, NIC 5CB24 | 2021-04-26 08:00 | 2021-04-30 16:00 | 8 | Continuous | 1950 | 2350 |  |  |  |  | N | N | N | Y | 2021-04-07 12:32
8-00462509 | Cancelled | 5L81 OOS | 5L81 SY PN upgrade | 5L81 | 2021-04-26 08:00 | 2021-04-30 16:00 | 8 | Continuous | 1950 | 2350 |  |  |  |  | N | N | N | Y | 2021-04-07 12:05
8-00512808 | Completed | 5L77 OOS | Marker ball replacement | 5L77, ACK 5B10 | 2021-04-26 08:00 | 2021-04-29 16:13 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-04-29 16:13
8-00518353 | Completed | 5L77 OOS | station maintenance | 5L77, ACK 5B10 | 2021-04-26 08:00 | 2021-04-30 14:45 | 4 | Continuous | [6 empty] | Y | N | N | Y | 2021-05-03 09:57
8-00525268 | Completed | MDN 5CB6 OOS | CPC control testing | MDN 5CB6 | 2021-04-27 08:00 | 2021-04-28 15:57 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-28 15:58
8-00525237 | Denied | ING 5CB12 OOS | CPC control testing | ING 5CB12 | 2021-04-27 08:00 | 2021-04-29 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-21 09:26
8-00525838 | Denied | NEL T2 OOS | CPC Non-ele | NEL T2 | 2021-04-27 08:00 | 2021-04-27 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-22 09:24
8-00539762 | Approved | WLT 60CB6 OOS | WLT 60CB6 BFPN | WLT 60CB6 | 2021-04-27 08:00 | 2021-04-27 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-23 09:48
8-00549404 | Completed | 5L94 outage (AltaLink) | X-ray for structure | 5L94 / 1201L | 2021-04-28 06:00 | 2021-04-29 13:44 | 2 | Return Evenings |  |  |  |  | 50 | 100 | N | N | Y | Y | 2021-04-29 13:44
8-00539755 | Approved | WLT 60CB1 OOS | WLT 60CB1 BFPN protection testing | WLT 60CB1 | 2021-04-28 08:00 | 2021-04-28 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-19 08:25
8-00527038 | Denied | SPG 2CB1 OOS | CPC Control Testing | SPG 2CB1 | 2021-04-28 08:00 | 2021-04-28 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-22 15:01
8-00531450 | Proposed | WLM T2 oos | WLM T2 Non-Elec PN PM | WLM T2 | 2021-04-28 08:00 | 2021-04-28 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-02 20:36
8-00429875 | Cancelled | GMS 5B5 oos | GMS CB and DS Insp | GMS 5B5, GMS 5CB5, GMS 5CB6 | 2021-04-29 08:00 | 2021-04-29 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-08 09:37
8-00540146 | Completed | MSA 2B7, 2D8 OOS | MSA 2D2CB8, 2D8 Inspection | MSA 2D2CB8, MSA 2D8, MSA 2B7 | 2021-04-29 08:00 | 2021-04-30 15:32 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-30 15:32
8-00429835 | Completed | 2L123, HWW T1 OOS | HWW 2D23 and 2CB5 work | HWW T1, 2L123 | 2021-04-30 08:00 | 2021-04-30 15:08 | 2 | Continuous | 1830 | 2230 |  |  |  |  | Y | N | Y | Y | 2021-04-30 15:08
8-00512981 | Completed | AMC 5CX1 OOS | CPC BFPN, EL MJRI/MNRI inspection, CB inspection | AMC 5CX1, AMC 5BPCB1 | 2021-04-30 15:00 | 2021-05-10 18:14 | 6 | Continuous | [6 empty] | Y | N | Y | Y | 2021-05-11 11:50
8-00541892 | Denied | 2L40 Out From BND 2D22 to BND 2D21, BND T1, 12B11, 12B1 OOS | LTC overhaul, Doble and Inspections | BND T1 | 2021-04-30 17:00 | 2021-05-13 16:00 | 48 | Continuous | [6 empty] | N | N | N | Y | 2021-03-11 11:09
8-00544334 | Cancelled | VIT SC3 OOS | Upgrade exciter and controls | VIT SC3 | 2021-05-01 08:00 | 2021-06-30 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-08 09:31
8-00433586 | Cancelled | DMR T5, 1CB12 OOS | DMR 1CB12 REPL | DMR T5, DMR 1CB12 | 2021-05-01 08:00 | 2021-05-31 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-15 09:24
8-00542759 | Completed | 2L76 OOS | installation of new footing | MLN T6, MLN T5, 2L76 | 2021-05-03 07:00 | 2021-05-14 17:49 | 2 | Return Evenings and Weekends | [6 empty] | Y | Y | Y | Y | 2021-05-14 18:35
8-00567741 | Completed | DMR SVC OOS | DMR SVC INSP and T8 Non EL PN | DMR T8, DMR SVC | 2021-05-03 08:00 | 2021-05-07 16:56 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-05-07 16:56
8-00537092 | Cancelled | DMR 1D2 OOS | DMR 1D2 replacement | DMR 1D2 | 2021-05-03 08:00 | 2021-05-06 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-09 08:02
8-00539671 | Approved | NVR 60CB1 OOS | NVR 60CB1 COND. Protection testing | NVR 60CB1 | 2021-05-03 08:00 | 2021-05-03 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-26 14:50
8-00530617 | Proposed | 2L95 | DE Str Repl | 2L95 | 2021-05-03 08:00 | 2021-05-13 16:00 | 2 | Return Weekends | [6 empty] | N | N | Y | Y | 2021-03-16 13:30
8-00482068 | Completed | 60L37, 60L45, KI2 60B1 OOS | CREATE TEMP BUS CUT | 60L45, 60L37, KI2 60B1 | 2021-05-04 07:00 | 2021-05-05 18:18 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-05 18:18
8-00512801 | Completed | 5L71 OOS | marker ball replacement (recall time: 3 hours) | 5L71 | 2021-05-04 08:00 | 2021-05-07 16:08 | 3 | Continuous | 2850 | 3150 | 2500 | 2500 | 850 | 1000 | N | N | N | Y | 2021-06-30 11:54
8-00428335 | Cancelled | PCB Bushing Replacement Project - SEA T2 | Replace PCB oil bushings | SEA T2 | 2021-05-04 08:00 | 2021-06-04 08:00 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-02 13:51
8-00513981 | Completed | 5L71 OOS | Spacers, Markerballs and Arcing Horns (recall time 6 hours) | 5L71 | 2021-05-04 08:00 | 2021-05-31 08:14 | 6 | Continuous | 2850 | 3150 | 2500 | 2500 | 850 | 1000 | Y | N | Y | Y | 2021-06-30 11:54
8-00518753 | Proposed | 2L39 OOS | Overview | 2L39 | 2021-05-04 08:00 | 2021-05-07 16:00 | 2 | Return Evenings | [6 empty] | N | N | N | Y | 2020-12-09 10:39
8-00525209 | Completed | ING 5CB4 OOS | CPC BFPN PM | ING 5CB4 | 2021-05-04 08:00 | 2021-05-06 16:38 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-06 16:38
8-00525191 | Completed | ARN 2CB2 OOS | CPC breaker fail PN PM | ARN 2CB2 | 2021-05-04 08:00 | 2021-05-04 15:09 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-04 15:09
8-00525316 | Cancelled | HWW T1 OOS | HWW T1, SS1, 2CVT23, 2CB5, 1D1, 1D1CB3, 1D2CB2, 1CB2, 1CB3 inspection | HWW 1B2, HWW T1, 2L123 | 2021-05-04 08:00 | 2021-05-22 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-30 13:05
8-00531104 | Cancelled | CWD T2, 25CB2 oos | CB PM and Doble | CWD T2 | 2021-05-04 08:00 | 2021-05-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-29 14:56
8-00530673 | Proposed | KDY 5CX1 oos | CX PM | KDY 5CX1 | 2021-05-04 08:00 | 2021-05-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2020-12-29 16:16
8-00527039 | Completed | SPG 2CB2 OOS | CPC BFPN PM | SPG 2CB2 | 2021-05-04 08:00 | 2021-05-04 14:10 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-04 14:10
8-00527465 | Completed | 60L17 NWR OOS | Detailed | 60L17 | 2021-05-04 08:00 | 2021-05-05 16:37 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-05 16:37
8-00527028 | Cancelled | CVN 60CB3 OOS | Inspection & Doble | CVN 60CB3 | 2021-05-04 08:00 | 2021-05-05 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-29 14:22
8-00526184 | Cancelled | 1L115 OOS | COB Insulator Replacements | 1L115 | 2021-05-04 08:00 | 2021-05-07 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-23 09:21
8-00526018 | Completed | NIC 5RX4 OOS | CB/RX/PN maintenance | NIC 5RX4, NIC 5CB44 | 2021-05-04 08:00 | 2021-05-12 18:38 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-05-12 18:49
8-00531208 | Proposed | SKA T1, 5CB2 oos | Non Elec PN PM & Trip Close Assessment | SKA 5CB2, SKA T1 | 2021-05-04 08:00 | 2021-05-04 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-04 17:10
8-00531167 | Proposed | FJN T3 oos | 25kV Hotspot Invvesigation | FJN T3 | 2021-05-04 08:00 | 2021-05-06 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-23 07:31
8-00533481 | Cancelled | WBK T3 OOS | WBK 1CB4 INSP | WBK T3 | 2021-05-04 08:00 | 2021-05-06 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-30 12:51
8-00539600 | Completed | 2L17/WLT 2B1 OOS | WLT INSULATOR DEFICIENCY PROGRAM | 2L17, WLT 2B1 | 2021-05-04 08:00 | 2021-05-09 14:12 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-05-09 14:13
8-00538057 | Cancelled | PVO 1CX2, 1CB27 OOS | INSP, CN | PVO 1CB26, PVO 1CX2 | 2021-05-04 08:00 | 2021-05-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-30 13:26
8-00540025 | Cancelled | SAY T3, 1B4 OOS | SAY 1D3, 1D2C4, 1D2CB5 Inspection | SAY T3, SAY 1B4, 1L48, SAY 1B3 | 2021-05-04 08:00 | 2021-05-06 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-27 14:24
8-00537091 | Cancelled | DMR SVC OOS | SVC PM | DMR SVC | 2021-05-04 08:00 | 2021-05-08 16:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-04-09 08:02
8-00561616 | Completed | 2L39 OOS | Overview Inspections. | 2L39, NEL 2CB4, NEL T1, NEL T5 | 2021-05-04 08:00 | 2021-05-07 11:42 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-05-07 11:42
8-00550941 | Completed | KLY 5RX1 oos | Non-Elec PM | KLY 5RX1 | 2021-05-04 08:00 | 2021-05-05 15:02 | 2 | Return Evenings | [6 empty] | N | N | Y | Y | 2021-05-05 15:03
8-00545378 | Completed | DMR 138KV all OOS except 1L101 and 1L105 | DMR OSP | 1L115, 1L119, 1L106, 1L116, 1L114, DMR T7, DMR T6, DMR T5, DMR 1B1, DMR 1B3, DMR T4, DMR 1B2, DMR 1B4, DMR 1D1, DMR 1D2, DMR SVC | 2021-05-04 08:00 | 2021-05-07 16:47 | 8 | Continuous | 2000 | 2400 |  |  |  |  | Y | Y | Y | Y | 2021-05-07 16:50
8-00548833 | Completed | 2L12 OOS | CMS 2D21/2D3 Replacement - Stage #1 | CMS 2DCB2, 2L12, CMS 2B1 | 2021-05-04 10:00 | 2021-05-18 14:58 | 4 | Continuous | [6 empty] | Y | N | N | Y | 2021-09-10 12:23
8-00482071 | Completed | KI2 T1, 60B2, 60B4, 60L37 OOS | REPLACE 60DCB2/3, REPLACE 60CB2/3, INSTALL 60SA21 | KI2 T1, 60L37, KI2 60B2, KI2 60B4 | 2021-05-05 07:00 | 2021-08-27 06:00 | 4 | Continuous | [6 empty] | N | Y | N | Y | 2021-08-27 08:21
8-00531211 | Proposed | SKA T2, 5CB12 oos | CB Trip Close Assessment | SKA 5CB12, SKA T2 | 2021-05-05 08:00 | 2021-05-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-04 17:10
8-00527040 | Completed | SPG 2CB3 OOS | CPC BFPN PM | SPG 2CB3 | 2021-05-05 08:00 | 2021-05-05 12:56 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-05 12:56
8-00541684 | Completed | PIK 2CB18 OOS | SF6 Leak Investigation | PIK 2CB18 | 2021-05-05 08:00 | 2021-05-06 16:14 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-06 16:15
8-00537033 | Approved | DMR T7, 2CB7 OOS | pn-2CB7 CN | DMR T7 | 2021-05-05 08:00 | 2021-05-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-04 14:34
8-00539673 | Completed | NVR 60CB3 OOS | NVR 60CB3 COND. Protection testing | NVR 60CB3 | 2021-05-05 08:00 | 2021-05-05 08:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-04 16:03
8-00538054 | Completed | PVO 1T1, 1CB1 OOS | CN | PVO 1CB1, PVO T1 | 2021-05-05 08:00 | 2021-05-05 13:22 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-05 13:25
8-00541690 | Denied | PIK 2RX22 OOS | High Contact Resistance Monitoring | PIK 2CB22, PIK 2RX2 | 2021-05-06 08:00 | 2021-05-06 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-05 08:30
8-00550944 | Completed | KLY 5RX6 oos | Non-Elec PM | KLY 5RX6 | 2021-05-06 08:00 | 2021-05-06 15:21 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-09 20:01
8-00527031 | Completed | 60L75 Out from CVN | Inspection & Doble | CVN TXM1, 60L75 | 2021-05-06 08:00 | 2021-05-06 16:00 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-05-08 14:52
8-00527470 | Completed | 60L35 NWR OOS | Detailed | 60L35 | 2021-05-06 08:00 | 2021-05-07 16:01 | 2 | Return Evenings | [6 empty] | N | N | Y | Y | 2021-05-08 12:18
8-00531101 | Cancelled | BMT T1 oos | Non-Elec PN PM | BMT T1 | 2021-05-06 08:00 | 2021-05-06 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-25 06:17
8-00527449 | Proposed | 60L75 OOS | Detailed & Jacket Testing | 60L75 | 2021-05-06 08:00 | 2021-05-06 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-16 10:56
8-00564953 | Completed | 60L75 OOS | Detailed and Jacket Testing | 60L75 | 2021-05-06 16:00 | 2021-05-07 17:28 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-05-07 17:28
8-00531103 | Completed | BMT T3 | Non-Elec PN PM | BMT T3 | 2021-05-07 08:00 | 2021-05-07 14:16 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-07 14:17
8-00512738 | Cancelled | 1L274 Out from 1D2L274 | Install markerballs | 1L274 (887L) | 2021-05-07 08:00 | 2021-05-07 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-03-16 13:52
8-00455808 | Completed | AMC 5CX2 OOS (with 5L82 OOS V/C) | AMC PN upgrade project | AMC 5CX2 | 2021-05-10 08:00 | 2021-05-17 09:41 | 72 | Continuous | [6 empty] | Y | N | Y | Y | 2021-06-02 03:30
8-00525795 | Completed | 2L240 OOS | End of life insulator replacements | 2L240 | 2021-05-10 08:00 | 2021-05-14 09:32 | 3 | Continuous | [6 empty] | Y | N | N | Y | 2021-05-14 09:32
8-00525187 | Denied | ARN T2, 2D2, 1D2, 1CB2, 2D33 OOS | Disconnect Maintenance, T2 inspection/doble/CPC non-el testing, 1CB2 control testing | ARN T2, ARN T9, 1L18, ARN 1B1, ARN 1B2, ARN 2B13 | 2021-05-10 08:00 | 2021-05-28 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-05 14:28
8-00518754 | Completed | 2L50 OOS | Detailed & Oil Sampling & Terminal Wash | 2L50 | 2021-05-10 08:00 | 2021-05-13 14:33 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-05-13 14:34
8-00529400 | Proposed | 1L361 oos | Str Repl | 1L361, GMS 1D21 | 2021-05-10 08:00 | 2021-05-14 08:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-17 07:17
8-00527027 | Denied | 60L76 OOS | DS Inspection, CB Insp & Doble, VT Insp & Doble | CVN 60CB1, CVN 60CB2, CVN 60CB3, CVN TXM2, 60L76 | 2021-05-10 08:00 | 2021-05-11 08:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-05-06 10:36
8-00527001 | Completed | 60L3 OOS, COK 60CB5, 60CB3 OOS, COK 60B4, 60B5 OOS | COK 60D24, 60D2CB4, 60D2CB5, 60VT5 Inspections | COK 60B4, COK 60B5, 60L3 | 2021-05-10 08:00 | 2021-05-12 15:01 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-12 15:09
8-00531207 | Completed | SKA 2CB12 oos | SKA CB CT Insp | SKA 2CB12 | 2021-05-10 08:00 | 2021-05-15 09:13 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-22 05:10
8-00533401 | Completed | 2L47 OOS | Structure Replacements | 2L47 | 2021-05-10 08:00 | 2021-05-14 13:52 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2022-06-07 10:50
8-00537094 | Approved | PAL 1CB10 OOS | PN-1CB10 CN & LOCH | PAL 1CB10 | 2021-05-10 08:00 | 2021-05-10 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-08 14:57
8-00538058 | Completed | PVO 1CX3, 1CB26 OOS | INSP, CN | PVO 1CB27, PVO 1CX3 | 2021-05-10 08:00 | 2021-05-13 11:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-13 11:01
8-00540028 | Completed | SAY T3, 2D3, 1D3 OOS | SAY T3, Non-electrical protection testing, inspection, doble testing, LTC inspection | SAY T3 | 2021-05-10 08:00 | 2021-05-14 15:34 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-05-14 15:34
8-00539675 | Completed | NVR 60CB5 OOS | NVR 60CB5 COND. Protection testing | NVR 60CB5 | 2021-05-10 08:00 | 2021-05-10 08:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-05 14:45
8-00539778 | Completed | 60l65 OUT FROM HCT, HCT T2 OOS | HCT T2 Non-electrical trip testing | HCT T2, 60L65 | 2021-05-10 08:00 | 2021-05-10 15:46 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-10 15:46
8-00539779 | Completed | 60L65 Out from HCT, HCT T2 OOS | HCT T2 LTC Overhaul | HCT T2, 60L65 | 2021-05-10 08:00 | 2021-05-20 12:51 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-05-20 12:51
8-00537031 | Completed | GLD T2, 1B3 OOS | PN - T2-NON-EL, T2 DOBL 1D2 INSP | GLD 1CB3, GLD 1B3, GLD T2 | 2021-05-10 08:00 | 2021-05-14 15:59 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-14 15:59
8-00533520 | Completed | ALZ T2/60D2/60CB6 OOS | T2 EL Inspection/doble & CPC non-el Testing & leak repair, SS1 inspection, CB inspection, disconnect maint. | ALZ 60CB1, ALZ 60CB6, ALZ 60CB7, ALZ T2, ALZ 60B2 | 2021-05-10 08:00 | 2021-05-22 14:30 | 6 | Continuous | [6 empty] | N | Y | N | Y | 2021-05-22 17:34
8-00537018 | Completed | PAL 1CB11 OOS | PN-1CB11 CN | PAL 1CB11 | 2021-05-11 08:00 | 2021-05-11 14:57 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-11 14:57
8-00539676 | Completed | NVR T1, 12CB11, 12CB12 OOS | NVR T1 Non-electrical | NVR T1 | 2021-05-11 08:00 | 2021-05-12 15:45 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-12 15:45
8-00542070 | Denied | 2L2 out from CKY, CKY 2B4 OOS | PM INSPECTIONS | CKY 2B4, 2L2 | 2021-05-11 08:00 | 2021-05-13 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-07 14:05
8-00531812 | Proposed | GLN T3 oos | GLN-T3 NON-ELE PN | GLN T3 | 2021-05-11 08:00 | 2021-05-11 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-04 11:33
8-00527003 | Completed | PCP 60CB2 OOS | CPC BFPN PM | PCP 60CB2 | 2021-05-11 08:00 | 2021-05-11 13:15 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-11 13:15
8-00527041 | Completed | SPG 2CB6 OOS | CPC Control Testing | SPG 2CB6 | 2021-05-11 08:00 | 2021-05-11 13:50 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-11 13:50
8-00531109 | Denied | DAW T2, 1B1, 1CX1 & 1CX2 oos | DAW DS PM | DAW 1D1CB1, DAW 1D2, DAW 1D2CB2, DAW T2, DAW 1DCB11, DAW 1DCB12, DAW 1CX1, DAW 1CX2, DAW 1B1 | 2021-05-11 08:00 | 2021-05-12 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-06 15:49
8-00517685 | Completed | 5L71, NIC 5B18 OOS | station PM (2 hours recall time) | 5L71, NIC 5B18, NIC 5CB18, NIC 5RX4, NIC 5CB8 | 2021-05-11 08:00 | 2021-05-12 18:38 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-05-28 03:30
8-00525211 | Completed | ING 5CB7 OOS | CPC BFPN PM | ING 5CB7, ING 5B6 | 2021-05-11 08:00 | 2021-05-14 15:36 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-14 18:00
8-00518366 | Completed | 5L75 OOS | station PM | 5L75, ACK 5B6 | 2021-05-12 08:00 | 2021-05-13 14:10 | 2 | Continuous | 2850 | 3150 | 2500 | 2500 | 850 | 1000 | Y | N | N | Y | 2021-05-13 14:14
8-00531813 | Proposed | GLN T5 oos | GLN-T5 NON-ELE PN | GLN T5 | 2021-05-12 08:00 | 2021-05-12 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-04 11:34
8-00532653 | Completed | 5L30, MSA T1, 5B1 OOS | MSA 5CB6 COND. Protection testing, 5D21, 5D1CB6, 5D1CB3, 5DCB1 Inspection, 12RX1 Non-electrical & PY/SY protection testing | MSA T1, 5L30, MSA 5B1 | 2021-05-12 08:00 | 2021-05-17 11:00 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-05-17 11:19
8-00537020 | Completed | PAL 1CB3 OOS | PN 1CB3 CN | PAL 1CB3, PAL 1B2 | 2021-05-12 08:00 | 2021-05-12 17:37 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-12 17:38
8-00533476 | Completed | END T2 OOS | END 1CB2 SF6 leak repairs, T2 oil leak repairs | END 1CB2, END T2 | 2021-05-12 16:00 | 2021-05-14 15:01 | 12 | Continuous | [6 empty] | N | Y | N | Y | 2021-05-14 15:01
8-00579151 | Completed | GMS 5RX1 oos | Gas Relay Calibration | GMS 5RX1, GMS 5NRX1 | 2021-05-13 07:00 | 2021-05-14 14:08 | 10 | Continuous | [6 empty] | Y | N | Y | Y | 2021-05-14 14:08
8-00539678 | Completed | NVR T2, 12CB13, 12CB14 OOS | NVR T2 Non-electrical | NVR T2 | 2021-05-13 08:00 | 2021-05-14 15:49 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-14 15:49
8-00531814 | Proposed | GLN T2 oos | GLN-T2 NON-ELE PN | GLN T2 | 2021-05-13 08:00 | 2021-05-13 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-04 11:36
8-00531113 | Approved | DAW T1, 25B1 oos | DAW DS PM | DAW T1 | 2021-05-13 08:00 | 2021-05-13 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-12 15:52
8-00527000 | Completed | COK 60B4, COK 60CB3 OOS | COK 60D2CB3, COK 60CB3 Inspection | COK 60CB3, COK 60B4, COK 60D2CB3 | 2021-05-13 08:00 | 2021-05-14 14:51 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-14 15:18
8-00527577 | Proposed | 60L76 OOS | Overview & Jacket Test | 60L76 | 2021-05-14 08:00 | 2021-05-14 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-02-04 09:02
8-00529134 | Cancelled | 5L2, GMS 5RX2, 5B4 | GMS DS PM | 5L2, GMS 5RX2, GMS 5B4 | 2021-05-14 08:00 | 2021-05-21 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-14 16:24
8-00538055 | Completed | PVO 1CB2 OOS | CN | PVO 1CB2 | 2021-05-14 08:00 | 2021-05-14 12:25 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-14 12:25
8-00537024 | Cancelled | 1L114, PAL 1CB2 OOS | PN-1CB2 BF PN | 1L114, PAL 1CB2 | 2021-05-14 08:00 | 2021-05-14 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-08 13:34
8-00581068 | Completed | BSY G3 OOS | CPC REQUIRED TO DO A LOAD TEST | BSY G3 | 2021-05-14 12:54 | 2021-05-17 15:00 | 2 | Continuous | 2400 | 2800 |  |  |  |  | N | N | Y | Y | 2021-05-18 13:10
8-00581127 | Completed | GMS 5RX1 OOS | Forced OOS | GMS 5RX1 | 2021-05-14 14:22 | 2021-06-09 10:13 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-06-09 10:15
8-00530071 | Completed | 2L101 oos | DE Str Repl | 2L101 | 2021-05-15 08:00 | 2021-05-21 18:49 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-21 18:49
8-00536297 | Cancelled | 5L2, GMS 5B12, 5B4, T12 oos | Insulator Repl on GMS 5B12 | GMS 2CB3, GMS 5B12, GMS 5CB1, GMS 5CB10, GMS 5CB6, GMS T14 | 2021-05-16 12:00 | 2021-05-20 18:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-15 12:04
8-00547469 | Completed | TIR 5RX13 OOS | TIR 5RX13 inspection, non-electrical trip testing, leak repair | TIR 5RX13 | 2021-05-17 08:00 | 2021-06-14 13:45 | 6 | Continuous | [6 empty] | N | N | N | Y | 2021-07-01 03:30
8-00547471 | Completed | TIR 5RX11 OOS | TIR 5RX11 inspection, non-electrical trip testing, Victaulic replacement | TIR 5RX11 | 2021-05-17 08:00 | 2021-06-14 13:45 | 6 | Continuous | [6 empty] | N | N | N | Y | 2021-06-15 17:03
8-00554853 | Completed | 5L82 OOS | For work on AMC 5BP2 switch | 5L82, AMC 5D22 (3), AMC 5D32 (3) | 2021-05-17 08:00 | 2021-05-21 19:23 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | N | Y | 2021-05-21 19:24
8-00530618 | Proposed | 2L354 oos | DE Str Repl | 2L354 | 2021-05-17 08:00 | 2021-05-21 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-16 13:30
8-00531451 | Proposed | WLM T3 oos | WLM T3 Non-Elec PN PM | WLM T3 | 2021-05-17 08:00 | 2021-05-17 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-02 20:35
8-00525311 | Completed | ING 2CB30 OOS | CPC BFPN; EL Inspection | ING 2CB30, 2L18 | 2021-05-17 08:00 | 2021-05-21 19:31 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-21 19:32
8-00525382 | Cancelled | BND T1 OOS | PCB Bushing Replacement Program | BND T1 | 2021-05-17 08:00 | 2021-06-25 17:00 | 120 | Continuous | [6 empty] | N | Y | N | Y | 2021-04-28 09:57
8-00366124 | Cancelled | 5L2 & GMS 5B4 OOS | GMS Reactor Replacement Project | 5L2, GMS 5D26, GMS 5RX2, GMS 5B4 | 2021-05-17 08:00 | 2021-05-20 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-13 11:59
8-00435261 | Completed | KLY T1 oos | Transformer Bushing Repl | KLY 12RX1, KLY T1 | 2021-05-18 08:00 | 2021-07-15 09:24 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-31 03:30
8-00512791 | Completed | 2L129 OOS | Terminal Washing & Defect Repair | 2L129 | 2021-05-18 08:00 | 2021-05-30 18:01 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-05-30 18:01
8-00512805 | Completed | 2L129 oos | NON-EL & PN | 2L129 | 2021-05-18 08:00 | 2021-05-28 12:20 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-05-30 18:01
8-00512812 | Completed | 2L129 OOS | INSP, DOBL, NON-EL, CN | 2L129, VIT 2CB41, VIT 2CB42, VIT PST1 | 2021-05-18 08:00 | 2021-05-30 18:02 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-05-30 18:03
8-00525234 | Completed | ING 5CB8 OOS | CPC BFPN PM | ING 5CB8 | 2021-05-18 08:00 | 2021-05-20 15:10 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-20 15:10
8-00532017 | Completed | SRS T3 oos | Trans, CB, DS Insp & Doble | SRS T3, SRS 1B3 | 2021-05-18 08:00 | 2021-05-20 18:38 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-20 18:39
8-00532658 | Completed | 2L47, MSA 2B8 OOS | MSA 2D25, 2D2CB9, 2D1CB8 Inspection | 2L47, MSA 2B8 | 2021-05-18 08:00 | 2021-05-20 09:05 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-05-20 09:13
8-00532660 | Approved | 2L47, HSP PT1, CT1 OOS | HSP 1MK1 - BCH PT1(3), BCH CT1(3) Inspection, Doble testing, OSYR | 2L47 | 2021-05-18 08:00 | 2021-05-20 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-17 14:28
8-00527005 | Completed | IOC 60CB2 OOS | CPC BFPN | IOC 60CB2 | 2021-05-18 08:00 | 2021-05-18 16:54 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-18 16:54
8-00539774 | Completed | 60L90 out from DCV | DCV 60VT1 Inspection and doble | 60L90 | 2021-05-18 08:00 | 2021-05-19 16:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-20 22:05
8-00530685 | Completed | WSN 5CB5 oos | CB Insp | WSN 5CB5 | 2021-05-18 11:00 | 2021-05-21 15:53 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-21 15:53
8-00527007 | Completed | IOC 60CB4 OOS | CPC Control | IOC 60CB4 | 2021-05-19 08:00 | 2021-05-19 15:46 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-19 15:46
8-00533512 | Completed | ARM T2 OOS | ARM T2 NON-ELE PM | ARM T2 | 2021-05-19 08:00 | 2021-05-19 15:12 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-19 15:12
8-00485186 | Cancelled | ANN T2, 12B2, 12CX2, 12B29, 12F51 Feeder Cable, 12F52 Feeder Cable, 12F53 Feeder Cable OOS | Replace 12D251, 12D351, 12D252, 12D352 | ANN T2 | 2021-05-20 07:00 | 2021-06-11 16:00 | 6 | Continuous | [6 empty] | N | N | N | Y | 2021-02-23 09:44
8-00530087 | Denied | 2L101 oos | Insp and doble SKA 2CVT5 | 2L101 | 2021-05-20 08:00 | 2021-05-20 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-17 13:54
8-00532040 | Proposed | WSN T7 | WSN-T7 NON-ELE PN PM | WSN T7 | 2021-05-20 08:00 | 2021-05-20 18:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-04 18:31
8-00532306 | Cancelled | GMS 5RX2 oos | GMS Reactor Repl | GMS 5RX2 | 2021-05-20 16:00 | 2021-10-01 16:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-01-05 10:17
8-00532041 | Proposed | WSN T5 oos | WSN-T5 NON-ELE PN | WSN T5 | 2021-05-21 08:00 | 2021-05-21 18:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-04 18:35
8-00525387 | Completed | SEA T2 OOS | PCB Bushing Replacement Program | SEA T2 | 2021-05-21 08:00 | 2021-06-29 10:19 | 48 | Continuous | [6 empty] | N | Y | N | Y | 2021-07-15 03:30
8-00537032 | Cancelled | PAL 1CB9 OOS | PN- 1CB9 BF & LOCH | PAL 1CB9 | 2021-05-21 08:00 | 2021-05-21 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-08 09:52
8-00537037 | Completed | GLD 1CB2 OOS | CB-1CB2 & 1CT2 INSP, 1CT2 DOBL | GLD 1CB2 | 2021-05-25 08:00 | 2021-05-27 13:15 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-05-27 13:15
8-00539777 | Completed | GLR T1 OOS | GLR T1 Non-electrical trip testing, 4CB1 inspection and doble testing | GLR T1 | 2021-05-25 08:00 | 2021-05-28 15:17 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-28 15:17
8-00540151 | Completed | MSA 2CB3 OOS | MSA 2CB3 Inspection & COND. protection testing | MSA 2CB3 | 2021-05-25 08:00 | 2021-05-28 13:31 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-28 13:32
8-00537881 | Completed | LTZ T1 OOS | NON-EL | LTZ T1 | 2021-05-25 08:00 | 2021-05-26 11:20 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-26 11:20
8-00525793 | Completed | 2L256 OOS | End of life structure and crossarm replacement | 2L256 | 2021-05-25 08:00 | 2021-06-02 13:28 | 3 | Continuous | [6 empty] | Y | N | N | Y | 2021-06-02 13:28
8-00525704 | Completed | SPL T2 OOS | SPL T1 PCB leak repair | SPL T2 | 2021-05-25 08:00 | 2021-06-24 13:13 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-24 13:15
8-00512983 | Completed | AMC 5CX2 OOS (5L82 OOS for V/C) | CPC BFPN MNRI Inspection, CB inspection, CVT inspection | AMC 5CX2 | 2021-05-25 08:00 | 2021-05-31 13:09 | 6 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-07 16:32
8-00518685 | Completed | 2L4 OOS | Structure Replacements | 2L4, CAM T2 | 2021-05-25 08:00 | 2021-05-28 18:42 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-05-28 18:43
8-00518765 | Completed | 2L40 out from BND to NEL | Overview & Jacket Test & Oil Sample | 2L40 | 2021-05-25 08:00 | 2021-05-27 17:22 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-05-27 17:22
8-00524114 | Cancelled | 5L7, WSN 5B6, KDS 5B3oos | WSN/KDY DS Insp | KDS 5B3, 5L7, KDY 5CX3, WSN 5B6, WSN 5RX6 | 2021-05-25 08:00 | 2021-05-31 16:00 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-05-21 11:11
8-00455810 | Completed | AMC 5CX1 and 5CX2 OOS (5L82 OOS for V/C) | Double bank outage required to Relocate OLD I/P R4 next to new 5L82 PY/SY R6 | AMC 5CX1, AMC 5CX2 | 2021-05-25 08:00 | 2021-05-25 16:38 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-07 16:32
8-00533479 | Completed | SCM T1 OOS | SCM T1 non-ELE PM | SCM T1 | 2021-05-25 08:00 | 2021-05-25 15:42 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-25 15:42
8-00532004 | Completed | SRS T2 oos | Transf Insp | SRS T2 | 2021-05-25 08:00 | 2021-05-26 18:47 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-26 18:47
8-00531206 | Completed | SKA 2CB11 oos | SKA CB CT Insp | SKA 2CB11 | 2021-05-25 08:00 | 2021-05-28 13:17 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-05-28 13:18
8-00527026 | Denied | 60L40, HPN 60D31 OOS | Inspection | 60L40, HPN 60D31, LOH 60D21 | 2021-05-25 08:00 | 2021-05-26 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-19 10:54
8-00527477 | Denied | 60L73 OOS | Detailed | 60L73 | 2021-05-25 08:00 | 2021-05-28 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-04 09:31
8-00526035 | Completed | NIC T2 OOS | PCB Bushing Replacement | NIC T2 | 2021-05-25 08:00 | 2021-06-27 15:29 | 120 | Continuous | [6 empty] | N | N | N | Y | 2021-06-27 15:31
8-00537882 | Cancelled | LTZ 25CB2, 25CB10 OOS | BFPN | LTZ T2 | 2021-05-26 08:00 | 2021-05-27 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-19 13:20
8-00537038 | Cancelled | DMR 1CB3 OOS | PN-1CB3 CN | DMR 1CB3 | 2021-05-26 08:00 | 2021-05-26 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-30 14:00
8-00537039 | Cancelled | GLD 1CB3 OOS | CB-1CB3 & 1CT3 INSP, 1CT3 DOBL | GLD 1CB3 | 2021-05-27 08:00 | 2021-05-28 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-19 15:42
8-00536797 | Cancelled | CBK 2CB8 OOS | CPC Protection testing | CBK 2CB8 | 2021-05-27 08:00 | 2021-05-28 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-12 08:53
8-00533530 | Completed | VNT T1 OOS | VNT 2D1CB8 INSP | 2L256, VNT 2CB8, VNT T1 | 2021-05-27 08:00 | 2021-05-27 13:40 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-27 13:41
8-00532003 | Completed | SRS T1 oos | Transf Insp and Doble | SRS T1 | 2021-05-27 08:00 | 2021-05-28 18:33 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-28 18:33
8-00533236 | Denied | 2L12, CKY 2B10 OOS | CMS 2CVT1 REPLACEMENT, CMS/CKY WAVETRAP REMOVALS, CKY 2B10 INSULATOR REPLACEMENT | 2L12, CKY 2B10 | 2021-05-29 07:00 | 2021-05-30 17:00 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-05-25 12:43
8-00573093 | Completed | 5L82 OOS | To make repairs on bus work near 5D22 | 5L82, AMC 5D22 (3) | 2021-05-30 08:00 | 2021-06-09 17:21 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-06-09 17:22
8-00427341 | Completed | ALZ T5 OOS | OSP Containment Program work | ALZ T5 | 2021-05-31 07:00 | 2021-08-23 13:34 | NR | Continuous | [6 empty] | Y | N | N | Y | 2021-08-23 13:35
8-00305820 | Completed | BSY Synchronous Condenser (G1) OOS | Inspection and Exciter Mtce | BSY G1 | 2021-05-31 07:00 | 2021-06-04 11:04 | 72 | Continuous | 2400 | 2800 |  |  |  |  | N | N | Y | Y | 2021-06-05 00:19
8-00511703 | Completed | 5L29 OOS | Detailed Inspections and Terminal Washing | 5L29 | 2021-05-31 08:00 | 2021-06-14 14:03 | 2 | Continuous | [6 empty] | Y | Y | N | Y | 2021-06-14 14:04
8-00518262 | Completed | 5L71 OOS | station PM (recall time: 4 hrs) | 5L71, SYA 5CX1 | 2021-05-31 08:00 | 2021-07-14 08:27 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-26 12:02
8-00525827 | Completed | MAN T2 OOS | TX Inspection/Doble, DS & RX inspections | MAN 2CB4, MAN 2CB6, MAN 2D2, MAN T2 | 2021-05-31 08:00 | 2021-06-04 14:41 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-06-04 15:41
8-00525317 | Completed | ING 2CX31, 2CX32 OOS | Electrical Inspection | ING 2CX31, ING 2CX32 | 2021-05-31 08:00 | 2021-06-04 16:20 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-04 16:20
8-00533280 | Completed | 5L29 OOS | TIR 5L29, 5RX - 1, 2, 3, 21, 22, 23 inspection, doble testing, non-electrical trip testing, 5CVT- 21, 22, 23 protection testing | TIR 5RX1, TIR 5RX11, TIR 5RX12, TIR 5RX13, TIR 5RX2, TIR 5RX21, TIR 5RX22, TIR 5RX23, TIR 5RX3, 5L29 | 2021-05-31 08:00 | 2021-06-14 14:03 | 6 | Continuous | [6 empty] | N | Y | N | Y | 2021-06-14 14:05
8-00531204 | Completed | SKA 2CB2 oos | CB Cond | SKA 2CB2 | 2021-05-31 08:00 | 2021-05-31 11:09 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-31 11:09
8-00531818 | Completed | GLN T1 oos | GLN T1 INSP/ Doble | GLN T1 | 2021-05-31 08:00 | 2021-06-11 11:37 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-06-27 03:30
8-00531443 | Proposed | SCK T2 oos | SCK T2 Non-Elec PN PM | SCK T2 | 2021-05-31 08:00 | 2021-05-31 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-05-20 06:05
8-00527002 | Completed | 60L26, COK 60CB5, COK 60CB6, COK 60B6 OOS | COK 60CB5, 60D1CB5, 60VT6, 60D25, 60D2CB6 Inspections | COK 60CB5, COK 60CB6, 60L26, COK 60B6 | 2021-05-31 08:00 | 2021-06-04 14:38 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-06-04 14:38
8-00529148 | Completed | WSN 5B13 oos | WSN DS Insp | WSN 5B13, WSN 5CB4, WSN 5CB6, WSN 5CB5 | 2021-05-31 08:00 | 2021-06-03 15:40 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-03 16:33
8-00570924 | Completed | NIC T2, NIC T6, 1CB15, 1CB19 OOS | NIC T6 Inspections, doble test and disconnect maintenance | NIC 1CB15, NIC 1CB19, NIC 2CB11, NIC T2, NIC T6 | 2021-05-31 08:00 | 2021-06-09 17:02 | 48 | Continuous | [6 empty] | N | Y | N | Y | 2021-06-27 15:31
8-00558615 | Completed |  |  | LDY T2, 1L138 | 2021-05-31 08:00 | 2021-06-11 13:28 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-11 13:28
8-00537912 | Cancelled | LDY T2, 25CB2 OOS | Tx: INSP, LTC INSP, DOBL CB: BFPN | LDY T2 | 2021-05-31 08:00 | 2021-06-04 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-12 12:22
8-00539674 | Completed | NVR 60CB4 OOS | NVR 60CB4 COND. Protection testing | NVR 60CB4 | 2021-05-31 08:00 | 2021-05-31 16:25 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-31 16:26
8-00538448 | Cancelled | VIT T9, T10, 2B11, 1B11 OOS | 1D1CB12, 1D2CB11, 1DCB14,1DCB15, 2DCB15 INSP's | VIT 1D1CB12, VIT 1D2CB11, VIT 2DCB15, VIT 1DCB14, VIT 1DCB15, VIT SC3, VIT SC4, VIT 1B11, VIT 2B11, VIT T10, VIT T9 | 2021-06-01 08:00 | 2021-06-01 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-28 12:41
8-00540120 | Cancelled | SQH T1, 25CB1 OOS | REPLACE 25KV CIRCUIT BREAKER | SQH T1 | 2021-06-01 08:00 | 2021-06-30 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-10 10:04
8-00537040 | Cancelled | DMR 5RX1/5CB51 OOS | PN-5CB51 CN | DMR 5RX1, DMR 5CB51 | 2021-06-01 08:00 | 2021-06-01 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-01 10:25
8-00531121 | Completed | DAW 1CB11, 1CX1 oos | CB Insp | DAW 1CX1, DAW 1CB11 | 2021-06-01 08:00 | 2021-06-01 13:56 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-01 13:56
8-00526962 | Completed | BSY 2CB1 OOS | CPC BFPN PM | BSY 2CB1 | 2021-06-01 08:00 | 2021-06-01 16:09 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-01 16:12
8-00531202 | Completed | SKA 2CB8 oos | SKA CB and CT Insp | SKA 2CB8 | 2021-06-01 08:00 | 2021-06-04 13:40 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-06-04 13:49
8-00525326 | Cancelled | KDS 5CB4 oos | PM | KDS 5CB4 | 2021-06-01 08:00 | 2021-06-01 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-19 14:23
8-00525205 | Completed | ARN T10 OOS | CPC Non-Ele | ARN T10 | 2021-06-01 08:00 | 2021-06-08 14:39 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-08 14:39
8-00366125 | Cancelled | GMS 5RX2 OOS | GMS Reactor Replacement Project | GMS 5RX2 | 2021-06-01 18:00 | 2021-08-25 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-31 12:32
8-00541703 | Completed | JHT 1CB11 OOS | PN-1CB11 BFPN& Dashpot | JHT 1CB11 | 2021-06-02 07:00 | 2021-06-03 12:20 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-03 12:20
8-00541682 | Completed | PIK 2CB17 OOS | Compressor Replacement | PIK 2CB17 | 2021-06-02 08:00 | 2021-06-02 18:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-03 00:47
8-00584527 | Completed | 1L115 out from DMR to LTZ | COB Insulator Replacements | 1L115, PVL T2 | 2021-06-02 08:00 | 2021-06-04 16:15 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-06-04 16:16
8-00536918 | Cancelled | DMR 5RX2, 5CB52 OOS | PN-5CB52 CN | DMR 5RX2, DMR 5CB52 | 2021-06-02 08:00 | 2021-06-02 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-01 10:25
8-00538458 | Completed | VIT 2CB7 OOS | INSP | VIT 2CB7 | 2021-06-02 08:00 | 2021-06-04 11:13 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-04 11:13
8-00526965 | Completed | BSY 2CB2 OOS | CPC BFPN PM | BSY 2CB2 | 2021-06-02 08:00 | 2021-06-03 09:31 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-03 09:32
8-00536919 | Cancelled | DMR 5RX4/5CB54 OOS | PN-5CB54 CN | DMR 5RX4, DMR 5CB54 | 2021-06-03 08:00 | 2021-06-03 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-01 10:25
8-00539788 | Completed | LBY T1 OOS | LBY 60D21, 12D1, SS1 Inspection | LBY 60D21, LBY T1, 60L69 | 2021-06-04 08:00 | 2021-06-08 16:29 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-08 16:30
8-00541692 | Cancelled | PIK 2CB7 OOS | SF6 Leak Investigation | PIK 2CB7 | 2021-06-04 08:00 | 2021-06-04 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-23 09:41
8-00512810 | Completed | 2L255 OOS | End of life structure and crossarm replacement | 2L255 | 2021-06-04 08:00 | 2021-06-11 14:12 | 3 | Return Weekends | [6 empty] | Y | N | N | Y | 2021-06-11 14:22
8-00538062 | Cancelled | JPT Outage | JPT 1D2CB1, 1D2CB2, 1D2CB3, 1D2CB4, 1D2CB5, 1D2CB6, 1D2CB8, 1D2CB9, 1CB8, 1DVT2,1VT1: INSPs 1CB8: BFPN | 1L115, 1L116, 1L112, 1L110, 1L124, 1L128 | 2021-06-06 08:00 | 2021-06-06 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-06-02 16:12
8-00570961 | Cancelled | BSY G4 OOS | Quarterly Cleaning of water line from Buntzen to BSY | BSY G4 | 2021-06-07 07:00 | 2021-06-11 07:00 | 4 | Continuous | 2400 | 2800 |  |  |  |  | N | N | N | Y | 2021-05-25 10:52
8-00460139 | Completed | 5L3 OOS | KDS 5D1CB2 replacement project | 5L3, KDS 5CB1, KDS 5CB3 | 2021-06-07 08:00 | 2021-06-22 17:46 | 72 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-06-22 18:13
8-00525227 | Completed | 5L3, PCN 5B1 oos | PCN DS PM | 5L3, PCN 5B1, PCN 5RX1 | 2021-06-07 08:00 | 2021-06-10 15:41 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-06-22 18:13
8-00524115 | Cancelled | 5L3 oos | Arcing Horn Inst | 5L3 | 2021-06-07 08:00 | 2021-06-18 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-19 14:22
8-00525321 | Cancelled | KDS 1CB1 oos | PM | KDS 5CB1 | 2021-06-07 08:00 | 2021-06-07 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-19 14:20
8-00525837 | Completed | MAN 2B3 OOS | DS & RX Inspections | MAN T3, MAN 2B3 | 2021-06-07 08:00 | 2021-06-11 16:42 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-06-11 16:42
8-00531452 | Proposed | 60L308, WLM T2, 60B2 oos | WLM 60PT1 Instp | 60L308, WLM 60B2, WLM T1 | 2021-06-07 08:00 | 2021-06-07 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-02 20:54
8-00533243 | Denied | 2L12, CMS T3 OOS | ROCK SCALING IN SWITCHYARD AND 2D21/2D3 REPLACEMENT | CMS 2D21, CMS 2D3, CMS T3, 2L12, CMS 2B1 | 2021-06-07 08:00 | 2021-06-24 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-01 08:16
8-00531817 | Completed | GLN 2B1 oos | GLN 2CB2, DS PM | GLN 2B1, GLN T1 | 2021-06-08 08:00 | 2021-06-11 11:37 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-11 11:52
8-00531139 | Completed | DAW T3, 25CB3 oos | Transf Insp & Doble | DAW T3 | 2021-06-08 08:00 | 2021-06-10 16:25 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-10 16:26
8-00526968 | Completed | BSY 2CB3 OOS | CPC BFPN PM | BSY 2CB3 | 2021-06-08 08:00 | 2021-06-08 14:58 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-23 09:57
8-00526259 | Completed | FLW 2CB1 OOS | CPC control testing | FLW 2CB1 | 2021-06-08 08:00 | 2021-06-09 16:14 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-09 16:14
8-00531132 | Completed | DAW 1CB13, 1CX3 oos | CB Insp | DAW 1CX3, DAW 1CB13 | 2021-06-08 08:00 | 2021-06-10 09:53 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-10 09:53
8-00530056 | Completed | GUI 5CX1 OOS | CX and CB inspection | GUI 5CB1, GUI 5CX1 | 2021-06-08 08:00 | 2021-06-14 09:49 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-30 03:30
8-00525323 | Proposed | KDS 5CB3 oos | PM | KDS 5CB3 | 2021-06-08 08:00 | 2021-06-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2020-12-09 15:54
8-00525325 | Cancelled | ING 2D26, 2D30 OOS | EL Disconnect Maintenance | ING 2RX2, ING 2CX2 | 2021-06-08 08:00 | 2021-06-09 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-07 15:56
8-00525236 | Completed | ING 5CB11 OOS | CPC control testing | ING 5CB11 | 2021-06-08 08:00 | 2021-06-10 20:28 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-06-10 20:29
8-00540134 | Approved | GIB T1, 1CB1, 25CB1 OOS | GIB 1CB1 COND. protection testing | GIB 1CB1, GIB T1 | 2021-06-08 08:00 | 2021-06-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-04 12:34
8-00587938 | Completed | 5L71 OOS | training (1.5 recall time) | 5L71 | 2021-06-08 10:00 | 2021-06-17 15:15 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-30 11:54
8-00531994 | Completed | TKW 1CB6 oos | Insp TKW 1CT6 | TKW 1CB6 | 2021-06-08 12:01 | 2021-06-08 18:37 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-08 18:37
8-00531995 | Completed | TKW 1CB8 oos | Insp TKW 1CT8 | TKW 1CB8 | 2021-06-09 08:00 | 2021-06-10 15:58 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-10 15:58
8-00531992 | Completed | TKW 1CB11 oos | Insp TKW 1CT11 | TKW 1CB11 | 2021-06-09 08:00 | 2021-06-09 14:14 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-09 14:14
8-00533136 | Denied | 1L31, GIB T2, 1B3 OOS | GIB 1D2 COND. protection testing | GIB T2, 1L31, GIB 1B3 | 2021-06-09 08:00 | 2021-06-09 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-03 10:46
8-00530619 | Completed | 2L352 oos | DE Str Repl | 2L352 | 2021-06-09 08:00 | 2021-06-15 10:25 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-06-15 10:25
8-00526969 | Completed | BSY 2CB4 OOS | CPC BFPN PM | BSY 2CB4 | 2021-06-09 08:00 | 2021-06-09 14:43 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-09 14:44
8-00525408 | Completed | CBN 2CB10 OOS | CPC BFPN | CBN 2CB10 | 2021-06-09 08:00 | 2021-06-10 15:09 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-10 15:09
8-00518768 | Cancelled | 2L45 OOS | Overview & Oil Sample | 2L45 | 2021-06-09 08:00 | 2021-06-09 16:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-06-02 14:41
8-00537075 | Cancelled | DMR 2CB4 OOS | PN-2CB4 BFPN | DMR 2CB4 | 2021-06-09 08:00 | 2021-06-09 16:00 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-11 09:30
8-00548524 | Cancelled | 2L90 OOS | replace str 14/2 | 2L90 | 2021-06-10 08:00 | 2021-06-10 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-19 09:51
8-00525830 | Cancelled | MAN 2CB4 OOS | CB Inspection | MAN 2CB4 | 2021-06-10 08:00 | 2021-06-11 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-03-12 16:09
8-00526261 | Completed | FLW 2CB2 OOS | CPC control testing | FLW 2CB2 | 2021-06-10 08:00 | 2021-06-10 15:27 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-10 21:06
8-00527480 | Completed | 60L18 OOS | Jacket Test | 60L18 | 2021-06-10 08:00 | 2021-06-10 14:17 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-10 14:17
8-00532651 | Completed | 5L29, MSA 5RX1 OOS | MSA 5RX1 Non-electrical trip testing, NERC requirement | MSA 5RX1, 5L29 | 2021-06-10 08:00 | 2021-06-10 15:22 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-06-14 14:04
8-00531997 | Completed | TKW 1CB9 oos | Insp TKW 1CT9 | TKW 1CB9 | 2021-06-10 12:01 | 2021-06-10 18:32 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-10 18:32
8-00540158 | Completed | SNK 2CB10 oos | Replace rupture discs on CB | SNK 2CB11 | 2021-06-13 09:00 | 2021-06-15 10:33 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-15 10:33
8-00564866 | Completed | MCA 5B9 and LS1 OOS | MCA station maintenance | MCA 5B9, MCA LS1 | 2021-06-13 22:00 | 2021-07-02 16:00 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-07-05 12:53
8-00306144 | Completed | BSY Synchronous Condenser (G4) OOS | Inspection and Exciter Mtce | BSY G4 | 2021-06-14 07:00 | 2021-06-17 14:59 | 48 | Continuous | 2400 | 2800 |  |  |  |  | N | N | Y | Y | 2021-06-17 14:59
8-00511277 | Cancelled | 5L72 OOS | MCA project work | 5L72, MCA T3 | 2021-06-14 08:00 | 2021-10-21 16:00 | 168 | Continuous | 2000 | 2400 |  |  |  |  | N | N | N | Y | 2020-11-20 08:02
8-00525833 | Cancelled | MAN 2D22, 2GD22, 2VT2, 2D2CB1, 2D1CB2, 2CB1 OOS | DS & VT Inspections, CPC BFPN | MAN 2CB1, MAN 2D1CB2, MAN 2D2CB1, MAN 2D22, 2L55 | 2021-06-14 08:00 | 2021-06-18 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-03-12 16:13
8-00518756 | Completed | 2L32 OOS | Overview | 2L32 | 2021-06-14 08:00 | 2021-06-21 09:20 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-06-21 09:24
8-00518751 | Cancelled | 2L55 OOS | Detailed & Oil Sample & Gauge Replacement | 2L55 | 2021-06-14 08:00 | 2021-06-18 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-27 16:56
8-00531984 | Proposed | BRN T1 oos | BRN-T1 NON-ELE PN | BRN T1 | 2021-06-14 08:00 | 2021-06-14 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-04 16:07
8-00526995 | Completed | 60L2 OOS, COK 60CB6, COK 60CB7, COK 60B7 OOS | COK 60CB6, 60CB7 inspections. 60D1CB6, 60D26,60D2CB7 60VT7 inspections. | 60L2, COK 60B7 | 2021-06-14 08:00 | 2021-06-18 14:59 | 3 | Continuous | [6 empty] | N | N | N | Y | 2021-06-18 14:59
8-00530054 | Completed | 5L87 OOS | station maintenance | 5L87, NIC 5B11, GUI 5CX1 | 2021-06-14 08:00 | 2021-06-17 10:02 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | N | Y | 2021-07-03 03:30
8-00529401 | Cancelled | 1L374 oos | Str Repl | 1L374 | 2021-06-14 08:00 | 2021-06-25 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-16 14:56
8-00540136 | Cancelled | GIB T2, 1CB3 OOS | GIB T2 Qualitrol installation. | GIB T2 | 2021-06-14 08:00 | 2021-06-17 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-26 14:43
8-00539792 | Cancelled | LYN T2, 12CB21 OOS | LYN T2 breather installation | LYN T2 | 2021-06-14 08:00 | 2021-06-16 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-15 10:26
8-00538429 | Completed | SAT 2RX1 OOS | INSP, NON-EL, DOBL | SAT 2RX1 | 2021-06-14 08:00 | 2021-06-25 09:17 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-06-25 09:18
8-00533518 | Completed | SCM T2 OOS | SCM T2 INSP, DOBL and non-ELE PM, 25VR1 INSP | SCM T2 | 2021-06-14 08:00 | 2021-06-18 12:10 | 8 | Continuous | [6 empty] | N | Y | N | Y | 2021-06-18 12:10
8-00534996 | Cancelled | MIN T2 & 2B6 oos | LNG Project - Connect and New 287kV Eqpt | MIN T2, MIN 2B6 | 2021-06-14 08:00 | 2021-06-18 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-26 13:50
8-00538433 | Completed | SAT 2CB8 OOS | CN | SAT 2CB8 | 2021-06-15 08:00 | 2021-06-15 11:39 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-15 16:58
8-00526262 | Completed | FLW 2CB3 OOS | CPC control testing | FLW 2CB3 | 2021-06-15 08:00 | 2021-06-15 16:21 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-15 16:21
8-00526971 | Completed | BSY 2CB5 OOS | CPC BFPN PM | BSY 2CB5 | 2021-06-15 08:00 | 2021-06-15 15:35 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-15 15:35
8-00533271 | Recalled | 5L31 OOS | TIR 5RX4, 5RX6 replace vicatulic fitting with stainless | TIR 5RX4, TIR 5RX5, 5L31 | 2021-06-15 08:00 | 2021-06-26 11:41 | 6 | Continuous | [6 empty] | Y | N | N | Y | 2021-06-28 09:18
8-00514236 | Completed | 5L31 OOS | Detailed & Terminal Washing | 5L31 | 2021-06-15 08:00 | 2021-06-28 14:20 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-06-28 14:20
8-00470776 | Completed | BRT T4, 2L19, BR1 T30, T3 OOS | BR1 T3 Replacement - OSP Stage 8 | 2L19, BR1 T3, BRT T4, BR1 T30 | 2021-06-15 08:00 | 2021-06-15 16:15 | 4 | Continuous | [6 empty] | Y | N | N | Y | 2021-06-15 16:32
8-00532652 | Completed | 5L31, MSA 5RX2 OOS | MSA 5RX2 Non-electrical trip testing, NERC requirement | MSA 5RX2 | 2021-06-16 08:00 | 2021-06-16 15:50 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-02 03:30
8-00533500 | Cancelled | ACK 5CB1 OOS | CB inspections | ACK 5CB1 | 2021-06-16 08:00 | 2021-06-18 16:00 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-06-16 11:13
8-00526974 | Completed | BSY 2CB8 OOS | CPC BFPN PM | BSY 2CB8 | 2021-06-16 08:00 | 2021-06-16 15:27 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-16 15:27
8-00538818 | Completed | KCL 2CB5 OOS | PN maintenance | KCL 2CB5 | 2021-06-16 08:00 | 2021-06-16 16:23 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-06-16 16:23
8-00539790 | Completed | LYN T1, 12CB11 OOS | LYN 12D1 Inspection | LYN T1 | 2021-06-16 08:00 | 2021-07-13 11:28 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-30 03:30
8-00536922 | Completed | DMR 5RX8/5CB58 OOS | PN-5CB58 CN; PN-5RX8 NON-EL | DMR 5RX8, DMR 5CB58 | 2021-06-16 08:00 | 2021-06-17 12:25 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-17 12:26
8-00540162 | Completed | SNK 2MB2 oos | CB Repair | SNK 2CB21, SNK 2MB2 | 2021-06-16 09:00 | 2021-06-18 11:20 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-18 11:21
8-00539592 | Completed | 2L14, WLT 2B5 OOS | WLT INSULATOR DEFICIENCY PROGRAM | 2L14, WLT 2B5, WLT 2B6 | 2021-06-17 08:00 | 2021-06-21 15:50 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-06-21 15:50
8-00542853 | Cancelled | 2L14 OOS | replace line structure | 2L14 | 2021-06-17 08:00 | 2021-06-30 16:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-06-16 10:14
8-00589826 | Completed | 5L87, KLY 5B7, 5RX6 oos | Disconnect PM at GUI and NIC on listed disconnects | 5L87, NIC 5D22 (3), KLY 5B7, KLY 5RX6, GUI 5D1, GUI 5D2 | 2021-06-17 08:00 | 2021-06-17 15:10 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | N | Y | 2021-06-17 15:11
8-00526263 | Completed | FLW 2CB4 OOS | CPC control testing | FLW 2CB4 | 2021-06-17 08:00 | 2021-06-17 14:45 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-17 15:20
8-00589832 | Completed | 5L87 OOS | disconnect maintence | 5L87, NIC 5B11, NIC 5D22 (3), GUI 5D1, GUI 5D2 | 2021-06-17 16:00 | 2021-06-18 12:47 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | N | Y | 2021-06-18 12:47
8-00589908 | Completed | 2L123, HWW T1 OOS | Flashed insulator replacement (90% flashed). | HWW T1, 2L123 | 2021-06-18 08:00 | 2021-06-18 16:21 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-06-18 16:22
8-00589822 | Cancelled | KIT SC2 OOS | RTA work | KIT SC2 | 2021-06-18 08:00 | 2021-07-02 15:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-11 15:04
8-00525386 | Denied | SEA T1 OOS | PCB Bushing Replacement Program | SEA T1 | 2021-06-18 17:01 | 2021-07-09 17:00 | 48 | Continuous | [6 empty] | N | N | N | Y | 2021-06-01 13:27
8-00607990 | Completed | BQN forced out |  | BQN 2CX1 | 2021-06-19 21:36 | 2021-06-22 18:31 | NR | Continuous | [6 empty] | N | N | Y | Y | 2021-06-22 18:31
8-00588149 | Completed | L81-87 OOS | RTA work | L81-87 | 2021-06-21 07:00 | 2021-06-30 16:33 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-01 16:33
8-00541679 | Cancelled | CLD T3 OOS | Oil Leak Repair | CLD T3 | 2021-06-21 08:00 | 2021-07-03 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-21 13:38
8-00536925 | Completed | DMR 5CB4, 5CB15 OOS | PN 5CB4, 5CB15 CN-BFPN | DMR 5CB4, DMR 5CB15 | 2021-06-21 08:00 | 2021-06-22 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-25 18:15
8-00536120 | Proposed | 60L20 OOS | Structure Replacements | 60L20 | 2021-06-21 08:00 | 2021-06-25 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-14 12:21
8-00525396 | Cancelled | 1L12 OOS | GTP Station Modification (1L14 line swap with 1L12) | 1L12 | 2021-06-21 08:00 | 2021-06-26 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-03-05 09:15
8-00525397 | Cancelled | 1L14 OOS | GTP Station Modification (1L14 line swap with 1L12), | 1L14 | 2021-06-21 08:00 | 2021-06-26 16:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-03-05 09:18
8-00531191 | Denied | GMS 1CB3 oos | GMS CB PM | GMS 1CB3 | 2021-06-21 08:00 | 2021-06-25 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-03 14:47
8-00533427 | Completed | 1L204 OOS | DUG 1D23, 1D2CB3 INSP | 1L204, DUG 1B4 | 2021-06-22 08:00 | 2021-06-25 13:26 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-25 13:26
8-00533132 | Completed | 60L22, 60L55, LAJ T2 OOS | T2 INSP 60DCB3 INSP, 60CVT1 A,B,C Insp, | 60L22, LAJ 60B1, LAJ T2, 60L55 | 2021-06-22 08:00 | 2021-06-22 15:57 | 0 | Continuous | [6 empty] | Y | Y | N | Y | 2021-06-22 17:01
8-00526264 | Completed | MLN 2CB7 OOS | CPC control testing | MLN 2CB7 | 2021-06-22 08:00 | 2021-06-22 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-25 18:12
8-00527483 | Completed | 60L30 OOS | Overview & Jacket Test & Oil Sample | 60L30 | 2021-06-22 08:00 | 2021-06-23 16:11 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-23 16:11
8-00526977 | Completed | BSY 2CB9 OOS | CPC BFPN PM | BSY 2CB9 | 2021-06-22 08:00 | 2021-06-22 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-25 18:13
8-00530058 | Denied | 2L263 OOS | CB inspections | 2L263 (72L), VNT 2B12 | 2021-06-22 08:00 | 2021-06-23 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-18 11:30
8-00530672 | Completed | WSN 5CB12 oos | CB Insp | WSN 5CB12 | 2021-06-22 08:00 | 2021-06-28 21:42 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-28 21:42
8-00525320 | Denied | ING 2DNCX11, 2D22, 2D24 | EL Disconnect Maintenance | ING 2RX1, ING 2CX11 | 2021-06-22 08:00 | 2021-06-24 16:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | N | Y | 2021-06-16 09:07
8-00525831 | Cancelled | MAN 2CB6 OOS | CB Inspection | MAN 2CB6 | 2021-06-22 08:00 | 2021-06-23 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-03-12 16:15
8-00525228 | Cancelled | 5L4 oos | PCN 5DG22 PM | 5L4 | 2021-06-22 08:00 | 2021-06-22 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-16 10:37
8-00536762 | Completed | SEL 5CB43,5RX3 | Protection System Maintenance | SEL 5RX3, SEL 5CB43 | 2021-06-22 08:00 | 2021-06-24 14:22 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-24 14:23
8-00538478 | Completed | 1L14 out from VIT to KSH to SHA | VIT 1D1CB13, 1D2CB12, 1D32 INSPs KSH 1D22, 1D1CB4, 1CVT4 INSPs SHA 1D21 INSP, CN 1CVT1 INSP | 1L14, VIT 1CB12, VIT 1CB13, KSH T2, SHA T1 | 2021-06-22 08:00 | 2021-06-23 16:25 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-06-23 16:25
8-00427337 | Cancelled | ALZ T3, 2B3 OOS | ALZ OSP Step 2: Fireproof Microwave Tower | ALZ T3 | 2021-06-22 16:00 | 2021-07-07 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-14 17:21
8-00526978 | Cancelled | BSY 2CB10 OOS | CPC BFPN PM | BSY 2CB10 | 2021-06-23 08:00 | 2021-06-23 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-18 15:10
8-00536926 | Completed | DMR 5RX7 OOS | 5RX7 NON-EL | DMR 5RX7 | 2021-06-23 08:00 | 2021-06-23 14:47 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-23 14:47
8-00592406 | Completed | ING 2RX1, 2CX11 OOS | DS Maint. CX hotspot repair | ING 2RX1, ING 2CX11 | 2021-06-23 08:00 | 2021-06-25 16:27 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-25 18:04
8-00536939 | Completed | PUN T4 OOS | PN-T4 NON-ELE PN | PUN T4 | 2021-06-24 08:00 | 2021-07-07 16:47 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-07 16:47
8-00533525 | Cancelled | MON T5 OOS | MON T5 non-ELE PM | MON T5 | 2021-06-24 08:00 | 2021-06-25 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-10 09:40
8-00526265 | Completed | MLN 2CB11 OOS | CPC control testing | MLN 2CB11 | 2021-06-24 08:00 | 2021-06-24 15:41 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-25 18:11
8-00530059 | Denied | 2l264 OOS | disconnect inspection | 2L264 (74L), VNT 2B4 | 2021-06-24 08:00 | 2021-06-25 16:00 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-06-18 11:25
8-00533428 | Cancelled | 1l242 OOS | VVW 1D23 INSP | 1L242 | 2021-06-24 08:00 | 2021-06-24 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-20 15:17
8-00525834 | Cancelled | MAN 2CB2 OOS | CB Inspection | MAN 2CB2 | 2021-06-24 08:00 | 2021-06-25 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-03-12 16:18
8-00527487 | Completed | 60L35 OOS | Detailed & Jacket Testing | 60L35 | 2021-06-24 16:00 | 2021-06-25 16:14 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-25 18:03
8-00526108 | Completed | 1L11 OOS | End of Life Structure Replacements | 1L11, KSH T3 | 2021-06-28 08:00 | 2021-06-30 19:53 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-06-30 19:54
8-00533407 | Denied | 1L220 OOS | Overview & Jacket Test & Oil Sample & Terminal Washing | 1L220 | 2021-06-28 08:00 | 2021-06-30 16:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-06-22 11:42
8-00533409 | Cancelled | 1L220 OOS | BKL 1D1CB6 and 1D21 INSP | BKL 1CB2, BKL 1CB6, BKL T1, 1L220 | 2021-06-28 08:00 | 2021-06-29 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-20 14:11
8-00533502 | Denied | ACK T2 OOS | ACK T2 NON-ELE PM | ACK T2 | 2021-06-28 08:00 | 2021-06-30 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-21 14:29
8-00525836 | Denied | MAN 2CB3, 2D23 OOS | CB Inspection | MAN 2CB3, MAN 2D23, 2L56 | 2021-06-28 08:00 | 2021-06-30 16:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-06-22 14:16
8-00524128 | Cancelled | 5L1 oos | Spacer Repl | 5L1, GMS 5RX1 | 2021-06-28 08:00 | 2021-07-07 16:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-06-27 22:16
8-00518787 | Denied | 2L56 OOS | Detailed & Jacket Test & Oil Sample | MPT 2CB3, CAM T3, CAM T4, 2L56, MPT T2 | 2021-06-28 08:00 | 2021-06-30 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-06-23 13:35
8-00536764 | Denied | SEL T1 OOS | Gas relay PM | SEL T1 | 2021-06-28 08:00 | 2021-06-29 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-23 08:23
8-00551497 | Cancelled | 5L32 OOS | Replace broken spacer and repair damaged conductor on 5L32 structure 27-1 | 5L32 | 2021-06-28 08:00 | 2021-06-29 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-06-27 16:25
8-00537096 | Completed | GCL T12, 1CB2, 60CB3 OOS | PN T12 NON-EL, 60CB2,1CB3 BF | GCL 1CB2, GCL T12, GCL 60CB3 | 2021-06-29 06:00 | 2021-06-30 11:52 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-30 11:52
8-00539769 | Cancelled | 2l14, CYP T3, 2CB3, 2D23 OOS | CYP 2D23, 2D1CB3, 2CVT3 Inspection | CYP 2CB3, 2L14, CYP T3 | 2021-06-29 08:00 | 2021-06-30 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-23 13:37
8-00576119 | Denied |  |  | 2L93, SVA 1D1, SVA 2D1, SVA T1 | 2021-06-29 08:00 | 2021-06-29 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-22 11:11
8-00526110 | Cancelled | 1L11 out from KSH | End of Life Structure Replacements | 1L11 | 2021-06-29 08:00 | 2021-06-30 16:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-06-18 13:10
8-00526980 | Completed | BSY 2CB11 OOS | CPC BFPN PM | BSY 2CB11, BSY G4 | 2021-06-29 08:00 | 2021-06-29 14:55 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-30 08:57
8-00526981 | Completed | BSY 2CB12 OOS | CPC BFPN PM | BSY 2CB12 | 2021-06-30 08:00 | 2021-06-30 14:56 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-30 14:56
8-00560768 | Cancelled | MSA T1/2B1/12RX1 OOS | MSA T1A Tertiary bushing replacement;2D1 inspection | MSA T1, MSA 2B1 | 2021-06-30 12:00 | 2021-06-30 16:00 | 1 | Continuous | [6 empty] | Y | Y | N | Y | 2021-06-30 11:17
8-00544742 | Proposed | HLD 1CB5 OOS | quA-ymn Solar Farm Project | HLD 1CB5 | 2021-07-01 08:00 | 2021-07-08 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-06 17:43
8-00544744 | Proposed | 1L55 OOS | quA-ymn Solar Farm Project | 1L55 | 2021-07-01 08:00 | 2021-07-08 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-06 17:42
8-00541700 | Completed | PAL T12 OOS | PAL T12 LTC OVHL | PAL T12 | 2021-07-02 08:00 | 2021-07-06 15:37 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-22 03:30
8-00613581 | Completed | 5L1, GMS 5RX1 oos | Spacer Repl | 5L1, GMS 5RX1 | 2021-07-02 08:00 | 2021-07-10 18:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2021-07-12 10:20
8-00540121 | Cancelled | SQH T2, 25CB2 OOS | REPLACE 25KV CIRCUIT BREAKER | SQH T2 | 2021-07-02 08:00 | 2021-07-31 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-10 10:10
8-00516446 | Cancelled | 5L62 OOS | GLN 5RX5 Inspection | 5L62, GLN 5RX5N, GLN 5RX5 | 2021-07-03 08:00 | 2021-07-04 16:00 | 2 | Return Evenings | [6 empty] | Y | Y | Y | Y | 2021-06-30 14:09
8-00511676 | Cancelled | 5L72 OOS | Placeholder for MCA SWGR Roof Project | 5L72 | 2021-07-05 07:00 | 2021-09-29 17:30 | 24 | Continuous | 2000 | 2400 | 2500 | 2500 | 850 | 1000 | N | N | Y | Y | 2021-05-26 07:56
8-00526199 | Proposed | 1L116 OOS | COB Insulator Replacements | 1L116 | 2021-07-05 08:00 | 2021-07-08 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-01-18 08:46
8-00533429 | Cancelled | HLD 1CB1 OOS | HLD 1CB1 - Solar Farm Project | HLD 1CB1 | 2021-07-05 08:00 | 2021-07-09 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-08 08:37
8-00539768 | Denied | CYP 2CB3 OOS | CYP 2CB3 inspection, protection testing | CYP 2CB3 | 2021-07-05 08:00 | 2021-07-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-30 11:53
8-00539601 | Completed | 2L11, WLT 2B8 OOS | INSULATOR DEFICIENCY PROGRAM | 2L11, WLT 2B8 | 2021-07-05 08:00 | 2021-07-08 16:13 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-24 03:30
8-00538786 | Cancelled | EFD T1 OOS | insp | EFD T1 | 2021-07-06 08:00 | 2021-07-09 08:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-24 08:41
8-00539771 | Denied | CYP T2 OOS | CYP T2 Non-electrical trip testing, ETM replacement | CYP T2 | 2021-07-06 08:00 | 2021-07-07 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-30 11:44
8-00536933 | Completed | DMR 2CB13 OOS | 2CT13 INSP & DOBLE | DMR 2CB13 | 2021-07-06 08:00 | 2021-07-06 18:07 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-06 18:08
8-00533623 | Cancelled | UHT T1, 3B1, 25F51 OOS | INSPECTIONS AND DOBLE TEST | UHT 3B1, UHT 3D2CB1, UHT 3D35, UHT T1 | 2021-07-06 08:00 | 2021-07-09 16:00 | 2 | Return Evenings | [6 empty] | N | Y | Y | Y | 2021-03-11 10:09
8-00587997 | Completed | 5L72 OOS | CB test (recall time: 1hr) | 5L72 | 2021-07-06 08:00 | 2021-07-06 12:00 | 1 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | N | Y | 2021-07-06 12:10
8-00533508 | Cancelled | HOP T11 | CPC non-electrical PM | HOP T11 | 2021-07-06 08:00 | 2021-07-06 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-06 08:05
8-00533123 | Completed | 60L55, LAJ 60CB3 OOS | 60CB3 INSP, 60CVT22 INSP (A,B,C) | LAJ 60CB3, 60L55 | 2021-07-06 08:00 | 2021-07-07 12:59 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-07-07 12:59
8-00532976 | Completed | MSA T1, 2B1 OOS | MSA 2CB2 Inspection & COND. protection testing, 2D1 Inspection, 2B1 protection testing | MSA 2CB2 | 2021-07-06 08:00 | 2021-07-09 16:09 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-09 16:09
8-00526982 | Completed | BSY 2CB13 OOS | CPC BFPN PM | BSY 2CB13 | 2021-07-06 08:00 | 2021-07-06 16:11 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-06 16:20
8-00530061 | Completed | ACK 5CB10 OOS | ACK 5D1CB1 INSP AND 5CB10 INSP AND DOBL | ACK 5CB10, ACK 5B9 | 2021-07-06 08:00 | 2021-07-08 16:32 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-07-08 16:33
8-00512758 | Completed | 2L294 Out from NLY | Replace defective insulators | 2L294 | 2021-07-06 08:00 | 2021-07-14 19:35 | 5 | Return Weekends |  |  |  |  | 850 | 500 | N | N | Y | Y | 2021-07-14 19:35
8-00512989 | Completed | RYC 5CX1 OOS | CPC/EL MJRI/MNRI Inspections | RYC 5CX1 | 2021-07-06 08:00 | 2021-07-23 12:52 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-23 12:52
8-00507171 | Completed | 5L63 Outage | 5L63 D/E install | 5L63 | 2021-07-07 08:00 | 2021-07-14 16:06 | 12 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-07-14 16:12
8-00526984 | Completed | BSY 2CB14 OOS | CPC BFPN PM | BSY 2CB14 | 2021-07-07 08:00 | 2021-07-07 14:43 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-07 14:44
8-00533509 | Cancelled | HOP T12 OOS | CPC non-electrical PM | HOP T12 | 2021-07-07 08:00 | 2021-07-07 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-06 08:39
8-00590897 | Completed | 5L63, TKW 5RX1 OOS | address oil leaks | 5L63, TKW 5RX1 | 2021-07-07 08:00 | 2021-07-14 16:06 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-14 16:15
8-00537095 | Completed | GCL T11, 1CB3, 60CB2 OOS | PN T11 NON-EL, 60CB2,1CB3 BF | GCL 1CB1, GCL T11, GCL 60CB2 | 2021-07-07 08:00 | 2021-07-07 14:53 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-07-07 14:53
8-00537093 | Completed | DMR 2CB24 OOS | 2CB24 INSP | DMR 2CB24 | 2021-07-08 08:00 | 2021-07-09 14:55 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-09 14:55
8-00538059 | Completed | PVO T3/ 25CB3 OOS | INSP | PVO T3 | 2021-07-08 08:00 | 2021-07-09 15:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-09 15:01
8-00539752 | Approved | WLT 2CB8 OOS | WLT 2CB8 BFPN protection testing | WLT 2CB8 | 2021-07-08 08:00 | 2021-07-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-07 13:51
8-00532001 | Completed | SRS T1 oos | SRS T1 PCB Bushing Replacement | SRS T1 | 2021-07-08 08:00 | 2021-09-08 20:01 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-08 20:01
8-00532025 | Proposed | HUS T3 oos | Transf Cond | HUS T3 | 2021-07-08 08:00 | 2021-07-08 14:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-04 17:42
8-00617173 | Completed | 5L29 Forced OOS | C Phase Cable PH leak at NCT | 5L29 | 2021-07-08 10:55 | 2021-08-20 13:44 | NR | Continuous | [6 empty] | Y | Y | N | Y | 2021-09-05 03:30
8-00539748 | Cancelled | WLT 2CB1 OOS | WLT 2CB1 BFPN protection testing | WLT 2CB1 | 2021-07-09 08:00 | 2021-07-09 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-09 09:51
8-00536938 | Completed | PUN T3 OOS | PN-T3 NON-ELE PN | PUN T3 | 2021-07-09 08:00 | 2021-07-09 14:23 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-09 14:23
8-00531153 | Cancelled | FJN T2 oos | PCB Bushing Repl | FJN T2 | 2021-07-09 08:00 | 2021-08-11 16:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-05 15:48
8-00532889 | Denied | 5L7 oos | Insulator Repl | 5L7 | 2021-07-10 08:00 | 2021-07-12 07:00 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-07-06 09:20
8-00550765 | Completed | MDN T3 OOS | Oil containment pit. | MDN 12RX31, MDN 12RX32, MDN T3 | 2021-07-11 12:00 | 2021-08-20 17:40 | 6 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-08-20 17:41
8-00427323 | Completed | ALZ T3 and ALZ 60B3 OOS | ALZ OSP Step 1: Proximity outage during T3 OSP construction | ALZ 60B3 | 2021-07-12 07:01 | 2021-07-29 15:35 | 4 | Return Evenings | [6 empty] | N | N | Y | Y | 2021-08-06 11:56
8-00427319 | Completed | ALZ T3 OOS | ALZ OSP Step 1: Install T3 OCP | ALZ T3 | 2021-07-12 07:01 | 2021-07-29 15:35 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2021-08-14 03:30
8-00518771 | Completed | 2L51 from BND to COK | 88C Oil Containment Project & Detailed & Jacket Test | BSY 2CB8, 2L51 | 2021-07-12 08:00 | 2021-07-30 21:26 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-07-30 21:26
8-00525374 | Cancelled | CSN T2 OOS | PCB Bushing Replacement Program - Inspection & Doble PM | CSN T2, CSN 2CB3, CSN 2B2, CSN T4 | 2021-07-12 08:00 | 2021-07-15 17:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-06 16:08
8-00525376 | Denied | HPN T5 OOS | PCB Bushing Replacement Program | HPN T5 | 2021-07-12 08:00 | 2021-08-27 17:00 | 96 | Continuous | [6 empty] | N | Y | N | Y | 2021-06-28 15:46
8-00531166 | Cancelled | FJN T2, 25B2 oos | FJN 25DCB2 Hotspot Repair | FJN T2 | 2021-07-12 08:00 | 2021-07-14 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-15 14:13
8-00526116 | Cancelled | 2L154 OOS | End of Life Structure Replacements | 2L154 | 2021-07-12 08:00 | 2021-07-15 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-16 08:06
8-00526994 | Completed | COK T2 OOS, COK 60CB7 COK 60CB8 OOS COK 60B8 OOS | COK 60CB8 inspection, COK 60D12, COK 60D1CB7, COK 60D2CB8 Inspections | COK T2, COK 60B8, COK 60CLB8 | 2021-07-12 08:00 | 2021-07-15 14:27 | 24 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-05 03:30
8-00530684 | Completed | WSN 5CB16 oos | CB Insp | WSN 5CB16 | 2021-07-12 08:00 | 2021-07-16 14:46 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-16 14:46
8-00550816 | Cancelled | KLY 5B12 outage | KLY DS Repair | KLY 5B12 | 2021-07-12 08:00 | 2021-07-23 16:00 | 2 | Return Weekends | [6 empty] | N | N | Y | Y | 2021-06-22 11:05
8-00550956 | Cancelled | KLY SC2 OOS | SC2 Major PM | KLY SC2 | 2021-07-12 08:00 | 2021-07-16 17:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-09 11:37
8-00533631 | Proposed | MSA 5CB5 OOS | MSA 5CB5 COND. Protection testing | MSA 5CB5 | 2021-07-12 08:00 | 2021-07-12 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-06 10:41
8-00539751 | Approved | WLT 2CB2 OOS | WLT 2CB2 BFPN protection testing | WLT 2CB2 | 2021-07-12 08:00 | 2021-07-12 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-08 22:41
8-00539763 | Completed | WLT T2 OOS | WLT T2 Non-electrical trip testing, ETM replacement | WLT T2, WLT 60D2 | 2021-07-12 08:00 | 2021-07-14 13:44 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-15 12:16
8-00538787 | Cancelled | EFD T2 OOS | INSP | EFD T2 | 2021-07-12 08:00 | 2021-07-16 08:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-24 08:39
8-00589370 | Completed | 1L274, 1L275 OOS | NTL 1VR1 lead replacement | NTL T1, NTL T2, 1L274 (887L), 1L275 (786L) | 2021-07-13 06:00 | 2021-07-13 16:47 | 2 | Continuous |  |  |  |  | 850 | 1000 | N | N | N | Y | 2021-07-13 16:48
8-00538047 | Completed | INV T4 OOS | INSP PM | INV T4 | 2021-07-13 08:00 | 2021-07-16 14:03 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-07-16 14:03
8-00540008 | Cancelled | GPT T1, 1L48 out from GPT | GPT 1CB1 COND. protection testing | GPT T1, 1L48 | 2021-07-13 08:00 | 2021-07-13 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-26 13:42
8-00533511 | Cancelled | KEN T1 OOS | CPC non-electrical PM | KEN T1 | 2021-07-13 08:00 | 2021-07-13 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-07 13:57
8-00526985 | Completed | BSY 2CB16 OOS | CPC BFPN PM | BSY 2CB16 | 2021-07-13 08:00 | 2021-07-13 16:42 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-13 16:42
8-00512730 | Completed | 1L274 Out from NTL | Refurbishment project | 1L274 (887L) | 2021-07-13 08:00 | 2021-07-13 16:00 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-07-13 16:49
8-00525648 | Completed | 1L158 OOS | KTS 1D1CB1,1D1CB2,1D22 INSP,& KKS | 1L158, KKS T1 | 2021-07-14 08:00 | 2021-07-14 16:11 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-07-15 11:59
8-00533133 | Cancelled | 60L22, 60L55, LAJ T2, LAJ 60B1 OOS | T2 Doble /TTR, 12VR1 | 60L22, LAJ 60B1, LAJ T2, 60L55 | 2021-07-14 08:00 | 2021-07-14 16:00 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-07-13 14:26
8-00533513 | Cancelled | KEN T2 OOS | CPC non-electrical PM | KEN T2 | 2021-07-14 08:00 | 2021-07-14 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-07 14:13
8-00533537 | Denied | VNT T6 OOS | VNT 1D2CB9, 1D6, 1D2CB8, 1D2CB7 AND 1D2CB5 INSP | VNT 1D2CB5, VNT 1D2CB7, VNT 1D2CB8, VNT 1D2CB9, VNT 1D6, VNT T6 | 2021-07-14 08:00 | 2021-07-16 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-06 11:47
8-00540011 | Cancelled | 1L33 out from GPT, GPT T2 OOS | GPT 1CB2 COND. protection testing | GPT T2, 1L33 | 2021-07-14 08:00 | 2021-07-14 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-26 13:44
8-00526113 | Denied | 1L157 OOS | End of Life Structure Replacements | 1L157 | 2021-07-15 07:00 | 2021-07-15 17:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-07 14:05
8-00525402 | Completed | 1L125, 1L157 OOS | KTS 1D2CB1,1D2CB2,1D1CB3,1D1CB4,1D21,1D23,1CVT21,1CVT23,1VT1 INSP & 1VT1 DOBLE,KKS,CSS | 1L125, 1L130, 1L137, 1L141, 1L157, 1L158 | 2021-07-15 07:00 | 2021-07-20 14:40 | 2 | Continuous | [6 empty] | Y | Y | N | Y | 2021-07-20 14:40
8-00525399 | Cancelled | 1L125, 1L157 OOS | Structure Replacement, | 1L125, 1L157 | 2021-07-15 08:00 | 2021-07-15 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-28 13:27
8-00525401 | Cancelled | 1L125, 1L157 OOS | KGH 1D22, 1D2CB6,1D2CB8,1CVT3 INSP | 1L125, 1L157 | 2021-07-15 08:00 | 2021-07-15 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-28 13:28
8-00617088 | Approved | KLY 5RX4 oos | NERC PM for PN | KLY 5RX4 | 2021-07-15 08:00 | 2021-07-16 16:00 | 1 | Continuous | 2000 | 2400 |  |  |  |  | N | N | N | Y | 2021-07-14 14:06
8-00525409 | Completed | COK T2, 60CLB8 OOS | COK T2 Inspection and Doble, COK 60D2 Inspection | COK T2, COK 60CLB8 | 2021-07-15 16:00 | 2021-07-29 10:50 | 24 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-29 10:52
8-00533493 | Cancelled | ROS T1 | Refurbishment and removal of PCB oil | ROS T1 | 2021-07-16 08:00 | 2021-08-20 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-11 15:46
8-00533494 | Denied | ROS T1 | CPC non-el PM | ROS T1 | 2021-07-16 08:00 | 2021-07-20 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-07-05 09:43
8-00590624 | Completed | 5L2 OOS | Maintenance on Disconnects | 5L2, GMS 5RX2, GMS 5B4 | 2021-07-16 08:00 | 2021-07-17 20:00 | 8 | Continuous | [6 empty] | Y | N | Y | Y | 2021-07-18 07:09
8-00620199 | Completed | 5L91 OOS | Forced OOS | 5L91 | 2021-07-16 16:11 | 2021-07-22 15:36 | NR | Continuous |  |  |  |  | 560 | 500 | N | N | Y | Y | 2021-07-22 15:47
8-00619678 | Completed | 2L103 OOS | cut over 2L103 & 2L107 line PNs, install 2SA21, connect 2B10 to 2D2CB10. | 2L103, MIN T2, MIN 2B1, MIN 2B10, MIN 2B6 | 2021-07-19 05:00 | 2021-07-23 14:47 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-23 14:48
8-00617859 | Cancelled | 2L103 OOS | RTA work | 2L103 | 2021-07-19 06:00 | 2021-07-22 16:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-15 10:03
8-00619738 | Completed | 2L103 OOS | RTA work | 2L103, KIT CB440, KIT 4040E | 2021-07-19 07:00 | 2021-07-22 15:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-26 02:42
8-00516477 | Completed | 2L103 OOS | Cut over 2L103 & 2L107 line pns, install 2SA21, remove 2D6.Connect 2B10 TO 2D2CB10 | 2L103, MIN T2, MIN 2B1, MIN 2B10, MIN 2B6 | 2021-07-19 07:00 | 2021-07-23 14:47 | 8 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-07-29 08:07
8-00525299 | Cancelled | CBN 5CB8 OOS | EL Insp/Doble, Hydraulic Hose replacements | CBN 5CB8 | 2021-07-19 08:00 | 2021-08-06 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-20 17:42
8-00512814 | Denied | 5L91 OOS | End of life insulator replacements | 5L91 | 2021-07-19 08:00 | 2021-07-23 16:00 | 2 | Continuous |  |  |  |  | 560 | 500 | N | N | N | Y | 2021-07-14 14:57
8-00533402 | Cancelled | 2L47 OOS | Structure Replacements | 2L47 | 2021-07-19 08:00 | 2021-07-23 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-20 14:52
8-00530688 | Denied | GMS 5B11 oos | GMS DS PM | GMS 5B11, GMS T11, GMS T13 | 2021-07-19 08:00 | 2021-07-25 08:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-15 08:43
8-00530683 | Completed | WSN 5CB6 oos | CB Insp | WSN 5CB6 | 2021-07-19 08:00 | 2021-07-22 15:43 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-22 15:43
8-00530652 | Cancelled | 2L352 oos | HMH T3 Energization | 2L352, HMH T2, HMH 2B4 | 2021-07-19 08:00 | 2021-07-23 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-07-15 08:41
8-00530655 | Proposed | 2L352 oos | DE Str Repl | 2L352 | 2021-07-19 08:00 | 2021-07-23 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-16 13:40
8-00529362 | Cancelled | GMS 5B11 oos | GMS DS PM | GMS 5B11 | 2021-07-19 08:00 | 2021-07-26 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-05 14:24
8-00617237 | Cancelled | 5L71 OOS (recall time: 24 hrs) | MCA Switchgear Roof Replacement Project | 5L71 | 2021-07-19 08:00 | 2021-07-29 16:00 | 24 | Continuous | 2850 | 3150 | 2500 | 2500 | 850 | 1000 | N | N | N | Y | 2021-07-22 09:26
8-00590639 | Completed | GMS 5RX2 OOS | (GMS Reactor Replacement Project) | GMS 5RX2 | 2021-07-19 08:00 | 2021-10-26 17:01 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | N | Y | 2021-10-26 17:07
8-00617731 | Completed | BSY G1 OOS | Chlorination of fresh water line from Buntzen to BSY | BSY G1 | 2021-07-20 08:00 | 2021-07-21 15:45 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-21 15:45
8-00617733 | Completed | BSY G4 OOS | Chlorination of fresh water line from Buntzen to BSY | BSY G4 | 2021-07-20 08:00 | 2021-07-21 15:47 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-21 15:47
8-00539772 | Denied | CYP T3, 60CB6, 60CB7 OOS | CYP 60D3, 60D1CB7 Inspection | CYP 60CB6, CYP T3, CYP 60D3, CYP 60CB7 | 2021-07-20 08:00 | 2021-07-21 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-13 14:15
8-00537969 | Completed | 60L299 OOS | INSP and DOBL all 3 phases | 60L299, 60L295, JOE 60B5 | 2021-07-20 08:00 | 2021-07-23 13:07 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-07-23 13:07
8-00517666 | Completed | SEL 5CB9 OOS | Station PM | SEL 5CB9 | 2021-07-20 08:00 | 2021-07-23 12:30 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-23 12:30
8-00524145 | Completed | MLS 5CX1 oos | CX Insp | MLS 5CX1, MLS 5CB1CX1 | 2021-07-20 08:00 | 2021-07-30 13:29 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-30 13:29
8-00524899 | Denied | 5L91 OOS | ACK 5D24 Inspections | ACK 5D1CB4, ACK 5D24, ACK 5D2CB3, 5L91, ACK 5B3 | 2021-07-20 08:00 | 2021-07-22 16:00 | 2 | Continuous |  |  |  |  | 560 | 500 | N | N | Y | Y | 2021-07-14 11:48
8-00525752 | Completed | 2L295 OOS | structure replacement | 2L295 | 2021-07-20 12:00 | 2021-07-24 00:11 | 8 | Continuous | [6 empty] | N | N | N | Y | 2021-07-24 00:12
8-00617781 | Cancelled | BSY G1 and G4 OFF LINE | BSY Chlorination outage - TTC calculation | BSY G1, BSY G4 | 2021-07-21 01:30 | 2021-07-21 07:00 | 0 | Continuous | 1600 | 2000 |  |  |  |  | N | N | Y | Y | 2021-07-23 09:30
8-00538790 | Cancelled | NTL T4 OOS | INSP and DOBLE all 3 phases | NTL T4 | 2021-07-21 08:00 | 2021-07-22 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-07 17:34
8-00537077 | Completed | DMR 1CB1 OOS | PN-1CB1 CN | DMR 1CB1 | 2021-07-22 08:00 | 2021-07-22 15:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-23 16:57
8-00617880 | Cancelled | 2L103 OOS | Replace MIN STN Term DE Insulators and Corona Rings | 2L103 | 2021-07-22 08:00 | 2021-07-22 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-15 10:03
8-00531169 | Completed | TLR T2, 2B8 oos | T2 and DS OSYR/MNRI | TLR T2, TLR 2B8 | 2021-07-22 08:00 | 2021-07-23 13:02 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-23 13:02
8-00619724 | Completed | 2L103 OOS | cut over 2L103 & 2L107 line PNs, install 2SA21, connect 2B10 to 2D2CB10 | 2L103, MIN T2, MIN 2B1, MIN 2B10, MIN 2B6 | 2021-07-22 15:00 | 2021-07-23 14:43 | 8 | Continuous | [6 empty] | Y | N | N | Y | 2021-07-23 14:48
8-00619278 | Completed | 2L103 OOS | Placeholder for new equipment energization | 2L103, MIN T2, MIN 2B1, MIN 2B10, MIN 2B6 | 2021-07-23 07:00 | 2021-07-23 14:19 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-07-23 14:48
8-00530065 | Approved | SEL 5CB9 OOS | 5CB9 Braker Fail PN testing | SEL 5CB9 | 2021-07-23 08:00 | 2021-07-23 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-22 10:50
8-00530656 | Cancelled | 2L352 OOS | Remove section of HMH 2B4 | 2L352 | 2021-07-24 08:00 | 2021-07-24 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-05 22:24
8-00529370 | Cancelled | GMS T11 | GMS T11 PM | GMS T11 | 2021-07-25 08:00 | 2021-07-27 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-07-23 18:49
8-00530658 | Cancelled | 2L86 OOS | Install Jumpers, Removal 2GD21, and Install New 2SAB6 | 2L86 | 2021-07-26 08:00 | 2021-07-29 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-05 22:36
8-00526186 | Completed | 1L115 OOS | COB Insulator Replacements | 1L115, PVL T2 | 2021-07-26 08:00 | 2021-07-29 16:12 | 2 | Continuous | [6 empty] | Y | Y | N | Y | 2021-07-29 16:12
8-00531172 | Completed | TLR 2CB7 oos | CB Insp | TLR 2CB7 | 2021-07-26 08:00 | 2021-07-27 13:51 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-27 13:51
8-00525412 | Denied | 1L121 OOS | SCA LDR LMU UPGRADE 1CVT21- CABLE REPL | 1L121, LDR 1D21, SCA 1D21 | 2021-07-26 08:00 | 2021-07-27 16:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-07-21 11:21
8-00524135 | Denied | 5L11 oos | Insulator Repl | 5L11 | 2021-07-26 08:00 | 2021-07-30 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-21 14:08
8-00512790 | Denied | 5L96 OOS | Marker ball and end of life insualtor replacements | 5L96 | 2021-07-26 08:00 | 2021-08-06 16:00 | 2 | Continuous |  |  |  |  | 560 | 450 | N | N | N | Y | 2021-07-19 15:47
8-00583154 | Cancelled | 5L83 OOS | Repairs | 5L83 | 2021-07-26 08:00 | 2021-07-30 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-23 14:46
8-00534221 | Denied | LDR 1CB5 OOS | PN-1CB5 BFPN & CABLE REPL | LDR 1CB5 | 2021-07-26 08:00 | 2021-07-30 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-21 11:21
8-00539773 | Completed | CYP T3, 60CB6, 60CB7 OOS | CYP T3 Inspection, doble testing, 60CVT3 inspection | CYP T3 | 2021-07-26 08:00 | 2021-07-29 15:15 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-29 15:15
8-00538780 | Proposed | KHS 2CB5, 2CB6 OOS | INSP | KHS 2CB6, KHS 2CB5 | 2021-07-27 08:00 | 2021-07-30 08:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-01-21 10:56
8-00537469 | Cancelled | 1L115 out from DMR to PVL, PVL T2, QLC T2 OOS | QLC 1D2 & 1D22 INSP & BUS CUT 1B2 & PN 1D2 CN;1D2CB3 INSP;T2 NON-EL 1D2 CN, 25CB2 BFPN | 1L115, PVL T2, QLC T2 | 2021-07-27 08:00 | 2021-07-29 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-07-16 14:58
8-00525690 | Completed | SEL 5CB11 OOS | CB maintenance/Doble testing | SEL 5CB11, SEL T4 | 2021-07-27 08:00 | 2021-07-30 11:27 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-30 11:27
8-00526198 | Denied | 1L115 OOS | COB Insulator Replacements | 1L115 | 2021-07-27 08:00 | 2021-07-29 16:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-07-15 14:21
8-00616619 | Completed | GUI 5CX1 oos | insp | GUI 5CX1 | 2021-07-27 10:00 | 2021-11-06 10:44 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-22 03:30
8-00531188 | Denied | GMS T13 oos | GMS T13 and DS PM | GMS 2CB1, GMS T13 | 2021-07-27 16:00 | 2021-07-30 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-26 09:26
8-00530686 | Denied | WSN 5RX3 oos | RX NON-ELE PN PM | WSN 5RX3 | 2021-07-28 08:00 | 2021-07-28 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-26 09:49
8-00537923 | Completed | HWD 25CB1 OOS | BFPN | HWD T1 | 2021-07-28 08:00 | 2021-07-28 15:50 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-27 11:49
8-00537928 | Cancelled | 1L115 out from JPT, 1L110 out from JPT, JPT 1CB2, 1CB4 OOS | BFPN, CN | 1L115, 1L110, JPT 1CB2, JPT 1CB4 | 2021-07-30 08:00 | 2021-07-30 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-24 10:13
8-00494309 | Completed | GMS 5B7 oos | Insulator Repl and Insp on GMS 500kV DS | GMS 5B7, GMS 5D1CB8 | 2021-07-30 08:00 | 2021-08-09 14:53 | 48 | Continuous | [6 empty] | Y | N | Y | Y | 2021-08-09 18:35
8-00614914 | Completed | 5L1 oos | Energizing GMS 5CB2 | 5L1, GMS 5CB2, GMS 5CB3 | 2021-07-30 12:00 | 2021-07-30 16:36 | 2 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2021-08-03 11:58
8-00622334 | Completed | 5L1 oos | GMS 5D21 test operate | 5L1 | 2021-07-30 12:00 | 2021-07-30 16:41 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-30 16:41
8-00540128 | Completed | SON T2, 60D2 OOS | T2 Doble, INSP, Non-EL PN, 60D2 INSP | SON 60D2, SON T2 | 2021-08-03 08:00 | 2021-08-17 14:40 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-17 14:41
8-00537019 | Approved | GLD 1CB1 OOS | PN 1CB1 CN | GLD 1CB1 | 2021-08-03 08:00 | 2021-08-03 16:00 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-30 14:30
8-00437857 | Completed | WSN T2, 12RX1 oos | PCB Bushing Repl | WSN 12RX1, WSN T2 | 2021-08-03 08:00 | 2021-12-03 16:00 | 336 | Continuous | [6 empty] | N | Y | Y | Y | 2021-12-19 03:30
8-00525702 | Completed | SPL T1 OOS | SPL T1 PCB leak repair | SPL T1 | 2021-08-03 08:00 | 2021-09-07 15:01 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-07 15:01
8-00525709 | Cancelled |  |  | GDN T3 | 2021-08-03 08:00 | 2021-09-03 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-17 07:17
8-00524112 | Completed | KDY 5CX3 oos | CX Insp | KDY 5CX3 | 2021-08-03 08:00 | 2021-08-27 12:01 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-27 12:02
8-00530064 | Completed | SEL 5CB8 OOS | SEL 5CB8 Braker Fail PN testing | SEL 5CB8 | 2021-08-03 08:00 | 2021-08-03 14:43 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-03 14:48
8-00531441 | Proposed | 1L365 oos | DE Str Repl | 1L365 | 2021-08-03 08:00 | 2021-08-13 16:00 | 2 | Return Weekends | [6 empty] | N | N | Y | Y | 2021-03-16 13:39
8-00531178 | Proposed | FOX T1 oos | FOX 1D1 Control Repair | FOX T1 | 2021-08-03 08:00 | 2021-08-04 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2020-12-31 14:58
8-00531173 | Completed | TLR 2CB8 oos | CB Insp | TLR 2CB8 | 2021-08-04 08:00 | 2021-08-05 15:09 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-05 15:09
8-00530062 | Completed | SEL 5CB5 OOS | 5CB5 Braker Fail PN testing | SEL 5CB5, SEL T1 | 2021-08-04 08:00 | 2021-08-04 12:08 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-04 12:08
8-00518772 | Denied | 2L20 OOS | Detailed | 2L20 | 2021-08-04 08:00 | 2021-08-06 16:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-07-22 10:43
8-00537026 | Approved | PAL 1CB6 OOS | PN-1CB6 BF PN | PAL 1CB6 | 2021-08-04 08:00 | 2021-08-04 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-03 15:17
8-00537998 | Completed | ATH T1 OOS | INSP and DOBL PM | ATH T1, ATH 60CB1 | 2021-08-04 08:00 | 2021-08-13 12:52 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-13 12:52
8-00539789 | Approved | LYN 2CB2 OOS | LYN 2CB2 Protection testing | LYN 2CB2, LYN T1 | 2021-08-05 08:00 | 2021-08-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-04 13:57
8-00537028 | Completed | PAL 1CB8 OOS | PN- 1CB8 BF PN & LOCH | PAL 1CB8 | 2021-08-05 08:00 | 2021-08-05 12:11 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-05 12:12
8-00533632 | Proposed | MSA 12RX2 OOS | MSA 12RX2 Non-electrical trip testing | MSA 12RX2 | 2021-08-05 08:00 | 2021-08-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-07 19:41
8-00305821 | Cancelled | BSY Synchronous Condenser (G1) OOS | Inspection and Exciter Mtce | BSY G1 | 2021-08-09 01:00 | 2021-08-20 23:00 | 192 | Continuous | 2400 | 2800 |  |  |  |  | N | N | Y | Y | 2021-07-16 09:12
8-00525411 | Completed | 1L117, LDR 1CB3 OOS | PN-1CB3 BFPN & CABLE REPL | 1L117, LDR 1CB3 | 2021-08-09 08:00 | 2021-08-09 14:07 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-09 14:07
8-00530055 | Cancelled | NIC 5RX11 OOS | NIC 5RX11 NON-ELE and 5RXN11 INSP | NIC 5RX11 | 2021-08-09 08:00 | 2021-08-10 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-17 14:13
8-00530057 | Cancelled | VAS 5RX1 oos | VAS 5RX1 non-ELE PM and look for source of RX oil leak | VAS 5RX1 | 2021-08-09 08:00 | 2021-08-12 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-06-17 14:15
8-00533404 | Completed | 1L44 OOS | Structure Replacements | 1L44 | 2021-08-09 08:00 | 2021-08-11 16:05 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-11 16:05
8-00532032 | Proposed | WSP T1, 1CB1 oos | WSP 1CB1 Investigate/Repair Supervisory Alarm | WSP 1CB1, WSP T1 | 2021-08-09 08:00 | 2021-08-10 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-04 17:59
8-00534219 | Cancelled | QLC T2 OOS | LTC INSP | QLC T2 | 2021-08-09 08:00 | 2021-08-20 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-19 15:19
8-00540115 | Cancelled | SAY 1CB5 OOS | SAY 1CB5 Inspection | SAY 1CB5 | 2021-08-09 08:00 | 2021-08-12 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-09 10:20
8-00540154 | Cancelled | MSA 2CB8 OOS | MSA 2CB8 Inspection | MSA 2CB8 | 2021-08-09 08:00 | 2021-08-13 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-13 13:10
8-00539838 | Denied | 1L44, SEC 1B5 OOS | SEC 1D25 Inspection & repair, 1D1CB3 Inspection | SEC 1CB3, SEC 1CB5, 1L44, SEC 1B5 | 2021-08-09 08:00 | 2021-08-11 16:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-08-03 13:10
8-00538781 | Proposed | KHS T1 OOS | INSP | KHS T1 | 2021-08-09 08:00 | 2021-08-13 08:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-01-21 10:58
8-00621298 | Completed | 5L7 oos | WSN and KDS DS Insp | KDS 5B3, 5L7, KDY 5CX3, WSN 5B6, WSN 5RX6 | 2021-08-09 08:00 | 2021-08-10 11:34 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-08-27 12:02
8-00570932 | Denied | 5L98 OOS | disconnect inspection | NIC 5B15, NIC 5B25, NIC 5RX11, 5L98, VAS 5RX1, VAS 5B11 | 2021-08-09 08:00 | 2021-08-13 16:00 | 2 | Continuous |  |  |  |  | 560 | 450 | N | N | N | Y | 2021-07-21 17:30
8-00541681 | Cancelled | GTP T12 OOS | Oil Leak Repair | GTP T12 | 2021-08-09 08:00 | 2021-08-27 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-21 15:17
8-00531183 | Cancelled | GMS T12 oos | GMS T12 PM | GMS 1B5, GMS T12 | 2021-08-10 08:00 | 2021-08-15 16:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-06 15:14
8-00525413 | Completed | 1L118, LDR 1CB4 OOS | PN-1CB4 BFPN & CABLE REPL | 1L118, LDR 1CB4 | 2021-08-10 08:00 | 2021-08-10 13:10 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-10 13:10
8-00536577 | Denied | 5L41, KLY 5B4, 5RX4, 5CB4, 5CB14 OOS | KLY 5D34, 5D1CB14, 5D2CB4 INSP | 5L41, KLY 5RX4, KLY 5B4 | 2021-08-11 08:00 | 2021-08-15 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-09 10:33
8-00482092 | Cancelled | 60L38, 60L46, KI2 60CB7, 60CB9 OOS | REMOVE 60DCB8 AND BUS THROUGH | KI2 60CB7, KI2 60CB9, 60L46, 60L38 | 2021-08-12 07:00 | 2021-10-20 17:00 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-08-05 09:44
8-00531133 | Completed | DAW 1CB14, 1CX4 oos | CB Insp | DAW 1CX4, DAW 1CB14 | 2021-08-12 08:00 | 2021-08-12 12:14 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-10 22:32
8-00626777 | Cancelled | 5L71 oos (2 hours recall) | Solenoid Replacement and timing testing | 5L71, MCA 5B10, MCA 5RX4, MCA 5CB10 | 2021-08-17 07:00 | 2021-08-17 17:30 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-12 08:35
8-00629473 | Completed | 5L29 oos | Work in Cable Pits at NCT and TXW | 5L29 | 2021-08-17 08:00 | 2021-08-20 13:44 | 6 | Continuous | [6 empty] | Y | N | Y | Y | 2021-08-20 14:12
8-00535772 | Completed | OFD T1 oos | Transf Insp and Doble | OFD T1 | 2021-08-17 08:00 | 2021-08-19 16:02 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-19 16:02
8-00533548 | Completed | ACK 5CB5 OOS | ACK 5CB5 INSP AND DOBL | ACK 5CB5 | 2021-08-17 08:00 | 2021-08-19 14:09 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-08-19 14:09
8-00538782 | Proposed | SPN 60VT2 OOS | insp | 60L271, SPN 60CB1, SPN 60CB2 | 2021-08-17 08:00 | 2021-08-17 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-07 10:08
8-00527008 | Cancelled | CSN T2 OOS | PCB Bushing Replacement Program - Inspection & Doble PM | CSN T2 | 2021-08-17 08:00 | 2021-09-17 17:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2020-12-15 12:34
8-00532023 | Proposed | HUS T2 oos | PCB Leak Repairs | HUS T2 | 2021-08-17 08:00 | 2021-09-17 17:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-04 17:36
8-00532024 | Proposed | HUS T2 oos | Transf Insp and Doble | HUS T2 | 2021-08-17 08:00 | 2021-08-18 17:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-07 11:17
8-00531836 | Cancelled | TAC T2 & T5 oos | TAC-T2/T5 NON-ELE PN | TAC T2, TAC T5 | 2021-08-17 08:00 | 2021-08-17 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-13 13:59
8-00540131 | Completed | SON T3 OOS | T3 Doble,INSP, Non-EL PN, | SON T3 | 2021-08-17 14:00 | 2021-10-19 15:23 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-04 03:30
8-00533439 | Completed | DUG 1CB1 OOS | DUG 1CB1 INSP | DUG 1CB1 | 2021-08-18 08:00 | 2021-08-19 14:44 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-19 14:44
8-00536914 | Cancelled | JOR T2, 1CS2, SS2 OOS | 1CS2 CN, T2 NON-EL | JOR T2, JOR 1CS2 | 2021-08-19 08:00 | 2021-08-19 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-10 11:10
8-00588065 | Completed | 2L2 OOS from CKY to RBW | CKY Insulator Deficiency OSP | RBW T2, 2L2 | 2021-08-19 08:00 | 2021-08-22 17:40 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-08-22 17:40
8-00536915 | Cancelled | JOR T1, SS1, 1CS1, 25CB1 OOS | 1CS1 CN | JOR T1, JOR 1CS1 | 2021-08-20 08:00 | 2021-08-20 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-22 18:00
8-00629724 | Cancelled | 5L29 loaded at 600MW and 5L31 OOS | load test | 5L31 | 2021-08-22 08:00 | 2021-08-23 08:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-08-22 12:14
8-00306091 | Cancelled | BSY Synchronous Condenser (G3) OOS | Inspection and Exciter Mtce | BSY G3 | 2021-08-23 01:00 | 2021-09-03 23:00 | 192 | Continuous | 2400 | 2800 |  |  |  |  | N | N | Y | Y | 2021-07-16 09:13
8-00626652 | Completed | 2L352 OOS | HMH Transf Repl Project | 2L352, HMH T2, HMH 2B4 | 2021-08-23 07:00 | 2021-08-27 14:05 | 8 | Continuous | [6 empty] | N | Y | N | Y | 2021-08-27 14:06
8-00627812 | Completed | 5L71 OOS (24 hrs recall) | MCA rooftop project | 5L71 | 2021-08-23 08:00 | 2021-08-31 18:07 | 24 | Continuous | 2850 | 3150 | 2500 | 2500 | 850 | 1000 | Y | N | N | Y | 2021-08-31 18:07
8-00539837 | Cancelled | PHR T3, 1B1 OOS | PHR T3 Inspection, Doble testing, 1D3 Inspection | PHR T3, PHR 1B1 | 2021-08-23 08:00 | 2021-08-27 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-25 18:00
8-00541695 | Cancelled | PIK 2CB7 OOS | SF6 Leak Repair | PIK 2CB7 | 2021-08-23 08:00 | 2021-08-26 16:00 | 10 | Continuous | [6 empty] | N | N | Y | Y | 2021-04-23 09:32
8-00541686 | Completed | PIK 2CB18 OOS | SF6 Leak Repair | PIK 2CB18 | 2021-08-23 08:00 | 2021-08-27 12:30 | 10 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-27 14:08
8-00533540 | Denied | NAK T1 OOS | NAK T1 INSP, DOBL and non-ELE PM | NAK T1 | 2021-08-23 08:00 | 2021-08-27 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-19 14:43
8-00535774 | Proposed | OFD T4 | Transf PM | OFD T4 | 2021-08-23 08:00 | 2021-08-23 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-13 14:19
8-00540116 | Completed | SAY 1CB4 OOS | SAY 1CB4 Inspection | SAY 1CB4 | 2021-08-23 08:00 | 2021-10-20 10:55 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-20 10:55
8-00539793 | Completed | NOR 60CB1 OOS | NOR 60CB1 Inspection, Doble | NOR 60CB1 | 2021-08-23 08:00 | 2021-09-03 10:51 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-03 10:51
8-00538796 | Completed | 60L225 OOS | Disconnect and T5 Gas relay PM | KCL 2B3, 60L225 (13L), KCL T5 | 2021-08-23 08:00 | 2021-08-27 15:48 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-27 15:49
8-00512743 | Cancelled | 1L275 OOS | Replace structure and install markerballs | 1L275 (786L) | 2021-08-23 08:00 | 2021-08-25 16:00 | 4 | Noncontinuous | [6 empty] | N | N | N | Y | 2021-08-19 17:49
8-00533416 | Completed | 2L41 OOS | COB Glass Replacement | 2L41 | 2021-08-23 08:00 | 2021-08-26 17:15 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-26 17:15
8-00531834 | Cancelled | TAC T3 oos | Transf Insp & Doble | TAC T3 | 2021-08-23 08:00 | 2021-08-27 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-13 14:00
8-00526040 | Completed | NIC 5RX3 OOS | PCB Bushing Replacement | NIC 5RX3 | 2021-08-23 08:00 | 2021-10-22 16:22 | 120 | Continuous | [6 empty] | Y | N | N | Y | 2021-10-22 16:24
8-00530088 | Cancelled | 2L101 oos | Struture Repl | 2L101 | 2021-08-23 09:00 | 2021-08-27 14:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-15 08:49
8-00548918 | Completed | CKY T5 OOS | CKY Insulator Deficiency Program | CKY 2CB6, CKY 2CB8, CKY T5, CKY 2B6 | 2021-08-23 12:00 | 2021-09-02 17:45 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-09-02 17:45
8-00427338 | Completed | ALZ 2B3 OOS | Proximity outage for Fireproofing Microwave Tower | ALZ T3, ALZ T4, ALZ 2B3 | 2021-08-24 07:01 | 2021-09-05 09:16 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-05 09:23
8-00526258 | Completed | 2L56 Out from CAM | CPC BFPN PM | CAM T3, CAM T4, 2L56, CAM 2B5 | 2021-08-24 08:00 | 2021-08-24 15:45 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-08-24 15:46
8-00531174 | Completed | TLR 2CB3 oos | Breaker Insp and CT Doble | TLR 2CB3 | 2021-08-24 08:00 | 2021-08-24 13:06 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-24 13:06
8-00621266 | Denied | MDN 2RX2 OOS | CS to add platform for MDN 2CB15. | MDN 2RX2, MDN 2CB15 | 2021-08-24 08:00 | 2021-08-27 16:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | N | Y | 2021-08-13 11:50
8-00538507 | Denied | VIT 2CB2, 2CB3 OOS | BFPN | VIT 2CB2 | 2021-08-24 08:00 | 2021-08-25 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-18 13:06
8-00535019 | Proposed | MIN 2B8 oos | LNG Project - Test Energize new 2L107 | MIN 2B8 | 2021-08-24 08:00 | 2021-08-25 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-06-28 10:38
8-00531177 | Completed | TLR 2CB6 oos | CB Insp and CT Doble | TLR 2CB6 | 2021-08-24 13:00 | 2021-08-24 15:24 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-25 15:17
8-00526379 | Completed | 1L274 out from EFT | test energization of EFD T1 | EFD T1, EFD T2, 1L274 (887L) | 2021-08-24 23:00 | 2021-08-25 04:07 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-25 04:07
8-00531176 | Completed | TLR 2CB5 oos | CB Insp and CT Doble | TLR 2CB5 | 2021-08-25 08:00 | 2021-08-25 12:50 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-25 12:50
8-00533544 | Completed | ACK 5RX7 OOS | ACK 5CB47 INSP AND DOBL | ACK 5RX7, ACK 5CB47 | 2021-08-25 08:00 | 2021-08-27 14:29 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-08-27 14:29
8-00531175 | Completed | TLR 2CB4 oos | CB Insp and CT Doble | TLR 2CB4 | 2021-08-25 13:00 | 2021-08-26 00:55 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-10 22:26
8-00482080 | Completed | 60L37, 60L45, KI2 60B1 OOS | CLOSE TEMP BUS CUT | 60L45, 60L37, KI2 60B1 | 2021-08-26 07:00 | 2021-08-27 08:17 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-08-27 11:21
8-00512754 | Denied | 2L113 OOS | conductor repair | 2L113 | 2021-08-26 08:00 | 2021-08-26 16:00 | 4 | Continuous |  |  |  |  | 850 | 700 | N | N | N | Y | 2021-08-18 09:33
8-00536799 | Denied | CBK 2CB5 OOS | CBK REPAIR 2D2CB5 WPID 762654 | CBK 2CB6, CBK 2D1CB6, CBK 2D2CB5, 2L113 | 2021-08-26 08:00 | 2021-08-27 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-18 09:34
8-00538793 | Completed | NTL T1 OOS | INSP and DOBL on 60VTT1 | NTL T1 | 2021-08-26 08:00 | 2021-08-26 14:55 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-11-26 11:18
8-00531154 | Completed | FJN T3 oos | PCN Bushing Repl | FJN T3 | 2021-08-26 12:00 | 2021-09-24 11:36 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-10 03:30
8-00482089 | Completed | KI2 T1, 60CB3, 60CB4 OOS | REPLACE 60DCB4, 60CB4 | KI2 60CB3, KI2 60CB4, KI2 T1 | 2021-08-27 11:00 | 2021-10-07 15:18 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-10-07 15:18
8-00535768 | Cancelled | OFD T3 oos | OFD T3 Insp and Doble | OFD 60D3, OFD T3 | 2021-08-27 12:00 | 2021-09-03 16:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-29 18:00
8-00633533 | Completed | 5L3 Forced Outage | Conductor Damage Repair Required | 5L3, PCN 5D21 | 2021-08-27 12:57 | 2021-09-23 16:15 | NR | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2021-09-23 16:19
8-00547051 | Completed | 2L339, MKL OOS | Customer Line Maintenance | 2L339 | 2021-08-29 10:00 | 2021-09-02 16:00 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-09-02 16:06
8-00623510 | Completed | 5L91 OOS | structure replacement | 5L91 | 2021-08-30 08:00 | 2021-09-01 16:41 | 3 | Continuous |  |  |  |  | 560 | 500 | N | N | N | Y | 2021-09-01 16:43
8-00628904 | Completed | 5L41, KLY 5B4, 5RX4 OOS | 5L41/KLY DS PM & 5RX4 leak repair | 5L41, KLY 5RX4, KLY 5B4 | 2021-08-30 08:00 | 2021-09-03 12:32 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-09-03 12:32
8-00624736 | Denied | 2L17 OOS | Tower painting | 2L17 | 2021-08-30 08:00 | 2021-09-01 16:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-08-24 21:53
8-00630981 | Completed | CHP 5CX1, 5CB1CX1 OOS | Annual maintenance | CHP 5CB1CX1, CHP 5CX1 | 2021-08-30 08:00 | 2021-09-03 18:04 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-09-03 18:05
8-00536765 | Completed | SEL T2 OOS | T2 Gas relay PM, Disconnect PM | SEL T2 | 2021-08-30 08:00 | 2021-08-31 20:10 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-31 20:10
8-00533546 | Completed | NAK T2 OOS | NAK T2 INSP, DOBL and non-ELE PM | NAK T2 | 2021-08-30 08:00 | 2021-08-31 14:29 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-31 14:29
8-00535111 | Cancelled | 2L13 OOS | change out end of life structures on 2L13 inside the Capilano Watershed | 2L13 | 2021-08-30 08:00 | 2021-09-10 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-11 17:11
8-00540117 | Completed | SAY T3 OOS | SAY T3 Requires fabrication and installation of threaded plug over probe opening | SAY T3 | 2021-08-30 08:00 | 2021-09-10 13:56 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-10 13:57
8-00512987 | Denied | CHP 5CX1, 5CB1CX1 OOS | CHP 5CX1 Minor Inspection. CHP 5CBCX1 Inspection. | CHP 5CB1CX1, CHP 5CX1 | 2021-08-30 08:00 | 2021-09-06 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-20 11:19
8-00524898 | Cancelled |  |  | 2L112, NLY T2 | 2021-08-30 08:00 | 2021-10-01 08:00 | 2 | Continuous | 2000 | 2000 |  |  | 560 | 600 | N | N | N | Y | 2020-12-08 17:37
8-00527531 | Completed | 60L50 OOS | Detailed Inspection | DGR T2, 60L50 | 2021-08-30 08:00 | 2021-09-02 17:51 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-02 17:52
8-00537022 | Completed | PAL 1CB4 OOS | PN 1CB4 CN | PAL 1CB4 | 2021-08-31 08:00 | 2021-08-31 15:32 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-16 03:30
8-00541697 | Completed | PIK 2CB8 OOS | SF6 Leak Repair | PIK 2CB8 | 2021-08-31 08:00 | 2021-09-03 09:30 | 10 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-03 09:30
8-00530624 | Completed | 2L86 oos | Stru Repl | 2L86 | 2021-08-31 09:00 | 2021-09-10 14:33 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2021-09-10 14:33
8-00527586 | Completed | 60L71 OOS | Replace DS switches at ING | 60L71, ING 60D23 | 2021-09-01 08:00 | 2021-09-21 11:04 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-07 03:30
8-00531218 | Cancelled | 2L102 oos | BQN RX & CB PM | 2L102, BQN 2CB231, BQN 2CB22, BQN T3, BQN 2LRX23, BQN 2RX232 | 2021-09-01 08:00 | 2021-09-01 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-20 13:19
8-00531220 | Cancelled | BQN T3, 25HF4 oos | BQN T3 Non Electrical PN PM | BQN T3 | 2021-09-01 08:00 | 2021-09-01 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-26 09:47
8-00543443 | Proposed | 2L90 OOS | Structure Replacements | 2L90 | 2021-09-01 08:00 | 2021-09-12 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-02 17:21
8-00547294 | Cancelled | TAT T1 oos | TAT Maintenance | TAT 2CB2, TAT T1 | 2021-09-01 08:00 | 2021-09-01 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-19 08:58
8-00535025 | Proposed | MIN 2B2 oos | LNG Project - Add 2CB2 & Commission 2L99 line pn | MIN 2B2 | 2021-09-01 08:00 | 2021-09-17 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-30 14:43
8-00533539 | Completed | ACK T3 OOS | ACK T3 NON-ELE PM | ACK T3 | 2021-09-01 08:00 | 2021-09-02 15:12 | 3 | Continuous | [6 empty] | Y | N | N | Y | 2021-09-02 15:17
8-00539794 | Denied | NOR T1, 12CB1 OOS | NOR T1 Non-electrical trip testing, NOR 12CB1 Doble Testing | NOR T1 | 2021-09-02 08:00 | 2021-09-03 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-01 09:52
8-00539796 | Denied | NOR T3. 12CB3 OOS | NOR T3 Non-electrical trip testing | NOR T3 | 2021-09-02 08:00 | 2021-09-02 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-31 09:58
8-00631764 | Completed | 5L96 OOS | markerball and spacer replacement | 5L96 | 2021-09-02 08:00 | 2021-09-03 17:15 | 6 | Continuous |  |  |  |  | 560 | 450 | N | N | N | Y | 2021-09-03 17:19
8-00632143 | Completed | PCN 5RX1 oos | Top-up Gas | PCN 5RX1 | 2021-09-02 08:00 | 2021-09-02 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-02 15:55
8-00531128 | Completed | DAW 1CB12, 1CX2 oos | CB Insp | DAW 1CX2, DAW 1CB12 | 2021-09-02 08:00 | 2021-09-02 13:12 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-02 13:17
8-00512764 | Completed | 5L96 OOS | Replace defective insulators and install markerballs | 5L96 | 2021-09-02 08:00 | 2021-09-03 17:15 | 3 | Continuous |  |  |  |  | 560 | 450 | N | N | N | Y | 2021-09-03 17:19
8-00306147 | Cancelled | BSY Synchronous Condenser (G4) OOS | Inspection and Exciter Mtce | BSY G4 | 2021-09-06 01:00 | 2021-09-17 23:00 | 192 | Continuous | [6 empty] | N | N | Y | Y | 2020-10-15 14:37
8-00635277 | Approved | KIT SC2 OOS | RTA work | KIT SC2 | 2021-09-06 06:00 | 2021-09-06 18:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-03 15:23
8-00538785 | Completed | 1L274 Out from BCK | INSP | 1L274 (887L) | 2021-09-06 06:00 | 2021-09-06 16:56 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-06 16:56
8-00527533 | Completed | 60L58 DPT OOS | Detailed & Terminal Washing | 60L58 | 2021-09-06 13:00 | 2021-09-06 19:26 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-09-06 19:26
8-00635279 | Approved | KIT SC1 OOS | RTA work | KIT SC1 | 2021-09-07 06:00 | 2021-09-07 18:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-03 16:28
8-00533350 | Completed | 2L143 OOS | Overview & Jacket Testing & Oil Sample | 2L143 | 2021-09-07 07:00 | 2021-09-09 19:46 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-09-09 19:47
8-00531223 | Proposed | MIN 2CB1 oos | CB PM | MIN 2CB1 | 2021-09-07 08:00 | 2021-09-07 12:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-30 14:45
8-00529406 | Proposed | 1L364 out from GMS to 1D1L364 | Str Repl | 1L364 | 2021-09-07 08:00 | 2021-09-10 08:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2020-12-31 13:17
8-00512857 | Cancelled | 5L42 OOS | Insulators and Tower Hardware | 5L42 | 2021-09-07 08:00 | 2021-09-24 16:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-08-26 08:54
8-00524269 | Cancelled | 5L12 oos | Insulator Repl | 5L12 | 2021-09-07 08:00 | 2021-09-08 16:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-09-07 11:02
8-00513979 | Completed | 5L98 OOS | insulator replacement | 5L98, VAS 5RX1, VAS 5B11 | 2021-09-07 08:00 | 2021-09-09 19:12 | 3 | Continuous |  |  |  |  | 560 | 450 | N | N | N | Y | 2021-09-09 19:18
8-00525755 | Completed | 2L299 OOS | Structure Replacement | 2L299 | 2021-09-07 08:00 | 2021-09-10 15:00 | 6 | Continuous | [6 empty] | N | N | N | Y | 2021-09-10 15:00
8-00525353 | Denied | ING T9 OOS | EL Inspection & Doble | ING T9 | 2021-09-07 08:00 | 2021-09-17 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-08-31 09:53
8-00635310 | Completed | 5L3 OOS | Conductor Rrepair | 5L3 | 2021-09-07 08:00 | 2021-09-23 16:15 | NR | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-09-23 16:19
8-00632674 | Completed | KLY 5B12 oos | KLY 500kV DS Replacement | KLY 5B12, KLY SC2, KLY T4 | 2021-09-07 08:00 | 2021-09-11 18:28 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-09-11 18:28
8-00541680 | Completed | GLS T1 OOS | Qualitrol Installation | GLS T1 | 2021-09-07 08:00 | 2021-09-10 10:44 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-10 10:45
8-00550817 | Cancelled | KLY 5RX2 oos | Non-Elec PM | KLY 5RX2 | 2021-09-07 08:00 | 2021-09-08 17:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-29 08:55
8-00562033 | Completed | MLS 5CX2 oos | CX Insp | MLS 5CX2 | 2021-09-07 08:00 | 2021-09-10 10:59 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-10 11:00
8-00539767 | Completed | CAP T2, 12CB60 OOS | CAP T2 Non-Electrical trip testing | CAP T2 | 2021-09-07 08:00 | 2021-09-07 15:20 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-07 15:20
8-00537071 | Proposed | DMR T4, 1CB11 OOS | 1CB11 REPLACE | DMR T4, DMR 1CB11 | 2021-09-07 08:00 | 2021-09-27 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-28 17:08
8-00536767 | Completed | SEL T2 T3 OOS | T3 Gas relay PM, Disconnect PM | SEL 2CB6, SEL 2CB7, SEL T2, SEL T3 | 2021-09-07 08:00 | 2021-09-10 11:43 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-10 22:16
8-00531224 | Proposed | MIN 2CB3 oos | CB PM | MIN 2CB3 | 2021-09-07 12:01 | 2021-09-07 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-30 14:44
8-00531217 | Completed | 2L102 oos | Unroll Wrapped Bundle | SKA 2B7, 2L102, BQN 2CX1, BQN 2RX22, BQN 2RX231, BQN 2RX232 | 2021-09-08 07:00 | 2021-09-08 20:10 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-09-08 20:11
8-00533535 | Completed | VNT 1CB10 OOS | VNT 1CB10 AND 1D2CB10 INSP | VNT 1CB10, VNT 1B10 | 2021-09-08 08:00 | 2021-09-10 12:39 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-09-10 12:39
8-00533547 | Cancelled | BBR T1 OOS | CPC non-electrical PM | 60L10, BBR T1 | 2021-09-08 08:00 | 2021-09-08 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-01 10:06
8-00534230 | Cancelled | PAL T3 and 1CB7 OOS | PN-T3 NON ELEC , 1CB7 BFPN & PVIN | PAL 1CB7, PAL T3 | 2021-09-08 08:00 | 2021-09-10 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-07 09:35
8-00539766 | Completed | CAP T1, 12CB1 OOS | CAP T1 Non-Electrical trip testing, 12CB1 protection testing | CAP T1 | 2021-09-08 08:00 | 2021-09-09 15:05 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-09 15:05
8-00539973 | Proposed | FVW T1, 1CB1, 25CB1 OOS | FVW 1CB1, 25CB1 COND. protection testing | FVW T1 | 2021-09-08 08:00 | 2021-09-09 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-09 11:51
8-00633090 | Completed | 5L29 OOS | Required for repairs on M3 pothead at CCB | 5L29 | 2021-09-08 08:00 | 2021-09-19 17:16 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2021-09-19 17:16
8-00632963 | Completed | BQN 2CX1 oos | CX Repair | BQN 2CX1 | 2021-09-09 07:00 | 2021-09-09 17:14 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-10 08:40
8-00580144 | Completed | 2L76 OOS | MLE Expansion project | CBN 2CB10, CBN T7, MLN T6, MLN T5, 2L76 | 2021-09-09 07:00 | 2021-09-15 16:18 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-09-15 16:18
8-00534231 | Cancelled | PAL 1CB11 OOS | 1CB11 PVIN | PAL 1CB11 | 2021-09-09 08:00 | 2021-09-09 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-11 18:00
8-00526122 | Denied | 1L131 OOS | End of Life Structure Replacements | 1L131 | 2021-09-10 07:00 | 2021-09-10 17:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-03 13:28
8-00531228 | Proposed | MIN T2 oos | MIN T2 Cond & Non-Elec PN PM | MIN T2 | 2021-09-10 08:00 | 2021-09-10 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-04 17:17
8-00590327 | Completed | 1L143 OOS | To Install Temp poles for connection of M03 | 1L143 | 2021-09-13 07:00 | 2021-09-15 22:07 | 3 | Return Evenings | [6 empty] | Y | N | Y | Y | 2021-10-01 03:30
8-00576546 | Cancelled | 2L103 OOS | for LNG Canada | 2L103, MIN 2B6, MIN 2D6 | 2021-09-13 08:00 | 2021-09-15 16:00 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2021-09-08 13:54
8-00539776 | Denied | 60L99 out from GLR, GLR T2, 60CB1, 60CB2 OOS | GLR 60D2, 60DCB2, 60CB2 Inspection and doble test | GLR 60CB1, GLR 60CB2, GLR 60DCB2, GLR 60D2, GLR T2, 60L99 | 2021-09-13 08:00 | 2021-09-16 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-09 15:20
8-00533351 | Completed | 2L142 OOS | Overview | GTP T14, 2L142 | 2021-09-13 08:00 | 2021-09-15 15:35 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-15 15:42
8-00526257 | Completed | CRK 5CX1, CRK 5CB1CX1 OOS | PM INSPECTIONS, PY/SY PN | CRK 5CX1 | 2021-09-13 08:00 | 2021-09-18 14:26 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-18 14:56
8-00530659 | Cancelled | 2L96 oos | DE Str Repl | 2L96 | 2021-09-13 08:00 | 2021-09-23 16:00 | 2 | Return Weekends | [6 empty] | N | N | Y | Y | 2021-08-24 13:36
8-00514048 | Cancelled | BRT T4 OOS | proximity outage | BRT T4, BRT 3B5 | 2021-09-13 08:00 | 2021-09-16 16:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-09-09 14:56
8-00460920 | Cancelled | 2l293 OOS | structure replacement | 2L293 | 2021-09-13 08:00 | 2021-09-24 16:00 | 6 | Continuous |  |  |  |  | 560 | 600 | N | N | Y | Y | 2020-11-05 09:27
8-00253260 | Completed | BSY G4 OOS | Major Inspection | BSY T4, BSY T14, BSY G4 | 2021-09-13 08:00 | 2021-12-03 21:00 | 960 | Continuous | [6 empty] | N | N | Y | Y | 2021-12-03 23:07
8-00637723 | Completed | KIT 2CX2 OOS | RTA work | KIT SC2 | 2021-09-14 07:00 | 2021-09-15 16:37 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-15 16:37
8-00623095 | Completed | KLY 2RX2 OOS | Oil Leak Repair | KLY 2RX2 | 2021-09-14 08:00 | 2021-09-16 16:06 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-20 22:39
8-00539786 | Completed | JLN T2, 12CB12 OOS | JLN 12CB12 protection testing | JLN T2 | 2021-09-14 08:00 | 2021-09-14 14:17 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-14 14:18
8-00539974 | Cancelled | FVW T2, 1CB2, 25CB2 OOS | FVW 25CB2 Inspection, 25CB2 COND. protection testing; FVW T2 leak repair. | FVW T2, 1L33 | 2021-09-14 08:00 | 2021-09-17 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-16 18:00
8-00533633 | Completed | ACK 5MB1 | ACK 5D49, 5D1CB9, 5D1CB5, 5D1CB1 AND 5D47 INSP | ACK 5RX7, ACK 5B9, ACK 5CX1, ACK 5MB1 | 2021-09-14 08:00 | 2021-09-16 15:11 | 4 | Noncontinuous | [6 empty] | N | N | N | Y | 2021-10-07 03:30
8-00509172 | Cancelled | 60L1 out from BND, 60L35 out from BND, BND 60CB4, 60CB5, 60CB10, 60CB11 OOS | BND 60VT10 inspection and doble | BND 60CB11, BND 60CB5, 60L35, BND 60CB10, 60L1, BND 60CB4 | 2021-09-14 08:00 | 2021-09-15 12:00 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-09-09 10:52
8-00509174 | Cancelled | 60L26 out from BND, BND 60CB15, 60CB13 OOS | Proximity CL for work on BND 60VT10 | BND 60CB13, BND 60CB15, 60L26 | 2021-09-14 08:00 | 2021-09-16 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-09 10:47
8-00525319 | Approved | 2L142, GTP T14 OOS | GTP 1CB14, 2CB14 CN PM | GTP 1CB14, GTP 2CB14, GTP T14, 2L142 | 2021-09-14 08:00 | 2021-09-15 16:00 | 1 | Continuous | [6 empty] | N | N | N | Y | 2021-09-13 13:48
8-00531171 | Completed | TLR T1 oos | TLR T1 and DS OSYR/MNRI | TLR T1, TLR 2B3, TLR 2B9 | 2021-09-14 08:00 | 2021-09-15 13:18 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-15 13:18
8-00536619 | Completed | 5L42. KLY 5B2, 5RX2, 5CB2, 5CB12 OOS | KLY 5D32, 5D1CB12, 5D2CB2 INSP | 5L42, KLY 5B2, KLY 5RX2 | 2021-09-15 06:00 | 2021-09-16 18:18 | 2 | Return Evenings | [6 empty] | Y | Y | Y | Y | 2021-09-16 18:20
8-00537027 | Completed | DMR 2CB3 OOS | 2CT3 INSP | DMR 2CB3 | 2021-09-15 08:00 | 2021-09-15 15:32 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-15 17:54
8-00539787 | Completed | JLN T1, 12CB11 OOS | JLN T1 Non-electrical trip testing, 12CB11 protection testing | JLN T1 | 2021-09-15 08:00 | 2021-09-16 13:07 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-16 13:08
8-00530660 | Completed | 2L96 oos | BLW DS PM | 2L96, BLW T2, BLW 2B2 | 2021-09-15 09:30 | 2021-09-16 15:31 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-10-02 03:30
8-00509190 | Cancelled | 60L35 out from BND, BND 60CB5, 60CB4, 60CB10 OOS | Proximity CL for work on BND 60VT14 | BND 60CB5, 60L35, BND 60CB10, BND 60CB4 | 2021-09-15 12:00 | 2021-09-16 16:00 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-09-09 10:49
8-00509187 | Cancelled | 60L26 Out From BND 60D27, BND 60CB15, 60CB13 OOS | BND 60VT14 Inspection and doble | BND 60CB13, BND 60CB15, 60L26 | 2021-09-15 16:00 | 2021-09-17 16:00 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-09-03 08:19
8-00533348 | Completed | 2L145 OOS | Overview & Oil Sample & SA Replacement | 2L145 | 2021-09-15 17:00 | 2021-09-21 10:01 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-09-21 10:02
8-00532899 | Completed | 1L384 Partial Outage | DE Stru Repl | 1L384 | 2021-09-16 08:00 | 2021-09-23 10:37 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-23 10:37
8-00525403 | Cancelled | CBN T4 OOS | CPC non-el Pm, | CBN T4 | 2021-09-16 08:00 | 2021-10-01 16:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-09-15 12:55
8-00537929 | Completed | 1L116 out from JPT, JPT 1CB6 OOS | BFPN, CN | 1L116, JPT 1CB6 | 2021-09-17 08:00 | 2021-09-17 14:36 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-09-17 18:46
8-00537777 | Denied | 2L13 OOS | change out end of life structures on 2L13 inside the Capilano Watershed | 2L13 | 2021-09-17 08:00 | 2021-10-04 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-10 10:50
8-00517673 | Completed | 5L92 OOS | Station PM | CBK 5D44, 5L92, CBK 5RX4, CBK 5D44/5GDRXN4, CBK 5RXN4 | 2021-09-18 08:00 | 2021-09-25 15:17 | 2 | Continuous |  |  |  |  | 110 | 300 | N | N | N | Y | 2021-09-25 15:17
8-00525327 | Cancelled | 2L145 OOS | PIK 2CVT7 INSP | 2L145 | 2021-09-20 08:00 | 2021-09-20 16:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-08-23 13:39
8-00525400 | Completed | BSY 2CB11, 2CB10 OOS | 2D4 Inspection | BSY 2CB10, BSY 2CB11, BSY G4 | 2021-09-20 08:00 | 2021-10-15 10:01 | 48 | Continuous | [6 empty] | N | N | N | Y | 2021-12-03 23:07
8-00512763 | Completed | 5L92 OOS | Replace defective insulators | 5L92 | 2021-09-20 08:00 | 2021-09-24 15:36 | 4 | Continuous |  |  |  |  | 110 | 300 | N | N | N | Y | 2021-09-25 15:17
8-00512804 | Completed | 5L72 OOS | Spacer replacement and end of life insulators (recall time: 4 hours) | 5L72 | 2021-09-20 08:00 | 2021-09-24 17:01 | 4 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2021-09-24 17:01
8-00532039 | Cancelled | WSN T4, T6, 2B7 oos | WSN T6 Non-Elec PN PM | WSN T4, WSN T6, WSN 2B7 | 2021-09-20 08:00 | 2021-09-20 18:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-15 15:50
8-00533411 | Cancelled | VLM T3 OOS | VLM 25D21, 25D22 INSP | VLM T3 | 2021-09-20 08:00 | 2021-09-22 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-01 14:43
8-00533396 | Completed | 2L13 OOS | Circuit Refurbishment | 2L13 | 2021-09-20 08:00 | 2021-09-28 08:05 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-09-28 08:07
8-00531442 | Cancelled | SCK T1 oos | Non-Elec PN PM | SCK T1 | 2021-09-20 08:00 | 2021-09-20 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-14 16:35
8-00538788 | Completed | NTL T4 OOS | insp | NTL T4 | 2021-09-20 08:00 | 2021-09-23 14:18 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-23 14:18
8-00539784 | Cancelled | 60L69 out from HSB, HSB T1, 60CB3 OOS | HSB 60D21, 60D2CB1, 60DCB3 Inspection | HSB 60CB3, HSB T1, 60L69 | 2021-09-20 08:00 | 2021-09-23 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-13 11:22
8-00540031 | Completed | SAY 2CB6 OOS | SAY 2CB6 Inspection | SAY 2CB6 | 2021-09-20 08:00 | 2021-09-24 13:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-24 13:00
8-00537042 | Completed | CBL T1 OOS | CBL T1 INSP DOBL, 25CB1 BFPN | CBL T1 | 2021-09-20 08:00 | 2021-09-24 13:31 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-24 13:31
8-00536932 | Cancelled | DMR 5RX5, 5CB55 OOS | PN 5RX5- NON-EL ;PN-5CB55 CN | DMR 5RX5, DMR 5CB55 | 2021-09-20 08:00 | 2021-09-20 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-17 08:15
8-00533524 | Cancelled | ALZ T3/60D3 OOS | T3 EL Inspection & CPC non-el Testing, SS2 inspection, disconnect maint, | ALZ 60D2CB3, ALZ 60D2CB4, ALZ 60D3, ALZ T3 | 2021-09-20 08:00 | 2021-09-24 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-19 10:23
8-00535026 | Cancelled | MIN 2B4 oos | LNG Project - Remove 2CB3 & 2CT3 & Commission new 2L100 PN | MIN 2B2 | 2021-09-20 08:00 | 2021-09-30 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-20 15:29
8-00617244 | Denied | SON 60CB22 OOS | SON RTU upgrade projec | 60L20, SON 60CB22 | 2021-09-20 08:00 | 2021-09-30 16:00 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-16 15:16
8-00548924 | Completed | CKY 2B20, 2L13 OOS | CKY Insulator Deficiency Program | CKY 2CB2, CKY 2CB20, CKY 2D27, 2L13, CKY 2B1, CKY 2B20 | 2021-09-20 08:00 | 2021-09-28 08:07 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-14 03:30
8-00637079 | Completed | 5L31 OOS | Complete the cable clamp installations | 5L31 | 2021-09-20 08:00 | 2021-09-24 22:40 | 4 | Continuous | [6 empty] | Y | Y | N | Y | 2021-09-24 22:40
8-00525385 | Cancelled | ANN T3 OOS | PCB Bushing Replacement Program | ANN T3 | 2021-09-20 16:00 | 2021-10-22 17:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-22 18:00
8-00628552 | Cancelled | 1L146 OOS | replacing structures | 1L146 | 2021-09-21 07:00 | 2021-09-23 17:00 | 3 | Return Evenings | [6 empty] | N | N | Y | Y | 2021-09-11 08:23
8-00570764 | Denied | 1L146 OOS | structures work | CLD T3, 1L146 | 2021-09-21 07:00 | 2021-09-23 18:00 | 6 | Return Evenings | [6 empty] | N | N | Y | Y | 2021-09-16 13:13
8-00587619 | Denied | 1L146 OOS | replacing structures | 1L146 | 2021-09-21 07:00 | 2021-09-23 17:00 | 3 | Return Evenings | [6 empty] | N | N | Y | Y | 2021-09-14 11:00
8-00624314 | Completed | TKW 2B2/T2/T4/12RX2/1B11 OOS | disconnect & CVT replacement project | TKW 1D4, TKW T2, TKW T4, TKW 1B11, TKW 2B2, TKW 12RX2 | 2021-09-21 08:00 | 2021-09-21 15:47 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-22 11:05
8-00635248 | Denied | 2L277 (71L) OOS | Disconnect Insp on NLY 2D1CB6 & 2D25. | NLY 2D1CB6, NLY 2D25, 2L277 (71L) | 2021-09-21 08:00 | 2021-09-22 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-20 15:45
8-00524902 | Cancelled | HLD T2 | PCB Bushing Replacement | HLD T2 | 2021-09-21 08:00 | 2021-10-21 16:00 | 120 | Continuous | [6 empty] | N | N | N | Y | 2021-06-17 15:42
8-00427093 | Cancelled | 1L143 OOS | JOR- POSITION MO3 PORTABLE SUB FOR TM-0159 PROJECT | 1L143 | 2021-09-21 08:00 | 2021-09-21 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2020-09-18 11:32
8-00529411 | Completed | 2L309, DKT 2B2 oos | DS Repair | DKT 2D2CB2, DKT 2B2, 2L309 | 2021-09-21 08:00 | 2021-09-21 14:12 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-09-21 14:12
8-00533349 | Completed | 2L146 OOS | Overview & Jacket Test & Oil Sample | 2L146 | 2021-09-21 12:00 | 2021-09-26 11:34 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-09-26 11:43
8-00527585 | Cancelled | 60L31 OOS | Replace DS switches at ING | ING 60CB14, ING 60CB2, 60L31 | 2021-09-22 08:00 | 2021-10-08 08:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-16 11:52
8-00627527 | Completed | 2L56 OOS | PM INSP. | MPT 2CB3, MAN 2B6, 2L56 | 2021-09-22 08:00 | 2021-09-24 16:09 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-09-24 16:39
8-00639746 | Completed | 2L79 OOS | Working within LOA of 2L79 for MLE Project | 2L79 | 2021-09-22 08:00 | 2021-09-25 01:17 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-25 01:18
8-00613765 | Approved |  |  | JPT 1CB8, JPT 1B1, NFD T3, 1L152 | 2021-09-22 08:00 | 2021-09-22 16:00 | 1 | Continuous | [6 empty] | N | N | N | Y | 2021-09-21 11:42
8-00533618 | Completed | CKY T9 | NON-ELE PN | CKY T9 | 2021-09-22 08:00 | 2021-09-22 18:10 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-22 18:11
8-00536902 | Completed | GOW 2CB2 OOS | COMPRESSOR REPLACEMENT | 2L146, GOW 2CB2, GOW T5 | 2021-09-22 08:00 | 2021-09-23 16:05 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-09-26 11:43
8-00524272 | Completed | KDY 5CX2 oos | CX Insp | KDY 5CX2 | 2021-09-23 08:00 | 2021-10-06 13:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-06 13:00
8-00531155 | Completed | PPS T1 oos | PCB Bushing Repl | PPS T1 | 2021-09-24 08:00 | 2021-11-05 12:08 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-05 12:08
8-00538569 | Completed | SHA T2, 25CB2 OOS | TX: INSP CB: INSP, BFPN | SHA T2 | 2021-09-24 08:00 | 2021-09-24 15:45 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-24 15:46
8-00619839 | Cancelled | BSY G1 & BSY G4 OOS | BSY Chlorination outage - TTC calculation | BSY G1, BSY G4 | 2021-09-24 08:00 | 2021-09-24 16:00 | 0 | Continuous | [6 empty] | N | N | N | Y | 2021-09-17 17:34
8-00639737 | Completed | 5L72 OOS | Spacer damper and insulator replacements (recall time: 4 hrs) | 5L72 | 2021-09-24 12:00 | 2021-10-15 13:13 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-10-15 13:22
8-00508951 | Completed | 5L72 OOS | MCA 5CVT23 & Bushing Replacement Project. (Recall time:5days) | 5L72 | 2021-09-24 12:00 | 2021-10-15 13:21 | 120 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2021-10-15 13:22
8-00639770 | Completed | 2L143 OOS | annual Cable work | 2L143 | 2021-09-26 11:00 | 2021-09-28 11:52 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-09-28 11:52
8-00623494 | Completed | 2L294 Out from CBK to AAL | FBC work | 2L294 | 2021-09-27 05:00 | 2021-09-27 14:19 | 4 | Continuous |  |  |  |  | 850 | 500 | N | N | N | Y | 2021-10-04 13:50
8-00484809 | Denied | 2L294 Out from CBK | Disconnect Maintenance | CBK 2CB7, CBK 2CB8, 2L294, CBK T7, CBK 2MB4 | 2021-09-27 07:00 | 2021-09-28 19:00 | 2 | Continuous |  |  |  |  | 850 | 500 | N | Y | Y | Y | 2021-09-14 07:43
8-00518265 | Completed | SYA 5CX2 | station PM (recall time: 4 hrs) | 5L72, SYA 5CX2 | 2021-09-27 08:00 | 2021-09-29 13:51 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-10-15 13:22
8-00530621 | Cancelled | 2L94 oos | Str Repl | 2L94 | 2021-09-27 08:00 | 2021-10-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-24 10:30
8-00580237 | Completed | 2L123 Out from HWW, HWW T1 OOS | HWW T1 INSP/DOBL | HWW 1B2, HWW T1, 2L123 | 2021-09-27 08:00 | 2021-10-08 14:15 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-08 14:30
8-00557308 | Completed | BKL 1CX1 OOS | Inspection PM's. | BKL 1CX1 | 2021-09-27 08:00 | 2021-09-29 13:58 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-29 14:02
8-00642798 | Cancelled | 5L29 OOS | Installation of (LEVEL V) CTs to monitor cable current. | 5L29 | 2021-09-27 08:00 | 2021-09-29 16:00 | 4 | Continuous | [6 empty] | Y | N | N | Y | 2021-09-26 17:41
8-00537023 | Completed | GLD T4 OOS | PN-T4 NON-EL | GLD T4 | 2021-09-27 08:00 | 2021-09-27 15:15 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-27 15:15
8-00638889 | Completed | MCA 5RX3 OOS | deficiency work | MCA 5RX3 | 2021-09-27 16:00 | 2021-11-05 15:39 | 6 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-11-05 15:40
8-00537085 | Proposed | DMR T5, 1CB12 OOS | 1CB12 REPL | DMR T5, DMR 1CB12 | 2021-09-28 08:00 | 2021-10-18 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-28 17:07
8-00533538 | Cancelled | SMW 60D21 OOS, 60L48 OOS at SMW | DS Maintenance | SMW 60D21, 60L48 | 2021-09-28 08:00 | 2021-09-29 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-12 12:14
8-00525350 | Completed | 2L10 Out from ING | EL Disconnect Maintenance | ING 2D2CB10, 2L10 | 2021-09-28 08:00 | 2021-09-29 16:39 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-05 08:42
8-00644957 | Approved | KMO T1 aand T3 OOS | Urgent RTA work | KMO BANK 1/2, KMO BANK 5/6 | 2021-09-28 10:00 | 2021-09-29 18:00 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-28 10:13
8-00538482 | Cancelled | SHA 1D22 OOS | CN | SHA T2, SHA 1D22 | 2021-10-01 08:00 | 2021-10-01 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-22 14:36
8-00536151 | Proposed | 60L208 OOS | End of life structure replacement | 60L208 | 2021-10-03 08:00 | 2021-10-22 08:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-01-14 13:10
8-00646790 | Completed | ING 2RX1 & 2CX11 Forced OOS | Failure of ING 2CB21 | ING 2CB21, ING 2RX1, ING 2CX11 | 2021-10-04 07:11 | 2022-06-23 19:05 | NR | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-07-09 03:30
8-00644641 | Completed | 5L29 OOS | Installation of (LEVEL V) CTs to monitor cable current. | 5L29 | 2021-10-04 08:00 | 2021-10-06 19:42 | 4 | Continuous | [6 empty] | Y | N | N | Y | 2021-10-06 19:44
8-00635288 | Denied | 5L31 OOS | Add clamps to 5L31 cables | 5L31 | 2021-10-04 08:00 | 2021-10-15 16:00 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-28 22:05
8-00635903 | Completed | 5L83 OOS | Tranmission Line (helicopter work) | 5L83, RYC 5CX1 | 2021-10-04 08:00 | 2021-10-15 16:48 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-10-15 17:13
8-00568187 | Completed | GLT OOS | TX and LTC inspection and TX Doble test | 60L8, GLT 60CB1, GLT T1 | 2021-10-04 08:00 | 2021-10-14 11:51 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2021-10-30 03:30
8-00550976 | Cancelled | KLY 2RX2 oos | Non-Elec PM | KLY 2RX2 | 2021-10-04 08:00 | 2021-10-05 17:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-07-29 13:57
8-00544661 | Completed | MDN 2RX1, 2CX1, 2CX2, 2B14 OOS | EL disconnect & RX inspections, 2RX1 CPC non-el | MDN 2RX1, MDN 2CX2, MDN 2B14, MDN 2CX1, MDN 2D14 | 2021-10-04 08:00 | 2021-10-08 10:34 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-10-08 13:07
8-00582725 | Completed | 60L79 out From ING | 60D1CB9 replacement | ING 60CB9, ING 60CB7, ING 60CB13, SCT T1, 60L79 | 2021-10-04 08:00 | 2021-10-19 10:52 | 8 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-10-19 10:53
8-00591864 | Denied | 60L76 OOS | PM INSP | CVN 60CB2, CVN 60CB3, 60L76 | 2021-10-04 08:00 | 2021-10-08 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-23 13:38
8-00534222 | Completed | QLC T2 OOS | TFR-T2, 25CB2,25VT2,SS2 INSP, T2 DOBLE | QLC T2 | 2021-10-04 08:00 | 2021-10-07 13:16 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-07 13:16
8-00538052 | Completed | KSH T2, 1D2, 25CB2, SS2 OOS | T2: NON-EL, DOBL DS: INSPs CB: INSP | KSH T2, KSH 1D2 | 2021-10-04 08:00 | 2021-10-08 15:06 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-08 15:07
8-00539259 | Completed | 5L52 OOS | BPA outage | 5L52 | 2021-10-04 08:00 | 2021-10-04 12:06 | 2 | Continuous | 2000 | 2400 | 1500 | 1900 |  |  | N | N | Y | Y | 2021-10-04 12:12
8-00538007 | Cancelled | FMT T1 OOS | INSP PM | FMT T1 | 2021-10-04 08:00 | 2021-10-08 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-20 11:15
8-00539770 | Denied | 60L99 out from CYP, CYP 60CB7, 60CB9 OOS | CYP 60D29, 60D2CB9, 60D1CB8, 60D2CB8 Inspection | CYP 60CB9, CYP 60D1CB8, CYP 60D2CB8, CYP 60D2CB9, CYP 60D29, 60L99, CYP 60CB7 | 2021-10-04 08:00 | 2021-10-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-28 14:20
8-00525373 | Completed | ING T8 OOS | PCB Bushing Replacement Program | ING T8 | 2021-10-04 08:00 | 2021-10-06 10:00 | 120 | Continuous | [6 empty] | Y | Y | N | Y | 2021-11-18 15:28
8-00518790 | Completed | 2L44 OOS | Detailed | 2L44 | 2021-10-04 08:00 | 2021-10-08 10:12 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-10-24 03:30
8-00525196 | Completed | 60L59, ARN 60D1CB3, 60VT2, 60D1CB2 OOS | VT Insp/Doble, DS Maint. | 60L59 | 2021-10-04 08:00 | 2021-10-07 09:37 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-23 03:30
8-00525270 | Cancelled | MDN 2RX1, 2RX11, 2RX14, 2D11 OOS | EL disconnect & RX inspections, 2RX1 CPC non-el | MDN 2RX1, MDN 2CX2, MDN 2B14, MDN 2CX1 | 2021-10-04 08:00 | 2021-10-08 16:00 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-02-05 10:37
8-00511663 | Completed | 5L72 OOS | MCA T3 GIB Testing (recall time: 2 days) | 5L72, MCA 5B6, MCA 5B7, MCA 5B77, MCA T3, MCA LS2, MCA 5BT3T4, MCA 5BT3 | 2021-10-04 08:00 | 2021-10-12 15:35 | 48 | Continuous | [6 empty] | N | N | N | Y | 2021-11-18 20:00
8-00512769 | Completed | 2L293 OOS | Replace structures and timbers | 2L293 | 2021-10-04 08:00 | 2021-10-08 15:41 | 6 | Continuous |  |  |  |  | 560 | 600 | Y | N | Y | Y | 2021-10-08 15:41
8-00530623 | Proposed | 2L95 oos | DE Str Repl | 2L95 | 2021-10-04 08:00 | 2021-10-04 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-08 11:27
8-00530661 | Cancelled | 2L94 oos | DE Str Repl | 2L94 | 2021-10-04 08:00 | 2021-10-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-08 11:28
8-00531459 | Cancelled | LNT 1CB1 oos | CB Insp | LNT 1CB1 | 2021-10-04 08:00 | 2021-10-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-22 15:01
8-00533410 | Cancelled | BKL T1 OOS | BKL T1 INSP and DOBL | BKL T1 | 2021-10-04 08:00 | 2021-10-08 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-09-09 13:58
8-00529410 | Completed | 2L308 oos | Str Repl | 2L308 | 2021-10-04 09:00 | 2021-10-15 11:49 | 24 | Continuous | [6 empty] | Y | N | N | Y | 2021-10-15 11:49
8-00635858 | Completed | 60L22 out from BR1 | replace emergent structures Heli only access. | 60L22 | 2021-10-04 14:00 | 2021-10-13 18:52 | 10 | Continuous | [6 empty] | Y | N | Y | Y | 2021-10-13 18:52
8-00555125 | Completed | MIN T3 OOS | LNG project | MIN T3 | 2021-10-04 16:00 | 2021-10-18 10:32 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-03 03:30
8-00635494 | Completed | 1L157 OOS | WOS Timber Replacement | 1L125, 1L130, 1L137, 1L157 | 2021-10-04 22:00 | 2021-10-05 04:58 | 6 | Continuous | [6 empty] | Y | N | Y | Y | 2021-10-24 04:00
8-00544662 | Cancelled | MDN 2RX2 OOS | CPC non-el PM | MDN 2RX2, MDN 2D13 | 2021-10-05 08:00 | 2021-10-07 16:00 | 3 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-10-05 06:22
8-00619800 | Cancelled | 5L62 Outage | GLN 5RX5 INSP, NON-EL PN | 5L62, GLN 5RX5N, GLN 5RX5 | 2021-10-05 08:00 | 2021-10-05 18:00 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-10-04 08:51
8-00532031 | Completed | HZN T2 oos | Insp and doble HZN T2, COND HZN T2 | HZN T2 | 2021-10-05 08:00 | 2021-10-06 17:44 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-22 03:30
8-00531462 | Cancelled | KAL T1 oos | Transf. Cond. | KAL T1 | 2021-10-05 08:00 | 2021-10-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-03-12 12:54
8-00525272 | Cancelled | MDN 2RX2 OOS | CPC non-el PM | MDN 2RX2 | 2021-10-05 08:00 | 2021-10-07 16:00 | 3 | Continuous | [6 empty] | N | N | N | Y | 2021-02-05 10:44
8-00565237 | Completed | 1L220 Out from BKL and BKL T1 OOS | CB replacement | BKL 1CB2, BKL 1CB6, BKL T1, 1L220 | 2021-10-05 12:00 | 2021-10-19 11:22 | 48 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-15 15:05
8-00537708 | Proposed | 1L220 OOS | Detailed | 1L220 | 2021-10-06 08:00 | 2021-10-08 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-01-19 11:33
8-00531463 | Proposed | KAL T2 oos | Transf. Cond. | KAL T2 | 2021-10-06 08:00 | 2021-10-06 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-04 17:18
8-00533414 | Cancelled | 1L220 Out from BKL | DS inspection | BKL 1CB2, BKL 1CB6, BKL T1, 1L220 | 2021-10-06 08:00 | 2021-10-08 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-10 18:00
8-00532030 | Completed | HZN T1 oos | Transf Insp & Doble | HZN T1 | 2021-10-06 13:00 | 2021-10-08 17:21 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-08 17:24
8-00639671 | Completed | SPD OOS | connect the high side of M09 for the SPD T1 PCB bushing replacement. | 60L285, 60L281 | 2021-10-06 23:00 | 2021-10-07 02:41 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-07 02:42
8-00532904 | Proposed | 1L384 Partial Outage | DE Str Repl | 1L384 | 2021-10-07 08:00 | 2021-10-18 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-06 13:06
8-00514053 | Cancelled | BRT T4 , 3D4 OOS | remove O/H conductor from 3D4 and 230KV gantry and install new gantry Tower near 3D4 and conductor O/H line. | BRT T4, BRT 3B5 | 2021-10-08 08:00 | 2021-10-12 16:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2021-08-18 09:08
8-00537025 | Cancelled | GLD T3, 1VT4 OOS | PN-T3 NON ELEC, 1VT4 DOBL | GLD 1B5, GLD T3 | 2021-10-08 08:00 | 2021-10-08 16:00 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-08 13:17
8-00521690 | Cancelled | 2L113, NTL 60 kV bus outage | NTL 60D21 realignment | 2L113, 60L285, 60L288, 60L292, 60L281 | 2021-10-11 08:00 | 2021-10-11 20:00 | 2 | Continuous |  |  |  |  | 850 | 700 | N | N | N | Y | 2021-09-20 08:02
8-00524271 | Cancelled | 5L2 oos | Insul Repl | 5L2 | 2021-10-12 08:00 | 2021-10-13 16:00 | 3 | Continuous | [6 empty] | N | Y | Y | Y | 2021-09-29 15:42
8-00517683 | Completed | 2L112 OOS | Oil spill containment installation | 2L112, NLY T1, NLY 2B4, NLY T2, NLY 2B5 | 2021-10-12 08:00 | 2021-11-10 16:38 | 2 | Continuous | 2000 | 2000 | 2500 | 2500 | 560 | 600 | N | N | Y | Y | 2021-11-10 16:42
8-00525800 | Completed | CSQ T2 and 2B4 OOS | T2 Inspection & Doble, DS, RX & SS inspections | CSQ T2, CSQ 2B4 | 2021-10-12 08:00 | 2021-10-15 17:20 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-20 11:55
8-00531460 | Completed | LNT 1CB2 oos | CB Insp | LNT 1CB2 | 2021-10-12 08:00 | 2021-10-14 08:43 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-14 08:48
8-00647691 | Cancelled | 60L4 & 60L5 & 60L6 OOS | Station Outage to LB1 | 60L6, 60L5, 60L4, LB1 60B1, LB1 60B2 | 2021-10-12 08:00 | 2021-10-12 16:00 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2021-10-08 15:29
8-00632922 | Completed | MDN 2RX2 OOS | Replace MDN 2CB15 mechanism | MDN 2RX2, MDN 2CB15 | 2021-10-12 08:00 | 2021-10-14 15:33 | 8 | Continuous | [6 empty] | N | N | N | Y | 2021-10-14 15:44
8-00544326 | Denied | CKY T6 OOS | Non Electrical trip testing and T6 PY/SY PN | CKY T6 | 2021-10-13 08:00 | 2021-10-13 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-06 13:16
8-00618514 | Completed | 5L1 OOS | Repair and Condition assessment of KDY 5BP1, 5D21/3 | 5L1, KDY 5CX1 | 2021-10-13 08:00 | 2021-10-14 18:49 | 2 | Continuous | 2000 | 2400 |  |  |  |  | Y | Y | N | Y | 2022-03-13 14:19
8-00533639 | Completed | VNT 1CB11 OOS | inspections | VNT 1CB11 | 2021-10-13 08:00 | 2021-10-14 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-20 18:39
8-00539753 | Completed | 2L14 and WLT 2B6 OOS | Station Disconnect inspections | 2L14, WLT 2CB9, WLT 2D1CB6, WLT 2D21, WLT 2D4, WLT 2B5, WLT 2B6 | 2021-10-13 08:00 | 2021-10-25 12:12 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-10 03:30
8-00540007 | Denied | 2L14 OOS | change out end of life structures inside the Capilano Watershed | 2L14 | 2021-10-13 08:00 | 2021-10-27 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-06 11:37
8-00527539 | Completed | 2L31 OOS | Detailed & Oil Sample & CV Replacement | 2L31 | 2021-10-13 08:00 | 2021-10-15 15:20 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-10-15 15:31
8-00635867 | Completed | 60L22 Out from LAJ | Replace emergent transmission structures Heli access only. | 60L22 | 2021-10-13 15:30 | 2021-10-22 16:07 | 10 | Continuous | [6 empty] | Y | N | N | Y | 2021-11-05 15:01
8-00530063 | Cancelled | 5L1, GMS 5RX1 oos | GMS DS PM | 5L1, GMS 5RX1, GMS 5B2 | 2021-10-14 08:00 | 2021-10-17 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-04 09:56
8-00531461 | Completed | LNT 1CB4 oos | CB Insp | LNT 1CB4 | 2021-10-14 08:00 | 2021-10-15 14:28 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-15 14:29
8-00526151 | Cancelled | 2L128 OOS | End of Life Structure Replacements | HWW T2, 2L128 | 2021-10-15 08:00 | 2021-10-15 16:00 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-10-14 10:12
8-00642616 | Completed | 60L11 OOS | replace structures and conductor | 60L11 | 2021-10-15 12:00 | 2021-10-20 12:55 | 12 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-10-20 12:55
8-00647418 | Completed | 5L72 OOS | Restore 5L72 temporary linecut at structure 0-7. | 5L72 | 2021-10-15 12:30 | 2021-10-15 15:26 | 1 | Continuous | 2000 | 2400 |  |  |  |  | N | N | N | Y | 2021-10-15 15:26
8-00647413 | Completed | 5L72 OOS | MCA 5CVT23 & Bushing Replacement Project (recall time: 5 days) | 5L72 | 2021-10-15 15:00 | 2021-10-24 18:57 | 120 | Continuous | 2000 | 2400 |  |  |  |  | Y | Y | N | Y | 2021-10-24 18:57
8-00631504 | Denied | KLY 5B12, T4, SC2 oos | KLY DS Repl | 5L42, KLY 5B12, KLY 5RX2, KLY SC2, KLY T4 | 2021-10-18 08:00 | 2021-10-22 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-10-01 08:44
8-00624665 | Denied |  |  | 2L14 | 2021-10-18 08:00 | 2021-10-22 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-06 11:35
8-00540114 | Completed | SAY 1CB6 OOS | SAY 1CB6 Inspection | SAY 1CB6 | 2021-10-18 08:00 | 2021-10-21 11:35 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-21 14:41
8-00533640 | Completed | VNT T6 OOS | VNT T6 INSP AND DOBL PM | VNT T6 | 2021-10-18 08:00 | 2021-10-22 11:43 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-22 11:43
8-00535029 | Cancelled | MIN 2B8 oos | LNG Project - Connect and Test new MIN 2CX1 | MIN 2B8 | 2021-10-18 08:00 | 2021-10-20 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-20 14:37
8-00536126 | Cancelled | 60L22 OOS | Structure Replacements | 60L22 | 2021-10-18 08:00 | 2021-10-30 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-10-07 13:49
8-00526154 | Completed | 1L127 OOS | End of Life Structure Replacements | 1L127 | 2021-10-18 08:00 | 2021-10-19 16:03 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-10-19 16:03
8-00533403 | Cancelled | 2L47 OOS | Structure Replacements | 2L47 | 2021-10-18 08:00 | 2021-10-22 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-05-20 14:52
8-00526015 | Completed | NIC 5RX3 OOS | INSP and DOBL | NIC 5RX3 | 2021-10-18 08:00 | 2021-10-22 16:24 | 8 | Continuous | [6 empty] | N | N | N | Y | 2021-10-22 16:24
8-00524895 | Completed | 5L94 & CBK 5RX5 OOS | NERC PM | CBK 5CB21, CBK 5CB23, 5L94 / 1201L, CBK 5RX5 | 2021-10-18 08:00 | 2021-10-27 19:53 | 4 | Continuous |  |  |  |  | 50 | 100 | N | N | N | Y | 2021-10-27 19:53
8-00512965 | Completed | 5L45, MDN T3 OOS | MDN 5CB4 Inspection and Doble test, MDN 5D22 Inspection | 5L45, MDN 12RX31, MDN 12RX32, MDN 5CB4, MDN 5D22, MDN T3, MDN 5MB2 | 2021-10-18 08:00 | 2021-10-22 17:25 | 8 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | N | Y | 2021-10-22 17:26
8-00366128 | Cancelled | 5L2 & GMS 5B4 OOS | GMS Reactor Replacement Project | 5L2, GMS 5RX2, GMS 5B4 | 2021-10-18 08:00 | 2021-10-20 08:00 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-10-14 13:19
8-00536921 | Proposed | DMR T6/ 1CB13 OOS | 1CB13 REPL | DMR T6, DMR 1CB13 | 2021-10-19 08:00 | 2021-11-13 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-28 17:03
8-00534659 | Completed | MDN T3 OOS | MDN 12D31 Inspection | MDN 12RX31, MDN 12RX32, MDN T3 | 2021-10-19 08:00 | 2021-10-22 14:42 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-22 14:43
8-00534395 | Submitted | LBH 60CBCX1 OOS | PN-60CBCX1 CN | LBH 60CBCX1, LBH 60CX1 | 2021-10-19 08:00 | 2021-10-19 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-12-01 14:51
8-00534397 | Cancelled | LBH 60CBCX2 OOS | PN-60CBCX2 CN | LBH 60CBCX2, LBH 60CX2 | 2021-10-19 08:00 | 2021-10-19 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-12 09:04
8-00632054 | Completed | 2L94 oos | Structure Repl | 2L94, SCK 2D1, SCK 2D22 | 2021-10-19 08:00 | 2021-10-22 15:03 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-22 15:03
8-00638205 | Completed | 2L51 OOS from HPN to BND | Storm drain crossing under circuit | 2L51 | 2021-10-19 08:00 | 2021-10-22 13:54 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-22 13:54
8-00427097 | Cancelled | 1L143 OOS | JOR- POSITION MO3 PORTABLE SUB FOR TM-0159 PROJECT | 1L143 | 2021-10-19 10:00 | 2021-10-19 14:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-09-08 11:22
8-00624339 | Completed | TKW T5 OOS | TKW disconnect & CVT replacement project | TKW T5, TKW 1B3 | 2021-10-19 12:00 | 2021-11-01 10:56 | 12 | Continuous | [6 empty] | N | Y | N | Y | 2021-11-01 17:15
8-00572027 | Cancelled | 1L143 OOS from SOO to CLD | Replace 12 end of life structures on | 1L143 | 2021-10-20 07:00 | 2021-10-22 18:00 | 6 | Return Evenings | [6 empty] | Y | Y | Y | Y | 2021-10-14 17:25
8-00534382 | Cancelled | LBH 60CB1, 60CB2 OOS | PN-60CB1 CN, 60CB2 CN | LBH 60CB1, LBH T11 | 2021-10-20 07:00 | 2021-10-20 12:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-12 09:05
8-00525348 | Cancelled | 2L57 Out from ING | EL Disconnect Maintenance | ING 2D2CB7, 2L57 | 2021-10-20 08:00 | 2021-10-20 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-22 18:00
8-00525405 | Completed | CBN T7 OOS | CPC non-el Pm | CBN T7 | 2021-10-20 12:01 | 2021-10-21 14:44 | 2 | Continuous | [6 empty] | Y | Y | N | Y | 2021-10-21 14:44
8-00647966 | Completed | 5L12 oos | Conductor Repair | 5L12 | 2021-10-21 11:00 | 2021-10-21 16:08 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-10-21 16:08
8-00645342 | Cancelled | 1L114 OOS | replace defective insulators | 1L114 | 2021-10-22 08:00 | 2021-10-25 16:00 | 2 | Return Weekends | [6 empty] | N | Y | N | Y | 2021-10-15 12:03
8-00654542 | Completed | 1L275 Forced OOS | line WORK REQUIRED | 1L275 (786L) | 2021-10-23 03:51 | 2021-10-28 17:05 | NR | Continuous | [6 empty] | N | N | Y | Y | 2021-10-28 17:37
8-00539275 | Proposed | SBR T1 OOS | Non-ELE PM | SBR T1 | 2021-10-23 08:00 | 2021-10-23 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-01-22 11:14
8-00525420 | Denied | 1L112 OOS | End of Life Structure Replacements | 1L112 | 2021-10-24 08:00 | 2021-10-24 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-18 15:40
8-00526021 | Cancelled | NIC 5RX8 OOS | PCB bushing | NIC 5RX8 | 2021-10-25 08:00 | 2021-11-26 17:00 | 336 | Continuous | [6 empty] | N | N | N | Y | 2021-10-15 13:14
8-00533496 | Completed | SAM T3 OOS | SAM T3 non-ELE, INSP and DOBL PM | SAM T3 | 2021-10-25 08:00 | 2021-11-02 16:36 | 8 | Continuous | [6 empty] | N | N | N | Y | 2021-11-02 16:36
8-00537086 | Completed | DMR SVC OOS | 1CB16 & 1CB17 BF PN | DMR 1CB17, DMR 1CB16, DMR SVC | 2021-10-25 08:00 | 2021-10-25 14:45 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-26 16:02
8-00619827 | Completed | 5L2 OOS | Placeholder for energizing new GMS 5RX2 & 5NRX2 | 5L2, GMS 5RX2, WSN 5CB3, GMS 5B4 | 2021-10-25 08:00 | 2021-10-26 17:01 | 8 | Continuous | [6 empty] | Y | N | N | Y | 2021-10-26 17:05
8-00616668 | Cancelled | MIN T2 OOS | MIN LNG:Remove MIN SS1 OLD and 25DSS1 OLD | MIN T2 | 2021-10-25 08:00 | 2021-10-29 14:00 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-21 14:56
8-00537089 | Cancelled | DMR 1CB16 OOS | PN- 1CB16 BF PN | DMR 1CB16, DMR SVC | 2021-10-25 09:00 | 2021-10-26 16:00 | 2 | Return Evenings | [6 empty] | N | N | Y | Y | 2021-10-20 15:24
8-00538816 | Cancelled | KCL 2CB2 OOS | BFPN test | KCL 2CB2 | 2021-10-26 08:00 | 2021-10-26 12:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-08 17:52
8-00621565 | Completed | 1L121 OOS | Line crews to replace 1L121 structures: 4/3, 4/8, 4/9, 5/1, 5/2, 5/4, 5/5. | 1L121 | 2021-10-26 08:00 | 2021-10-29 15:52 | 2 | Continuous | [6 empty] | Y | Y | N | Y | 2021-11-14 03:30
8-00574716 | Cancelled | 5L71 OOS | NIC 5D24 Inspection. (recall: 2 hrs) | 5L71, NIC 5B18, NIC 5RX4 | 2021-10-26 08:00 | 2021-10-26 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-20 13:26
8-00526134 | Completed | 1L105 OOS | End of Life Structure Replacements | 1L105 | 2021-10-26 08:00 | 2021-10-29 17:23 | 2 | Continuous | [6 empty] | Y | Y | N | Y | 2021-10-29 17:23
8-00527551 | Completed | 2L40 out from BND to NEL | Detail Cable Inspections | 2L40, NEL 2CB4, NEL T4 | 2021-10-26 08:00 | 2021-10-29 18:00 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-10-29 18:00
8-00525801 | Denied | CSQ 2GD1, 12D81, SS1, 12D1, 12D11 OOS | DS & SS Inspections | CSQ 2B2 | 2021-10-26 08:00 | 2021-10-29 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-19 16:19
8-00633009 | Completed | BQN 2CX1 OOS | CX PM | BQN 2CX1 | 2021-10-26 10:15 | 2021-10-28 17:23 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-28 17:23
8-00533627 | Cancelled | UHT 3CB1 OOS | CB TRIP TESTING | UHT 3CB1 | 2021-10-26 11:00 | 2021-10-26 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-08 16:02
8-00538817 | Cancelled | kcl 2cb3 oos | bfpn test | KCL 2CB3 | 2021-10-26 12:00 | 2021-10-26 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-07-08 17:52
8-00536913 | Completed | PIK 2CB7/2CB8 OOS | PVRP & AFCH | PIK 2CB7 | 2021-10-27 07:00 | 2021-10-27 12:31 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-27 12:33
8-00538577 | Completed | VIT SC2 OOS | MNRI, MJRI, H2 UPGRADE | VIT SC2 | 2021-10-27 08:00 | 2021-11-19 18:51 | 72 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-19 18:51
8-00634288 | Completed | 2L44 OOS | PM INSP | MAN 2CB2, 2L44, SPG 2D21 | 2021-10-27 08:00 | 2021-10-28 13:15 | 2 | Continuous | [6 empty] | Y | Y | N | Y | 2021-10-28 13:16
8-00631505 | Completed | KLY 5B12, KLY T4 & KLY SC2 OOS | KLY 5B12 SY PN Upgrade | KLY 5B12, KLY SC2, KLY T4 | 2021-10-27 08:00 | 2021-11-01 14:46 | 5 | Continuous | [6 empty] | Y | Y | N | Y | 2021-11-01 14:46
8-00568437 | Completed | 5L13 OOS | KLY Disconnect PM | 5L13, WSN 5B7, WSN 5RX7, KLY 5B5 | 2021-10-27 08:00 | 2021-10-29 15:43 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-11-05 15:01
8-00524266 | Completed | MLS 5CX3 oos | CX Insp | MLS 5CB1CX3, MLS 5CX3 | 2021-10-27 08:00 | 2021-11-19 12:04 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-19 12:04
8-00533628 | Cancelled | UHT 3CB3 OOS | CB TRIP TESTING | UHT 3CB3 | 2021-10-27 09:00 | 2021-10-27 12:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-08 16:01
8-00533629 | Cancelled | UHT 3CB4 OOS | CB TRIP TESTING | UHT 3CB4 | 2021-10-27 13:00 | 2021-10-27 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-08 16:02
8-00528126 | Completed | 60L33 OOS, SEA PN/TC: , YVR Op. Restr.: Test Operate Auto Changeover Scheme | SEA 60KV Changeover | SEA 60D23, SEA 60D24, 60L33 | 2021-10-28 02:00 | 2021-10-28 02:55 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-10-28 02:56
8-00548900 | Completed | 60L62 part out at WLT | for structure relocations | 60L62 | 2021-10-28 08:00 | 2021-11-01 13:19 | 96 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-01 13:19
8-00654266 | Completed | 5L42 OOS | LOA for KLY work | 5L42, KLY 5B2, KLY 5RX2 | 2021-10-28 08:00 | 2021-10-28 16:27 | 4 | Continuous | [6 empty] | Y | Y | Y | Y | 2021-10-28 16:27
8-00626348 | Cancelled | KLY T4, SC2, 2RX2 oos | KLY DS Repl, KLY 5B12 PY PN Upgrade and PCB Lighting Repl | 2L93, KLY 2RX2, KLY 2B6, KLY 2B7 | 2021-10-29 08:00 | 2021-10-29 16:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-10-28 10:59
8-00656989 | Completed | 2L99 oos | Emergency Hotspot Repair on MIN 2D25 | 2L99, MIN 2B4, MIN 2B1, MIN 2B2, MIN 2B3 | 2021-10-31 11:00 | 2021-10-31 15:39 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-31 15:42
8-00550500 | Completed | 2L299 and KCL 2B14 OOS | PT replacement | 2L299, KCL 2B14, KCL 2CB14, KCL 2CB15, KCL 2CB16 | 2021-11-01 08:00 | 2021-11-26 16:21 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-11-26 16:22
8-00533611 | Cancelled | CKY 60CB1 OOS | CB TRIP TESTING | CKY 60CB1 | 2021-11-01 08:00 | 2021-11-01 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-14 12:05
8-00533612 | Completed | CKY 60CB10 OOS | CB TRIP TESTING | CKY 60CB10 | 2021-11-01 08:00 | 2021-11-04 10:03 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-04 10:03
8-00538568 | Completed | SHA T1, 25CB1 OOS | TX: INSP CB: INSP, BFPN | 1L14, SHA T1 | 2021-11-01 08:00 | 2021-11-12 10:38 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-12 10:38
8-00526044 | Completed | NIC 5RX10 OOS | PCB bushing replacement | NIC 5RX10 | 2021-11-01 08:00 | 2022-02-28 14:21 | 120 | Continuous | [6 empty] | N | N | N | Y | 2022-02-28 14:53
8-00533412 | Cancelled | NIC T5 OOS | NIC T5 INSP and DOBL | NIC T3, NIC T5 | 2021-11-01 08:00 | 2021-11-09 16:00 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-10-22 16:41
8-00533465 | Completed | DUG 1B3 AND T3 OOS | inspection | DUG 1CB2, DUG 1B3, DUG T3, DUG 1CB3 | 2021-11-01 08:00 | 2021-11-30 15:17 | 6 | Continuous | [6 empty] | N | N | N | Y | 2021-12-16 03:30
8-00532002 | Denied | SRS T2 oos | PCB Bushing Replacement | SRS T2 | 2021-11-01 08:00 | 2021-12-01 12:00 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-28 13:46
8-00531164 | Denied | PPS T2 oos | PCB Bushing Repl | PPS T2 | 2021-11-01 08:00 | 2021-11-26 12:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-26 10:35
8-00525804 | Completed | 2L20 and CSQ 2B7 OOS | DS Inspections at CSQ | CSQ 2CB1, MAN 2CB2, CSQ 2B7, CSQ 2CB7, 2L20 | 2021-11-01 08:00 | 2021-11-05 11:38 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-11-05 11:39
8-00525796 | Proposed | 1l209 oos | strcuture replacement | 1L209 | 2021-11-01 08:00 | 2021-11-12 07:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2020-12-10 16:59
8-00617256 | Cancelled | SON 60CB21 OOS | SON RTU upgrade project. | 60L21, SON 60CB21 | 2021-11-01 09:00 | 2021-11-11 16:00 | 3 | Continuous | [6 empty] | N | N | N | Y | 2021-10-28 14:38
8-00658438 | Completed | VIT SC3 OOS | Forced outage | VIT SC3 | 2021-11-01 13:16 | 2021-12-15 12:28 | NR | Continuous | [6 empty] | Y | N | N | Y | 2021-12-15 12:28
8-00534407 | Cancelled | JHT 1CB11 OOS | PN-1CB11 BFPN | JHT 1CB11 | 2021-11-02 08:00 | 2021-11-02 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-22 15:49
8-00536937 | Cancelled | DMR 1CB8 OOS | DMR 1CB8 , INSP & DOBLE | DMR 1CB8 | 2021-11-02 08:00 | 2021-11-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-04 18:00
8-00536911 | Completed | PIK 2CB17 OOS | PRESSURE VESSEL REPLACEMENT AND AIR FILTER CHANGE (PVRP & AFCH) | PIK 2CB17 | 2021-11-03 07:00 | 2021-11-03 11:24 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-03 12:19
8-00534414 | Cancelled | JHT 1CB12 OOS | PN-1CB12 BFPN | JHT 1CB12 | 2021-11-03 08:00 | 2021-11-03 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-22 15:49
8-00533642 | Completed | ACK 5CB2 OOS | inspection and doble | ACK 5CB2 | 2021-11-03 08:00 | 2021-11-05 14:28 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-11-05 14:28
8-00533614 | Cancelled | CKY 60CB2 OOS | CB TRIP TESTING | CKY 60CB2 | 2021-11-03 08:00 | 2021-11-03 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-14 12:53
8-00617267 | Cancelled | 60L21 out from SON | SON RTU upgrade project. Cut over VT wiring to new RTU panel. | 60L21 | 2021-11-03 10:30 | 2021-11-05 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-28 14:41
8-00536910 | Completed | PIK 2CB13 OOS | PRESSURE VESSEL REPLACEMENT AND AIR FILTER CHANGE (PVRP & AFCH) | PIK 2CB13 | 2021-11-04 07:00 | 2021-11-04 14:05 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-04 14:05
8-00533615 | Cancelled | CKY 60CB3 OOS | CB TRIP TESTING | CKY 60CB3 | 2021-11-04 08:00 | 2021-11-04 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-14 12:54
8-00534448 | Cancelled | JHT 1CB13 OOS | PN-1CB13 BFPN | JHT 1CB13 | 2021-11-04 08:00 | 2021-11-04 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-22 15:49
8-00534450 | Cancelled | JHT 1CB14 OOS | PN-1CB14 BFPN | JHT 1CB14 | 2021-11-05 08:00 | 2021-11-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-22 15:49
8-00533617 | Cancelled | CKY 60CB6 OOS | CB TRIP TESTING | CKY 60CB6 | 2021-11-05 08:00 | 2021-11-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-14 12:56
8-00533641 | Completed | VNT 1CB4 OOS | inspection | VNT 1CB4 | 2021-11-08 08:00 | 2021-11-10 13:18 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-11-10 13:18
8-00534451 | Cancelled | JHT 1CB15 OOS | PN-1CB15 BFPN | JHT 1CB15 | 2021-11-08 08:00 | 2021-11-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-22 15:50
8-00534234 | Cancelled | OYR 1CB1 OOS | PN-1CB1 BFPN & 1CT1 REPL; PN-T1 NON-ELE PN | OYR 1CB1, OYR T1 | 2021-11-08 08:00 | 2021-11-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-27 15:29
8-00643976 | Completed | 5L79 OOS | PCB lighting replacement | 5L79, NIC 5B16 | 2021-11-08 08:00 | 2021-11-08 15:22 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-08 17:01
8-00525811 | Cancelled | CSQ 2CB4, 2GD2CB4, 2GD1CB4 OOS | DS & CB Inspection & LOCH | CSQ 2CB4 | 2021-11-08 08:00 | 2021-11-12 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-20 10:01
8-00512464 | Cancelled | 5L51 OOS | Insulator Maintenance | 5L51 | 2021-11-08 08:00 | 2021-11-10 16:00 | 2 | Continuous |  |  | 1500 | 1900 |  |  | N | N | Y | Y | 2021-09-27 12:20
8-00526200 | Proposed | 1L116 OOS | COB Insulator Replacements | 1L116 | 2021-11-08 09:00 | 2021-11-10 15:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-10-03 21:14
8-00534235 | Cancelled | OYR 1CB2 OOS | PN-1CB2 CN | OYR T2, OYR 1CB2 | 2021-11-09 08:00 | 2021-11-09 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-27 15:25
8-00661918 | Completed | KLY 5B11, and 5L13 OOS | Forced Outage on KLY 5B11 | KLY 5B11, 5L13 | 2021-11-09 17:00 | 2021-11-11 16:27 | 72 | Continuous | [6 empty] | Y | N | N | Y | 2021-11-11 16:27
8-00534456 | Cancelled | JHT 1CB2 OOS | PN-1CB2 BFPN | JHT 1CB2 | 2021-11-10 08:00 | 2021-11-10 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-22 15:50
8-00527559 | Completed | 2L55 OOS | Cable Overview Inspection | 2L55 | 2021-11-12 08:00 | 2021-11-12 16:01 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-11-13 21:51
8-00518611 | Completed | BPA - RAS WS-A & B Controllers Outage | BPA RAS OUTAGE | ING 5D25 | 2021-11-13 07:00 | 2021-11-13 19:09 | 2 | Continuous | 800 | 1200 | 100 | 400 |  |  | Y | N | N | Y | 2021-11-13 19:47
8-00512467 | Completed | 5L52 OOS | Insulator Maintenance | 5L52 | 2021-11-15 08:00 | 2021-11-16 14:38 | 2 | Continuous | 2000 | 2400 | 1500 | 1900 |  |  | N | N | N | Y | 2021-11-16 14:42
8-00527562 | Completed | 2L44 OOS | Overview | 2L44 | 2021-11-15 08:00 | 2021-11-19 09:49 | 2 | Continuous | [6 empty] | Y | Y | N | Y | 2021-11-19 10:02
8-00533438 | Denied | NIC 5B7/T3 OOS | 5D2CB7, 5D3, 5D1CB17 INSP, 5CB7 INSP and DOBL | NIC T3, NIC 5B7, NIC 5CB7 | 2021-11-15 08:00 | 2021-11-19 16:00 | 12 | Continuous | [6 empty] | N | Y | N | Y | 2021-11-12 08:08
8-00534460 | Cancelled | JHT 1CB7 OOS | PN-1CB7 BFPN | JHT 1CB7 | 2021-11-15 08:00 | 2021-11-15 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-22 15:50
8-00533534 | Cancelled | ALZ 60VT4, 60L48 OOS | EL Inspection | SMW T1, 60L48 | 2021-11-15 08:00 | 2021-11-16 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-11-09 15:32
8-00536934 | Cancelled | DMR 1CB7 OOS | DMR 1CB7 , INSP & DOBLE | DMR 1CB7 | 2021-11-15 08:00 | 2021-11-17 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-19 18:00
8-00537035 | Cancelled | PAL T5, T6, T12, 1CB5 OOS | PAL T12 NON-EL, T5,T6, PN-1CB5 BF | PAL 1CB12, PAL T5 | 2021-11-15 08:00 | 2021-11-17 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-09 13:56
8-00540185 | Completed | 60L90 out from DCV, DCV T1 OOS | DCV 60D1, 60GD1 Disconnect replacement | 60L90, DCV T1 | 2021-11-15 08:00 | 2021-12-03 13:48 | 6 | Continuous | [6 empty] | N | Y | Y | Y | 2021-12-03 14:03
8-00645568 | Completed | SKA T2, 5MB2 oos | Energizing SKA 12VR2 | SKA 12RX2, SKA T2, SKA T4, SKA 5MB2, SKA 2B5 | 2021-11-15 08:00 | 2021-11-15 10:58 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-15 15:33
8-00533097 | Denied | 2L1 out from RBW 2D1, RBW T1 OOS | PM INSPECTIONS | RBW T1, 2L1 | 2021-11-15 10:00 | 2021-11-18 08:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-11-08 12:58
8-00537989 | Cancelled | 60L295 JOE T1 OOS | INSP and DOBL all 3 phases | JOE 60CB5, 60L295 | 2021-11-16 08:00 | 2021-11-19 16:00 | 2 | Continuous | [6 empty] | N | Y | N | Y | 2021-11-16 09:15
8-00534237 | Cancelled | PML 1D1,1D2 OOS OAAT | PN 1D1,1D2, CN OAAT | PML 1D1, PML 1D2 | 2021-11-16 08:00 | 2021-11-16 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-09 13:52
8-00533620 | Denied | FCN 2CB3 OOS | CB TRIP TESTING | FCN 2CB3 | 2021-11-16 08:00 | 2021-11-16 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-12 11:00
8-00664433 | Completed | 60L21 OOS | Forced OOS | 60L21 | 2021-11-16 10:16 | 2021-11-25 15:30 | NR | Continuous | [6 empty] | N | N | N | Y | 2021-11-25 15:30
8-00659480 | Completed | SKA 2CB12 oos | CB PN PM | SKA 2CB2, SKA T5, SKA 2CB12 | 2021-11-17 08:00 | 2021-11-17 12:32 | 0 | Continuous | [6 empty] | Y | N | Y | Y | 2021-11-17 12:33
8-00533644 | Completed | VNT 2CB8 OOS | VNT 2CB8 INSP | VNT 2CB8 | 2021-11-17 08:00 | 2021-11-18 14:40 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-11-18 14:40
8-00525821 | Cancelled | CSQ 2CB5 OOS | CB Inspection | CSQ 2CB5 | 2021-11-17 08:00 | 2021-11-18 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-14 16:58
8-00533112 | Cancelled | 2L1 out from FCN 2D22, FCN T2 OOS | INSPECTIONS AND DOBLE TEST | RBW T1, 2L1, FCN 2B2, FCN T2 | 2021-11-18 08:00 | 2021-11-22 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-11-08 15:03
8-00533510 | Denied | 2L240 OOS | ACK 2CL240 INSP | 2L240, SAM T4 | 2021-11-18 08:00 | 2021-11-18 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-11-15 14:47
8-00534465 | Cancelled | JHT 1CB5 OOS | PN-1CB5 BFPN | JHT 1CB5 | 2021-11-18 08:00 | 2021-11-18 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-22 15:51
8-00657707 | Completed | PCN 5CB2 oos | CB PM | PCN 5CB2 | 2021-11-18 08:00 | 2021-11-18 13:12 | 0 | Continuous | [6 empty] | Y | N | Y | Y | 2021-11-18 13:12
8-00657705 | Completed | PCN 5CB1 oos | CB PM | PCN 5CB1 | 2021-11-19 08:00 | 2021-11-19 12:04 | 0 | Continuous | [6 empty] | Y | N | Y | Y | 2021-11-19 12:04
8-00525812 | Cancelled | CSQ 2D3 OOS | DS Inspection | CSQ 2D3 | 2021-11-19 08:00 | 2021-11-19 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-04-14 16:54
8-00651289 | Completed | 5L4 oos | Oil Samples | 5L4, GMS 5B8 | 2021-11-20 07:00 | 2021-11-20 16:53 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2021-11-20 16:53
8-00518688 | Completed | 2L49 OOS | Structure Replacements | 2L49 | 2021-11-22 08:00 | 2021-11-26 16:19 | 3 | Continuous | [6 empty] | N | N | N | Y | 2021-11-26 16:22
8-00530663 | Cancelled | 2L86 oos | HMH T1 Energization | 2L86 | 2021-11-22 08:00 | 2021-11-26 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-11-22 09:22
8-00525680 | Approved | CBK 5CB13 OOS | CB maintenance/Doble testing | CBK 12RX7, CBK 5CB13 | 2021-11-23 07:00 | 2021-11-24 16:00 | 1 | Continuous | [6 empty] | N | N | N | Y | 2021-11-22 12:59
8-00533443 | Completed | 1L206 OOS | SVA 1D21, 1D2CB8, 1D2CB10 INSP | SVA 1B8, 1L206 | 2021-11-23 08:00 | 2021-11-25 15:33 | 4 | Continuous | [6 empty] | N | Y | N | Y | 2021-11-25 15:34
8-00655962 | Completed | 2L255 OOS | End of life structure and cross arm replacements | 2L255 | 2021-11-23 08:00 | 2021-11-26 15:34 | 3 | Continuous | [6 empty] | N | N | N | Y | 2021-11-26 15:34
8-00650856 | Completed | 1L274 Out from POC | Structure Repl | 1L274 (887L) | 2021-11-23 08:00 | 2021-12-17 16:10 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2021-12-17 16:10
8-00533643 | Completed | VNT 1CB1 | CB INSP | VNT 1CB1 | 2021-11-23 08:00 | 2021-11-24 14:45 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-11-24 14:45
8-00533536 | Denied | ALZ 60VT1 | EL Inspection | ALZ 60CB1, ALZ 60CB2, 60L47 | 2021-11-23 08:00 | 2021-11-24 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-10-05 12:17
8-00536774 | Completed | SEL 5CB1 OOS | 5CB1 Braker Fail PN testing | SEL 5CB1 | 2021-11-23 08:00 | 2021-11-23 14:32 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-11-23 14:32
8-00538048 | Cancelled | KHS 2CB4, 2CB7 OOS | INSP | KHS 2D2, KHS 2CB6, KHS 2CB4, KHS 2D2CB4, KHS 2D1CB6, KHS T2 | 2021-11-23 08:00 | 2021-11-26 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-11-01 10:24
8-00538451 | Completed | VIT 2CB5 OOS | INSP | VIT 2CB5 | 2021-11-23 08:00 | 2021-11-25 15:23 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-25 15:23
8-00653477 | Completed | NIC 1CB15 OOS | NIC 1CB15 CT Ratio Change | NIC 1CB15 | 2021-11-23 12:00 | 2021-11-23 16:14 | 24 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-23 16:15
8-00536782 | Approved | SEL 5CB2 OOS | 5CB2 Braker Fail PN testing | SEL 5CB2 | 2021-11-24 08:00 | 2021-11-24 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-11-23 09:29
8-00536784 | Completed | SEL 5CB3 OOS | 5CB3 Braker Fail PN testing | SEL 5CB3 | 2021-11-25 08:00 | 2021-11-25 14:59 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-11-25 15:00
8-00533645 | Completed | VNT 2CB3 OOS | VNT 2CB3 INSP | VNT 2CB3 | 2021-11-25 08:00 | 2021-11-26 13:21 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-11-26 13:21
8-00525404 | Cancelled | CBN T6 OOS | CPC non-el Pm, | CBN T6 | 2021-11-25 08:00 | 2021-11-26 12:00 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-11-19 08:29
8-00536788 | Completed | SEL 5CB4 OOS | 5CB3 Braker Fail PN testing | SEL 5CB4 | 2021-11-26 08:00 | 2021-11-26 11:29 | 2 | Continuous | [5 empty] | 700 | N | N | N | Y | 2021-11-26 11:29
8-00537473 | Approved | HWW 1CB1 OOS | 1CB1 CN | HWW 1CB1 | 2021-11-26 08:00 | 2021-11-26 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-25 10:27
8-00548914 | Completed | 2L2 Part Out CKY | CKY BUS Insulator replacements | RBW T2, CKY 2B4, 2L2 | 2021-11-26 12:00 | 2021-12-01 10:41 | 2 | Continuous | [6 empty] | Y | Y | N | Y | 2021-12-17 03:30
8-00656707 | Approved | 2L299 oos | VT energization | 2L299 | 2021-11-26 16:00 | 2021-11-26 18:00 | 1 | Continuous | [6 empty] | N | N | N | Y | 2022-01-27 19:47
8-00536789 | Completed | SEL 2CB9 OOs | 2CB9 Breaker fail PN Test | SEL 2CB9 | 2021-11-29 08:00 | 2021-11-29 13:36 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-11-29 13:37
8-00525684 | Completed | CBK 5CB23 | CB maintenance/Doble testing | CBK 5CB23 | 2021-11-29 08:00 | 2021-12-03 13:41 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-12-03 13:49
8-00518691 | Completed | 2L50 OOS | Structure Replacements | 2L50 | 2021-11-29 08:00 | 2021-12-03 17:55 | 2 | Continuous | [6 empty] | Y | Y | N | Y | 2021-12-03 17:55
8-00533434 | Completed | DUG 1CB3 OOS | DUG 1CB3 INSP | DUG 1CB3 | 2021-11-29 08:00 | 2021-12-01 13:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-12-01 13:00
8-00527537 | Completed | 60L52 OOS | Detailed & Jacket Test & Terminal Washing | 60L52, DGR T3 | 2021-11-29 08:00 | 2021-12-06 11:44 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-12-06 11:52
8-00650502 | Completed | 60L22 OOS | Removal of 60WT1 and 60CC1 permanently from 60L22 line in Lajoie switchyard | 60L22, LAJ 60CB2 | 2021-11-29 11:00 | 2021-12-03 12:52 | 3 | Continuous | [6 empty] | Y | N | N | Y | 2021-12-03 12:52
8-00536791 | Completed | SEL 2CB10 OOS | 2CB10 Breaker fail PN Test | SEL 2CB10 | 2021-11-30 08:00 | 2021-11-30 12:38 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-11-30 15:03
8-00527563 | Cancelled | 2L50 OOS | Overview | 2L50 | 2021-11-30 08:00 | 2021-12-03 16:00 | 2 | Continuous | [6 empty] | Y | Y | N | Y | 2021-11-25 17:55
8-00533433 | Completed | HFY T1 OOS | HFY T1 INSP and DOBL | HFY T1 | 2021-11-30 08:00 | 2022-08-10 07:58 | 4 | Continuous | [6 empty] | N | N | N | Y | 2022-08-26 03:30
8-00669629 | Completed | 2L102 OOS | Forced Outage | 2L102 | 2021-11-30 09:42 | 2021-12-04 17:20 | NR | Continuous | [6 empty] | N | N | N | Y | 2021-12-04 17:25
8-00669931 | Completed | 5L94 (1201L) OOS | Foced Outage (Fault location in AB) | 5L94 / 1201L | 2021-11-30 20:24 | 2021-12-03 11:31 | NR | Continuous | [6 empty] | N | N | Y | Y | 2021-12-03 11:57
8-00532015 | Cancelled | SRS T3 oos | PCB Bushing Replacement | SRS T3 | 2021-12-02 08:00 | 2022-01-07 17:00 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-19 08:47
8-00519315 | Cancelled | MCA 5B6 OOS | Placeholder for MCA G3/T3 Sync Testing via 5CB7 | MCA 5B6, MCA LS2 | 2021-12-03 09:00 | 2021-12-03 11:00 | 2 | Continuous | [6 empty] | Y | N | N | Y | 2021-12-05 18:00
8-00306092 | Completed | BSY Synchronous Condenser (G1) OOS | Inspection and Exciter Mtce | BSY G1 | 2021-12-06 01:00 | 2021-12-09 16:42 | 192 | Continuous | [6 empty] | N | N | Y | Y | 2021-12-09 16:42
8-00527542 | Recalled | 60L53 OOS | Detailed & Jacket Test & Repair Alarm | DGR T1, 60L53 | 2021-12-06 08:00 | 2021-12-06 15:44 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-12-06 15:48
8-00540186 | Completed | 60L92 out from DCV, DCV T3 OOS | DCV 60D3, 60GD3 Disconnect replacement | 60L92, DCV T3 | 2021-12-06 08:00 | 2021-12-23 15:36 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2021-12-23 15:48
8-00534233 | Cancelled | JHT 1CB1 OOS | PN-1CB1 BFPN & 1CT1 REPL | JHT 1CB1 | 2021-12-07 08:00 | 2021-12-16 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-03 09:03
8-00665065 | Completed | KLY 12RX1 oos | KLY 12CB2 NREC PM | KLY 12RX1 | 2021-12-07 08:00 | 2021-12-07 14:29 | 1 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-12-07 14:29
8-00669358 | Completed | WTS T2 OOS | FBC Outage | WTS T2 | 2021-12-07 08:00 | 2021-12-08 13:21 | 0 | Continuous | [6 empty] | Y | N | N | Y | 2021-12-08 13:21
8-00542173 | Cancelled | 1L274 Out from POC | structure replacement | 1L274 (887L) | 2021-12-07 08:00 | 2021-12-23 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-11-29 15:05
8-00525671 | Completed | CBK 5CB11 | Breaker fail PM | CBK 12RX6, CBK 5CB11 | 2021-12-08 07:00 | 2021-12-09 15:25 | 1 | Continuous | [6 empty] | N | N | N | Y | 2021-12-09 15:26
8-00533331 | Cancelled | 60L93 OOS | Overview & Terminal Washing | 60L93 | 2021-12-08 08:00 | 2021-12-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-12-01 12:04
8-00664331 | Approved | SKA T2, 12RX2 oos | SKA 5CB12 NERC Condition Assessment | SKA 12RX2, SKA 5CB12, SKA T2 | 2021-12-08 08:00 | 2021-12-08 12:00 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2021-12-07 09:38
8-00669866 | Completed | SKA T1, 12RX1 oos | SKA 5CB2 NERC Condition Assessment | SKA 12RX1, SKA 5CB2, SKA T1 | 2021-12-08 12:01 | 2021-12-08 14:24 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2021-12-08 14:25
8-00536203 | Cancelled | 2L93 OOS | Structure Replacements | 2L93 | 2021-12-13 08:00 | 2021-12-15 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-12-07 13:15
8-00533467 | Cancelled | BKL STATCOM | BKL Statcom INSP | BKL STATCOM | 2021-12-13 08:00 | 2021-12-17 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-10-19 07:24
8-00518692 | Cancelled | 2L57 OOS | COB Glass Replacement | 2L57 | 2021-12-13 08:00 | 2021-12-17 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-05-20 14:54
8-00526056 | Denied | 2L255 OOS | ACK 2CL255 INSP AND 2CT26 INSP AND DOBL | 2L255 | 2021-12-14 08:00 | 2021-12-14 16:00 | 2 | Continuous | [6 empty] | N | N | N | Y | 2021-11-18 13:03
8-00526058 | Denied | 2L256 OOS | ACK 2CL256 INSP AND 2CT25 INSP AND DOBL | 2L256, VNT T1 | 2021-12-15 08:00 | 2021-12-15 16:00 | 4 | Continuous | [6 empty] | N | N | N | Y | 2021-11-18 13:12
8-00674919 | Completed | 5L72 OOS | MCA 5CB7 POW Testing. | 5L72, MCA 5CB7, MCA 5CB9, NIC 5CB13, NIC 5CB3 | 2021-12-18 12:00 | 2021-12-18 20:40 | 0 | Continuous | [6 empty] | N | N | N | Y | 2021-12-18 20:41
8-00674929 | Completed | 5L71 OOS | MCA 5CB10 POW Testing. | 5L71, MCA 5CB11, NIC 5CB18, NIC 5CB8, MCA 5CB10 | 2021-12-19 12:00 | 2021-12-19 14:51 | 0 | Continuous | [6 empty] | Y | N | N | Y | 2021-12-19 14:51
8-00672209 | Approved | KCL 2CB15 and PY RAS PLC OOS | RAS testing and 2CB15 Relay timing test | KCL 2CB15 | 2021-12-23 08:00 | 2021-12-23 12:00 | 0 | Continuous | [6 empty] | N | N | N | Y | 2021-12-22 11:00
8-00674908 | Approved | KCL 2CB15, SY RAS OLC OOS | RAS testing and 2CB15 Relay timing test. | KCL 2CB15 | 2021-12-23 12:30 | 2021-12-23 16:00 | 0 | Continuous | [6 empty] | N | N | N | Y | 2021-12-22 11:09
8-00678872 | Completed | RYC 5CX1 OOS | Forced OOS | RYC 5CX1 | 2021-12-30 15:07 | 2022-01-14 15:09 | NR | Continuous | [6 empty] | N | N | N | Y | 2022-01-30 03:30