## 2022 AOP
2022 Annual Plan Extract
Outage # | Outage Status | AP Outage Title | Outage Purpose | Requested Equipment | Start Date (MM/DD/YYYY HH:MM:SS) | Complete Date (MM/DD/YYYY HH:MM:SS) | Recall Time (Hours) | Outage Type : Continuous /Daily | Path 3 (N->S) ING to CUS (MW) | Path 3 (N->S) BC to US (MW) | Path 3 (S->N)CUS to ING (MW) | Path 3 (S->N) US to BC (MW) | Path 1 BC AB (W->E) BC to AB (MW) | Path 1 (E->W) AB to BC (MW) | Resource Impact | Load Impact | Posted To Plan | Under Review AOP | Revision Date (MM/DD/YYYY HH:MM:SS)
8-00500872 | Completed | MCA 5RX4 OOS | Forced Outage | MCA 5RX4 | 2020-09-20 08:25 | 2022-10-03 21:25 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-03 21:26
8-00493276 | Cancelled | MCA 5RX4 Forced outage | Forced Outage | MCA 5RX4 | 2020-10-10 08:00 | 2022-04-05 16:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2020-10-05 10:20
8-00464149 | Completed | MCA 5RX4 OOS | Replacement Project of 5RX4 all phases | MCA 5RX4 | 2021-03-09 07:00 | 2022-10-03 21:25 | 12000 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-10-03 21:26
8-00646790 | Completed | ING 2RX1 & 2CX11 Forced OOS | Failure of ING 2CB21 | ING 2CB21, ING 2RX1, ING 2CX11 | 2021-10-04 07:11 | 2022-06-23 19:05 | NR | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-07-09 03:30
8-00532015 | Cancelled | SRS T3 oos | PCB Bushing Replacement | SRS T3 | 2021-12-02 08:00 | 2022-01-07 17:00 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-19 08:47
8-00306148 | Cancelled | BSY Synchronous Condenser (G4) OOS | Inspection and Exciter Mtce | BSY G4 | 2022-01-03 01:00 | 2022-01-14 23:00 | 192 | Continuous | [6 empty] | N | N | Y | Y | 2021-11-10 15:47
8-00539780 | Completed | 60L99 out from HCT, HCT T1, 12CB1 OOS | HCT T1 Non-electrical trip testing, 60D1, 60GD1 Inspection | HCT T1, 60L99 | 2022-01-04 08:00 | 2022-01-04 15:02 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-01-04 15:02
8-00534405 | Proposed | JHT 1CB10 OOS | PN-1CB10 BFPN | JHT 1CB10 | 2022-01-05 08:00 | 2022-01-14 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-22 15:52
8-00536213 | Cancelled | 1L243 OOS | Structure Replacements | 1L243 | 2022-01-10 08:00 | 2022-01-24 16:00 | 4 | Return Weekends | [6 empty] | Y | N | Y | Y | 2022-01-06 12:19
8-00682392 | Completed | ACK 5CX2 OOS | FORCED OOS | ACK 5CX2 | 2022-01-10 18:20 | 2022-01-28 15:07 | NR | Continuous | [6 empty] | Y | N | Y | Y | 2022-01-28 15:07
8-00682396 | Completed | ACK 5CX2 OOS | FORCED OOS | ACK 5CX2, ACK 5CB50 | 2022-01-10 18:20 | 2022-01-20 08:34 | NR | Continuous | [6 empty] | Y | N | Y | Y | 2022-01-20 08:34
8-00683590 | Completed | 5L98 OOS | Forced OOS | 5L98 | 2022-01-13 09:53 | 2022-01-13 14:44 | NR | Continuous |  |  |  |  | 450 | 560 | N | N | Y | Y | 2022-01-13 14:47
8-00538053 | Denied | KSH T3 OOS | NON-EL, PYPN, SYPN | KSH T3 | 2022-01-14 08:00 | 2022-01-14 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-01-06 11:46
8-00665711 | Cancelled | 1L274 OOS | 1L274 Refurbishment Project | 1L274 (887L) | 2022-01-18 08:00 | 2022-01-25 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-01-18 07:14
8-00534454 | Proposed | JHT 1CB16 OOS | PN-1CB16 BFPN | JHT 1CB16 | 2022-01-19 08:00 | 2022-01-28 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-22 15:53
8-00675908 | Completed | 2L27 OOS | Induction testing | 2L27 | 2022-01-21 08:00 | 2022-01-21 14:58 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-01-21 14:58
8-00533630 | Completed | SQH 60CB6, 60L70 OOS | INSPECTION AND SF6 LEAK REPAIR | 60L70, SQH 60CB6 | 2022-01-25 08:00 | 2022-01-28 15:38 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-01-28 15:46
8-00541663 | Completed | 1L117, 1L118, 1L121 OOS | LDR 1D21 & 1D22 INSP | 1L121, 1L117, 1L118, LDR 1B1, LDR 1B2 | 2022-01-25 08:00 | 2022-01-26 13:27 | 2 | Return Evenings | [6 empty] | Y | Y | Y | Y | 2022-01-26 14:10
8-00536935 | Cancelled | CMX T1 OOS | PN-T1 NON-ELE PN | CMX T1 | 2022-01-25 08:00 | 2022-01-25 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-12-29 13:32
8-00536936 | Cancelled | CMX T2 OOS | PN-T2 NON-ELE PN | CMX T2 | 2022-01-26 08:00 | 2022-01-26 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-12-29 13:31
8-00688418 | Completed | 5L82 OOS | Forced OOS | 5L82, NIC 5B28, NIC 5RX9 | 2022-01-28 04:44 | 2022-02-06 20:50 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-02-06 20:50
8-00647860 | Completed | 5L77 OOS | blackstart test | 5L77, ACK 5B10 | 2022-01-30 10:00 | 2022-01-30 15:47 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-01-30 15:47
8-00538579 | Completed | VIT SC2 OOS | MNRI | VIT SC2 | 2022-01-31 08:00 | 2022-02-03 12:21 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-02-03 12:21
8-00680301 | Completed | 5L94/1201L OOS | AltaLink work to correct SF6 condition of line end breaker on 5L94/1201L | 5L94 / 1201L | 2022-01-31 11:30 | 2022-01-31 13:28 | 2 | Continuous |  |  |  |  | 50 | 100 | N | N | Y | Y | 2022-01-31 13:50
8-00534229 | Proposed | JHT 1CB8 OOS | PN-1CB8 BFPN & 1CT8 REPL | JHT 1CB8 | 2022-02-01 08:00 | 2022-02-10 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-22 15:53
8-00665714 | Cancelled | 1L274 OOS | 1L274 Refurbishment Project | 1L274 (887L) | 2022-02-01 08:00 | 2022-02-08 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-01-05 11:49
8-00306093 | Cancelled | BSY Synchronous Condenser (G3) OOS | Inspection and Exciter Mtce | BSY G3 | 2022-02-07 01:00 | 2022-02-18 23:00 | 192 | Continuous | [6 empty] | N | N | Y | Y | 2021-12-17 12:16
8-00537925 | Approved | HWD T2 OOS | 25CB2 BFPN, 1D2 INSP | HWD T2, HWD 1D2 | 2022-02-08 08:00 | 2022-02-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-02-02 15:54
8-00540111 | Completed | SAY 2CB5 OOS | SAY 2CB5 Inspection | SAY 2CB5 | 2022-02-08 08:00 | 2022-02-10 13:11 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-02-10 13:11
8-00657094 | Completed | 60L1 Out From BND 60D28, BND 60CB10, 60CB11 OOS | BND 60VT10 INSPECTION AND DOBLE | BND 60CB11, BND 60CB10, 60L1 | 2022-02-08 08:00 | 2022-02-08 15:57 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-02-24 03:30
8-00657098 | Denied | 60L26 Out From BND 60D27, BND 60CB15, 60CB13 OOS | PROXIMITY CL FOR WORK ON BND 60VT10, BND 60VT14 INSPECTION AND DOBLE | BND 60CB13, BND 60CB15, 60L26 | 2022-02-08 08:00 | 2022-02-11 16:00 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-02-03 15:33
8-00685153 | Completed | 2L113 OOS | CBK 2D23 hotspot repair | CBK 2CB6, CBK 2CB9, 2L113, NTL 60CB12, CBK 2B5 | 2022-02-08 08:00 | 2022-02-09 14:24 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-02-09 14:24
8-00692197 | Completed | 5L83 OOS | Emergency repairs on Shot Guy Wire. | 5L83 | 2022-02-09 08:00 | 2022-02-11 17:14 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-02-11 17:14
8-00657103 | Denied | 60L35 Out From BND 60D32, BND 60CB10, 60CB4, 60CB5 OOS | PROXIMITY CL FOR WORK ON BND 60VT14 | BND 60CB5, 60L35, BND 60CB10, BND 60CB4 | 2022-02-09 16:00 | 2022-02-11 16:00 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-02-03 15:33
8-00539836 | Denied | 2L5 out from CKY, CKY 2D26, 2D1CB2, 2D1CB3 OOS | PM INSPECTIONS, 2D1CB2 HOT SPOT REPAIR | CKY 2D26, CKY 2B2, 2L5 | 2022-02-14 08:00 | 2022-02-18 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-02-08 10:22
8-00534464 | Proposed | JHT 1CB9 OOS | PN-1CB9 BFPN | JHT 1CB9 | 2022-02-15 08:00 | 2022-02-24 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-22 15:54
8-00678465 | Cancelled | 2L294 OOS from NLY to AAL | Replace structures and repair conductor. | 2L294 | 2022-02-22 11:00 | 2022-02-27 16:00 | 4 | Continuous |  |  |  |  | 850 | 500 | N | N | Y | Y | 2022-02-11 09:12
8-00537021 | Completed | GLD T1 OOS | PN-T1 NON-EL | GLD T1 | 2022-02-24 08:00 | 2022-02-24 14:24 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2022-02-24 14:24
8-00535779 | Completed | 60L395 oos | DS PM and SA Repl | 60L395 | 2022-02-28 08:00 | 2022-03-03 16:03 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-03-03 16:03
8-00512723 | Cancelled | 2L294 OOS | Replace structures, timbers and lacing | 2L294 | 2022-02-28 08:00 | 2022-03-04 16:00 | 6 | Continuous |  |  |  |  | 850 | 500 | N | N | Y | Y | 2022-01-31 12:40
8-00305824 | Completed | BSY Synchronous Condenser (G3) OOS | Inspection and Exciter Mtce | BSY G3 | 2022-03-01 01:00 | 2022-03-05 05:58 | 10 | Continuous |  | 2800 |  |  |  |  | N | N | Y | Y | 2022-03-15 15:02
8-00537693 | Denied | 2L142 OOS | Detailed Inspection | GTP T14, 2L142 | 2022-03-01 07:00 | 2022-03-04 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-02-25 01:10
8-00593257 | Completed | NIC T3 OOS | Leak repair | NIC T3, NIC T5, NIC 5B7, NIC 5CB7 | 2022-03-01 08:00 | 2022-04-08 06:26 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-24 03:30
8-00393987 | Cancelled | PCN 5RX1 oos | Reactor Replacement | PCN 5RX1 | 2022-03-01 08:00 | 2022-06-30 16:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2021-12-15 10:40
8-00680489 | Completed | BSY G1, G3 and G4 Units Outages | Chlorination of fresh water line from Buntzen to BSY | BSY G1, BSY G3, BSY G4 | 2022-03-01 08:00 | 2022-03-04 21:16 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-03-15 15:02
8-00670210 | Completed | 5L41 OOS | KLY 5B4 OOS for PCB Lighting Replacement | 5L41, KLY 5B4 | 2022-03-02 08:00 | 2022-03-02 17:13 | 2 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2022-03-02 17:13
8-00660989 | Completed | 2L294 Out from CBK to ALL | CBK 2D24 Inspection | 2L294, CBK 5CB13, CBK 5CB23, CBK 2MB4 | 2022-03-02 08:00 | 2022-03-04 14:14 | 2 | Continuous |  |  |  |  | 850 | 500 | N | N | Y | Y | 2022-03-04 14:15
8-00667952 | Cancelled | CRK 5CX1 OOS | Replace Damping Resistors | CRK 5CX1 | 2022-03-03 08:00 | 2022-03-04 18:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-02-17 14:47
8-00305826 | Cancelled | BSY Synchronous Condenser (G1) OOS | Inspection and Exciter Mtce | BSY G1 | 2022-03-07 01:00 | 2022-03-18 23:00 | 192 | Continuous | [6 empty] | N | N | Y | Y | 2022-01-05 15:10
8-00543445 | Proposed | 2L19 OOS | Structure Replacements | 2L19 | 2022-03-07 08:00 | 2022-03-10 16:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-02-25 15:02
8-00697155 | Completed | BRT T4 / 3B5 OOS | BRT T4 C Phase Bushing replacement | BRT T4, BRT 3B5 | 2022-03-07 08:00 | 2022-03-11 22:07 | 16 | Continuous | [6 empty] | Y | N | Y | Y | 2022-03-27 03:30
8-00537696 | Completed | 2L143 OOS | Detailed Inspection | 2L143 | 2022-03-08 06:00 | 2022-03-11 14:40 | 6 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-03-11 14:40
8-00537770 | Completed | CBK T6 | CPC testing | 60L289, CBK 12CX2, CBK 12RX6, CBK T6, 60L270 | 2022-03-08 08:00 | 2022-03-09 14:53 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-03-09 14:53
8-00533497 | Approved | WAH T1 OOS | CPC non-el PM | WAH T1, 3L3 | 2022-03-08 08:00 | 2022-03-22 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-03-07 12:30
8-00687920 | Completed | 2L255 OOS | Replace end of life structure and cross arms | 2L255 | 2022-03-08 08:00 | 2022-03-11 14:48 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-03-11 14:48
8-00675442 | Completed | NIC T3 OOS | Leak Repairs | NIC T3 | 2022-03-10 16:00 | 2022-04-11 16:48 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-27 03:30
8-00697151 | Completed | BRT T4 / 2L19 / 3B5/BR1 T3/ BR1 T30/ 2B4 OOS | BRT T4 C Phase Bushing replacement and leak repair | 2L19, BR1 T3, BRT T4, BRT 3B5, BRT 2B4, BR1 T30 | 2022-03-11 08:00 | 2022-03-18 17:25 | 48 | Continuous | [6 empty] | Y | N | Y | Y | 2022-03-18 17:25
8-00701823 | Denied | 5L98 OOS | Line outage required for the testing of NIC 5CB25 POW Controller. | NIC 5CB25, NIC 5CB5, 5L98, VAS 5CB22, VAS 5CB12 | 2022-03-11 09:00 | 2022-03-11 16:00 | 1 | Continuous |  |  |  |  | 560 | 450 | N | N | Y | Y | 2022-03-09 15:59
8-00695903 | Completed | 5L44 OOS | LOA Proximity for work on 60L79 | 5L44 | 2022-03-11 10:00 | 2022-03-11 15:37 | 2 | Continuous | 1700 | 2100 | 1500 | 1900 |  |  | Y | N | Y | Y | 2022-03-11 15:41
8-00572109 | Cancelled | 5L1 outage | KDY 5CX1 work | 5L1 | 2022-03-12 08:00 | 2022-03-14 16:00 | 2 | Return Evenings | [6 empty] | N | N | Y | Y | 2022-03-09 09:46
8-00537698 | Completed | 2L145 OOS | Detail inspection | 2L145 | 2022-03-14 06:00 | 2022-03-18 15:23 | 6 | Continuous | [6 empty] | N | Y | Y | Y | 2022-03-18 15:23
8-00702779 | Completed | 5L1, KDY 5CX1, GMS 5B2, WSN 5B2 oos | Test Energizre 5L1 | 5L1, KDY 5CX1, WSN 5B2, GMS 5B2 | 2022-03-14 08:00 | 2022-03-14 08:01 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2022-03-13 14:19
8-00704340 | Completed | 73L OOS | FBC work | 73L | 2022-03-17 07:00 | 2022-03-19 19:32 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-03-19 19:32
8-00703153 | Completed | 2L294 OOS | Urgent repair damaged insulators | 2L294 | 2022-03-18 08:00 | 2022-03-18 15:22 | NR | Continuous |  |  |  |  | 850 | 500 | N | N | Y | Y | 2022-03-18 15:22
8-00537699 | Completed | 2L146 OOS | Detail inspection | 2L146 | 2022-03-21 06:00 | 2022-03-25 16:05 | 6 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-03-25 16:06
8-00675424 | Completed | NIC T5 OOS | LTC rebuild. | NIC 2CB12, NIC T3, NIC T5 | 2022-03-21 08:00 | 2022-03-31 16:18 | 48 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-11 16:48
8-00699827 | Completed | 2L294 Out from CBK to AAL | FBC work within AAL (Maintenance of AAL 2D21) | 2L294, AAL T1, AAL 2B1 | 2022-03-22 07:30 | 2022-03-23 10:28 | NR | Continuous |  |  |  |  | 850 | 500 | N | N | Y | Y | 2022-03-23 10:28
8-00682648 | Completed | 5L52 OOS | Replace end-of-life transmission insulators | 5L52 | 2022-03-22 08:00 | 2022-03-31 14:21 | 2 | Return Evenings and Weekends | 2000 | 2400 | 1500 | 1900 |  |  | N | N | Y | Y | 2022-03-31 14:23
8-00703180 | Completed | 5L98 OOS | NIC 5CB25 POW Controlle | NIC 5CB25, NIC 5CB5, 5L98, VAS 5CB22, VAS 5CB12 | 2022-03-25 08:00 | 2022-03-25 16:00 | 1 | Continuous |  |  |  |  | 560 | 450 | N | N | Y | Y | 2022-03-25 17:48
8-00533108 | Cancelled | 2L1 out from PEM 2D1 to 2D2 - Community Outage | PM INSPECTIONS | 2L1 | 2022-03-26 08:00 | 2022-03-26 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-02-08 12:38
8-00705153 | Completed | CSQ 2CB1 OOS | Trip testing from PN | CSQ 2CB1, CSQ 2CB7 | 2022-03-29 08:00 | 2022-03-29 15:06 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-03-29 15:06
8-00705135 | Completed | CSQ 2CB3 OOS | Trip testing via PN | CSQ 2CB3 | 2022-03-30 08:00 | 2022-03-30 15:59 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-03-30 15:59
8-00700029 | Proposed | 1L363 oos | GMS 1CVT2 Insp | 1L363 | 2022-04-04 08:00 | 2022-04-04 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-03-02 23:41
8-00705729 | Completed | ING 5CB3 OOS | Routine CPC BFPN PM, 5L51, T4, T8, 5MB2 PYSY PN OAT | ING 5CB3 | 2022-04-05 08:00 | 2022-04-07 15:21 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-07 15:22
8-00705158 | Completed | CSQ 2CB4 OOS | Trip testing from PN | CSQ 2CB4 | 2022-04-05 08:00 | 2022-04-05 14:29 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-05 14:29
8-00703249 | Completed | SRS T3 oos | PCB Bushing Repl | SRS T3 | 2022-04-05 08:00 | 2022-04-14 09:19 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-14 09:19
8-00705168 | Completed | CSQ 2CB5 OOS | Trip testing from PN | CSQ 2CB5 | 2022-04-06 08:00 | 2022-04-06 15:34 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-06 15:35
8-00667597 | Completed | 5L51 OOS | insection of ING 5GD23 | ING 5B3, 5L51 | 2022-04-06 08:00 | 2022-04-07 15:02 | 4 | Continuous |  |  | 1500 | 1900 |  |  | N | N | Y | Y | 2022-04-07 15:12
8-00628234 | Completed | 5L71, MCA 5B10, 5RX4 OOS | MCA 5B10 GIB Zones 4/5/6 Inspections for 5RX4 Project. | 5L71, MCA 5B10, MCA 5RX4 | 2022-04-06 16:00 | 2022-04-07 17:42 | NR | Continuous | [6 empty] | Y | N | Y | Y | 2022-05-08 23:22
8-00688874 | Approved | ACK 2CB10 OOS | Breaker Fail OOS | ACK 2CB10 | 2022-04-07 08:00 | 2022-04-07 16:00 | 48 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-07 09:12
8-00707659 | Completed | SKA 2CB1 oos | SKA 2CB1 PN CN | SKA 2CB1 | 2022-04-08 08:00 | 2022-04-08 13:30 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-08 13:30
8-00707661 | Completed | SKA 2CB5 oos | SKA 2CB5 PN CN | SKA 2CB5 | 2022-04-08 11:01 | 2022-04-08 13:33 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-08 13:33
8-00707664 | Completed | SKA 2CB6 oos | SKA 2CB6 PN CN | SKA 2CB6 | 2022-04-08 13:01 | 2022-04-08 13:31 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-08 13:32
8-00707665 | Approved | SKA 60CB7 oos | SKA 60CB7 PN CN | SKA 60CB7 | 2022-04-08 16:01 | 2022-04-08 18:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-06 13:45
8-00703242 | Completed | SKA 2RX2 oos | SKA 2RX2 NON-ELEC PN PM | SKA 2RX2 | 2022-04-11 08:00 | 2022-04-14 13:16 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-14 13:16
8-00703210 | Approved | TKW 5CB2 oos | TKW 5CB2 PN CN | TKW 5CB2 | 2022-04-11 08:00 | 2022-04-11 12:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-08 15:29
8-00711977 | Denied | GTP 1CB1 OOS | for Protection testing | GTP 1CB1 | 2022-04-11 08:00 | 2022-04-13 16:00 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-07 14:16
8-00688872 | Completed | 2L264 (74L) and 2B4 OOS | VNT Disconnect Iinspections | 2L264 (74L), VNT 2B4 | 2022-04-11 08:00 | 2022-04-12 14:46 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-04-12 14:46
8-00687957 | Completed | 1L243 out from NIC | 1D1CB17 and 1D1CB18 Inspection | 1L243, NIC 1CB17, NIC 1CB18 | 2022-04-11 08:00 | 2022-04-12 15:12 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-04-12 15:12
8-00687493 | Completed | NTL T4 OOS | NTL T4 Disconnect Inspections, 60VTT4 Inspection/Doble Testing and 2CB2 BFPN Testing | NTL 2CB2, NTL T4 | 2022-04-11 08:00 | 2022-04-22 13:19 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-22 13:19
8-00668053 | Completed | HPN T4, HPN 2B3 OOS | Bushing Replacement and Disconnect Inpsections | HPN T4, HPN 2B3, HPN T7 | 2022-04-11 08:00 | 2022-04-19 08:56 | 8 | Continuous | [6 empty] | N | Y | Y | Y | 2022-06-07 15:18
8-00661228 | Denied | GTP 1CB1 | 138 kV Bus Split - For Line Position Swap | GTP 1CB1 | 2022-04-11 08:00 | 2022-04-13 16:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-07 14:03
8-00663940 | Completed | BND T1 OOS | PCB Bushing Replacemenrt | BND T1 | 2022-04-11 08:00 | 2022-07-27 14:13 | 120 | Continuous | [6 empty] | N | Y | Y | Y | 2022-08-12 03:30
8-00703228 | Approved | TKW 1CB11 oos | TKW 1CB11 Insp/Doble & BF PN CN | TKW 1CB11 | 2022-04-11 12:00 | 2022-04-11 19:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-08 16:13
8-00703213 | Completed | TKW 5CB12 oos | TKW 5CB12 PN CN | TKW 5CB12 | 2022-04-12 08:00 | 2022-04-13 06:11 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-13 06:12
8-00703313 | Denied | SKA T5 oos | SKA T5 NON-ELEC PN PM | SKA T5 | 2022-04-12 08:00 | 2022-04-12 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-08 16:18
8-00705753 | Completed | ING 5CB5 OOS | Trip testing from PN | ING 5CB5 | 2022-04-12 08:00 | 2022-04-14 10:45 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-14 10:46
8-00703227 | Approved | TKW 1CB6 oos | TKW 1CB6 Grading Cap Repl & BF PN CN | TKW 1CB6 | 2022-04-12 12:00 | 2022-04-12 19:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-11 10:49
8-00703219 | Approved | TKW 5CB13 oos | TKW 5CB13 PN CN | TKW 5CB13 | 2022-04-13 08:00 | 2022-04-13 12:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-12 09:54
8-00703934 | Completed | 5L45 OOS | replacement of PCB lighting within LOA | CK5 5CB13, 5L45, CK5 5CB3 | 2022-04-13 10:00 | 2022-04-13 17:45 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-04-29 03:30
8-00703237 | Approved | TKW 1CB8 oos | TKW 1CB8 Insp,DOBL & Grading Cap Repl | TKW 1CB8 | 2022-04-13 12:00 | 2022-04-13 19:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-12 10:42
8-00703220 | Approved | TKW 5CB23 oos | TKW 5CB23 PN CN | TKW 5CB23 | 2022-04-14 08:00 | 2022-04-14 12:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-12 12:29
8-00703251 | Completed | SRS T2 oos | PCB Bushing Repl | SRS T2 | 2022-04-14 08:00 | 2022-05-12 10:44 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-12 10:44
8-00707285 | Completed | 60L3 OOS between 60D2L3 and HNY 60D22 | Cable maintenance | 60L3 | 2022-04-14 08:00 | 2022-04-14 16:02 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-04-17 11:34
8-00703241 | Approved | TKW 1CB9 oos | TKW 1CB9 Insp,DOBL & Grading Cap Repl | TKW 1CB9 | 2022-04-14 12:00 | 2022-04-14 18:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-13 13:36
8-00668057 | Completed | HPN T4 OOS | PCB Bushing Replacements | HPN T4 | 2022-04-18 08:00 | 2022-06-07 15:18 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-23 03:30
8-00702377 | Completed | 2L101 OOS | Insulator Replacement | 2L101 | 2022-04-19 07:00 | 2022-04-20 16:42 | 2 | Return Evenings | [6 empty] | Y | N | Y | Y | 2022-04-20 16:42
8-00702435 | Completed | ARN 2B2 OOS | DS Inspection | ARN 2CB3, ARN 2CB2, ARN 2B2, ARN T12 | 2022-04-19 08:00 | 2022-04-22 12:29 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-04-22 18:18
8-00705755 | Completed | ING 5CB6 OOS | Trip testing from PN | ING 5CB6 | 2022-04-19 08:00 | 2022-04-22 11:22 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-22 11:22
8-00705958 | Completed | CK5 5CB2 OOS | Breaker maintenance | CK5 5CB2 | 2022-04-19 08:00 | 2022-04-22 15:53 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-22 15:53
8-00690562 | Completed | 2L240 OOS | End of life structure and cross arm replacements | 2L240, SAM T4 | 2022-04-19 08:00 | 2022-04-21 15:41 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-04-21 15:42
8-00705738 | Completed | 60L19 OOS | Cable testing | 60L19 | 2022-04-21 08:00 | 2022-04-22 11:37 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-22 11:37
8-00700039 | Cancelled | GMS 5B3 oos | GMS CB & DS Insp and DOBL | GMS 5B3, GMS 5D3, GMS 5D4 | 2022-04-21 08:00 | 2022-04-22 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-08 13:37
8-00700040 | Cancelled | GMS 5B3 oos | GMS CVT Insp | GMS 5CB3 | 2022-04-21 08:00 | 2022-04-21 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-08 13:55
8-00688876 | Approved | ACK 2CB12 OOS | Breaker Fail PN OOS | ACK 2CB12 | 2022-04-21 08:00 | 2022-04-21 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-20 12:27
8-00708694 | Completed | ARN 2CB16 OOS | Breaker Protection Maintenance | ARN 2CB16 | 2022-04-22 08:00 | 2022-04-22 14:35 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-22 14:35
8-00306151 | Completed | BSY Synchronous Condenser (G4) OOS | Inspection and Exciter Mtce | BSY G4 | 2022-04-25 01:00 | 2022-05-09 17:15 | 192 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-10 00:46
8-00687359 | Completed | 5L91 OOS | Station DS inpsection of SEL 5D23 | 5L91, SEL 5CB11, SEL 5CB9 | 2022-04-25 08:00 | 2022-04-29 14:30 | 2 | Continuous |  |  |  |  | 560 | 500 | Y | N | Y | Y | 2022-04-29 14:30
8-00658526 | Completed | 2L22 OOS | Structure Replacements | 2L22 | 2022-04-25 08:00 | 2022-04-29 16:29 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-04-29 16:29
8-00662446 | Completed | 2L55 OOS | Detailed & Oil Samples & Jacket Testing | 2L55 | 2022-04-25 08:00 | 2022-04-29 22:03 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-04-29 22:14
8-00667618 | Completed | 2L75 OOS | Inspection of MLN 2CVT9 EL Insp | MLN 2B9, CBN 2CB10, CBN T4, CBN T7, MLN T6, MLN T5, 2L75 | 2022-04-25 08:00 | 2022-04-25 14:46 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-04-25 14:47
8-00705241 | Completed | MPT 2CB1 OOS | Trip testing from PN | MPT 2CB1 | 2022-04-25 08:00 | 2022-04-26 14:02 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-26 14:02
8-00713245 | Completed | CKY 2CB20 OOS | RTU project | CKY 2CB20, CKY T6 | 2022-04-25 08:00 | 2022-05-02 08:45 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-04 08:08
8-00688181 | Approved | NIC T2 OOS | For work on NIC 5CB27 | NIC T2, NIC 5CB27 | 2022-04-26 08:00 | 2022-04-26 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-25 12:10
8-00705960 | Completed | CK5 5CB13 OOS | CK5 - 5CB13 Trip Testing | CK5 5CB13 | 2022-04-26 08:00 | 2022-04-26 14:58 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-27 09:34
8-00706055 | Completed | GIB 1CB3 OOS | GIB 1CB3 COND. protection testing | GIB 1CB3 | 2022-04-26 08:00 | 2022-04-26 11:45 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-26 11:45
8-00667594 | Completed | ING 5B10 and T5 OOS | Inspection of ING 5D5 | ING T5, ING 5B10, ING 12RX5 | 2022-04-27 08:00 | 2022-04-29 16:23 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-04-29 16:27
8-00707797 | Proposed | VIT 2CB4 | CN | VIT 2CB4 | 2022-04-27 08:00 | 2022-04-27 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-19 20:54
8-00705961 | Completed | CK5 5CB2 OOS | CK5 5CB2 Trip Testing | CK5 5CB2 | 2022-04-27 08:00 | 2022-04-27 13:41 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-27 13:41
8-00705261 | Completed | MPT 2CB2 OOS | trip testing from PN | MPT 2CB2 | 2022-04-27 08:00 | 2022-04-28 13:08 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-28 13:09
8-00705962 | Completed | CK5 5CB22 OOS | CK5 5CB22 Trip Testing | CK5 5CB22 | 2022-04-28 08:00 | 2022-04-28 11:45 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-28 11:45
8-00706069 | Completed | SEC 1CB3 OOS | SEC 1CB3 NERC COND. protection testing | SEC 1CB3 | 2022-04-28 08:00 | 2022-04-28 09:45 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-28 10:04
8-00700373 | Completed | MDN 2CB10 OOS | Inspections | MDN 2CB10 | 2022-04-28 08:00 | 2022-04-28 12:17 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-04-28 12:17
8-00709225 | Completed | 2L123 & DMR 2B14 & HWW T1 OOS | Skywire Repair and DS inspections | DMR 2B14, HWW T1, 2L123 | 2022-04-28 08:00 | 2022-04-29 16:09 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-04-29 16:38
8-00708696 | Completed | ARN 2CB17 OOS | Routine CPC BFPN PM | ARN 2CB17 | 2022-04-29 08:00 | 2022-04-29 15:15 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-29 15:16
8-00705963 | Completed | CK5 5CB23 OOS | CK5 5CB23 Trip Testing | CK5 5CB23 | 2022-04-29 08:00 | 2022-04-29 12:48 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-29 13:04
8-00716529 | Completed | MDN 2CX3 OOS | Maintenance | MDN 2CX3 | 2022-04-29 08:00 | 2022-04-29 14:31 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-04-29 14:31
8-00708110 | Cancelled | 2L1 out from BRT to 2D1L1 | Replace 2L1 lattice tower 56-4 | RBW T1, 2L1 | 2022-05-02 07:00 | 2022-05-06 16:00 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-04-26 18:29
8-00688200 | Completed | VVW T2 | T2 NON Electrical | VVW T2 | 2022-05-02 07:00 | 2022-05-02 13:51 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-05-02 13:52
8-00690546 | Completed | 2L256 OOS | End of life structure and cross arm replacements | 2L256 | 2022-05-02 08:00 | 2022-05-10 15:53 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-10 15:53
8-00698003 | Completed | KDY 5CX1 oos | CX Insp | KDY 5CX1 | 2022-05-02 08:00 | 2022-05-19 13:46 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-19 13:46
8-00681439 | Completed | 5L44 OOS | Tower clearance - Raising for SkyTrain | 5L44 | 2022-05-02 08:00 | 2022-05-27 11:08 | 10 | Continuous | 1700 | 2100 | 1500 | 1900 |  |  | Y | N | Y | Y | 2022-05-27 11:08
8-00669242 | Completed | CK5 5RX1 OOS | TRIP TESTING and NON-ELEC PN | CK5 5RX1, CK5 5MB2 | 2022-05-02 08:00 | 2022-05-05 09:24 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-05-21 03:30
8-00686799 | Completed | 1L274 out from EFT to 1D2L274 | Replace Timbers and Install Markerballs | 1L274 (887L) | 2022-05-02 08:00 | 2022-05-03 14:18 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-03 14:19
8-00687782 | Completed | KHS 2CB4 OOS | KHS 2CB4 Breaker Inspection and BFPN Testing | KHS 2CB4 | 2022-05-02 08:00 | 2022-05-06 18:52 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-06 18:53
8-00427100 | Cancelled | 1L143 OOS | JOR- POSITION MO3 PORTABLE SUB FOR TM-0159 PROJECT | 1L143 | 2022-05-02 08:00 | 2022-05-02 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-01-19 08:11
8-00669613 | Completed | 2L76 OOS | MLE TM0157 OSP Stage 4 | 60L8, 60L7, 60L100, MLE 2B1, MLE T1, 2L76 | 2022-05-02 08:00 | 2022-05-16 15:45 | 8 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-16 15:45
8-00662447 | Completed | 2L39 OOS | Overview & Oil Samples | BSY 2CB8, 2L39, NEL 2CB4, NEL T1, NEL T5 | 2022-05-02 08:00 | 2022-05-06 09:59 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-06 10:08
8-00707700 | Completed | JPT 1CB5 | CN | JPT 1CB5, 1L128 | 2022-05-02 08:00 | 2022-05-03 13:34 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-03 13:34
8-00703271 | Completed | ING T9, 60CL5 OOS | Oil samples and MNRI | ING T9 | 2022-05-02 08:00 | 2022-05-06 15:30 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-06 15:30
8-00702478 | Cancelled | MFE 1CX1 oos | MFE 1CX1 Insp | MFE 1CX1 | 2022-05-02 08:00 | 2022-05-02 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-04 18:00
8-00702481 | Completed | WLM T2 oos | PCB Bushing Repl | WLM T2 | 2022-05-02 08:00 | 2022-06-15 16:25 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-15 16:26
8-00715576 | Completed | MLE 2CB2 OOS, 2L76, MLE T1, 2CB1 PY/SY PN OOS OAT | MLE TM0157 OSP Stage 4 | MLE 2CB2 | 2022-05-02 08:00 | 2022-05-16 13:19 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-16 20:57
8-00715053 | Completed | CKY 2CB9 OOS | RTU Porject Outages | CKY 2CB10, CKY 2CB9, CKY 60CB3 | 2022-05-02 08:00 | 2022-05-04 08:07 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-04 08:08
8-00713870 | Completed | MPT 2CB3 OOS, MPT T1, 2L44 PY/SY PN OOS OAT | CN PM | MPT 2CB3 | 2022-05-02 08:00 | 2022-05-03 14:59 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-03 14:59
8-00688764 | Completed | NAK T1 OOS | NAK T1/12VR1 (T1 non EL's, and 12VR1 Repairs) | NAK T1 | 2022-05-02 11:30 | 2022-06-01 14:17 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-17 03:30
8-00706837 | Completed | WLT T1 & WLT 60B2 OOS | WLT 60D1 replacement | WLT T1, WLT 60B2 | 2022-05-02 12:00 | 2022-05-19 12:08 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-19 12:39
8-00713279 | Completed | ING 5CB10 OOS | NERC CPC CB CN PM | ING 5CB10 | 2022-05-03 08:00 | 2022-05-05 14:15 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-05-05 14:16
8-00688205 | Completed | 2L92 and SVA T3 OOS | T3 NON Electrical | 2L92, SVA T3, SVA 2B5 | 2022-05-03 08:00 | 2022-05-05 13:03 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-05 13:03
8-00688168 | Completed | 5L98 OOS | Disconnect Inspection at NIC 5D31, 5D51, 5D1CB25 and 5D2CB15 | NIC 5CB25, NIC 5CB5, NIC 5RX11, 5L98, VAS 5RX1 | 2022-05-03 08:00 | 2022-05-06 13:08 | 2 | Continuous |  |  |  |  | 560 | 450 | N | N | Y | Y | 2022-05-06 13:08
8-00674355 | Completed | MDN T2 OOS | CPC non-electrical testing | MDN T2 | 2022-05-03 08:00 | 2022-05-05 14:05 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-05 14:05
8-00713894 | Completed | MPT 2CB4 OOS | CN PM | MPT 2CB4 | 2022-05-04 08:00 | 2022-05-05 15:06 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-05 15:06
8-00718814 | Completed | MAN 2CB3 OOS | Breaker maintenance | MAN 2CB3 | 2022-05-04 08:00 | 2022-05-04 14:59 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-16 20:41
8-00715054 | Completed | CKY 2CB8 OOS | RTU Project Work | CKY 2CB8, CKY 60CB1, CKY 60CB3 | 2022-05-04 12:00 | 2022-05-06 14:04 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-06 14:04
8-00714838 | Completed | MPT 2CB6 OOS | Maintenance | MPT 2CB6 | 2022-05-06 08:00 | 2022-05-06 13:23 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-06 13:23
8-00714413 | Completed | SYH T2 OOS | SYH T2 Transformer Maintenance | SYH T2, 2L57 | 2022-05-06 08:00 | 2022-05-06 15:53 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-06 15:54
8-00713991 | Denied | KLY 5B12 oos | KLY 5B12 SY PN replacement project | KLY 5B12, KLY T4 | 2022-05-07 08:00 | 2022-05-07 18:00 | 5 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-02 10:56
8-00714902 | Completed | 2L40 from BND to BSY | Hotspot Repairs and Inspection | BSY 2CB10, BSY 2CB9, BND T1, 2L40, NEL 2CB4, NEL T3, NEL T4 | 2022-05-07 08:00 | 2022-05-07 14:09 | 3 | Continuous | [6 empty] | N | Y | Y | Y | 2022-07-27 14:13
8-00712779 | Completed | 5L31 OOS | TIR RXs Non-electrical trip testing, non-electrical re-wiring, & ETM installation | TIR 5RX14, TIR 5RX15, TIR 5RX25, TIR 5RX26, TIR 5RX4, TIR 5RX5, TIR 5RX6, 5L31 | 2022-05-09 08:00 | 2022-05-27 09:32 | 6 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-27 16:46
8-00662448 | Completed | 2L50 OOS | Detailed & Oil Sample | CSQ 2CB1, 2L50 | 2022-05-09 08:00 | 2022-05-13 12:14 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-05-13 12:14
8-00661230 | Completed | GTP SS11 OOS | For Station Reconfiguration | GTP T11 | 2022-05-09 08:00 | 2022-05-11 14:14 | 8 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-11 14:14
8-00705967 | Completed | TIS - 2CB1 | TIS - 2CB1 Trip Testing | TIS 2CB1 | 2022-05-10 08:00 | 2022-05-10 16:06 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-10 16:09
8-00702453 | Completed | 2L352 oos | HMH CVT Insp | 2L352, HMH 2CB1, HMH T3 | 2022-05-10 08:00 | 2022-05-10 15:34 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-26 03:30
8-00701985 | Completed | 2L352 oos | Structure Repl | 2L352 | 2022-05-10 08:00 | 2022-05-15 19:45 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-15 19:51
8-00700372 | Completed | BSY G3 OOS | Inspections | BSY G3 | 2022-05-10 08:00 | 2022-06-09 17:36 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-09 17:36
8-00667607 | Completed | 2L6 OOS | Inspection of ING 2D25 | ING 2CB6, ING 2CB5, ARN 2CB10, ARN 2CB11, 2L6, SYH T1 | 2022-05-10 08:00 | 2022-05-11 16:34 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-16 20:34
8-00658515 | Completed | 5L83 OOS | Insulator Replacement | 5L83 | 2022-05-10 08:00 | 2022-05-13 15:18 | 2 | Continuous |  |  | 1200 | 1600 |  |  | Y | N | Y | Y | 2022-05-13 15:18
8-00718513 | Completed | 2L52 OOS | Flood light installation | 2L52, MDN 2CB17, MDN 2CB18, MDN 2B17 | 2022-05-11 07:00 | 2022-05-12 15:26 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-12 15:50
8-00705968 | Completed | TIS - 2CB2 | TIS - 2CB2 Trip Testing | TIS 2CB2 | 2022-05-11 08:00 | 2022-05-11 15:46 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-11 15:47
8-00670738 | Completed | 5L71 OOS | MCA Switchgear Roof Replacement Project Deficiencies. | 5L71 | 2022-05-11 08:00 | 2022-05-30 17:32 | 8 | Continuous | 2850 | 3150 | 2500 | 2500 | 850 | 1000 | Y | N | Y | Y | 2022-05-30 17:33
8-00690541 | Completed | 5L98 OOS | Flashed Insulator Replacements | 5L98, VAS 5CB13, VAS 5RX1 | 2022-05-11 08:00 | 2022-05-13 14:24 | 2 | Continuous |  |  |  |  | 560 | 500 | N | N | Y | Y | 2022-05-13 14:24
8-00668486 | Cancelled | 1L11 OOS | Structure Replacements | 1L11 | 2022-05-11 08:00 | 2022-05-12 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-05 10:08
8-00716376 | Cancelled | KI2 T1, 12RX1 OOS | Tree removal near equipment | KI2 12RX1, KI2 T1 | 2022-05-12 08:00 | 2022-05-12 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-14 18:00
8-00703246 | Approved | SRS 1CB4 oos | SRS 1CB4 PN CN | SRS 1CB4 | 2022-05-12 14:00 | 2022-05-12 16:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-10 09:00
8-00704843 | Completed | MLN T6, T3 OOS | Disconnect Switch Inspection | MLN T3, MLN 2B10, MLN T6, MLN 2CB10, MLN 2D2CB11, MLN 2CB11 | 2022-05-13 08:00 | 2022-05-13 15:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-31 20:04
8-00661241 | Completed | 2L142 and 1L14 OOS | For PN upgrades at GTP | 1L14, GTP 1CB1, GTP 1B1, GTP T11, KSH T2, SHA T1, GTP T14, 2L142 | 2022-05-13 08:00 | 2022-05-16 19:50 | 8 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-05-16 19:54
8-00721595 | Completed | 5L12 oos | Commission POW of WSN 5CB15 | 5L12 | 2022-05-13 09:00 | 2022-05-13 21:01 | 1 | Continuous | [6 empty] | Y | N | Y | Y | 2022-05-13 21:48
8-00723073 | Completed | 2L93 OOS | Replace failed transmission structure | 2L93 | 2022-05-13 09:00 | 2022-05-13 15:15 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-13 15:15
8-00712584 | Cancelled | 5L71. MCA 5B10, 5RX4 OOS | MCA 5B10 GIB Zones 4/5/6 Inspections for 5RX4 Project. | 5L71, MCA 5B10, MCA 5RX4 | 2022-05-13 16:00 | 2022-05-30 17:00 | 144 | Continuous | [6 empty] | Y | N | Y | Y | 2022-04-25 08:37
8-00719431 | Completed | ING 230KV Cap Banks OOS | Equipment Inspection requiring Neutral Cable OOS | ING 2CB22, ING 2RX2, ING 2CX2 | 2022-05-14 08:00 | 2022-05-14 14:52 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-14 14:53
8-00612586 | Completed | 1L274 out from 1D4L274 to POC | Create bus cut #1 and #2 at BCK | 1L274 (887L) | 2022-05-15 06:00 | 2022-05-15 17:33 | 5 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-15 22:42
8-00709271 | Cancelled | DMR 5L31 | DMR 5L31 Cable Support | 5L31 | 2022-05-15 08:00 | 2022-05-28 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-16 15:59
8-00705372 | Completed | 2L309, SNK 2B1 oos | SNK DS and CT Insp | SNK 2B1, 2L309 | 2022-05-16 08:00 | 2022-05-17 15:48 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-17 16:04
8-00723618 | Completed | 5L82 OOS | AMC 5CX2 PN Replacement, and NIC inspection | 5L82, NIC 5B28, NIC 5RX9 | 2022-05-16 08:00 | 2022-05-19 17:03 | 7 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-04 03:30
8-00715071 | Cancelled | CKY T4 OOS | DS Control Upgrades | CKY 2D4, CKY T4 | 2022-05-16 08:00 | 2022-05-20 16:00 | 8 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-03 16:52
8-00662450 | Completed | 2L32 OOS | Overview & Replace Blocks | CSQ 2CB1, 2L32 | 2022-05-16 08:00 | 2022-05-18 13:55 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-18 13:57
8-00690524 | Completed | 5L76 OOS | Flashed Insulator Replacements | 5L76 | 2022-05-16 08:00 | 2022-05-18 09:10 | 2 | Continuous |  |  |  |  | 850 | 1000 | N | N | Y | Y | 2022-05-18 09:18
8-00686282 | Completed | 2L113 OOS | CBK DS inspections | CBK 2CB6, CBK 2CB9, 2L113, NTL 60CB11, 60L281 | 2022-05-16 08:00 | 2022-05-17 15:13 | 2 | Continuous |  |  |  |  | 850 | 700 | N | N | Y | Y | 2022-05-17 15:58
8-00701971 | Completed | 2L95 oos | Structure Repl | 2L95 | 2022-05-16 10:00 | 2022-05-19 15:02 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-19 15:02
8-00700361 | Completed | MDN 5CB2 OOS | NERC PM - Breaker to be operated few times - PN OOS OAT | MDN 5CB2, MDN 5CB3, MDN T1 | 2022-05-17 08:00 | 2022-05-17 16:33 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-17 16:33
8-00666740 | Completed | 2L63 OOS | Disconnect & Breaker Inspection | ARN 2CB14, ARN 2CB15, ARN 2D34, SYH T3, 2L63 | 2022-05-17 08:00 | 2022-05-18 16:30 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-18 16:31
8-00705970 | Completed | UHT T1 OOS | PM Inspections, and non electrical testing | UHT 3B1, UHT T1 | 2022-05-17 09:00 | 2022-05-19 15:24 | 1 | Return Evenings | [6 empty] | N | N | Y | Y | 2022-05-19 15:24
8-00705369 | Completed | 2L309, DKT 2B2 oos | DKT DS Insp and SSVT DOBL | DKT 2B2, 2L309 | 2022-05-18 08:00 | 2022-05-18 16:23 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-18 16:30
8-00718439 | Completed | 2L45 OOS | Check cable oil pressure | 2L45 | 2022-05-18 08:00 | 2022-05-18 15:48 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-06-03 03:30
8-00633579 | Completed | 5L82 OOS | AMC PN Replacement Project | 5L82, AMC 5CX2 | 2022-05-19 16:01 | 2022-06-01 16:19 | 7 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-07 16:32
8-00718425 | Completed | 2L33 OOS | Cable Maintenance - Oil Pressure | 2L33, MDN T2, 2L44 | 2022-05-21 08:00 | 2022-05-21 15:50 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-05-21 15:52
8-00687458 | Completed | SEL 2CB4 OOS | inspection | SEL 2CB4 | 2022-05-23 08:00 | 2022-05-26 12:34 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-05-26 12:34
8-00690538 | Completed | 5L96 OOS | Flashed Insulator Replacements | 5L96 | 2022-05-24 08:00 | 2022-06-01 21:13 | 2 | Return Weekends |  |  |  |  | 560 | 450 | N | N | Y | Y | 2022-06-02 11:12
8-00699183 | Completed | KDY 5CX3 oos | CX PM | KDY 5CX3 | 2022-05-24 08:00 | 2022-06-13 15:12 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-13 15:12
8-00661255 | Cancelled | GTP 1CB1 00S | PN upgrade work | GTP 1CB1 | 2022-05-24 08:00 | 2022-05-26 16:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-16 08:21
8-00716384 | Completed | MDN T3 OOS | PCB MDN T3 Bushing Replacement pre-checks | MDN 12RX31, MDN 12RX32, MDN T3 | 2022-05-24 08:00 | 2022-05-25 11:18 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-05-25 11:18
8-00725647 | Completed | 5L31 OOS | Installation of markerballs | 5L31 | 2022-05-24 08:00 | 2022-05-27 16:45 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-27 16:46
8-00712753 | Completed | CSQ 2CB6 OOS | CB & PN Tests | CSQ 2CB6 | 2022-05-24 08:00 | 2022-05-24 11:58 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-24 11:59
8-00700365 | Completed | MDN 5CB7 OOS | NERC PM - CB & PN Testing | MDN 5CB7 | 2022-05-24 08:00 | 2022-05-25 15:15 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-25 15:16
8-00702349 | Completed | CBK 2CB9 OOS | CBK 2CB9 CN pm, and CBK 2D1CB9 insp | CBK 2CB9 | 2022-05-24 08:00 | 2022-05-25 13:35 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-25 13:35
8-00686877 | Completed | 5L96 OOS | Replace Defective Insulators and Install Markerballs | 5L96 | 2022-05-24 11:00 | 2022-06-01 21:14 | 4 | Return Weekends |  |  |  |  | 560 | 450 | N | N | Y | Y | 2022-06-02 11:11
8-00718159 | Completed | ING 2CB21, 2RX1, 2CX11 OOS | ING 2CB21 Replacement | ING 2CB21, ING 2RX1, ING 2CX11 | 2022-05-24 16:00 | 2022-06-23 19:05 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-23 21:33
8-00718444 | Completed | 2L64 OOS | Cable Maintenance - Oil Pressure | 2L64 | 2022-05-25 08:00 | 2022-05-25 16:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-05-25 16:00
8-00712759 | Completed | CSQ 2CB7 OOS | CB & PN Tests | CSQ 2CB7 | 2022-05-25 08:00 | 2022-05-25 11:34 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-26 08:39
8-00709902 | Completed | HMH 60CB11 OOS | Insp & Doble Test | CRQ 60CB1, HMH 60CB11 | 2022-05-25 08:00 | 2022-05-26 14:56 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-05-26 14:57
8-00687301 | Completed | KCL 2CB9 OOS | Breaker Fail PM | KCL 2CB15, KCL T7, KCL 2CB9 | 2022-05-25 08:00 | 2022-05-25 15:42 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-25 15:47
8-00687304 | Completed | KCL 2CB13 OOS | Breaker Fail PM | KCL 2CB10, KCL 2CB13 | 2022-05-26 08:00 | 2022-05-26 14:15 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-26 14:15
8-00686295 | Completed | CBK 2CB 10 OOS | CBK 2CB10 BFPN Testing | CBK 12RX7, CBK 2CB10 | 2022-05-26 08:00 | 2022-05-26 14:16 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-26 14:16
8-00666760 | Completed | ING 5MB2, T4, 12RX4 OOS | ING 5D4 Inspection | ING 12RX4, ING T4, ING 5MB2 | 2022-05-26 16:00 | 2022-05-31 19:16 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-05-31 20:21
8-00687306 | Completed | KCL 2CB16 oos | Breaker Fail PM | KCL 2CB14, KCL 2CB16 | 2022-05-27 08:00 | 2022-05-27 15:13 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-05-27 16:09
8-00705380 | Completed | 1L360, TAY 1B21 oos | TAY DS, CVT Insp and PN CN | 1L360, TAY 1B21 | 2022-05-30 08:00 | 2022-05-31 14:33 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-31 14:33
8-00723605 | Completed | SFY 60MB2 OOS | Disconnect maintenance | SFY 60D2CB31, SFY 60D2CB32, SFY 60D2CB33, SFY 60MB2 | 2022-05-30 08:00 | 2022-05-31 12:56 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-31 12:57
8-00724427 | Completed | MPT T2 OOS, 2B4/5 Switching OOS | MPT T2 Non-El PM | MPT T2 | 2022-05-30 08:00 | 2022-05-30 15:59 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-30 15:59
8-00726810 | Cancelled | ING 2CX2, 2RX2, 2CB22 OOS | PCB Inventory | ING 2CB22, ING 2RX2, ING 2CX2 | 2022-05-30 08:00 | 2022-05-30 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-30 17:26
8-00687312 | Completed | KCL 2CB6 OOS | Breaker Inspoection | KCL 2CB6 | 2022-05-30 08:00 | 2022-06-03 13:34 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-09 15:26
8-00687336 | Completed | NLY T1 OOS | Inpsection and Doble Test | NLY T1 | 2022-05-30 08:00 | 2022-06-03 17:43 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-03 17:44
8-00688765 | Completed | GTP 1CB2 OOS | 1L12 PN upgrade work | GTP 1CB2 | 2022-05-31 08:00 | 2022-06-01 15:21 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-01 15:21
8-00688769 | Completed | GOW 1CB3 OOS | 1L112 PN Upgrade work | GOW 1CB3 | 2022-05-31 08:00 | 2022-06-01 14:58 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-01 14:58
8-00666741 | Completed | CAM T2, 2CB4 OOS | CB Control Tests & Inspection | 2L4, CAM 2CB4, CAM T2 | 2022-05-31 08:00 | 2022-06-02 15:39 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-06-02 15:40
8-00701988 | Completed | BLW 2CX1 oos | CX Insp | BLW 2CX1 | 2022-05-31 08:00 | 2022-05-31 16:30 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-31 16:55
8-00702930 | Completed | TKW T2, 12RX2 oos | TKW T2 Leak Repair | TKW T2, TKW 12RX2 | 2022-06-01 08:00 | 2022-06-10 16:27 | 12 | Continuous | [6 empty] | N | Y | Y | Y | 2022-06-10 16:28
8-00728634 | Completed | AMC 5CX2 OOS | AMC PN Upgrade Project | AMC 5CX2 | 2022-06-01 16:01 | 2022-06-07 16:32 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-07 16:32
8-00730236 | Completed | CSQ T2, 2B4 OOS | CSQ T2 Doble/TTR | CSQ T2, CSQ 2B4 | 2022-06-02 08:00 | 2022-06-02 19:33 | 16 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-14 15:17
8-00728625 | Completed | BSY G3, 2CB6, 2CB7 OOS | 2CB6 and 2CB7 CPC PM | BSY 2CB6, BSY 2CB7, BSY G3 | 2022-06-02 08:00 | 2022-06-03 15:33 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-09 17:36
8-00728149 | Completed | CRK 5CX1 OOS | CRK Disconnect Inspection | 5L42, CRK 5CX1 | 2022-06-02 08:00 | 2022-06-10 13:00 | 4 | Continuous | 2300 | 2700 |  |  |  |  | N | N | Y | Y | 2022-06-10 17:16
8-00725690 | Completed | 2L18, HPL OOS | HPL transformer inspection/maintenance | 2L18 | 2022-06-02 08:00 | 2022-06-02 14:55 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-02 15:00
8-00718351 | Proposed | KLY 5B12, T4 oos | CT Wiring for KLY 5B12 SY PN Repl Project | KLY 5B12, KLY T4 | 2022-06-02 08:00 | 2022-06-04 18:00 | 5 | Continuous | [6 empty] | N | N | Y | Y | 2022-05-24 11:44
8-00659407 | Completed | 5L42, KLY 5B12, 5B2, T4 OOS | KLY PN Upgrade and DS Replacement | 5L42, KLY 5B12, KLY 5B2, KLY T4 | 2022-06-02 08:00 | 2022-06-08 13:00 | 4 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-06-10 17:16
8-00726813 | Approved | ING 2CX2, 2RX2, 2CB22 | PCB Inventory | ING 2CB22, ING 2RX2, ING 2CX2 | 2022-06-03 08:00 | 2022-06-03 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-02 15:25
8-00306094 | Cancelled | BSY G3 OOS | Inspection and Exciter Maintenance | BSY G3 | 2022-06-06 01:00 | 2022-06-17 23:00 | 192 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-08 18:00
8-00666743 | Completed | ING T2 OOS | ING T2 EL Insp & Doble Test | ING T2 | 2022-06-06 08:00 | 2022-06-22 08:41 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-23 20:40
8-00667599 | Cancelled | 2L27 OOS | Inspection of ING 2CVT19 | 2L27 | 2022-06-06 08:00 | 2022-06-17 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-10 16:38
8-00667621 | Completed | WHY 2CB3, T3 OOS | WHY 2CB3 CPC Control Outage | WHY 2CB3, WHY T3 | 2022-06-06 08:00 | 2022-06-07 17:09 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-07 17:09
8-00681435 | Completed | 2L27 OOS | Install a new steel h-frame and new conductor | 2L27 | 2022-06-06 08:00 | 2022-06-16 11:08 | 10 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-06-16 11:08
8-00687420 | Completed | 5L92 OOS | SEL disconnect Switch inpsections | 5L92, SEL 5CB3, SEL 5CB4 | 2022-06-06 08:00 | 2022-06-10 16:39 | 2 | Continuous |  |  |  |  | 110 | 300 | N | N | Y | Y | 2022-06-27 03:30
8-00688777 | Completed | GTP T13 OOS | PN Upgrades for line position swap | GTP T13 | 2022-06-06 08:00 | 2022-06-07 13:44 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-07 13:45
8-00688778 | Completed | GOW 1CB4 OOS | PN upgrades for line position swap | GOW 1CB4 | 2022-06-06 08:00 | 2022-06-08 15:05 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-08 15:10
8-00719793 | Denied | MLN 2CB7 OOS | MLE Expansion project - PN cutover | MLN 2CB7 | 2022-06-07 08:00 | 2022-06-10 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-01 15:48
8-00728509 | Completed | 5L92 OOS | Tranmission line work | 5L92 | 2022-06-07 08:00 | 2022-06-10 15:49 | 4 | Continuous |  |  |  |  | 110 | 300 | N | N | Y | Y | 2022-06-11 09:02
8-00700366 | Completed | MDN 5CB8 OOS | NERC PM - Breaker Testing - PN OOS OAT | MDN 5CB8 | 2022-06-07 08:00 | 2022-06-08 15:42 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-06-08 15:43
8-00701995 | Completed | 2L354 oos | RBF, BLW DS Insp | 2L354, RBF T1 | 2022-06-07 08:00 | 2022-06-07 13:38 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-07 13:48
8-00705383 | Completed | 1L367, TAY 1B21 oos | TAY DS, CVT Insp & PN CN | 1L367, FJN 1B6, TAY 1B32 | 2022-06-07 08:00 | 2022-06-07 15:11 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-07 15:20
8-00543444 | Proposed | 60L29 OOS | Structure Replacements | 60L29 | 2022-06-07 08:00 | 2022-06-15 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2021-02-02 17:25
8-00730070 | Completed | 5L42 and KLY 5CB11 OOS | KLY 5CB12 Repairs | 5L42, KLY 5B2, KLY 5CB11, KLY 5CB12 | 2022-06-07 16:00 | 2022-06-10 17:16 | NR | Continuous | [6 empty] | Y | N | Y | Y | 2022-06-26 03:30
8-00455945 | Completed | AMC 5CX1 OOS | AMC 5CX1 PN upgrade project STEP 3 | AMC 5CX1 | 2022-06-08 07:00 | 2022-07-19 09:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-29 15:29
8-00724162 | Completed | 2L40 OOS, BND T1, 2D21 OOS | Install Motor and Test Operate BND 2D21 | BND 2D21, BND T1, 2L40, NEL 2CB4, NEL T3, NEL T4 | 2022-06-08 08:00 | 2022-06-08 14:06 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-07-27 14:13
8-00708864 | Completed | ARN 2CB5 OOS | Routine CPC BFPN PM | ARN 2CB5 | 2022-06-08 08:00 | 2022-06-09 15:05 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-06-09 15:05
8-00705382 | Completed | 1L367, FJN 1B6 oos | FJN DS, CVT Insp & PN CN | 1L367, FJN T2, FJN 1B6 | 2022-06-09 08:00 | 2022-06-09 15:38 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-09 15:38
8-00730675 | Completed | 60L1 OOS | 60L1 Structural Work | 60L1 | 2022-06-09 08:00 | 2022-06-09 14:56 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-09 14:57
8-00733602 | Completed | 5L42, KLY 5B2, 5CB11, 5CB12 OOS | Repairs to KLY 5CB12 | 5L42, KLY 5B2, KLY 5CB11, KLY 5CB12 | 2022-06-13 08:00 | 2022-06-14 17:07 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-06-30 03:30
8-00711615 | Completed | SFY 60CB12 OOS | Breaker Inspection/Testing | SFY 60CB12 | 2022-06-13 08:00 | 2022-06-15 12:01 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-15 12:01
8-00686796 | Completed | 2L294 Out from CBK to AAL | Structure replacements | 2L294 | 2022-06-13 08:00 | 2022-06-17 13:18 | 6 | Continuous |  |  |  |  | 850 | 500 | N | Y | Y | Y | 2022-06-17 14:23
8-00667640 | Completed | CRK 5CX1 OOS | PM MJRI AND MJ06 | CRK 5CX1 | 2022-06-13 08:00 | 2022-06-18 12:15 | 6 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-18 12:16
8-00669770 | Completed | 2L76 OOS | MLE Stn Upgrade Stg 6 - Gantry Tower #2 Install within MLE 2B1 LOA | MLN T6, MLN T5, MLE 2B1, MLE T1, 2L76 | 2022-06-13 08:00 | 2022-06-20 10:55 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-07-06 03:30
8-00697972 | Completed | 5L1 oos | Spacer Repl | 5L1, GMS 5RX1, GMS 5B2 | 2022-06-14 08:00 | 2022-06-24 20:57 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-06-29 12:33
8-00697995 | Cancelled | 5L1, GMS 5RX1, 5B2 oos | GMS 5RX1 NON-EL PN PM | 5L1, GMS 5RX1, GMS 5B2 | 2022-06-14 08:00 | 2022-06-25 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-10 08:52
8-00713787 | Completed | ING 2CB19 OOS | Routine CPC CB CN PM | ING 2CB19 | 2022-06-14 08:00 | 2022-06-14 16:27 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-14 16:27
8-00730241 | Completed | ARN 2MB1, 2B2, T12 OOS | ARN lighting upgrade within 2MB1 LOA | ARN 2B2, ARN 2MB1, ARN T12 | 2022-06-14 08:00 | 2022-06-15 15:15 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-06-16 13:03
8-00702475 | Completed | WSN T2, 12RX1 OOS | Bushing Replacement | WSN 12RX1, WSN 2CB6, WSN T2 | 2022-06-15 08:00 | 2022-07-20 14:27 | 48 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-20 15:20
8-00713879 | Completed | ING 2CB23, 2CX31, 2CX32 OOS | Routine CPC BFPN PM | ING 2CB23, ING 2CX31, ING 2CX32 | 2022-06-15 08:00 | 2022-06-17 15:11 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-17 15:11
8-00688802 | Cancelled | GTP T13 OOS | PN upgrades for 1L12/1L14 line position swap | GTP T13 | 2022-06-15 08:00 | 2022-06-17 16:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-13 13:36
8-00253270 | Completed | BSY G1 OOS | Major Inspection | BSY T1, BSY T11, BSY G1 | 2022-06-15 08:00 | 2022-11-17 17:29 | 720 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-17 17:29
8-00731133 | Completed | KLY 5CB11 OOS | CB Repair | KLY 5CB11 | 2022-06-16 08:00 | 2022-06-24 12:12 | 48 | Continuous | [6 empty] | Y | N | Y | Y | 2022-06-24 12:12
8-00702253 | Proposed | 1L373 oos | Structure Repl | 1L373 | 2022-06-17 08:00 | 2022-06-17 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-03-09 11:46
8-00726311 | Completed | 2L18, HPL OOS | SF6 gas sampling on HPL 2CB2 | 2L18 | 2022-06-17 15:30 | 2022-06-27 16:16 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-06-27 16:16
8-00669793 | Completed | 2L76, MLE 2B1, 2B4 OOS | MLE Upgrade - Modify 2B1 and Connect T1 to 2B4 | MLN T6, MLN T5, MLE 2B1, 2L76, MLE 2B4 | 2022-06-20 07:00 | 2022-06-30 15:02 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-06-30 15:29
8-00667983 | Completed | HPN 2B7 OOS (2L51 Out from HPN) | CBs and Disconnects MTCE | HPN 2CB8, HPN 2D1CB7, HPN 2D2CB8, 2L51, HPN 2B7 | 2022-06-20 08:00 | 2022-06-23 18:47 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-23 18:48
8-00717989 | Completed | ING 2MB2 OOS | ING 2CB21 Replacement | ING 2CB21, ING 2MB2, 2L18 | 2022-06-20 08:00 | 2022-06-23 19:05 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-06-27 16:16
8-00712129 | Completed | ARN HF2, 2B16 OOS | CPC NERC PM for HF2 and HP2 | ARN 2B16 | 2022-06-20 08:00 | 2022-07-09 00:22 | 5 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-09 00:22
8-00703312 | Completed | TKW 5CB23 oos | CB Insp & DOBL | TKW 5CB13 | 2022-06-21 08:00 | 2022-06-24 17:17 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-06-24 17:17
8-00730260 | Completed | 2L10, ARN 2CB1, 2CB2 OOS | ARN Lighting Upgrade | ARN 2CB1, ARN 2CB2, 2L10 | 2022-06-22 07:00 | 2022-06-22 16:27 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-06-22 16:28
8-00667632 | Completed | RYC 5CX1 OOS | RYC 5CX1 Inspection | RYC 5CX1 | 2022-06-22 08:00 | 2022-07-04 14:55 | 48 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-04 14:55
8-00666744 | Completed | ING 5B6 and ING T2 OOS | Inspection of ING 5D2 | ING 5CB6, ING 5CB7, ING T2, ING 5B6 | 2022-06-22 08:00 | 2022-06-23 20:14 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-23 20:40
8-00697990 | Cancelled | 5L1 oos | GMS 5D21 Repair | 5L1, GMS 5D21, GMS 5B2 | 2022-06-23 08:00 | 2022-06-24 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-17 15:31
8-00724626 | Cancelled | KI2 2CB13 OOS | CPC CB CN PM | KI2 2CB13 | 2022-06-23 08:00 | 2022-06-23 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-22 15:51
8-00723352 | Completed | ING 2MB2, 2MB4 OOS | ING 2CB21 Energization | ING 2CB17, ING 2CB9, ING 2CB8, ING 2CB1, ING 2MB2, ING 2RX1, ING 2MB4, 2L18, ING 2CX11 | 2022-06-23 08:00 | 2022-06-23 19:05 | 2 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2022-06-27 16:16
8-00713892 | Cancelled | ING 2CB20 OOS | Routine CPC CB CN PM | ING 2CB20 | 2022-06-24 08:00 | 2022-06-24 13:28 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-22 15:51
8-00707912 | Cancelled | DAW T3, 1B5 oos | DAW DS Insp | DAW T3, DAW 1CX3, DAW 1CX4, DAW 1B5 | 2022-06-24 08:00 | 2022-06-24 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-13 01:44
8-00730908 | Completed | COK T2, 60L2 OOS | Replace COK 60D1CB7, requiring 60B6/7 OOS | COK 60B7, COK 60B8 | 2022-06-27 08:00 | 2022-07-12 12:12 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-07-12 12:12
8-00738581 | Cancelled | 2L45 OOS | Emergent Work for distribution duct bank to cross | CSN 2CB4, 2L45, CSN 2CB5 | 2022-06-27 08:00 | 2022-07-08 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-06-26 19:44
8-00699189 | Completed | MLS 5CX2 oos | CX and PN PM | MLS 5CX2 | 2022-06-27 08:00 | 2022-06-30 15:08 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-30 15:08
8-00699184 | Completed | 5L12 oos | Insulator Repl | 5L12 | 2022-06-27 08:00 | 2022-06-29 19:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-01 16:38
8-00664629 | Completed | BSY 2CB1 & 2CB2 OOS | Disconnects Inspection | BSY 2CB1, BSY 2CB2, BSY G1 | 2022-06-27 08:00 | 2022-07-16 15:58 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-17 17:29
8-00713897 | Completed | ING 2CB17 OOS | Routine CPC CB CN PM | ING 2CB17 | 2022-06-28 08:00 | 2022-06-28 15:40 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-28 15:40
8-00730501 | Completed | 60L76 OOS | CVN 60CB2 Energization | 60L76 | 2022-06-30 08:00 | 2022-06-30 12:13 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-06-30 12:13
8-00727768 | Completed | 5L4, GMS 5B8, PCN 5B4 oos | Oil leak check | 5L4, PCN 5B4, GMS 5B8 | 2022-06-30 08:00 | 2022-06-30 15:27 | NR | Continuous | [6 empty] | Y | N | Y | Y | 2022-06-30 15:38
8-00687478 | Completed | 60L288, 60L285, 60L292 and 60L281 OOS | NTL 60D21 Repairs | 2L113, 60L285, 60L288, 60L292, 60L281 | 2022-07-01 08:00 | 2022-07-01 16:53 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-07-01 16:54
8-00305830 | Cancelled | BSY Synchronous Condenser (G1) OOS | Inspection and Exciter Mtce | BSY G1 | 2022-07-04 01:00 | 2022-07-15 23:00 | 192 | Continuous | [6 empty] | N | N | Y | Y | 2022-01-05 15:11
8-00688207 | Completed | 5L11 OOS | KLY Disconnect Switch inpsections of KLY 5D21, 5DCB31, 5D2CB1 and 5D1CB11 | 5L11, KLY 5B1, KLY 5RX1, WSN 5B4, WSN 5RX3 | 2022-07-04 08:00 | 2022-07-08 16:40 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-07-08 16:40
8-00699191 | Cancelled | 5L11 oos | Insulator Repl | 5L11 | 2022-07-04 08:00 | 2022-07-06 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-28 09:19
8-00699192 | Cancelled | 5L11 oos | MLS DS and BP Insp | 5L11, MLS 5CX1, MLS 5D21, MLS 5D31 | 2022-07-04 08:00 | 2022-07-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-28 09:17
8-00699193 | Cancelled | 5L11 oos | WSN DS Insp | 5L11, WSN 5B4 | 2022-07-04 08:00 | 2022-07-08 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-28 09:12
8-00693609 | Completed | 60L8, GLT OOS | GLT 60DCB1 Repair | 60L8, GLT T1 | 2022-07-04 08:00 | 2022-07-07 13:11 | 5 | Continuous | [6 empty] | N | Y | Y | Y | 2022-07-07 13:11
8-00730278 | Completed | 2L63 Out from ARN | ARN lighting upgrade project | ARN 2CB14, ARN 2CB15, 2L63 | 2022-07-05 07:00 | 2022-07-05 15:45 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-05 15:45
8-00733348 | Completed | 60L14 OOS | Disconnect Inspection | MIS T1, 60L14 | 2022-07-05 08:00 | 2022-07-05 15:14 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-05 15:16
8-00733519 | Completed | NEL T3, T5, 2B3, 2B4 OOS | NEL T3 Hot Spot Repair and Disconnects INSP | NEL 2B3, NEL T3, NEL T5, NEL 2B4 | 2022-07-05 08:00 | 2022-07-08 15:27 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-07-08 15:27
8-00732956 | Completed | 2L50, MUR 2B9 OOS | Disconnects Inspection at MUR | CSQ 2CB1, 2L50, MUR 2B9 | 2022-07-05 08:00 | 2022-07-08 11:17 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-07-08 11:17
8-00730275 | Completed | 2L6 Out from ARN, ARN 2B11 OOS | ARN lighting upgrade projectrrr | ARN T10, 2L6, ARN 2B11 | 2022-07-06 07:00 | 2022-07-06 16:16 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-07-06 16:16
8-00738733 | Completed | MDN 12RX31 OOS | SF6 Sampling | MDN 12RX31 | 2022-07-06 08:00 | 2022-07-06 11:36 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-06 11:36
8-00742540 | Completed | MDN 5CB1 OOS | Repair MDN 5GD1CB1 (Forced OOS) | MDN 5CB1 | 2022-07-07 08:00 | 2022-10-13 15:22 | NR | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2022-10-13 15:23
8-00713899 | Completed | ING 2CB12 OOS | CPC BFPN PM | ING 2CB12 | 2022-07-07 08:00 | 2022-07-08 07:06 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-08 07:06
8-00741818 | Completed | ACK 5RX8 OOS | ACK 5CB48 Add SF6 | ACK 5RX8, ACK 5CB48 | 2022-07-07 10:00 | 2022-07-07 14:50 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-07-07 14:54
8-00740368 | Completed | ARN HF2, 2B16 OOS | CPC NERC PM (Extension of current outage) | ARN 2B16 | 2022-07-08 16:00 | 2022-07-22 14:49 | 5 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-22 14:56
8-00624217 | Completed | 2L299, KCL 2MB4 OOS | KCL Unit 1 Black start testing | 2L299, KCL 2CB11, KCL 2CB14, KCL 2CB15, KCL 2CB16, KCL 2MB4, KCL T7, SEL 2CB12, SEL 2CB13 | 2022-07-10 08:00 | 2022-07-10 13:36 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-10 13:36
8-00699194 | Completed | 5L2, GMS 5B4, 5RX2 OOS | Spacer Replacements & GMS Equipment Maintenance | 5L2, GMS 5RX2, GMS 5B4 | 2022-07-10 14:00 | 2022-07-22 19:06 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-07-22 19:11
8-00742602 | Completed | 5L71 and 5L72 OOS | MCA Plant Islanded for 600V Project | 5L71, 5L72, MCA LS1, MCA LS2, MCA LS3 | 2022-07-10 22:00 | 2022-07-11 01:11 | 1 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2022-07-11 15:49
8-00740481 | Cancelled | 2L103 OOS | RTA work | 2L103 | 2022-07-11 06:00 | 2022-07-13 18:00 | 2 | Return Evenings | [6 empty] | N | N | Y | Y | 2022-07-07 10:50
8-00702477 | Completed | KDS T1 oos | KDS T1 NON-ELEC PN PM | KDS T1, KDS T3 | 2022-07-11 07:00 | 2022-07-11 19:46 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-07-12 01:49
8-00730887 | Completed | 2L20, CSQ 2B7 OOS | Detailed Inspection | MAN 2CB2, CSQ 2B7, 2L20 | 2022-07-11 08:00 | 2022-07-14 15:03 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-07-14 15:03
8-00714013 | Cancelled | ING 2CB22, 2RX2 OOS | BFPN PM | ING 2CB22 | 2022-07-11 08:00 | 2022-07-13 16:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-07-07 13:40
8-00699200 | Cancelled | 5L2, GMS 5B4 oos | GMS 5D22 Repair | 5L2, GMS 5D22, GMS 5D2CB11, GMS 5D2CB5, GMS 5B4 | 2022-07-11 08:00 | 2022-07-22 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-06 10:51
8-00699203 | Completed | KDY 5CX2 oos | CX PM | KDY 5CX2 | 2022-07-11 08:00 | 2022-07-21 22:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-21 22:01
8-00687422 | Completed | SEL 5CB1 and 5CB2 OOS | Inspection and Breaker Inspection/Doble | SEL 5CB1, SEL 5CB2, SEL 5B1 | 2022-07-11 08:00 | 2022-07-14 16:28 | 2 | Continuous | [5 empty] | 700 | N | N | Y | Y | 2022-07-14 16:28
8-00655958 | Completed | 2L103 OOS | Test Operate MIN 2D1BC1 | 2L103, MIN 2B10, MIN 2CB2 | 2022-07-12 08:00 | 2022-07-12 18:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-22 15:17
8-00733037 | Completed | 2L40 Out from BND, NEL 2B6 OOS | DS Inspection | 2L40, NEL 2CB4, NEL T3, NEL T4, NEL 2B6 | 2022-07-12 08:00 | 2022-07-14 18:35 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-07-14 18:35
8-00720618 | Completed | ARN 2CB16 OOS | Routine CPC BFPN PM | ARN 2CB16 | 2022-07-12 08:00 | 2022-07-12 15:41 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-12 17:43
8-00707911 | Completed | 1L377, TAY 1B31 oos | TAY DS, CVT Insp | 1L377, TAY 1B31 | 2022-07-12 08:00 | 2022-07-14 08:24 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-14 08:32
8-00739930 | Completed | ING T2, 2B6, T7 OOS | Insp/Mtce on ING T2 & 2B6 | ING T2, ING T7, ING 2B6, ING 2CB7, ING 2CB6 | 2022-07-12 08:00 | 2022-07-13 16:04 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-13 16:04
8-00742882 | Cancelled | 2L103, MIN 2B1, 2B10 oos | Test operate DS control and maintenance work at MIN | 2L103, MIN 2B1, MIN 2B10, MIN 2CB2 | 2022-07-13 06:00 | 2022-07-13 18:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-13 06:10
8-00708867 | Completed | ARN 2CB8 OOS | CPC NERC PM | ARN 2CB8 | 2022-07-13 08:00 | 2022-07-13 15:22 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-13 15:23
8-00700356 | Completed | COK 2CB4 OOS | NERC PM, Breaker Testing | COK 2CB4 | 2022-07-13 08:00 | 2022-07-13 14:53 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-07-13 14:53
8-00724638 | Completed | KI2 2CB12 OOS | Routine CPC CB CN PM | KI2 2CB12 | 2022-07-14 08:00 | 2022-07-14 12:15 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-14 12:16
8-00705384 | Completed | 1L377, DAW 1B6 oos | DAW DS and CVT Insp | 1L377, DAW 1B6 | 2022-07-14 08:00 | 2022-07-15 18:19 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-15 18:20
8-00706330 | Cancelled | 2L99 OOS | MIN 2D1CB4 Motor Op Replacement | 2L99, MIN 2D1CB4 | 2022-07-14 08:00 | 2022-07-15 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-04 12:01
8-00708874 | Completed | ARN 2CB10 OOS | CPC NERC PM | ARN 2CB10, ARN 2B8 | 2022-07-14 08:00 | 2022-07-14 14:25 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-14 14:25
8-00684754 | Completed | 2L99 OOS | Test Operate MIN 2D25 | 2L99, SKA 2B2, MIN 2B4, MIN 2B1, MIN 2B2, MIN 2B3 | 2022-07-14 08:00 | 2022-07-15 15:07 | 4 | Return Evenings | [6 empty] | Y | N | Y | Y | 2022-07-15 15:12
8-00655955 | Cancelled | 2L99 OOS | Test Operate MIN 2D25 | 2L99 | 2022-07-14 08:00 | 2022-07-15 16:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-07-04 11:57
8-00669192 | Cancelled | CBN 2CB5 OOS | CBN 2CB5 Pressure Vessel Maintenance | CBN 2CB5 | 2022-07-15 08:00 | 2022-07-15 16:00 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-14 10:06
8-00732520 | Completed | NEL 2B5, T1, T4 OOS | NEL 2D1 INSP | NEL 2B5, NEL 2D1, NEL T1, NEL T3, NEL T4 | 2022-07-15 08:00 | 2022-07-15 08:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-14 18:35
8-00731176 | Cancelled | 2L56 OOS | 2L56 Inspection & Maintenance | 2L56 | 2022-07-18 07:00 | 2022-07-19 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-15 13:02
8-00731175 | Completed | 2L32 OOS | Replace Blocks | CSQ 2CB1, 2L32 | 2022-07-18 08:00 | 2022-07-22 19:13 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-22 19:17
8-00733123 | Completed | NEL T2, 2B1 OOS | DS & CB Inspection | NEL T2, NEL 2B1 | 2022-07-18 08:00 | 2022-07-22 16:21 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-22 16:21
8-00736507 | Completed | 2L76, MLE T1 OOS | MLE Stn Upgrade Stage 9A | 60L8, 60L7, UHT 3RX1, 60L100, MLE 2B1, MLE T1, 2L76, MLE 2B5, MLE 2B6, MLE 2B4 | 2022-07-18 08:00 | 2022-07-26 10:12 | 6 | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-29 09:18
8-00702482 | Completed | WLM T3 oos | zWLM T3 and VT Insp | WLM T3 | 2022-07-18 08:00 | 2022-07-29 13:31 | 6 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-29 13:31
8-00648143 | Cancelled | MDN T3, 12RX31 and 12RX32 OOS | PCB Bushing Replacement project | MDN 12RX31, MDN 12RX32, MDN T3 | 2022-07-18 08:00 | 2022-08-19 16:00 | 96 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-07-12 13:35
8-00699204 | Cancelled | MLS 5CX1 oos | CX PM | MLS 5CX1 | 2022-07-18 08:00 | 2022-07-22 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-07 13:13
8-00743005 | Cancelled | MDN 5CB1 Forced OOS | MDN 5GD1CB1 SF6 Leak Repair | MDN 5CB1 | 2022-07-18 08:00 | 2022-08-30 08:00 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-07-20 18:00
8-00742844 | Completed | 5L72 OOS | Replace emergent broken insulators and replace failed marker balls. | 5L72 | 2022-07-18 08:00 | 2022-07-22 16:11 | 6 | Continuous | [6 empty] | Y | N | Y | Y | 2022-07-22 16:12
8-00745291 | Cancelled | 2L56 OOS | Cross-arm replacement | 2L56 | 2022-07-18 08:00 | 2022-07-19 18:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-15 13:01
8-00745965 | Completed | 5L81 OOS | AMC 5CX1 PN upgrade | 5L81, AMC 5CX1, MDN 5CB8 | 2022-07-19 07:00 | 2022-07-19 15:41 | 7 | Continuous | 1950 | 2350 |  |  |  |  | N | N | Y | Y | 2022-07-29 15:29
8-00744590 | Completed | ARN 2B11, T10 OOS | 2B11 Bus Work | ARN T10, ARN 2B11 | 2022-07-19 08:00 | 2022-07-19 16:23 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-19 16:23
8-00742576 | Cancelled | ING 12CB5, 12RX5 OOS | CPC NERC PN PM | ING 12RX5 | 2022-07-19 08:00 | 2022-07-19 12:00 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-21 18:00
8-00703301 | Completed | 2L102 oos | SKA DS Insp | SKA 2B7, 2L102, 2L379, 2L374 | 2022-07-19 08:00 | 2022-07-19 18:25 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-20 03:55
8-00703304 | Completed | 2L102 oos | BQN 2NRX231CT1/2/3 Insp | 2L379, 2L374 | 2022-07-19 08:00 | 2022-07-20 03:54 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-20 03:55
8-00741652 | Completed | ARN 2CB14 | CPC NERC BFPN PM | ARN 2CB14 | 2022-07-19 08:00 | 2022-07-20 13:10 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-20 13:11
8-00738807 | Completed | ING 2CB20 OOS | Routine CPC CB CN PM | ING 2CB20 | 2022-07-19 08:00 | 2022-07-19 13:13 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-19 13:13
8-00728354 | Completed | HPN 2CB7 OOS | HPN 2CB7 INSP | HPN 2CB7, HPN T5 | 2022-07-19 08:00 | 2022-07-20 11:19 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-20 11:19
8-00745821 | Completed | 5L81 OOS | AMC 5CX1 PN upgrade | 5L81, AMC 5CX1, MDN 5CB8 | 2022-07-19 16:00 | 2022-07-20 15:21 | 7 | Continuous | 1950 | 2350 |  |  |  |  | N | N | Y | Y | 2022-07-29 15:29
8-00736426 | Cancelled | BSY G1, G3, G4 OOS | Flow meter replacement, requiring all units OOS at the same time | BSY G1, BSY G3, BSY G4 | 2022-07-20 07:00 | 2022-07-21 07:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-23 18:00
8-00703311 | Completed | BQN 2CX1 oos | BQN 2CX1 PM | BQN 2CX1 | 2022-07-20 08:00 | 2022-07-22 11:59 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-15 17:09
8-00741760 | Completed | VIT SC3 OOS | VIT SC3/SC4 protection swap over. | VIT SC3 | 2022-07-20 08:00 | 2022-07-20 20:33 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-07-21 11:27
8-00667626 | Completed | AMC 5CX1 OOS | AMC 5CX1 minor inspection and 5BPCB1 maintenance | 5L81, AMC 5CX1 | 2022-07-20 16:00 | 2022-07-29 15:15 | 24 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-29 15:29
8-00633552 | Completed | 5L81 OOS | LOA for work within AMC station | 5L81, MAN 2CB2, AMC 5CX1, 2L27, MDN 5CB8, 2L44 | 2022-07-20 16:00 | 2022-07-29 15:26 | 7 | Continuous | 1950 | 2350 |  |  |  |  | Y | N | Y | Y | 2022-08-18 10:56
8-00700033 | Proposed | 5L2, GMS 5B12 OOS | New RTU Status Testing | 5L2, GMS 5CB11, GMS 5D22, GMS 5D26, GMS 5B4 | 2022-07-21 08:00 | 2022-07-22 16:00 | 2 | Return Evenings | [6 empty] | N | N | Y | Y | 2022-07-18 09:09
8-00741663 | Approved | ARN 2CB15 OOS | Trip testing | ARN 2CB15 | 2022-07-21 08:00 | 2022-07-22 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-20 14:29
8-00742575 | Approved | ING 12RX4 OOS | CPC NERC PN PM | ING 12RX4 | 2022-07-21 08:00 | 2022-07-21 16:00 | 1 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-07-20 14:30
8-00736519 | Approved | 5L12 oos | Energizing KLY 5CB13 | 5L12, KLY 5B3, KLY 5CB13 | 2022-07-21 15:00 | 2022-07-21 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-20 14:33
8-00709961 | Cancelled | 2L40, BND T1, BSY 2CB9/10, NEL 2CB1/6 OOS | BND T1 Test Energization | BSY 2CB10, BSY 2CB9, BND T1, 2L40, NEL 2CB1, NEL 2CB4, NEL 2CB6, NEL T3, NEL T4 | 2022-07-21 16:00 | 2022-07-21 17:00 | 1 | Continuous | [6 empty] | N | Y | Y | Y | 2022-07-18 13:24
8-00532038 | Completed | WSN T4, 12RX2 OOS | Bushing Replacement | WSN 12RX2, WSN T4 | 2022-07-22 08:00 | 2022-08-05 12:16 | 168 | Continuous | [6 empty] | N | Y | Y | Y | 2022-11-07 15:14
8-00741734 | Denied | 2L45 OOS | To support distribution duct bank work | 2L45 | 2022-07-26 08:00 | 2022-07-31 16:00 | 1 | Continuous | [6 empty] | N | Y | Y | Y | 2022-07-22 14:46
8-00749199 | Completed | RYC 5CX1 Forced OOS | Auto Isolated | RYC 5CX1 | 2022-07-26 16:21 | 2022-11-14 14:42 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-11-14 14:42
8-00707928 | Proposed | GMS 5CB6 oos | GMS CB Status Test | GMS 5CB6 | 2022-07-27 08:00 | 2022-07-27 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-18 09:10
8-00687335 | Completed | NLY T2, NLY 2CB4, and 2CB6 OOS | NLY CB TESTINg | 2L112, NLY 2CB4, NLY T1, NLY 2CB6, NLY T2 | 2022-07-27 08:00 | 2022-07-27 18:53 | 2 | Continuous | 2850 | 2850 | 2650 | 2650 |  |  | N | N | Y | Y | 2022-07-27 19:02
8-00712770 | Completed | SAY 2CB5 | SAY 2CB5 NERC COND. | SAY 2CB5 | 2022-07-27 12:00 | 2022-07-27 17:39 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-27 17:39
8-00749747 | Completed | TKW 5RX1 forced out | Forced outage | TKW 5RX1 | 2022-07-27 16:53 | 2022-07-28 14:04 | NR | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-07-28 14:04
8-00707929 | Proposed | GMS 5CB4 oos | GMS CB Status Test | GMS 5CB4 | 2022-07-28 08:00 | 2022-07-28 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-18 09:11
8-00707930 | Proposed | GMS 5CB7 oos | GMS CB Status Test | GMS 5CB7 | 2022-07-29 08:00 | 2022-07-29 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-18 09:12
8-00750323 | Completed | AMC 5CX1 OOS | 5CVT1 Issue | AMC 5CX1 | 2022-07-29 15:33 | 2022-08-04 15:28 | NR | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-16 11:18
8-00699490 | Recalled | 2L14 OOS | change out end of life structures inside the Capilano Watershed | 2L14 | 2022-08-01 08:00 | 2022-08-15 18:40 | 10 | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-15 18:42
8-00700041 | Completed | 5L2, GMS 5B12, T12 oos | GMS 5B12 insulator repl, 5D2CB6 repair and DC cable testing | 5L2, GMS 1B5, GMS 5B12, GMS T12, GMS 5B4 | 2022-08-02 08:00 | 2022-08-05 14:52 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-07 10:45
8-00669187 | Completed | CBN 2CB9 OOS | Breaker Maintenance | CBN 2CB9, UHT 3RX1 | 2022-08-02 08:00 | 2022-08-02 15:41 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-08-02 15:41
8-00701434 | Cancelled | GMS 5B12, T12 oos | GMS DS Status Test | GMS 1D12, GMS 5B12, GMS 5D14, GMS T12, GMS 5D12 | 2022-08-02 08:00 | 2022-08-06 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-26 16:11
8-00702925 | Cancelled | 2L102 oos | Damper, Marker balls and winch work on 2L102 | 2L102 | 2022-08-02 08:00 | 2022-08-02 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-03-28 12:52
8-00705502 | Cancelled | CBN 5CB5 OOS | Inpsection and Doble | CBN 5CB8 | 2022-08-02 08:00 | 2022-08-10 16:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-16 11:15
8-00723693 | Completed | CBN 5CB8 OOS | NERC CPC BFPN PM | CBN 5CB8 | 2022-08-02 08:00 | 2022-08-03 13:32 | 2 | Return Evenings | [6 empty] | N | N | Y | Y | 2022-08-03 15:42
8-00749443 | Completed | ING 2CX32, 2RX32 OOS | Investigate ING 2CX32 unbalance | ING 2CX32, ING 2RX32 | 2022-08-02 08:00 | 2022-08-02 17:14 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-02 17:15
8-00744447 | Completed | HPN 2CB6 OOS | Mtce/Insp & Leak Repair | HPN 2CB6 | 2022-08-02 08:00 | 2022-08-12 15:57 | 6 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-12 15:58
8-00746567 | Completed | 2L56 OOS | Emergency Cross-arms Replacement | MPT 2CB3, CAM T3, CAM T4, 2L56, MPT T2 | 2022-08-02 08:00 | 2022-08-05 14:40 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-05 14:40
8-00749595 | Completed | ARN HF2 OOS | Replace damaged cable | ARN 2B16 | 2022-08-03 08:00 | 2022-08-09 13:34 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-09 13:34
8-00749923 | Completed | ING 2CX31 OOS | Investigate ING 2CX31 unbalance | ING 2CX31, ING 2RX31 | 2022-08-03 08:00 | 2022-08-03 17:03 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-03 17:04
8-00730967 | Completed | 2L40, BND T1 OOS | Proximity clearance & PCB lighting replacement | BND T1, 2L40, NEL 2CB4, NEL T3, NEL T4 | 2022-08-03 08:00 | 2022-08-03 15:40 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-08-03 15:40
8-00707932 | Cancelled | GMS 5CB10 oos | GMS CB Status Test | GMS 5CB10 | 2022-08-03 08:00 | 2022-08-03 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-28 08:25
8-00707933 | Cancelled | GMS 5CB1 oos | GMS CB Status Test | GMS 5CB1 | 2022-08-04 08:00 | 2022-08-04 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-28 08:27
8-00701454 | Proposed | GMS T12, 1B5, 1B6 oos | GMS DS Status Test | GMS 1B5, GMS T12, GMS 1B6 | 2022-08-04 08:00 | 2022-08-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-02 11:21
8-00714051 | Completed | ING 2CB8 OOS | Routine CPC BFPN PM | ING 2CB8 | 2022-08-04 08:00 | 2022-08-04 16:23 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-04 16:23
8-00749855 | Approved | 5L2, GMS 5B12, T12 oos | Insulator Repl on 5B12 | 5L2, GMS 5B12, GMS 5CB1, GMS 5CB10, GMS 5CB11, GMS T12, GMS 5B4 | 2022-08-04 15:00 | 2022-08-06 16:00 | 5 | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-04 08:54
8-00752156 | Completed | AMC 5CX1 Forced OOS | Ongoing OSU Issue | AMC 5CX1 | 2022-08-04 23:07 | 2022-08-18 15:27 | NR | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-18 15:27
8-00738293 | Completed | MCA LS2 OOS | MCA T4 no load phase testing | MCA T4, MCA LS2 | 2022-08-05 06:00 | 2022-08-05 21:35 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-16 08:03
8-00714049 | Approved | ING 2CB7 OOS | Routine CPC BFPN PM | ING 2CB7 | 2022-08-05 08:00 | 2022-08-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-04 09:33
8-00702243 | Completed | 1L390 oos | Structure Repl | 1L390 | 2022-08-07 05:00 | 2022-08-07 10:27 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-08-07 10:49
8-00700042 | Completed | GMS 5B11, T11 , T13, 1B3, LR1 oos | GMS DS Mtce and Cable testing | GMS 1B3, GMS 5B11, GMS T11, GMS T13 | 2022-08-07 08:00 | 2022-08-19 18:54 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-20 13:50
8-00747438 | Cancelled | 5L41, KLY 5B4 OOS | KLY 5CB14 repairs | 5L41, KLY 5CB14, KLY 5B4 | 2022-08-07 08:00 | 2022-08-09 16:00 | NR | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2022-08-05 14:07
8-00750940 | Completed | 2L45 OOS | Proximity for distribution work | 2L45 | 2022-08-08 08:00 | 2022-08-11 10:46 | 1 | Continuous | [6 empty] | N | Y | Y | Y | 2022-08-11 10:46
8-00699208 | Completed | MLS 5CX3 oos | MLS 5CX3 CX & PN PM | MLS 5CX3 | 2022-08-08 08:00 | 2022-08-10 14:05 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-10 14:05
8-00686875 | Cancelled | 5L92 OOS | Replace Defective Insulators | 5L92 | 2022-08-08 08:00 | 2022-08-12 16:00 | 4 | Continuous |  |  |  |  | 110 | 300 | N | N | Y | Y | 2022-07-04 15:07
8-00662453 | Completed | 2L51 Out from COK to BND | Detailed & Oil Sample | BSY 2CB8, BND T2, HPN T5, 2L51, 60L18 | 2022-08-08 08:00 | 2022-08-12 16:40 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-08-12 16:40
8-00701436 | Cancelled | GMS T11, 1B3 oos | GMS DS Status Test | GMS 1B3, GMS 5B11, GMS T11, GMS T13 | 2022-08-08 08:00 | 2022-08-09 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-01 11:06
8-00714056 | Completed | ING 2CB5 OOS | Routine CPC BFPN PM | ING 2CB5 | 2022-08-08 08:00 | 2022-08-09 14:42 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-09 14:42
8-00723683 | Completed | CBN 5CB7 OOS | NERC CPC BFPN PM | CBN 5CB7 | 2022-08-08 08:00 | 2022-08-09 14:40 | 2 | Return Evenings | [6 empty] | N | N | Y | Y | 2022-08-09 14:41
8-00688317 | Completed | GUI 5CX1 OOS | Inspection | GUI 5CX1 | 2022-08-09 08:00 | 2022-08-12 13:29 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-28 03:30
8-00699188 | Completed | WSN 5RX5 oos | NON-EL PN PM | WSN 5RX5 | 2022-08-09 08:00 | 2022-08-22 15:09 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-22 15:09
8-00731340 | Completed | 2L76 OOS | Connect new MLE T3 | 60L8, 60L7, 60L100, MLE 2B1, MLE T1, 2L76, MLE T3, MLE 2B4 | 2022-08-10 07:00 | 2022-08-10 20:50 | 4 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-08-24 08:13
8-00714070 | Completed | ING 2CB6 OOS | Routine CPC BFPN PM | ING 2CB6 | 2022-08-10 08:00 | 2022-08-11 12:21 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-11 12:21
8-00749934 | Cancelled | 5L71 OOS | MCA 5RX4 B PHASE DOBLE TESTING | 5L71, MCA 5B10, MCA 5RX4 | 2022-08-10 08:00 | 2022-08-11 16:00 | 3 | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-08 15:42
8-00705498 | Cancelled | CBN 5CB7 OOS | Inpsection and Doble | CBN 5CB7 | 2022-08-11 08:00 | 2022-08-19 16:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-06 13:32
8-00669226 | Completed | CAM T3 OOS | PCB Bushing Replacement | CAM T3 | 2022-08-12 08:00 | 2022-09-16 15:42 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-16 15:43
8-00701428 | Proposed | 1L364, GMS 1B4 oos | GMS DS and CB Status Test | 1L364, GMS 1CB4, GMS 1CB5, GMS 1D23, PPS 1D1, GMS 1B4 | 2022-08-14 08:00 | 2022-08-15 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-09 16:46
8-00700049 | Cancelled | GMS 1B6 oos | GMS DS Insp | GMS 1B6 | 2022-08-15 08:00 | 2022-08-15 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-16 09:49
8-00702480 | Completed | WLM T1 oos | WLM T1, VT Insp | WLM T1 | 2022-08-15 08:00 | 2022-08-18 14:34 | 6 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-18 14:34
8-00707913 | Cancelled | 2L315, TLR 2B7 oos | TLR DS, CVT Insp | TLR 2D1CB6, TLR 2D27, TLR 2D2CB7, TLR 2B7, 2L315 | 2022-08-15 08:00 | 2022-08-15 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-21 14:33
8-00713888 | Cancelled | ING 2CB18 OOS | CPC CB CN PM | ING 2CB18 | 2022-08-15 08:00 | 2022-08-16 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-11 09:10
8-00729071 | Completed | 60L75 OOS | SHL DS Replacement | SHL 60CB3, SHL 60CB4, CVN 60CB1, CVN 60CB4, 60L75, SHL 60CB1 | 2022-08-15 08:00 | 2022-08-29 11:15 | 8 | Continuous | [6 empty] | N | Y | Y | Y | 2022-09-14 03:30
8-00720758 | Completed | CBN 2CB10 OOS | MLE expansion - CBN 2L79 PY PN replacement | CBN 2CB10 | 2022-08-15 08:00 | 2022-08-18 10:28 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-18 10:28
8-00664634 | Completed | COK T1 OOS | Tx Non-electrical PN Testing | COK T1 | 2022-08-15 08:00 | 2022-08-17 15:41 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-17 15:42
8-00693161 | Completed | 60L75 OOS | CVN DS Replacement | SHL 60CB3, SHL 60CB4, CVN 60CB1, CVN 60CB4, 60L75, SHL 60CB1 | 2022-08-15 08:00 | 2022-08-29 10:27 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-09-14 03:30
8-00742205 | Completed | SPG 2B4, T13 OOS | SPG 2CB3 testing & clutch kit installation | SPG 2CB3, SPG T13, SPG 2B4 | 2022-08-15 08:00 | 2022-08-19 14:43 | 5 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-19 14:43
8-00684755 | Completed | 5L62 Outage | Tower relocation for the TY-9168 CGL TLR project | 5L62 | 2022-08-16 08:00 | 2022-08-19 20:35 | 24 | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-19 20:52
8-00684756 | Completed | 5L62 Outage | GLN 5RX5 INSP Non-Elec NERC PM | 5L62, GLN 5RX5N, GLN 5RX5 | 2022-08-16 08:00 | 2022-08-17 16:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-22 15:15
8-00700806 | Completed | CBN 5B1, 5CB1 OOS | NERC CPC BFPN PM | CBN 5CB1, CBN 5B1 | 2022-08-16 08:00 | 2022-08-17 13:20 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-17 13:20
8-00658953 | Completed | 60L47 OOS | VT inspection and doble test | ALZ 60CB1, ALZ 60CB2, 60L47 | 2022-08-18 08:00 | 2022-08-19 15:11 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-19 15:12
8-00707920 | Proposed | 1L361, GMS 1B1, 1B7, 1B8 oos | GMS DS Status Test | 1L361, GMS 1D21, GMS 1B1, GMS 1B7, GMS 1B8 | 2022-08-19 08:00 | 2022-08-19 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-09 16:48
8-00664972 | Completed | KCL 2MB1 and 2MB3 OOS | KCL 2CT31 to isolate | KCL 2MB1, KCL 2MB3 | 2022-08-22 07:00 | 2022-08-22 13:30 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-09-07 17:04
8-00700043 | Proposed | 2L308 oos | Spacer Repl | GMS 2D13, GMS 2D1CB1, GMS T13, 2L308 | 2022-08-22 08:00 | 2022-09-02 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-05 13:49
8-00686879 | Denied | 2L293 OOS | Replace structures and Timbers | 2L293 | 2022-08-22 08:00 | 2022-09-01 16:00 | 10 | Continuous |  |  |  |  | 560 | 600 | Y | N | Y | Y | 2022-08-18 19:56
8-00687931 | Approved | KLY 5CB14 | 5CB14 BFPN | KLY 5CB14 | 2022-08-22 08:00 | 2022-08-24 16:00 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-08-19 14:48
8-00707914 | Completed | 1L349, SLS T1, 2MB1 oos | SLS DS Insp | SLS T1, SLS 2MB1, 1L349 | 2022-08-22 08:00 | 2022-08-23 19:39 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-23 19:39
8-00700045 | Proposed | GMS T14, 2CB3 oos | GMS CT Insp | GMS 2CB3, GMS T14 | 2022-08-22 08:00 | 2022-08-22 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-02 12:49
8-00701459 | Proposed | GMS T14 oos | GMS DS and CB Status Testing | GMS 2CB3, GMS 2D14, GMS T14 | 2022-08-22 08:00 | 2022-08-23 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-17 09:06
8-00701987 | Proposed | 2L96 oos | Structure Repl | 2L96 | 2022-08-22 08:00 | 2022-08-26 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-05 13:53
8-00719992 | Completed | 2L64 OOS | Jacket Fault Repair | 2L64 | 2022-08-22 08:00 | 2022-09-01 15:38 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-01 15:38
8-00735482 | Completed | 5L41 OOS | KLY 5D34 / 5RX4 Replacement | 5L41, CHP 5CX1, KLY 5RX4, KLY 5B4 | 2022-08-22 08:00 | 2022-08-26 19:07 | 6 | Continuous | 2400 | 2800 |  |  |  |  | N | N | Y | Y | 2022-08-26 19:15
8-00754634 | Completed | 2L64, SPG 2B3 OOS | Disconnects Insp/Mtce | 2L64, SPG 2B3 | 2022-08-22 08:00 | 2022-08-26 10:58 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-26 10:58
8-00750023 | Completed | MDN 12RX31 Forced OOS | SF6 Leak Repair | MDN 12RX31 | 2022-08-22 08:00 | 2022-08-25 15:43 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-25 15:43
8-00664984 | Completed | KCL 2MB1, 2MB3 and T6 OOS | KCL 2CT31 Removal/install | KCL 2MB4, KCL T7 | 2022-08-23 07:00 | 2022-08-23 18:14 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-23 18:14
8-00664987 | Cancelled | KCL 2BM1 & 2BM3 OOS | KCL 2CT31 wiring/testing/Commissoning | KCL 2MB1, KCL 2MB3 | 2022-08-23 16:00 | 2022-09-02 16:00 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-04-27 14:41
8-00707915 | Proposed | GMS T13 oos | GMS DS Status Testing | GMS T13 | 2022-08-24 08:00 | 2022-08-25 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-02 12:52
8-00744375 | Completed | 60L7 Out from MLN to BAL | 60D3L7 Maintenance | 60L7, BAL T1 | 2022-08-24 08:00 | 2022-08-24 17:28 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-24 17:28
8-00744386 | Completed | 60L8 out from MLN 60D22 | Switch Maintenance on 60D4L8 | 60L8, BAL T2, GLT T1 | 2022-08-25 08:00 | 2022-08-26 10:38 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-26 10:38
8-00753526 | Cancelled | ING T4, 12RX4 OOS | Replace broken gas relay cables and functional tests | ING 12RX4, ING T4 | 2022-08-25 08:00 | 2022-08-26 16:00 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-24 10:31
8-00749851 | Completed | 60L75 OOS | Test and commission 60SA21 | SHL 60CB4, 60L75, SHL 60CB1 | 2022-08-29 08:00 | 2022-09-02 08:57 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-02 08:57
8-00753016 | Completed | 60L75 out from CVN | Testing CVN 60A21 | CVN 60CB1, CVN 60CB4, 60L75 | 2022-08-29 08:00 | 2022-09-02 08:55 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-02 08:55
8-00743982 | Completed | HPN 2B1, T6, T8 OOS | T6 and Disconnect INSP | HPN T6, HPN 2B1, HPN T8 | 2022-08-29 08:00 | 2022-09-01 17:29 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-01 17:30
8-00700044 | Cancelled | GMS T13, 2CB1 oos | GMS CT Insp | GMS 2CB1, GMS T13 | 2022-08-29 08:00 | 2022-08-29 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-29 09:17
8-00701460 | Proposed | GMS T13 oos | GMS DS and CB Status Testing | GMS 5B11, GMS T13 | 2022-08-29 08:00 | 2022-08-29 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-06-02 12:53
8-00710475 | Completed | ARN 2B4 Switching: OOS, ARN T11 OOS | CPC Routine NON-ELE PM, 25D112 Hot Spot Repair | ARN T11 | 2022-08-29 08:00 | 2022-09-02 09:45 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-02 09:45
8-00726091 | Completed | ING 5CB9 OOS | NERC CPC CB CN PM | ING 5CB9 | 2022-08-30 08:00 | 2022-08-31 17:26 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-31 17:27
8-00703922 | Completed | ING 2CB23, 2CX31, 2CX32 OOS | ING 2CT23 INSP and ING lighting upgrade project | ING 2CB23, ING 2CX31, ING 2CX32 | 2022-08-30 08:00 | 2022-08-30 15:38 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-30 15:39
8-00703360 | Completed | 5L61 OOS for switching | WSN 5RX1 Gas Replay Repair | WSN 5RX1 | 2022-08-30 08:00 | 2022-08-31 14:50 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-08-31 14:50
8-00701986 | Completed | 2L95 oos | Structure Repl | 2L95 | 2022-08-30 08:00 | 2022-09-01 19:47 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-01 19:47
8-00664648 | Completed | 60L4 OOS | Trip testing of LB1 60CB4 | LB1 60CB4, 60L4 | 2022-08-30 08:00 | 2022-08-30 15:02 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-08-30 15:02
8-00669208 | Completed | CBN T6, T7 OOS, 60L14, 60L12 Out from CBN | T6, T7 INSP & Doble, DS INSP | 60L14, 60L12, CBN T6, CBN 60B2, CBN 60B3, CBN 60B5, CBN 60CB6, CBN T7 | 2022-08-31 08:00 | 2022-09-14 12:22 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-30 03:30
8-00692417 | Cancelled | CBN T6 OOS | CPC non-ele testing | CBN T6 | 2022-09-01 08:00 | 2022-09-02 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-30 09:31
8-00701456 | Proposed | 2L308 oos | GMS DS Status Test | 2L308 | 2022-09-01 08:00 | 2022-09-02 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-12 13:41
8-00707916 | Cancelled | 2L330 SLS 2B12 oos | SLS DS Insp and PN work | 2L330, SLS 2B12 | 2022-09-05 08:00 | 2022-09-05 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-07-21 14:24
8-00662458 | Completed | 2L45 OOS | Detailed cable inspections | CSN 2CB4, 2L45, 2L58, CSN 2CB5 | 2022-09-06 07:00 | 2022-09-09 17:32 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-09 17:32
8-00742426 | Completed | AMC 5CX2 OOS | 5CX2 Deficiency Work | AMC 5CX2 | 2022-09-06 07:00 | 2022-09-12 14:01 | 7 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-12 14:02
8-00755488 | Completed | 2L50 OOS | Tower Painting between BSY and MUR | 2L50 | 2022-09-06 08:00 | 2022-09-09 16:13 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-09 16:48
8-00755892 | Completed | KI2 2CB12 OOS | CPC CB CN PM | KI2 2CB12 | 2022-09-06 08:00 | 2022-09-07 13:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-09 10:09
8-00664651 | Completed | 60L6 OOS | LB1 60CB6 BFPN PM | LB1 60CB6, 60L6 | 2022-09-06 08:00 | 2022-09-06 13:36 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-09-06 13:36
8-00664038 | Completed | MDN T2 OOS | T2 EL Inspection & Doble Test, Non-ELE PN Test, CB & DS INSP | MDN 2CB11, MDN 5CB8, MDN 2B10, MDN T2, MDN 5CB5, MDN 2CB10 | 2022-09-06 08:00 | 2022-09-22 14:38 | 6 | Continuous | [6 empty] | Y | N | Y | Y | 2022-09-22 14:39
8-00534228 | Completed | DMR T1, 5MB2, 2MB2, 5B15, 5B5 OOS | DMR T1 INSP, Non EL PN , CB & Disc INSP, Doble | DMR 5CB24, DMR 5CB15, DMR T1, DMR T4 | 2022-09-06 08:00 | 2022-09-15 16:49 | 6 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-15 16:49
8-00737076 | Completed | 2L79 OOS | Relocate 2L79 to new gantry tower, Test/Energize MLE 2CB4/2B3 | 60L8, 60L7, 60L100, MLE 2B2, MLE T2, 2L79, MLE 2B3, MLE 2B4 | 2022-09-06 08:00 | 2022-09-07 08:25 | 4 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-09-23 03:30
8-00732541 | Completed | STV 2CB4 OOS | STV 2CB4 Replacement | STV 2CB4 | 2022-09-06 08:00 | 2022-10-05 13:55 | 48 | Continuous | [6 empty] | N | Y | Y | Y | 2022-10-05 13:55
8-00720764 | Completed | CBN 2CB5 OOS | CBN 2L79 PY PN Replacement | CBN 2CB5 | 2022-09-06 08:00 | 2022-09-21 12:59 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-09-21 16:50
8-00711089 | Completed | SPG 2CB1 OOS | SPG 230 KV PN Upgrade - 2CB1 Cutover & Tests | SPG 2CB1 | 2022-09-06 08:00 | 2022-09-07 20:06 | 4 | Return Evenings | [6 empty] | N | N | Y | Y | 2022-09-07 20:06
8-00707918 | Completed | 2L312, SLS 2B11 oos | SLS DS Insp and PN Settings Change | 2L312, SLS 2B11 | 2022-09-06 08:00 | 2022-09-06 17:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-09-06 17:00
8-00702455 | Completed | WSN 2B7, T4, T6 oos | WSN DS Insp | WSN T4, WSN T6, WSN 2B7 | 2022-09-06 08:00 | 2022-09-09 15:43 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-07 15:14
8-00702239 | Cancelled | 1L384 oos | Structure Repl | 1L384 | 2022-09-06 11:00 | 2022-09-09 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-22 09:49
8-00707919 | Completed | 2L312, SNK 2B12 oos | SNK DS Insp | 2L312, SNK 2B12, SNK 2MB2 | 2022-09-07 08:00 | 2022-09-07 16:43 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-09-07 16:50
8-00714031 | Completed | ING 2CB9 OOS | CPC BFPN PM | ING 2CB9 | 2022-09-07 08:00 | 2022-09-08 07:56 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-08 07:56
8-00688171 | Completed | KLY 5CB35 | 5CB35 CN | KLY 5CB35, KLY 5RX5 | 2022-09-07 08:00 | 2022-09-07 16:57 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-09-07 16:57
8-00761108 | Completed | 2L79 OOS | Relocate 2L79 to new gantry tower (continued) | 60L8, 60L7, 60L100, MLE 2B2, MLE T2, 2L79, MLE 2B3 | 2022-09-07 08:00 | 2022-09-23 10:01 | 4 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-10-09 03:30
8-00751414 | Completed | ING 5B10, T5 OOS | ING 5D5 Mtce, Stn Lighting Upgrade | ING T5, ING 5CB10, ING 5CB11, ING 5B10 | 2022-09-08 07:00 | 2022-09-08 18:51 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-09-08 18:52
8-00758553 | Denied | ING 2CB7 OOS | CPC BFPN PM | ING 2CB7 | 2022-09-08 08:00 | 2022-09-09 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-06 14:57
8-00761559 | Completed | CBN T1/T2 PYPN OOS (OAT) | CBN 2L79 PY PN replacement | CBN 2CB5 | 2022-09-08 08:00 | 2022-09-08 11:52 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-21 16:50
8-00712209 | Completed | SPG 2CB2 OOS | SPG 230 kV PN Upgrade | SPG 2CB2 | 2022-09-08 08:00 | 2022-09-09 15:27 | 4 | Return Evenings | [6 empty] | N | N | Y | Y | 2022-09-09 15:27
8-00764062 | Completed | CBN 5CB7 Forced OOS | Oil Leak on Phase B. CB operated as bus (DC pulled) | CBN 5CB7 | 2022-09-10 16:23 | 2022-11-29 14:55 | NR | Continuous | [6 empty] | N | Y | Y | Y | 2022-11-29 15:14
8-00711113 | Completed | SPG T12 OOS | SPG 230 PN Upgrade, T12 CT Modifications | SPG T12 | 2022-09-12 08:00 | 2022-09-15 14:43 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-09-15 14:44
8-00712537 | Completed | 2L79, CBN T4, T7 OOS | 2L79 PN Replacement | 60L8, 60L7, CBN T4, CBN 2B6, CBN T7, 60L100, 2L79 | 2022-09-12 08:00 | 2022-09-21 16:00 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-09-22 10:42
8-00714079 | Completed | ING 2CB4 OOS | Routine CPC BFPN PM | ING 2CB4 | 2022-09-12 08:00 | 2022-09-12 15:51 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-12 15:51
8-00707672 | Cancelled | 1L115 (LTZ-PVL-QLC-DMR) LTZ 1D21 | LTZ 1D21 | 1L115, LTZ 1D21 | 2022-09-12 08:00 | 2022-09-12 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-06 12:32
8-00709220 | Cancelled | 1L115 | PVL 1D2 | 1L115, PVL 1D2 | 2022-09-12 08:00 | 2022-09-13 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-09-06 12:31
8-00687432 | Completed | 2L286 (84L) OOS | Inspection on SEL 2D1CB8 and SEL 2D1CB9 | SEL 2MB1, 2L286 (84L) | 2022-09-12 08:00 | 2022-09-13 15:42 | 2 | Return Evenings | [6 empty] | Y | N | Y | Y | 2022-09-13 15:43
8-00686869 | Cancelled | 2L294 out from NLY to AAL | Structure Replacements | 2L294 | 2022-09-12 08:00 | 2022-09-16 16:00 | 7 | Continuous |  |  |  |  | 850 | 500 | N | N | Y | Y | 2022-09-01 13:57
8-00700023 | Completed | 2L322 oos | Spacer Repl | 2L322 | 2022-09-12 08:00 | 2022-09-19 17:45 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-20 09:59
8-00699210 | Cancelled | 5L3 oos | Spacer Repl | 5L3, PCN 5RX1 | 2022-09-12 08:00 | 2022-09-23 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-06 11:37
8-00699211 | Cancelled | 5L3 oos | PCN 5RX1 NON-EL PN PM and RX Investigation | 5L3, PCN 5D41, PCN 5RX1 | 2022-09-12 08:00 | 2022-09-14 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-09-06 11:38
8-00663944 | Completed | BND T2 OOS | PCB Bushing Replacement | BND T2 | 2022-09-12 08:00 | 2022-12-07 15:12 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-07 15:12
8-00761215 | Completed | 2L294 Out From NLY 2D23 to AAL 2D22 | LOA to NLY 2B3 / 2L294 part during testing of NLY 2PT3, Structure replacement on 2L294 between NLY and AAL | 2L294, NLY 2CB3, NLY 2CB4, NLY 2B3 | 2022-09-12 08:00 | 2022-09-20 12:36 | 10 | Continuous |  |  |  |  | 850 | 500 | N | N | Y | Y | 2022-09-20 15:47
8-00753805 | Completed | WHY T2 OOS, 2L22 Switching OOS | CPC NON-ELE PM | WHY T2 | 2022-09-12 08:00 | 2022-09-14 12:18 | 3 | Continuous | [6 empty] | N | Y | Y | Y | 2022-09-14 12:18
8-00764393 | Completed | AMC 5CX2 OOS | To prevent MDN T3 overload during MDN T2 outage | AMC 5CX2 | 2022-09-12 16:00 | 2022-09-22 14:45 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-22 14:45
8-00763923 | Completed | 2L57 OOS | Urgent wires and insulators replacement | SYH T2, 2L57 | 2022-09-13 08:00 | 2022-09-16 18:17 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-09-18 15:28
8-00699212 | Cancelled | KDS 5CB1 oos | KDS 5CB1 PVRP | KDS 5CB1 | 2022-09-13 08:00 | 2022-09-13 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-08 15:07
8-00702928 | Cancelled | SKA T1, 12RX1 oos | SKA CB Insp and Transf PN PM | SKA 12RX1, SKA 5CB2, SKA T1 | 2022-09-13 08:00 | 2022-09-14 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-12 12:04
8-00714083 | Completed | ING 2CB11 OOS | Routine CPC BFPN PM | ING 2CB11 | 2022-09-14 08:00 | 2022-09-15 15:05 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-15 15:05
8-00701425 | Cancelled | 1L363 oos | GMS DS and CB Status Test | GMS 1CB3, GMS 1D22, GMS 1B2, 1L363 | 2022-09-14 08:00 | 2022-09-15 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-09 11:48
8-00753811 | Completed | WHY T3 OOS, 2L27 Switching OOS | CPC NON-ELE PM | WHY T3 | 2022-09-14 12:00 | 2022-09-16 15:16 | 3 | Continuous | [6 empty] | N | Y | Y | Y | 2022-09-16 15:16
8-00764728 | Completed | CBN T6, T7, 60L12, 60L14 Out from CBN | CBN 60 kV Disconnect and CB Maintenance | 60L14, 60L12, CBN T6, CBN 60B2, CBN 60B3, CBN 60B5, CBN 60B6, CBN T7 | 2022-09-14 14:00 | 2022-09-28 10:21 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-28 10:21
8-00764734 | Completed | CBN T6 OOS | T6 Doble Test, Inspection | CBN T6 | 2022-09-14 14:00 | 2022-09-27 16:33 | 48 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-13 03:30
8-00764737 | Completed | CBN T7 OOS | T7 Doble Test, Inspection | CBN T7 | 2022-09-14 14:00 | 2022-09-28 10:37 | 48 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-06 02:30
8-00702929 | Denied | SKA T2, 12RX2 oos | SKA CB PM, T2 ETM repair, 12RX2 cables repl | SKA 12RX2, SKA 5CB12, SKA 5D2, SKA T2 | 2022-09-15 08:00 | 2022-09-16 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-12 12:05
8-00711135 | Completed | SPG 2CB1 OOS | SPG 230 kV PN Upgrade | SPG 2CB1 | 2022-09-16 08:00 | 2022-09-19 16:24 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-26 16:25
8-00747720 | Completed | COK 2CB3 OOS | BFPN PN PM Test | COK 2CB3 | 2022-09-16 08:00 | 2022-09-16 15:02 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-16 15:03
8-00711662 | Completed | 1L14, GTp T13, 1CB2, KSH T2, SHA T1 OOS | Stage 4: Restore Temporary Bus Cut-2 between GTP 1B3 and 1D23. | 1L14, GTP 1CB2, GTP T13, KSH T2, SHA T1 | 2022-09-18 07:00 | 2022-09-18 13:03 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-18 13:07
8-00534232 | Completed | DMR T2, 5B4, 2MB2 OOS | DS INSP | DMR 5CB4, DMR 5CB14, DMR T2, DMR 2CB15, DMR 2CB4, DMR 2CB3, DMR T7 | 2022-09-19 08:00 | 2022-10-02 10:53 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-10-02 10:53
8-00761371 | Completed | 5L31 OOS | Cable Inspections | 5L31 | 2022-09-19 08:00 | 2022-09-21 12:08 | 4 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-09-21 12:08
8-00761228 | Cancelled | MCA 5CB6 OOS | Modify control wiring, followed by open/close test. | MCA 5CB6 | 2022-09-19 13:00 | 2022-09-19 18:00 | 1 | Continuous | [6 empty] | Y | N | Y | Y | 2022-09-22 15:46
8-00705373 | Completed | 2L322, TLR 2B5 oos | TLR DS Insp | 2L322, TLR 2B5 | 2022-09-19 16:00 | 2022-09-21 19:10 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-21 20:42
8-00669228 | Completed | CAM T4 OOS | PCB bushing Replacement | CAM T4 | 2022-09-20 08:00 | 2022-11-17 09:56 | 120 | Continuous | [6 empty] | N | Y | Y | Y | 2022-12-03 03:30
8-00690514 | Cancelled | 5L71 OOS | Spacer Damper Replacements | 5L71 | 2022-09-20 08:00 | 2022-09-30 16:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-09-13 12:52
8-00762984 | Approved | CAM 2CB6, T3, T4 OOS | CPC 2CB6 BFPN firmware upgrade | CAM 2CB6, CAM T3, CAM T4, CAM 2B5 | 2022-09-20 08:00 | 2022-09-20 16:00 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-20 13:14
8-00764838 | Completed | 5L71 OOS | Spacer Damper Replacements | 5L71 | 2022-09-20 08:00 | 2022-09-29 17:03 | 3 | Continuous | [6 empty] | Y | N | Y | Y | 2022-09-29 17:04
8-00749006 | Completed | HPN 2CB5 OOS | NERC PM | HPN 2CB5 | 2022-09-20 08:00 | 2022-09-20 15:33 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-20 15:39
8-00761231 | Cancelled | MCA 5CB9 OOS | Modify control wiring, followed by open/close test. | MCA 5CB9 | 2022-09-20 13:00 | 2022-09-20 18:00 | 1 | Continuous | [6 empty] | Y | N | Y | Y | 2022-09-22 15:46
8-00767137 | Completed | BSY G4 Forced OOS | Fault Investigation | BSY G4 | 2022-09-20 18:03 | 2022-10-06 09:30 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-10-06 13:25
8-00759371 | Cancelled | 2L112 OOS | BPA Outage | 2L112 | 2022-09-21 06:00 | 2022-09-21 11:30 | NR | Continuous | 2000 | 2000 | 2500 | 2500 | 560 | 600 | N | N | Y | Y | 2022-09-12 12:59
8-00761236 | Cancelled | MCA 5CB10 OOS | Modify control wiring, followed by open/close test. | MCA 5CB10 | 2022-09-21 07:00 | 2022-09-21 13:00 | 1 | Continuous | [6 empty] | Y | N | Y | Y | 2022-09-22 15:46
8-00762806 | Completed | ING 2CB7 | NERC CPC BFPN PM | ING 2CB7 | 2022-09-21 08:00 | 2022-09-22 12:56 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-22 12:56
8-00765218 | Completed | 2L18, HPL OOS | HPL 2CB1, 2CB2 Maintenance | 2L18 | 2022-09-21 08:00 | 2022-09-23 15:01 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-23 15:01
8-00658517 | Completed | 5L51 OOS | Tower Raise | 5L51 | 2022-09-21 08:00 | 2022-09-22 15:06 | 3 | Continuous |  |  | 1500 | 1900 |  |  | N | N | Y | Y | 2022-09-22 15:12
8-00650740 | Completed | MLE 2B2, T2 OOS | Install MLE 2CB3, old gantry tower removal | MLE 2B2, MLE T2 | 2022-09-21 08:00 | 2022-11-04 11:28 | 48 | Continuous | [6 empty] | N | Y | Y | Y | 2022-11-04 11:28
8-00748014 | Completed | 5L71 OOS | MCA Switchgear Roof Replacement Project Deficiencie | 5L71 | 2022-09-21 10:00 | 2022-09-29 17:03 | 2 | Continuous | 2850 | 3150 | 2500 | 2500 | 850 | 1000 | N | N | Y | Y | 2022-09-29 17:04
8-00761241 | Cancelled | MCA 5CB11 OOS | Modify control wiring, followed by open/close test. | MCA 5CB11 | 2022-09-21 13:00 | 2022-09-21 18:00 | 1 | Continuous | [6 empty] | Y | N | Y | Y | 2022-09-22 15:47
8-00753787 | Completed | 5L91 OOS | FLAR Jb Modifications | 5L91, SEL 5CB11, SEL 5CB9 | 2022-09-22 07:00 | 2022-09-22 14:58 | 2 | Continuous |  |  |  |  | 560 | 500 | N | N | Y | Y | 2022-09-22 14:58
8-00688620 | Completed | SVA 1CX1 and SVA 1B7 OOS | Inspection | SVA 1CB7, SVA 1CB8, SVA 1B7, SVA 1CX1 | 2022-09-22 08:00 | 2022-09-28 10:27 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-28 10:27
8-00727150 | Cancelled | VNT 1CX1 OOS | VNT 1CB16 CN PM (NERC) | VNT 1CB16 | 2022-09-22 09:00 | 2022-09-22 16:00 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-27 18:00
8-00733049 | Completed | MUR T2, 60B13, 12RX32 OOS | MUR T2 Non-Electrical PM | MUR T2, MUR 60B13 | 2022-09-26 08:00 | 2022-09-27 16:08 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-09-27 16:08
8-00712236 | Completed | SPG 2CB2 OOS | SPG 230 kV PN Upgrade - 2CB2 CT Mods | SPG 2CB2 | 2022-09-26 08:00 | 2022-09-26 17:17 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-26 17:17
8-00712741 | Cancelled | MSA 5L30, 5B1, T1, 5CB6, 5CB3 | MSA 5CB3 + 5CB6 NERC COND. 5D1CB6, 5D1CB3 INSP | MSA 5CB3, MSA 5CB6, MSA T1, 5L30, MSA 5B1, MSA 5D1CB3 (3), MSA 5D1CB6 (3) | 2022-09-26 08:00 | 2022-09-30 16:00 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-24 10:59
8-00702485 | Cancelled | HMH T6 oos | HMH T6 LTC Overhaul | HMH T5, HMH T6 | 2022-09-26 08:00 | 2022-09-30 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-26 09:55
8-00699220 | Completed | 5L7 oos | KDY DS & BP Insp and WSN DS Insp | KDS 5B3, 5L7, KDY 5CX3, WSN 5B6, WSN 5RX6 | 2022-09-26 08:00 | 2022-10-03 16:54 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-10-03 16:55
8-00685556 | Completed | 5L94 (1201L) OOS | CBK 5D25 Disconnect Inspections | 5L94 / 1201L, NTL 60CB12, CBK 5B5, CBK 5B6 | 2022-09-26 08:00 | 2022-09-27 19:29 | 4 | Continuous |  |  |  |  | 50 | 100 | N | Y | Y | Y | 2022-10-13 03:30
8-00672696 | Completed | 5L94/1201L OOS | AltaLink work | CBK 5CB21, CBK 5CB23, 5L94 / 1201L, NTL 60CB12 | 2022-09-26 08:00 | 2022-09-27 18:55 | 6 | Continuous |  |  |  |  | 50 | 100 | N | Y | Y | Y | 2022-09-27 18:55
8-00669544 | Completed | 2L264 (74L) OOS | VNT 2CVT24 replacement | 2L264 (74L), VNT 2B4 | 2022-09-26 08:00 | 2022-10-14 13:39 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-30 03:30
8-00764774 | Completed | 60L8 OOS | Line structures replacement | 60L8, BAL T2, PKL T2, GLT T1 | 2022-09-26 08:00 | 2022-09-29 15:35 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-09-29 15:43
8-00765477 | Completed | ING T5, 5B10 OOS | ING 5D5 Troubleshooting | ING T5, ING 5B10, ING 5D5, ING 12RX5 | 2022-09-26 08:00 | 2022-09-26 13:23 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-26 13:24
8-00766052 | Completed | ING T5, 5B10 OOS | ING 5D5 Troubleshooting | ING T5, ING 5B10, ING 5D5, ING 12RX5 | 2022-09-26 08:00 | 2022-09-26 13:23 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-26 13:24
8-00751441 | Denied | NEL 2CB3 OOS | NEL 2CB3 Inspection | NEL 2CB3 | 2022-09-26 08:00 | 2022-09-27 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-22 09:27
8-00748079 | Completed | 5L82 OOS | Spacer and Insulator replacement | 5L82 | 2022-09-26 08:00 | 2022-10-20 12:07 | 8 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2022-10-20 12:08
8-00760614 | Completed | 60L35 Out from BND | Switch Replacement | BND 60CB5, 60L35, BND 60CB10, BND 60CB4 | 2022-09-27 08:00 | 2022-09-28 06:57 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-28 06:57
8-00764687 | Completed | CK5 5MB2, 5RX1 Switching OOS | To manually open 5D1CB22 & 5D2CB22 | CK5 5CB21, CK5 5CB22, CK5 5CB23, CK5 5RX1 | 2022-09-27 13:00 | 2022-09-27 14:40 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-27 14:40
8-00754401 | Completed | CK5 5CB22 OOS | 5CB22 & 5D2CB22 Maintenance | CK5 5CB22 | 2022-09-27 13:00 | 2022-09-29 13:42 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-29 13:45
8-00767803 | Completed | 5L94 OOS | Component Replacements on Structures #45 - 459 | 5L94 / 1201L, NTL 60CB12 | 2022-09-27 16:00 | 2022-09-28 15:49 | 6 | Continuous |  |  |  |  | 50 | 100 | N | N | Y | Y | 2022-09-28 15:49
8-00767817 | Completed | 5L94 OOS | 5SARXN5 replacement | 5L94 / 1201L, NTL 60CB12, CBK 5B5, CBK 5B6 | 2022-09-27 16:00 | 2022-09-28 15:31 | 4 | Continuous |  |  |  |  | 50 | 100 | N | N | Y | Y | 2022-09-28 15:31
8-00711393 | Completed | SPG 2CB3 OOS | SPG 230 kV PN Upgrade - 2CB3 Mods & Tests | SPG 2CB3 | 2022-09-28 08:00 | 2022-09-29 15:29 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-29 15:30
8-00664014 | Completed | 2L51 OOS | BND 2CT24/2CT23 Inpsection and 2VT2 insp & Doble | BND T2, 2L51 | 2022-09-28 08:00 | 2022-10-07 15:34 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-07 15:34
8-00732547 | Completed | 2L58, STV T2 OOS | Connect new STV 2SA22 to STV 2B2 | STV T2, 2L58, STV 2B2 | 2022-09-29 08:00 | 2022-10-05 13:56 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-10-21 03:30
8-00761261 | Cancelled | KCL T7, SS2 OOS | KCL T7 PCB Bushing Replacement and 12CB7 BFPN | KCL T7 | 2022-09-29 09:00 | 2022-10-10 15:00 | 120 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-28 08:40
8-00764693 | Approved | CK5 5MB2, 5RX1, 5CB22 OOS | Test operate 5D1CB22 & 5D2CB22 | CK5 5CB21, CK5 5CB22, CK5 5CB23, CK5 5RX1, CK5 5MB2 | 2022-09-29 12:00 | 2022-09-29 16:00 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-29 05:41
8-00769715 | Completed | BRT T4 / 2B4, 2L19, BR1 T3, T30 OOS | BRT T4 - Stage 6 | 2L19, BR1 T3, BRT T4, BRT 3B5, BRT 2B4, BR1 2D30, BR1 T30 | 2022-09-29 16:00 | 2022-10-01 16:30 | 14 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-20 16:26
8-00770565 | Completed | 5L94 (1201L) OOS | Line maintenance | CBK 5CB21, CBK 5CB23, 5L94 / 1201L | 2022-09-30 07:00 | 2022-10-06 17:37 | 6 | Continuous |  |  |  |  | 50 | 100 | N | Y | Y | Y | 2022-10-22 03:30
8-00687874 | Completed | 5L71 and MCA 5B10 OOS | MCA 5B10 & NIC 5B18 de-energized for switching 5D34 close | 5L71, MCA 5B10, NIC 5B18 | 2022-09-30 08:00 | 2022-10-03 09:32 | 1 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-03 09:33
8-00687882 | Completed | 5L71 OOS | MCA 5RX4 First Energization for Soak Test and Operation. | 5L71 | 2022-09-30 16:00 | 2022-10-03 09:32 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-03 09:33
8-00699219 | Cancelled | 5L7 oos | Spacer Repl | 5L7 | 2022-09-30 16:00 | 2022-10-03 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-22 10:38
8-00554083 | Completed | 5L72 OOS | Hi-Pot testing | 5L72, MCA 5B7, MCA 5B9, MCA 5RX3, MCA LS1 | 2022-10-03 07:00 | 2022-10-11 12:00 | 8 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-11 14:41
8-00712261 | Completed | SPG 2CB4 OOS | SPG 230 kV PN Upgrade - 2CB3 Mods & Tests | SPG 2CB4 | 2022-10-03 08:00 | 2022-10-04 16:52 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-04 16:52
8-00705830 | Completed | HPN 2CB1 OOS | Inspection & Doble Test | HPN 2CB1 | 2022-10-04 08:00 | 2022-10-07 17:48 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-07 17:48
8-00687960 | Completed | 5L13 OOS | 5CB5 BFPN | KLY 5CB5, 5L13 | 2022-10-04 08:00 | 2022-10-04 16:30 | NR | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-04 16:31
8-00769843 | Completed | MUR T2, T3, 12RX32 OOS | Proximity for MUR Lighting Replacement Project | MUR T2, MUR T3, MUR 2B1, MUR 60B13 | 2022-10-04 08:00 | 2022-10-06 15:31 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-06 15:31
8-00767907 | Completed | CBN 2CB5 OOS | CBN 2L79 SY PN Replacement | CBN 2CB5 | 2022-10-04 08:00 | 2022-10-05 08:51 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-05 08:51
8-00770550 | Completed | 2L58 Out from STV | Test and work for 2SA22 and 2CB4 | STV 2CB4, STV T2, STV 2B2 | 2022-10-05 08:00 | 2022-10-07 17:12 | 6 | Continuous | [6 empty] | N | Y | Y | Y | 2022-10-07 17:12
8-00707770 | Completed | VIT SC2 | 4 KV & SLIPRING REPAIR | VIT SC2 | 2022-10-05 08:00 | 2022-10-20 15:31 | 72 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2022-10-20 15:32
8-00771959 | Completed | 5L94 OOS | CBK 5D25 inspection and maintanance | CBK 5CB21, CBK 5CB23, 5L94 / 1201L | 2022-10-06 08:00 | 2022-10-06 17:30 | 6 | Continuous |  |  |  |  | 50 | 100 | N | N | Y | Y | 2022-10-06 18:52
8-00770746 | Completed | WSN 5RX1 oos with 5L61 out for switching | Energizing WSN 5RX1 | WSN 5RX1 | 2022-10-06 10:00 | 2022-10-06 12:33 | 1 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-06 19:38
8-00770572 | Completed | STV 2CB4 OOS | STV 2CB4 Test & Commissioning | STV 2CB4 | 2022-10-07 08:00 | 2022-10-12 12:02 | 6 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-10-12 12:02
8-00767895 | Approved | 2L58 Out from STV | STV 2SA22 Eplan | STV T2, 2L58, KI2 2B5, STV 2B2 | 2022-10-07 08:00 | 2022-10-07 09:00 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-06 09:54
8-00760169 | Completed | 60L75 OOS | Test Energization for CVN and SHL CBs | SHL 60CB4, CVN 60CB1, CVN 60CB4, 60L75, SHL 60CB1 | 2022-10-07 08:00 | 2022-10-08 14:55 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-10-08 14:55
8-00711409 | Completed | SPG 2CB3 OOS | CT Mods and Trip Testing | SPG 2CB3 | 2022-10-11 08:00 | 2022-10-12 14:58 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-12 14:58
8-00729076 | Completed | 60L5 OOS | Re&Re 60D22 and 60D2CB1, Install 60SA22, Remove 60GD22 | SHL 60CB2, 60L5, SHL 60CB1 | 2022-10-11 08:00 | 2022-10-28 22:46 | 8 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-28 22:46
8-00691163 | Denied | 5L13, KLY 5B11 | 5D1CB1, 5D1CB3 Replacement | KLY 5B11, KLY 5D1, KLY 5D1CB1, KLY 5D1CB2, KLY 5D1CB21 (3), KLY 5D1CB3, KLY 5D1CB4, KLY 5D1CB5, 5L13 | 2022-10-11 08:00 | 2022-10-17 16:00 | NR | Continuous | [6 empty] | N | N | Y | Y | 2022-09-28 14:17
8-00686274 | Denied | CBK T7 OOS | CBK T7, CBs and Disconnects Inspection | CBK 12CX3, CBK 12RX7, CBK T7 | 2022-10-11 08:00 | 2022-10-21 16:00 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-10-06 16:02
8-00667627 | Cancelled | 5L82 OOS | AMC 5D22/5D32/5BP2 Insp. | 5L82, AMC 5D22 (3), AMC 5D32 (3), AMC 5BPCB2 | 2022-10-11 08:00 | 2022-10-21 16:00 | 72 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-05 10:02
8-00769849 | Completed | MUR 2B6 OOS | Lighting Upgrade (Proximity Outage) | MUR 2B6 | 2022-10-11 08:00 | 2022-10-11 18:48 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-11 18:48
8-00772411 | Completed | 5L82 OOS | Spacers and Insulators replacements | 5L82, AMC 5D22 (3), AMC 5D32 (3) | 2022-10-11 08:00 | 2022-10-20 12:07 | 8 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2022-10-20 12:08
8-00757789 | Completed | 2L293 Out from NLY | NLY 2PT2 Replacement | 2L293, NLY 2CB2, NLY 2CB3, NLY 2B2 | 2022-10-11 08:00 | 2022-10-27 11:44 | 10 | Continuous |  |  |  |  | 560 | 600 | Y | N | Y | Y | 2022-10-27 11:44
8-00742800 | Completed | 5L44 OOS | To restore MDN bus cut to MDN 5CB1 | 5L44, MDN 5CB2, MDN 5CB1, MDN 5B1 | 2022-10-11 08:00 | 2022-10-13 15:22 | 4 | Continuous | 1700 | 2100 | 800 | 1200 |  |  | Y | N | Y | Y | 2022-10-13 15:23
8-00772977 | Completed | 5L44 OOS | End of life insulators replacement | 5L44 | 2022-10-11 08:00 | 2022-10-14 15:27 | 4 | Continuous | 1700 | 2100 | 800 | 1200 |  |  | Y | N | Y | Y | 2022-10-14 15:27
8-00770605 | Approved | 2L79 OOS | To open CBN 2D23 and check indication to new SY PN | CBN T4, CBN T7, 2L79, MLE 2B3 | 2022-10-11 10:00 | 2022-10-11 11:00 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-07 09:31
8-00701989 | Completed | 2L352 OOS | Structure Repl | 2L352, 60L301 | 2022-10-11 10:00 | 2022-10-17 18:18 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-17 18:18
8-00732555 | Completed | 2L62, STV 2B4, T3 OOS | Connect new STV 2SA23 to STV 2B4 | STV T3, 2L62, STV 2B4 | 2022-10-12 08:00 | 2022-10-18 15:57 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-11-03 03:30
8-00662466 | Completed | 2L31 OOS | Detailed & Oil Sample | 2L31 | 2022-10-12 08:00 | 2022-10-14 12:28 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-10-14 12:29
8-00704273 | Completed | ING 2CX2, 2RX2 OOS | DS, RX Inspections | ING 2RX2, ING 2CX2 | 2022-10-17 08:00 | 2022-10-21 14:21 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-10-21 14:21
8-00702454 | Cancelled | SCK T2 oos | SCK T2 Insp and DOBL | SCK T2 | 2022-10-17 08:00 | 2022-10-28 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-29 09:12
8-00712273 | Completed | 2L9 and CKY 2B8 OOS | PM Inspection at CKY | CKY 2CB8, CKY 2CB9, LYN 2CB2, LYN T1, 2L9 | 2022-10-17 08:00 | 2022-10-21 16:08 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-21 16:09
8-00711418 | Completed | SPG T13 OOS, 2B4 Switching OOS | T13 CT Mods & PN Tests | SPG T13 | 2022-10-17 08:00 | 2022-10-21 16:50 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-02 18:21
8-00720075 | Completed | 2L55 OOS | Cable Inspection & to facilitate City water installation | 2L55 | 2022-10-17 08:00 | 2022-10-25 12:56 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-10-25 12:56
8-00770611 | Completed | CBN 2CB10 OOS | CBN 2L79 SY PN replacement | CBN 2CB10 | 2022-10-17 08:00 | 2022-10-18 10:52 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-18 11:01
8-00767543 | Completed | HPN T4 OOS, 2B3 Switching OOS | Cable jacket testing | HPN T4 | 2022-10-17 08:00 | 2022-10-17 16:05 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-17 16:05
8-00773513 | Approved | 2L62, STV 2B4, T3 OOS | Energization of STV 2CB4, 2SA23 | STV T3, 2L62, STV 2B4 | 2022-10-17 16:00 | 2022-10-17 16:30 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-13 13:22
8-00765967 | Completed | 5L52 OOS | ING lighting upgrade project | ING 5B5, 5L52 | 2022-10-18 07:00 | 2022-10-18 17:41 | 2 | Continuous |  |  | 1500 | 1900 |  |  | N | N | Y | Y | 2022-10-18 17:42
8-00701990 | Completed | 2L94 oos | Structure Repl | 2L94 | 2022-10-18 07:00 | 2022-10-19 21:20 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-19 21:20
8-00770760 | Completed | ING 2CB18 OOS | Routine CPC CB CN PM | ING 2CB18 | 2022-10-18 08:00 | 2022-10-18 16:49 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-18 16:49
8-00772412 | Approved | ING 2RX2 OOS | CPC NON-ELE PM | ING 2RX2 | 2022-10-18 08:00 | 2022-10-20 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-17 14:19
8-00772418 | Approved | ING 2CB22 OOS | CPC NERC BFPN PM | ING 2CB22 | 2022-10-18 08:00 | 2022-10-20 16:00 | 2 | Return Evenings | [6 empty] | N | N | Y | Y | 2022-10-17 14:23
8-00758981 | Completed | HPN 2CB3 OOS | CB Insp | HPN 2CB3 | 2022-10-18 08:00 | 2022-10-20 13:53 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-20 13:53
8-00752363 | Completed | 1L18 out from VIT 1D44 to 1D45 to SAL 1D21 | SAL 1CC1 INSP/DOBL & 1D21 INSP | 1L18, SAL T1 | 2022-10-18 08:00 | 2022-10-18 15:18 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-18 15:26
8-00775960 | Completed | 60L7 OOS | Emergency structure replacement | 60L7, PKL T1 | 2022-10-18 08:00 | 2022-10-18 16:38 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-10-18 16:38
8-00775669 | Completed | 2L154 OOS | End of Life Structure Replacements | 2L154 | 2022-10-18 16:15 | 2022-10-21 17:13 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-21 17:21
8-00775882 | Completed | 2L154 and GLD 1B1 OOS | GLD 1D1 & 1D4 Engineering Inspection | GLD 1CB1, GLD 1CB2, GLD T1, GLD T4 | 2022-10-19 08:00 | 2022-10-21 11:55 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-21 12:03
8-00427104 | Cancelled | 1L143 OOS | POSITION MO3 PORTABLE SUB FOR TM-0159 PROJECT | 1L143 | 2022-10-20 08:00 | 2022-10-20 16:00 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-01-19 08:11
8-00760874 | Cancelled | 2L129 ARN 2CB6, 2CB7 OOS | Terminal Washing | ARN 2CB6, ARN 2CB7, 2L129 | 2022-10-20 08:00 | 2022-10-30 16:00 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-17 15:23
8-00762851 | Completed | 2L129 OOS | Annual Inspections & Cleaning | ARN 2CB6, ARN 2CB7, 2L129 | 2022-10-20 08:00 | 2022-10-30 14:45 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-30 15:18
8-00772524 | Completed | AMC 5CX2 OOS | AMC 5BPCB2 Inspection/Test | AMC 5CX2 | 2022-10-20 16:00 | 2022-10-20 16:01 | 6 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-20 13:57
8-00306153 | Cancelled | BSY Synchronous Condenser (G4) OOS | Inspection and Exciter Mtce | BSY T4, BSY G4 | 2022-10-25 01:00 | 2022-10-28 23:00 | 96 | Continuous | [6 empty] | N | N | Y | Y | 2022-09-28 09:43
8-00769224 | Completed | 2L18, HPL OOS | PN Testing, DS Inspection | ING 2D2CB30, 2L18 | 2022-10-25 08:00 | 2022-10-26 15:10 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-26 15:10
8-00750938 | Completed | 2L129 OOS | ARN disconnect repair and station lighting upgrade | ARN 2CB6, ARN 2CB7, 2L129 | 2022-10-25 08:00 | 2022-10-30 14:45 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-30 15:06
8-00757842 | Completed | 5L71 OOS | Inspection of SYA 5CX1 | SYA 5CX1 | 2022-10-25 08:00 | 2022-10-27 22:31 | 6 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-27 22:31
8-00757318 | Completed | NEL 2CB3 OOS | CB Inspection | NEL 2CB3, 60L18 | 2022-10-25 08:00 | 2022-10-26 14:58 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-26 14:58
8-00754750 | Completed | 5L41 OOS | KLY 5CB14 Repair | 5L41, KLY 5B4 | 2022-10-25 08:00 | 2022-10-28 15:59 | 0 | Continuous | 2400 | 2800 |  |  |  |  | N | N | Y | Y | 2022-10-28 15:59
8-00776541 | Completed | ALZ T3 and ALZ 60B3 OOS | ALZ 60VTT3 Failure | ALZ T3, ALZ 60B3 | 2022-10-25 08:00 | 2022-10-28 15:09 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-13 03:30
8-00775367 | Completed | BR2 T8, 3L14 OOS | Initial energization of T7 with BRT 3CB2 | BR2 T8, 3L14 | 2022-10-25 08:00 | 2022-10-25 17:30 | 1 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-25 17:30
8-00765627 | Completed | SAT 2CB1 OOS | NERC Work | SAT 2CB1 | 2022-10-25 10:00 | 2022-10-25 15:54 | 0 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-25 15:54
8-00728372 | Completed | 2L9 OOS | Structure Replacements | 2L9 | 2022-10-25 16:00 | 2022-10-28 18:16 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-10-28 18:16
8-00718305 | Completed | WSN 5RX2 oos | Bushing Replacement | WSN 5RX2 | 2022-10-26 08:00 | 2022-12-15 14:37 | 120 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-12-15 14:37
8-00663788 | Completed | 2L44 OOS | Cable overview inspection | 2L44 | 2022-10-26 08:00 | 2022-10-28 16:39 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-10-28 16:42
8-00776858 | Completed | ARN 2MB2 OOS | Station lighting upgrade | ARN 2MB2 | 2022-10-26 08:00 | 2022-10-28 12:36 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-28 13:08
8-00778405 | Completed | 5L41 OOS | End of life insulators replacement | 5L41 | 2022-10-26 08:00 | 2022-10-27 16:22 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-27 16:22
8-00765635 | Cancelled | SAT 2Cb6 and 2CB7 OOS OAT | NERC PM on SAT 2CB6 & 2CB7 CN OAAT | SAT 2CB6, SAT 2CB7 | 2022-10-27 08:00 | 2022-10-27 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-29 18:00
8-00768298 | Completed | 5L4 OOS | Bushing - Oil Top Up | 5L4 | 2022-10-27 08:00 | 2022-10-27 17:20 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-27 17:20
8-00776619 | Completed | 2L154 OOS | End of Life Structure Replacements | 2L154 | 2022-10-27 14:00 | 2022-10-28 18:21 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-28 18:21
8-00774725 | Completed | 2L143, ESQ 2CB3 and T13/12HF3 OOS | Work on ESQ 2D23 INSP | 2L143, ESQ 2CB3, ESQ T13 | 2022-10-28 09:00 | 2022-10-28 18:19 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-28 18:19
8-00712318 | Completed | 2L1, PEM 2D1, PEM 2D2, PEM 2CVT1 | PM Inspection | PEM T1, 2L1, PEM T2, FCN T2 | 2022-10-30 09:00 | 2022-10-30 18:01 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-10-30 18:01
8-00662474 | Completed | 2L33 OOS | Detailed cable inspection | 2L33 | 2022-10-31 08:00 | 2022-11-04 15:38 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-11-04 15:38
8-00664614 | Completed | MDN 2B14, 2CX1, 2CX2, 2RX1 OOS | MDN 2D11 Inspection | MDN 2RX1, MDN 2CX2, MDN 2B14, MDN 2CX1, MDN 2D11 | 2022-10-31 08:00 | 2022-10-31 15:45 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-31 15:56
8-00667630 | Completed | CHP 5CX1 OOS | CHP 5CX1 EL & CPC Inspection | CHP 5CX1 | 2022-10-31 08:00 | 2022-11-04 15:17 | 48 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-04 15:17
8-00779787 | Completed | 60L75 OOS | Install concrete footing for future 60CVT3 | 60L75 | 2022-10-31 08:00 | 2022-11-11 07:50 | 10 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-11 07:55
8-00746395 | Completed | 2L56 OOS | Detailed inspection and maintenance | MPT 2CB3, CAM T3, CAM T4, 2L56, MPT T2 | 2022-10-31 08:00 | 2022-11-03 15:13 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-11-03 15:13
8-00704243 | Completed | ING 2RX1 OOS | DS, RX Inspection | ING 2B21, ING 2RX1, ING 2CX11 | 2022-11-01 08:00 | 2022-11-04 15:28 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-11-04 15:29
8-00780847 | Completed | 5L83 OOS | Emergency Leg Repairs | 5L83, RYC 5CX1 | 2022-11-02 08:00 | 2022-11-02 16:15 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-02 16:20
8-00779227 | Completed | 5L1 OOS | required for WSN 5RX2 proximity outage | 5L1, WSN 5B2, WSN 5RX2 | 2022-11-03 06:00 | 2022-11-03 16:57 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-03 16:57
8-00780558 | Completed | KLY 5CB14 OOS | NERC CN & BF PM. | KLY 5CB14 | 2022-11-03 08:00 | 2022-11-03 15:34 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-03 15:35
8-00427105 | Cancelled | 1L143 OOS | JOR- POSITION MO3 PORTABLE SUB FOR TM-0159 PROJECT | 1L143 | 2022-11-04 08:00 | 2022-11-04 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-01-19 08:12
8-00776732 | Completed | MLE 2B2, T2 OOS | Install 2CB3, 2D1CB3 | MLE 2B2, MLE T2 | 2022-11-04 08:00 | 2022-12-01 15:09 | 48 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-01 16:38
8-00775407 | Completed | GLD 1CB7 OOS | GLD 1CB7 CN | GLD 1CB7 | 2022-11-04 08:00 | 2022-11-04 13:52 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-04 13:52
8-00760379 | Cancelled | GLD 1CB7 OOS, 1L120 PYPN, SYPN, 1L157 PYPN SYPN OOS | GLD 1CB7 CN | GLD 1CB7 | 2022-11-04 08:00 | 2022-11-04 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-31 09:57
8-00747262 | Cancelled | CBN 5CB7 OOS | Repair, Inspection | CBN 5CB7 | 2022-11-04 16:00 | 2022-11-25 16:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-06 17:00
8-00744421 | Completed | MCA 5B9 OOS | MCA T2 First Energization from Grid | MCA 5B9, MCA T2, MCA LS1 | 2022-11-06 10:00 | 2022-11-06 10:29 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-06 10:29
8-00305837 | Cancelled | BSY Synchronous Condenser (G1) OOS | Inspection and Exciter Mtce | BSY G1 | 2022-11-07 01:00 | 2022-11-18 23:00 | 192 | Continuous | [6 empty] | N | N | Y | Y | 2022-08-25 10:03
8-00658523 | Cancelled | 2L4 OOS | Structure Replacement | ING T2, 2L4, CAM T2 | 2022-11-07 08:00 | 2022-11-10 16:00 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-11-07 09:31
8-00772686 | Completed | 2L51 OOS | Oil Sampling | BSY 2CB3, BSY 2CB7, BSY 2D33, 2L51 | 2022-11-07 08:00 | 2022-11-10 15:38 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-10 15:38
8-00778178 | Completed | MLN 2CB7 OOS | Cutover to new 2L76 PN | MLN 2CB7 | 2022-11-07 08:00 | 2022-11-10 15:39 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-10 15:40
8-00780798 | Completed | RYC 5CX1 OOS | Replace failed component, testing | RYC 5CX1 | 2022-11-07 08:00 | 2022-11-14 14:26 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-14 14:42
8-00772362 | Completed | MDN 12RX32 OOS | CPC NERC PM | MDN 12RX32 | 2022-11-08 08:00 | 2022-11-09 15:24 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-09 15:24
8-00767796 | Completed | 2L90 OOS | To replace structure 21/02 | 2L90 | 2022-11-09 08:00 | 2022-11-22 12:14 | 6 | Noncontinuous | [6 empty] | N | N | Y | Y | 2022-11-22 12:15
8-00758150 | Completed | MSA T1/T5/2B9/2B1 OOS | Close Temporary Bus Cut #1 on MSA 2B9 between 2D2CB10 & up to bus junction to T5 (2D5 & 2D1CB9) | MSA T1, MSA T5, MSA 2B9, MSA 2CB2 | 2022-11-09 08:00 | 2022-11-10 13:46 | 4 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-11-10 13:46
8-00782259 | Completed | KI2 2CB12 OOS | CPC NERC PM | KI2 2CB12 | 2022-11-09 08:00 | 2022-11-17 10:00 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-17 10:00
8-00761225 | Completed | KI2 2CB13 OOS | CPC NERC PM | KI2 2CB13 | 2022-11-09 12:00 | 2022-11-09 15:06 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-17 11:00
8-00785361 | Completed | 5L40, 5L41, CBN T1, T2, 5B12, 5MB2, 2B1 OOS | De-energize CBN 5CB7 to allow for repair | 5L40, 5L41, CBN T1, CBN T2, CBN 2B1, CBN 5B12, UHT 3RX1, UHT 3RX4, FLW 2CB3, FLW T2, CBN 5MB2 | 2022-11-09 22:00 | 2022-11-09 22:55 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-11-09 22:56
8-00785193 | Completed | CBN 5CB7 OOS | Hydraulic Hose Replacement | CBN 5CB7 | 2022-11-09 22:30 | 2022-11-29 14:55 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-29 15:12
8-00781773 | Completed | AMC 5CX2, 5BPCB2 OOS | SF6 Gas Top Up, Testing | AMC 5CX2, AMC 5BPCB2 | 2022-11-10 08:00 | 2022-11-14 15:05 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-14 15:05
8-00781005 | Completed | 5L1 OOS | Proximity outage to allow WSN 5RX2 bushing install | 5L1, GMS 5RX1, WSN 5B2, WSN 5RX2 | 2022-11-10 08:00 | 2022-11-10 16:19 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-10 16:19
8-00783181 | Cancelled | ING 2CB18 OOS | NERC CPC | ING 2CB18 | 2022-11-10 08:00 | 2022-11-10 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-12 18:00
8-00780601 | Cancelled | KLY 5CB12 OOS | TRIP TESTING FROM PN | KLY 5CB12 | 2022-11-14 08:00 | 2022-11-14 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-10 11:56
8-00777516 | Completed | 2L64 & SPG 2B3 OOS | SPG DS inspection & repair | SPG 2CB2, SPG 2CB3, 2L64 | 2022-11-14 08:00 | 2022-11-15 14:32 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-11-15 14:53
8-00783853 | Completed | 2L79 OOS, MLE 2L76 PY PN OOS | MLE 2CB2-CT1 primary injection testing | UHT 3RX1, UHT 3RX4, MLN T6, MLN T5, 2L79 | 2022-11-15 13:00 | 2022-11-15 17:15 | 1 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-11-15 17:15
8-00772694 | Completed | 2L64 OOS | Cable detailed inspection | 2L64 | 2022-11-15 16:00 | 2022-11-18 14:43 | 4 | Continuous | [6 empty] | Y | N | Y | Y | 2022-11-18 14:52
8-00783278 | Completed | ING 60CB5 OOS | Routine CPC CB CN PM | ING 60CB5 | 2022-11-16 08:00 | 2022-11-16 17:15 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-16 17:15
8-00690640 | Completed | 1L218 Out from VNT | End of life structure and cross arm replacements | 1L218 | 2022-11-16 12:00 | 2022-12-06 11:46 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-06 11:46
8-00783279 | Completed | ING 60CB7 OOS | Routine CPC CB CN PM | ING 60CB7 | 2022-11-17 08:00 | 2022-11-17 16:27 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-11-17 16:27
8-00783408 | Completed | 2L309 oos | Pole Replacement | 2L309 | 2022-11-17 08:00 | 2022-11-18 13:18 | 4 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-11-18 13:36
8-00785038 | Completed | MUR T2, 60B13 OOS | MUR T2 Low Oil Topup | MUR T2, MUR 60B13 | 2022-11-18 08:00 | 2022-11-18 17:32 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-11-18 17:32
8-00789233 | Completed | MCA 5RX4 OOS | Installation of LOA fencing | MCA 5RX4 | 2022-11-21 08:00 | 2022-12-13 14:31 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-12-13 14:31
8-00774818 | Completed | 60L5 OOS | Install new WTR (Westridge) tap | LB1 60CB5, 60L5 | 2022-11-21 08:00 | 2022-11-29 16:57 | 4 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-11-29 17:04
8-00662475 | Completed | 2L20 OOS | Detailed cable inspections | CAM T4, 2L20 | 2022-11-21 08:00 | 2022-11-24 14:38 | 2 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-11-24 14:38
8-00663790 | Completed | 2L50 OOS | Cable Inspection & Mtce | 2L50 | 2022-11-21 08:00 | 2022-11-25 14:31 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-11-25 14:31
8-00306097 | Cancelled | BSY G3 OOS | Inspection and Exciter Mtce | BSY T3, BSY G3 | 2022-11-22 01:00 | 2022-11-25 23:00 | 96 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-24 18:00
8-00788459 | Completed | 5L83 OOS | RYC 5D2 Urgent Inspection/Mtce | 5L83, RYC 5CX1 | 2022-11-22 08:00 | 2022-11-22 15:31 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-22 15:31
8-00782575 | Completed | 5L79 OOS | Disconnect Switch repair and Inspection | ACK 5CB1, 5L79, ACK 5B1 | 2022-11-22 08:00 | 2022-11-22 17:14 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-11-22 17:14
8-00788695 | Completed | 60L4 OOS | Proximity for 60L5 line work | 60L4 | 2022-11-23 08:00 | 2022-11-24 16:27 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-11-24 16:27
8-00788698 | Completed | 2L79, MLE 2L76 PY PN OOS | MLE 2CB2 Tests | UHT 3RX1, 60L100, MLN T6, MLN T5, 2L79 | 2022-11-24 12:00 | 2022-11-24 14:06 | 1 | Noncontinuous | [6 empty] | Y | N | Y | Y | 2022-11-24 14:12
8-00787821 | Completed | 2L51 OOS | Oil Leak Repair | BSY 2CB3, BSY 2CB7, BSY 2D33, 2L51 | 2022-11-28 08:00 | 2022-12-03 12:52 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-03 12:52
8-00702484 | Denied | HMH T5 oos | HMH T5 LTC Overhaul | HMH T5 | 2022-11-28 08:00 | 2022-12-09 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-10-23 13:15
8-00728381 | Completed | 2L22 OOS | End of life structure replacement | 2L22 | 2022-11-28 08:00 | 2022-12-09 15:19 | 2 | Return Weekends | [6 empty] | N | Y | Y | Y | 2022-12-09 15:19
8-00787518 | Completed | 60L20 Out from SON | emergent structure replacement | 60L20, SON T3 | 2022-11-28 09:00 | 2022-11-30 11:44 | 4 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-11-30 11:45
8-00788010 | Completed | 1L116 out from DMR to LTZ | Insulator Replacements | 1L115, 1L116, LTZ 1CB1, LTZ 1CB3, PVL T1, QLC T1 | 2022-11-29 07:00 | 2022-12-01 17:41 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-12-01 18:06
8-00777408 | Completed | VIT 1CB4 OOS | Work on VIT 1CB4 CN PM - NERC | VIT 1CB3, VIT 1CB4 | 2022-12-01 08:00 | 2022-12-01 12:59 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-12-01 13:08
8-00791033 | Completed | 5L12 oos | KLY 5D1CB13 Repair and LOA for work on KLY 5CB4 | 5L12, KLY 5B3, KLY 5RX3 | 2022-12-03 08:00 | 2022-12-04 16:13 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-04 16:13
8-00792420 | Completed | 5L41 OOS | test energization of KLY 5CB14 | 5L41, KLY 5CB14, KLY 5B4 | 2022-12-04 16:00 | 2022-12-04 17:46 | 1 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | Y | Y | 2022-12-04 17:47
8-00793609 | Completed | 2L18 OOS | HPL 2CB1 Maintenance | 2L18 | 2022-12-05 08:00 | 2022-12-06 16:32 | 4 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-06 17:07
8-00745760 | Completed | 2L55, CSN 2B1 OOS | Work inside CSN HIS1 Switchgear | 2L55, CSN 2B1 | 2022-12-05 08:00 | 2022-12-08 13:59 | 6 | Continuous | [6 empty] | N | Y | Y | Y | 2022-12-08 13:59
8-00663791 | Completed | 2L32 OOS | Detailed & Oil Sample | CSQ 2CB1, 2L32 | 2022-12-05 08:00 | 2022-12-09 16:07 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-09 16:08
8-00783897 | Completed | 2L76 OOS | MLE Expansion Project - Cutover to 2L76 SY PN | 60L8, 60L7, 60L100, 2L76 | 2022-12-07 08:00 | 2022-12-09 17:33 | 1 | Return Evenings | [6 empty] | Y | Y | Y | Y | 2022-12-09 17:42
8-00778165 | Completed | 2L76, MLN 2B7 OOS | MLE Expansion project | MLN 2B7, 2L76 | 2022-12-07 08:00 | 2022-12-09 17:37 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-12-09 17:42
8-00778827 | Cancelled | 60L1 OOS | Structure & Conductor Replacement | 60L1 | 2022-12-07 08:00 | 2022-12-16 16:00 | 12 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-05 11:58
8-00778835 | Cancelled | 60L26 OOS | Structure & Conductor Replacement | 60L26 | 2022-12-07 08:10 | 2022-12-16 16:00 | 12 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-05 11:58
8-00792371 | Completed | ING 2CX2, 2RX2 OOS | ING 2CX2 PCB Testing (Sampling) | ING 2CB22, ING 2RX2, ING 2CX2 | 2022-12-09 08:00 | 2022-12-09 14:20 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-09 14:20
8-00794287 | Completed | 60L73 OOS | Structure Replacement | 60L73, NKL 60CB10 | 2022-12-12 08:00 | 2022-12-13 17:15 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-12-13 17:21
8-00795578 | Completed | 2L45, SPG 2B5, 2B6 OOS | SPG 2GDB5, 2GD2CB6 Mtce | 2L45, SPG 2B5, SPG 2B6 | 2022-12-12 08:00 | 2022-12-16 17:12 | 6 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-16 17:12
8-00745772 | Completed | 2L45 OOS | Work inside CSN HIS2 Switchgear | CSN 2CB4, 2L45, CSN 2CB5 | 2022-12-12 08:00 | 2022-12-16 14:59 | 6 | Continuous | [6 empty] | N | Y | Y | Y | 2023-01-01 03:30
8-00664026 | Completed | 2L51 Out from COK, COK 2B2, T3 OOS | DS PM at COK | BSY 2CB3, BSY 2CB7, BSY 2D33, COK T3, 2L51, COK 2B2, MDN T2 | 2022-12-12 08:00 | 2022-12-16 17:54 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-12-16 17:54
8-00794959 | Completed | 2L17 OOS | LYN T2 Energization | LYN 2CB2, LYN T2, 2L17, WLT 2CB1, WLT 2CB2 | 2022-12-12 14:00 | 2022-12-12 15:33 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-12-12 15:34
8-00650745 | Completed | 2L79 OOS | Connect MLE 2CB3 Riser | 60L8, 60L7, UHT 3RX4, 60L100, MLE 2B2, MLE T2, 2L79, MLE 2B3 | 2022-12-14 07:00 | 2022-12-14 17:13 | 4 | Continuous | [6 empty] | Y | Y | Y | Y | 2022-12-14 17:14
8-00700374 | Completed | MDN 2CB11 OOS | CB Inspection | MDN 2CB11 | 2022-12-14 08:00 | 2022-12-16 15:01 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-16 15:01
8-00794149 | Completed | ACK 5MB1, 5CX1 OOS | Gas top up | ACK 5RX7, ACK 5CX1, ACK 5CB49, ACK 5MB1 | 2022-12-15 08:00 | 2022-12-15 14:32 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-12-15 14:32
8-00791043 | Completed | MLE 2B2 OOS | MLE 2CB3 Energization | MLE 2B2, MLE T2, MLE 2CB2 | 2022-12-15 09:30 | 2022-12-15 13:05 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-15 13:06
8-00794275 | Approved | BRT T4, 2L19, BR1 T3/T30 OOS | E-plan placeholder for new BRT 2D4 | 2L19, BR1 T3, BRT 2D4, BRT T4, BRT 3B5, BRT 2B4, BR1 T30 | 2022-12-15 14:00 | 2022-12-15 16:00 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-15 07:36
8-00798091 | Completed | COK 2B5 OOS | LOA for COK 2D3 Inspection | COK T2, COK 2B6, COK 2B5, COK 2CB5 | 2022-12-16 08:00 | 2022-12-16 16:46 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-12-16 16:47
8-00796496 | Cancelled | AMC 5CX1 OOS | AMC 5BPCB1 Air Hose Replacement | AMC 5CX1, AMC 5BPCB1 | 2022-12-17 08:00 | 2022-12-17 16:00 | 3 | Continuous | [6 empty] | Y | N | Y | Y | 2022-12-16 10:10
8-00769086 | Completed | 5L4, GMS 5B7/8/9 oos | GMS Blackstart testing | 5L4, GMS 5B7, GMS 5B9, GMS 5B8 | 2022-12-17 08:00 | 2022-12-17 14:53 | 2 | Continuous | [6 empty] | Y | N | Y | Y | 2022-12-17 14:53
8-00762381 | Completed | 5L75 OOS | Black start of REV G1 & G2 | ACK 5CB6, ACK 5CB8, 5L75, REV T8 | 2022-12-18 09:00 | 2022-12-18 12:42 | 1 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-18 12:42
8-00793029 | Cancelled | BSY G3 OOS | Brush Gear Maintenance | BSY T3, BSY G3 | 2022-12-19 08:00 | 2022-12-21 20:00 | 8 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-19 12:03
8-00791934 | Completed | CK5 5RX1 OOS | CT removals | CK5 5CB31, CK5 5RX1 | 2022-12-19 08:00 | 2022-12-19 13:50 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | Y | Y | 2022-12-19 14:58
8-00786449 | Completed | 2L55 OOS | Facilitate CoV work (sewer mains installation) | HPN 2CB6, 2L55 | 2022-12-19 08:00 | 2022-12-21 13:45 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-12-21 16:20
8-00798066 | Completed | ING 12RX4 OOS | Emergency Hotspot Repair | ING 12RX4 | 2022-12-19 08:00 | 2022-12-27 16:42 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2023-01-09 07:08
8-00795052 | Cancelled | 60L5 OOS | Change CT Ratio | SHL 60CB2, 60L5, SHL 60CB1 | 2022-12-20 08:00 | 2022-12-21 17:00 | 4 | Continuous | [6 empty] | N | Y | Y | Y | 2022-12-23 18:00
8-00798584 | Completed | ARN 60CB1, T10 OOS | Routine CPC CB CN PM | ARN 60CB1 | 2022-12-27 08:00 | 2022-12-29 08:40 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-12-29 08:40
8-00800779 | Completed | ING T4, 12RX4 OOS | ING 12D4 failed to operate, investigate and repair | ING 12RX4, ING T4 | 2022-12-27 08:00 | 2022-12-27 16:42 | 2 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-27 16:42
8-00767845 | Completed | MDN 2CB10 OOS | CB Inspection | MDN 2CB10 | 2022-12-27 08:00 | 2022-12-29 15:42 | 3 | Continuous | [6 empty] | N | N | Y | Y | 2022-12-29 15:42
8-00800774 | Completed | 2L22, WHY T2 OOS | Investigate and repair WHY 2D2 | 2L22, WHY 2CB3, WHY 2D2, WHY T2, WHY 2B2 | 2022-12-28 08:00 | 2022-12-28 15:32 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-12-28 15:44
8-00798590 | Completed | ARN 60CB3, T9 OOS | Routine CPC CB CN PM | ARN 60CB3 | 2022-12-29 08:00 | 2022-12-30 17:46 | 2 | Continuous | [6 empty] | N | Y | Y | Y | 2022-12-30 17:47