## Annual Plan Extract
2024 Annual Plan Extract
Outage # | Outage Status | AP Outage Title | Outage Purpose | Requested Equipment | Start Date (MM/DD/YYYY HH:MM:SS) | Complete Date (MM/DD/YYYY HH:MM:SS) | Recall Time (Hours) | Outage Type : Continuous /Daily | Path 3 (N->S) ING to CUS (MW) | Path 3 (N->S) BC to US (MW) | Path 3 (S->N)CUS to ING (MW) | Path 3 (S->N) US to BC (MW) | Path 1 BC AB (W->E) BC to AB (MW) | Path 1 (E->W) AB to BC (MW) | Resource Impact | Load Impact | Revision Date (MM/DD/YYYY HH:MM:SS)
8-00253033 | Implemented | BSY G2 Forced OOS | Synchronous Condenser Forced OOS | BSY G2 | 2016-08-26 00:43 | 2025-12-31 23:59 | 2 | Continuous | [6 empty] | N | N | 2024-01-30 13:24
8-00771511 | Implemented | KDY 5CX3 OOS | Forced OOS | KDY 5CX3 | 2022-10-03 14:21 | 2025-12-31 16:00 | NR | Continuous | [6 empty] | N | N | 2024-02-20 19:02
8-00795393 | Completed | KLY 5RX3 OOS | Forced OOS | KLY 5RX3 | 2022-12-06 05:17 | 2023-10-31 12:00 | NR | Continuous | [6 empty] | N | N | 2023-11-03 15:42
8-00799221 | Completed | MDN 2RX1 OOS | MDN 2CB14 POW Failure (cant be switched in) | MDN 2RX1 | 2022-12-16 09:52 | 2023-08-10 12:45 | NR | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-08-16 10:43
8-00799265 | Completed | HPN 12CB4 Forced OOS | Bird strike damage | HPN T4 | 2022-12-19 08:00 | 2024-04-04 13:21 | NR | Continuous | [6 empty] | N | N | 2024-04-04 13:21
8-00590589 | Completed | WAH T1 & 3L3 OOS | With WAH G1 refurbishment outage, there is no cooling water to operate T1 | WAH T1, 3L3 | 2023-02-27 08:00 | 2023-07-21 14:37 | 2 | Continuous | [6 empty] | N | N | 2023-07-21 14:38
8-00827402 | Completed | VIT SC4 OOS | Exciter Upgrades | VIT SC4 | 2023-03-13 08:00 | 2023-07-11 16:43 | NR | Continuous | [6 empty] | N | N | 2023-07-11 16:43
8-00669173 | Cancelled | MUR T2 OOS | PCB Bushing Replacements | MUR T2 | 2023-03-15 08:00 | 2023-04-29 16:00 | 120 | Continuous | [6 empty] | N | Y | 2022-07-26 16:28
8-00814171 | Completed | 60L89, HSB T2 OOS | Replace 60DCB3 | HSB 60CB3, HSB T2, 60L89 | 2023-03-20 08:00 | 2023-04-17 17:36 | 8 | Continuous | [6 empty] | N | N | 2023-04-17 17:36
8-00706833 | Completed | JOR T1/T2/T11 /1B1 OOS | JOR OSP Step 15 | JOR T1, JOR T2, JOR 1B1 | 2023-03-21 20:00 | 2023-05-11 10:02 | 4 | Continuous | [6 empty] | Y | Y | 2023-05-11 10:02
8-00796922 | Completed | SON T2, 60B1 | SON CB/DS/IT Replacement (JB) Bypass OSP Rev 3 Step #5 & 6 | SON 60CB21, SON 60CB22, SON T2, SON 60B1 | 2023-03-22 19:30 | 2023-05-29 11:16 | 48 | Continuous | [6 empty] | Y | Y | 2023-05-29 11:17
8-00825158 | Completed | 2L77 OOS | Replace emergent test-&-treat failed 2L77 structure 31-6 | 2L77 | 2023-03-27 08:00 | 2023-04-01 16:18 | 3 | Continuous | [6 empty] | Y | N | 2023-04-01 16:18
8-00788143 | Completed | 60L61 out from WLT , WLT 60B6 OOS | 0962 WLT OSP Step 13 | 60L61, WLT 60D26, WLT 60B6 | 2023-03-30 07:00 | 2023-04-12 11:00 | 7 | Continuous | [6 empty] | N | N | 2023-04-12 11:01
8-00794429 | Completed | 60L66 out from 60D1L66 to CAP | install New TX bushings in new transformers at Capilano Substation | 60L66 | 2023-03-30 08:00 | 2023-04-13 07:52 | 4 | Continuous | [6 empty] | N | Y | 2023-04-13 08:08
8-00775801 | Completed | REV 5MB2 OOS | Doble Tests | REV 5MB2 | 2023-03-30 22:00 | 2023-04-02 22:48 | 4 | Continuous | [6 empty] | Y | N | 2023-04-02 22:48
8-00806495 | Completed | MUR T2, 60B13, 12RX32 OOS | MUR T2 PCB Bushing Repl | MUR T2, MUR 60B13 | 2023-04-01 08:00 | 2023-04-06 16:35 | 8 | Continuous | [6 empty] | N | Y | 2023-04-06 16:35
8-00828168 | Completed | 2L51, BND T2 OOS | Emergency BND 2VT2 Repl | BND T2, 2L51, 2L51 | 2023-04-01 08:00 | 2023-04-19 13:14 | 8 | Continuous | [6 empty] | N | Y | 2023-04-19 13:14
8-00794753 | Completed | 60L129, LBH 60CX1, CX2, T11, T12, GCL 60B4, T11, T12 OOS | 60L129, LBH 60CX1, CX2, T11, T12, GCL 60B4, T11, T12 | 60L129, GCL T11, GCL T12, LBH T11, LBH T12 | 2023-04-02 07:00 | 2023-04-02 20:23 | NR | Continuous | [6 empty] | Y | N | 2023-04-02 20:23
8-00813651 | Completed | 2L1 out from BRT to 2D1L1 | Replace 2L1 STR 11-2A. | 2L1 | 2023-04-03 07:00 | 2023-04-06 09:28 | 3 | Continuous | [6 empty] | Y | Y | 2023-04-06 09:33
8-00814411 | Completed | CRK 5CX1 OOS | Fibre optic cables mtce | CRK 5CX1 | 2023-04-03 08:00 | 2023-04-05 13:16 | 4 | Continuous | [6 empty] | N | N | 2023-04-05 15:06
8-00815878 | Completed | WLM T1 OOS | WSN T1 Insp and Doble testing | WLM T1 | 2023-04-03 08:00 | 2023-04-14 11:14 | 2 | Continuous | [6 empty] | N | N | 2023-04-14 11:14
8-00797161 | Completed | 1L123, HWD T2, HWW 1B9, JPT 1CB9 OOS | HWD 1D2, JPT 1CB9, 1CVT3, HWD 1GD2, HWW 1D2CB9, 1D1CB10, 1D25, 1CVT25, JPT 1D1CB9 INSP | JPT 1CB9, HWD T2, 1L123 | 2023-04-03 08:00 | 2023-04-12 12:54 | NR | Continuous | [6 empty] | N | Y | 2023-04-12 12:54
8-00791445 | Completed | 2L4, CAM T2 OOS | Replace EOL Structures | BSY 2CB8, 2L4, CAM T2 | 2023-04-03 08:00 | 2023-04-06 15:46 | 2 | Continuous | [6 empty] | Y | Y | 2023-04-07 12:34
8-00801117 | Denied | 60L50 OOS | Detailed Inspection | 60L50 | 2023-04-03 08:00 | 2023-04-07 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-03-27 15:14
8-00802835 | Completed | 1L127 OOS | End of Life Structure Replacements | PAL 1CB10, 1L127 | 2023-04-03 08:00 | 2023-04-06 14:35 | NR | Continuous | [6 empty] | Y | N | 2023-04-06 15:31
8-00803265 | Proposed | 60L14, MIS 60B1 OOS | MIS 60VT1 replacement - PCB | 60L14, MIS 60B1 | 2023-04-03 08:00 | 2023-04-14 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-02-22 09:28
8-00805680 | Completed | MDN 2CB14, 2RX1, 2CX1, 2CX2 OOS | CPC Breaker Fail Testing, RX non-ele Testing, DS Mtce | MDN 2RX1, MDN 2CB14, MDN 2CX2, MDN 2CX1, MDN 2D11 | 2023-04-03 08:00 | 2023-04-06 15:12 | 4 | Continuous | [6 empty] | N | N | 2023-04-06 15:12
8-00805862 | Completed | ARN T2 OOS, 1L18 Out from ARN, GLS OOS | ARN DS Maintenance & 1L18 Terminal Wash | ARN 1CB2, 1L18, GLS T1 | 2023-04-03 08:00 | 2023-04-06 13:57 | 2 | Continuous | [6 empty] | N | N | 2023-04-06 13:57
8-00806920 | Cancelled | CBK 5D45 OOS | Replace 5D45 B Phase Interupter | CBK 5D45 | 2023-04-03 08:00 | 2023-04-13 16:00 | 12 | Continuous | [6 empty] | N | N | 2023-02-13 14:06
8-00807566 | Completed | SVA T1 OOS | PCB Bushing Replacement | SVA T1, SVA 2B4 | 2023-04-03 08:00 | 2023-04-06 11:24 | 8 | Continuous | [6 empty] | N | N | 2023-04-06 23:41
8-00620617 | Completed | 5L72 OOS | For MCA Switchgear Roof Replacement. | 5L72 | 2023-04-03 09:00 | 2023-06-30 13:23 | 24 | Continuous | [6 empty] | Y | N | 2023-06-30 13:23
8-00815115 | Completed | 5L72, NIC 5B13, MCA 5B7 OOS | Switching outage to open 500kV devices for 5L72 & MCA 5RX3 OOS. | 5L72, MCA 5B7, NIC 5B13 | 2023-04-03 09:00 | 2023-04-03 17:09 | 0 | Continuous | [6 empty] | N | N | 2023-04-03 17:09
8-00793775 | Cancelled | 1L103, EFM 2MK2 OOS | 1L103, EFM 2MK2 | 1L103 | 2023-04-04 08:00 | 2023-04-05 16:00 | NR | Continuous | [6 empty] | N | N | 2023-03-17 15:13
8-00811318 | Completed | ARN 2CB12 OOS | NERC BFPN PM | ARN 2CB12 | 2023-04-04 08:00 | 2023-04-05 17:59 | 2 | Continuous | [6 empty] | N | N | 2023-04-05 18:00
8-00812185 | Completed | JHT 1CB1 OOS | JHT 1CB1 INSP | JHT 1CB1 | 2023-04-04 08:00 | 2023-04-05 13:04 | 2 | Continuous | [6 empty] | N | N | 2023-04-05 13:07
8-00716478 | Cancelled | DAW T1 OOS | DAW T1 bushing replacement pre-checks | DAW T1 | 2023-04-05 08:00 | 2023-04-06 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-03-30 12:09
8-00814416 | Completed | 5L42 OOS | CK5 5CVT2 PM INSP | CK5 5CB2, CK5 5CB22, CK5 5RX1, 5L42, CRK 5CX1 | 2023-04-05 08:00 | 2023-04-06 17:52 | 4 | Continuous | 2000 | 2400 |  |  |  |  | Y | Y | 2023-04-06 17:53
8-00819627 | Cancelled | KLY T4, 2RX2 OOS | KLY T4 Non-EL PN PM | KLY 2RX2, KLY T4 | 2023-04-05 08:00 | 2023-04-06 16:00 | NR | Return Evenings | [6 empty] | N | N | 2023-03-07 12:26
8-00833286 | Completed | 5L42, KLY 5B2 OOS | KLY 5D2CB2 Repair | 5L42, CRK 5CX1, KLY 5B2, KLY 5RX2 | 2023-04-05 08:00 | 2023-04-06 17:26 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-04-06 17:26
8-00837100 | Completed | ING 2CX31, 2CX32 OOS | Doble Test & Repair. Caps are not functional | ING 2CX31, ING 2CX32 | 2023-04-06 08:00 | 2023-04-17 15:03 | 2 | Continuous | [6 empty] | N | N | 2023-04-17 15:04
8-00814546 | Cancelled | 5L42, KLY 5B2 OOS | KLY 5D1CB12 INSP | 5L42, KLY 5B2, KLY 5D1CB12, KLY 5RX2 | 2023-04-06 08:00 | 2023-04-06 16:00 | 4 | Continuous | 2000 | 2400 |  |  |  |  | Y | Y | 2023-03-31 10:30
8-00799685 | Cancelled | 2L14 OOS | End of life structure replacement on 2L14 | 2L14 | 2023-04-06 08:00 | 2023-04-07 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-03-30 08:24
8-00811841 | Completed | NEL 2CB4 OOS | NEL 2CB4 BFPN PM | NEL 2CB4 | 2023-04-06 08:00 | 2023-04-06 14:46 | 2 | Continuous | [6 empty] | N | N | 2023-04-06 14:46
8-00806514 | Cancelled | 2L11, WLT T2, 2B8, 2B2 OOS | Stn Insulator Replacement | 2L11, WLT T2, WLT 2B8, WLT 2B2 | 2023-04-10 08:00 | 2023-04-14 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-01-20 09:20
8-00686933 | Cancelled | AVO T1 OOS | Bushing Replacement Project | AVO T1 | 2023-04-10 08:00 | 2023-05-05 16:00 | NR | Continuous | [6 empty] | N | N | 2023-02-24 09:52
8-00763314 | Completed | CKY T5 OOS | LTC Inspection | CKY T5, CKY T9 | 2023-04-11 07:00 | 2023-04-19 11:00 | 24 | Continuous | [6 empty] | Y | Y | 2023-04-19 11:01
8-00805682 | Completed | MDN 2CB5, 2RX2 OOS | CPC Breaker Fail Testing & RX non-ele testing | MDN 2RX2, MDN 2CB15 | 2023-04-11 07:00 | 2023-04-14 13:17 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-04-14 13:17
8-00803303 | Completed | 2L90 OOS | Replace Emergent Structures | 2L90 | 2023-04-11 08:00 | 2023-04-19 12:34 | NR | Continuous | [6 empty] | N | N | 2023-04-19 12:34
8-00806503 | Cancelled | SPG T13 OOS | PCB Bushing Replacement | SPG T13 | 2023-04-11 08:00 | 2023-05-19 16:00 | 8 | Continuous | [6 empty] | N | Y | 2023-01-20 14:52
8-00807605 | Denied | NAK T1 OOS | PCB Bushing Replacement | NAK T1 | 2023-04-11 08:00 | 2023-05-11 16:00 | NR | Continuous | [6 empty] | N | N | 2023-04-06 11:22
8-00809093 | Completed | 5L83, NIC 5B22 OOS | NIC 5D28 INSP, CPC PM | NIC 5B22, NIC 5RX8, 5L83, RYC 5CX1 | 2023-04-11 08:00 | 2023-04-14 17:14 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-04-14 17:16
8-00809647 | Proposed | ACK 5CB47 OOS | CPC CN CA | ACK 5CB47 | 2023-04-11 08:00 | 2023-04-11 16:00 | NR | Continuous | [6 empty] | N | N | 2023-02-01 09:21
8-00812069 | Completed | JHT 1B4 OOS | JHT 1CB4 INSP | JHT 1CB4, JHT 1B4 | 2023-04-11 08:00 | 2023-04-12 15:40 | 2 | Continuous | [6 empty] | N | N | 2023-04-12 15:40
8-00811694 | Completed | CSQ T1, 2B2 OOS | DS INSP | CSQ 2D2CB2, CSQ T1, CSQ 2B2 | 2023-04-11 08:00 | 2023-04-13 11:27 | 2 | Continuous | [6 empty] | N | N | 2023-04-13 11:27
8-00811320 | Completed | ARN 2CB13 OOS | CPC Breaker Fail PN PM | ARN 2CB13 | 2023-04-11 08:00 | 2023-04-12 13:19 | 2 | Continuous | [6 empty] | N | N | 2023-04-12 13:24
8-00811327 | Completed | ING 2CB11 OOS | CB Inspection | ING 2CB11 | 2023-04-11 08:00 | 2023-04-12 14:44 | 2 | Continuous | [6 empty] | N | N | 2023-04-13 02:27
8-00810113 | Completed | MDN T1 OOS | Oil Leak Repair | MDN T1 | 2023-04-11 08:00 | 2023-06-05 16:20 | 120 | Continuous | [6 empty] | N | N | 2023-06-05 16:41
8-00817839 | Completed | 5L83 OOS | Emergency Structure Repair | NIC 5B22, NIC 5RX8, 5L83, RYC 5CX1 | 2023-04-11 08:00 | 2023-04-14 17:14 | 2 | Continuous | 2400 | 2800 |  |  |  |  | N | N | 2023-04-14 17:17
8-00813174 | Completed | SEC T2, 1CB12 OOS | WLT 60L92 - 60D1CB4, 60D2CB3 INSP | SEC 1CB12, SEC T2 | 2023-04-11 08:00 | 2023-04-11 15:06 | NR | Continuous | [6 empty] | N | N | 2023-04-11 15:06
8-00835404 | Approved | WSN 5CB5 oos | CB PN PM | WSN 5CB5 | 2023-04-11 08:00 | 2023-04-11 12:00 | 1 | Continuous | [6 empty] | N | N | 2023-04-05 14:36
8-00834043 | Completed | 5L12 oos | WSN DS hotspot repair | 5L12, WSN 5B5, WSN 5RX5 | 2023-04-11 08:00 | 2023-04-11 20:00 | 4 | Continuous | [6 empty] | N | N | 2023-04-13 19:57
8-00833818 | Completed | MUR 2CB2 OOS | CB INSP | MUR 2CB2 | 2023-04-12 08:00 | 2023-04-14 14:41 | 2 | Continuous | [6 empty] | N | N | 2023-04-14 14:41
8-00815869 | Completed | WSN 5RX3 OOS | WSN 5RX3 Non-EL PN | WSN 5RX3 | 2023-04-12 08:00 | 2023-04-12 17:01 | NR | Continuous | [6 empty] | N | N | 2023-04-12 17:02
8-00810897 | Denied | VIT 2CB14, 1CB14 OOS | VIT 2CB14, 1CB14 CN | VIT 2CB14, VIT 1CB14, VIT SC4, VIT T9 | 2023-04-12 08:00 | 2023-04-12 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-04-06 14:27
8-00808879 | Completed | 1L377 out from DAW | Intall Tap for new TVC customer | 1L377 | 2023-04-12 08:00 | 2023-04-26 19:22 | 8 | Continuous | [6 empty] | Y | N | 2023-04-26 19:22
8-00811076 | Cancelled | VIT 2CB15, 1CB15 OOS | VIT 2CB15 & 1CB15 CN | VIT 2CB15, VIT 1CB15, VIT SC3, VIT T10 | 2023-04-13 08:00 | 2023-04-13 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-04-06 15:08
8-00811322 | Completed | ARN 2CB18 OOS | CPC Breaker Fail PN PM | ARN 2CB18 | 2023-04-13 08:00 | 2023-04-14 17:42 | 2 | Continuous | [6 empty] | N | N | 2023-04-14 17:52
8-00812203 | Completed | JHT 1CB7 OOS | JHT 1CB7 INSP | JHT 1CB7 | 2023-04-13 08:00 | 2023-04-14 13:36 | 2 | Continuous | [6 empty] | N | N | 2023-04-14 13:36
8-00788493 | Completed | WLT T1, 60B2 OOS | 60B2 Insulator Deficiency Work | WLT T1, WLT 60B2 | 2023-04-13 08:00 | 2023-04-25 14:35 | 3 | Continuous | [6 empty] | N | N | 2023-04-25 14:35
8-00818809 | Cancelled | 5L94 OOS | CBK 5RX4 test energization and restoration | 5L94 / 1201L | 2023-04-13 08:00 | 2023-04-13 16:00 | 1 | Continuous | [6 empty] | N | N | 2023-02-13 14:11
8-00813175 | Completed | SEC 1CB4 OOS | SEC 1CB4 COND NERC | SEC 1CB4 | 2023-04-13 08:00 | 2023-04-13 13:56 | NR | Continuous | [6 empty] | N | N | 2023-04-13 16:32
8-00812805 | Cancelled | SPD T1, 60D1 OOS | Inspections & doble | SPD 60D1, SPD T1 | 2023-04-13 08:00 | 2023-04-13 16:00 | NR | Continuous | [6 empty] | N | N | 2023-04-11 09:38
8-00813004 | Approved | WSN 5CB1 OOS | CB PN & POW CN | WSN 5CB1 | 2023-04-13 08:00 | 2023-04-13 16:00 | NR | Continuous | [6 empty] | N | N | 2023-04-12 11:14
8-00813011 | Cancelled | WSN 5CB15 OOS | WSN 5CB15 PN & POW CN | WSN 5CB15 | 2023-04-13 08:00 | 2023-04-13 16:00 | NR | Continuous | [6 empty] | N | N | 2023-04-05 08:53
8-00813014 | Cancelled | WSN 5CB5 OOS | WSN CB PN & POW CN | WSN 5CB5 | 2023-04-14 08:00 | 2023-04-14 16:00 | NR | Continuous | [6 empty] | N | N | 2023-04-05 08:54
8-00796968 | Completed | ALZ T2 | ALZ T2 LTC oil sample | ALZ T2 | 2023-04-14 08:00 | 2023-04-14 14:10 | 4 | Continuous | [6 empty] | N | N | 2023-04-14 14:10
8-00809660 | Proposed | ACK 5B2 OOS | 5D2, 5D1CB3 and 5D2CB2 INSP | ACK 5B2 | 2023-04-15 08:00 | 2023-04-17 16:00 | NR | Continuous | [6 empty] | N | N | 2023-02-01 09:20
8-00812919 | Cancelled | CHS 1D21, 1D22, 1D2 OOS | To replace 1D21, 1D22, 1D2 | CHS 1D2, CHS 1D21, CHS 1D22 | 2023-04-15 08:00 | 2023-04-15 12:00 | 0 | Continuous | [6 empty] | N | N | 2023-03-17 09:37
8-00833535 | Completed | 5L42 OOS | Test energize KLY 5CB2 | 5L42, KLY 5B2 | 2023-04-15 08:00 | 2023-04-15 13:02 | 2 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | 2023-04-15 14:45
8-00692409 | Cancelled | 1L146 OOS | City of Langford Pole Relocation | 1L146 | 2023-04-16 08:00 | 2023-04-19 16:00 | 6 | Continuous | [6 empty] | Y | N | 2023-02-01 14:17
8-00832603 | Completed | 5L94 Switching Outage | isolation of CBK 5RX5 | 5L94 / 1201L | 2023-04-17 07:00 | 2023-04-17 07:44 | NR | Continuous |  |  |  |  | 50 | 100 | N | N | 2023-04-17 08:01
8-00833824 | Completed | 2L18, HPL OOS | HPL 2CB1 Removal | 2L18 | 2023-04-17 07:30 | 2023-05-11 13:36 | 4 | Continuous | [6 empty] | N | N | 2023-05-15 13:54
8-00833693 | Cancelled | ARN 2CB6 OOS | CPC NERC PM | ARN 2CB6 | 2023-04-17 08:00 | 2023-04-18 16:00 | 2 | Continuous | [6 empty] | Y | N | 2023-04-17 11:42
8-00830646 | Completed | 2L128 / SAT 2MB3 OOS | TVI to complete defective insulator change-outs on 2L128: 34/3, 49/1, 70/1, 79/1 & SAT Disconnect Bulletins | SAT 2MB3, HWW T2, 2L128 | 2023-04-17 08:00 | 2023-04-20 18:34 | 2 | Continuous | [6 empty] | N | N | 2023-04-20 18:34
8-00812944 | Completed | DMR 5RX5 OOS | DMR 5CB55, 5RX5 - CN & NETS | DMR 5RX5, DMR 5CB55 | 2023-04-17 08:00 | 2023-04-18 11:43 | 2 | Return Evenings | [6 empty] | N | N | 2023-04-18 11:43
8-00813016 | Cancelled | WSN 5CB6 OOS | WSN CB PN & POW CN | WSN 5CB6 | 2023-04-17 08:00 | 2023-04-17 16:00 | NR | Continuous | [6 empty] | N | N | 2023-04-19 18:00
8-00813179 | Completed | 5L30, MSA T1, 5B1 OOS | MSA 5L30 - 5D1CB6, 5D1CB3 INSP, 5SA21 BUTN | MSA 12RX1, MSA T1, 5L30, MSA 5B1 | 2023-04-17 08:00 | 2023-04-21 16:48 | 4 | Continuous | [6 empty] | Y | N | 2023-04-21 16:48
8-00819317 | Completed | CBK 5RX5 OOS | Install the Aux cooling | CBK 5RX5 | 2023-04-17 08:00 | 2023-04-21 19:24 | 6 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | 2023-04-21 19:24
8-00814547 | Completed | 5L87 OOS | 5D1 Failure Investigation, 5CX1 PM | 5L87, GUI 5CX1, GUI 5D1 | 2023-04-17 08:00 | 2023-04-20 16:47 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-04-20 16:47
8-00786901 | Completed | WLT T1 OOS | non-electrical trip testing, fall protection anchor inspection, oil piping corrective work, 60D1 inspection | WLT T1, WLT 60B2 | 2023-04-17 08:00 | 2023-04-20 16:12 | 6 | Continuous | [6 empty] | N | N | 2023-05-01 22:31
8-00764535 | Completed | BSY G3 OOS | Superchlorination & G3 Maintenance | BSY T3, BSY G3 | 2023-04-17 08:00 | 2023-04-21 16:05 | 24 | Continuous | [6 empty] | N | N | 2023-04-21 16:45
8-00805353 | Cancelled | MDN T1 OOS | CPC non-ele protection testing | MDN T1 | 2023-04-17 08:00 | 2023-04-21 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-02-02 13:22
8-00805874 | Completed | 2L10, ARN 2CB1, 2CB2 OOS | ARN DS/CB Mtce | ARN 2CB1, ARN 2CB2, 2L10 | 2023-04-17 08:00 | 2023-04-20 14:23 | 2 | Continuous | [6 empty] | N | N | 2023-04-20 14:23
8-00798479 | Cancelled | 2L90 OOS | EOL Structure Replacements | 2L90 | 2023-04-17 08:00 | 2023-04-21 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-04-04 09:17
8-00801121 | Denied | 60L51 OOS | Detailed Inspection | DGR T4, 60L51 | 2023-04-17 08:00 | 2023-04-21 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-04-12 09:46
8-00807960 | Completed | HSY T11 , 2CB11 OOS | HSY T11 INSP/DOBL/Non-EL, 2CB11 INSP | HSY T11, HSY 2B1 | 2023-04-17 08:00 | 2023-04-28 15:35 | 8 | Continuous | [6 empty] | N | N | 2023-04-28 15:36
8-00807975 | Completed | GTP 1D1CB2/1D2CB1 OOS | GTP 1D1CB2 INSP, GTP 1D2CB1 INSP | GTP 1B2, GTP T12 | 2023-04-17 08:00 | 2023-04-18 10:31 | 4 | Continuous | [6 empty] | N | N | 2023-04-18 10:32
8-00811325 | Completed | ING 2CB10 OOS | CB Inspection | ING 2CB10 | 2023-04-17 08:00 | 2023-04-18 13:57 | 2 | Continuous | [6 empty] | N | N | 2023-04-18 13:58
8-00805996 | Completed | 2L31, CSQ 2B3 OOS | CSQ DS INSP | BSY 2CB5, BSY 2CB8, 2L31, CSQ 2B3 | 2023-04-17 08:30 | 2023-04-21 14:16 | 2 | Continuous | [6 empty] | Y | Y | 2023-04-21 14:17
8-00798021 | Completed | CVN 60CB4 OOS | CVN 60CB4 Replacement | CVN 60CB4 | 2023-04-17 12:00 | 2023-05-24 11:48 | 792 | Continuous | [6 empty] | N | Y | 2023-05-24 11:49
8-00764522 | Cancelled | BSY G1 OOS | Superchlorination & BSY G1 Mtce | BSY T1, BSY G1 | 2023-04-18 08:00 | 2023-04-20 16:00 | 24 | Continuous | [6 empty] | N | N | 2023-04-22 18:00
8-00690010 | Cancelled | 2L240 OOS | End of Life Structure and Cross Arm Replacement | 2L240 | 2023-04-18 08:00 | 2023-04-20 16:00 | NR | Continuous | [6 empty] | N | N | 2022-02-03 14:45
8-00805381 | Completed | MDN 5CB1 OOS | CPC Control Testing | MDN 5CB1, MDN 5CB5 | 2023-04-18 08:00 | 2023-04-19 15:36 | 2 | Continuous | [6 empty] | N | N | 2023-04-19 15:36
8-00812188 | Completed | JHT 1Cb14 OOS | JHT 1CB14 INSP | JHT 1CB14 | 2023-04-18 08:00 | 2023-04-19 13:37 | 2 | Continuous | [6 empty] | N | N | 2023-04-19 13:37
8-00814163 | Completed | 60L69 out from HSB, HSB T1 OOS | Replace 60D21, 60D1CB3 | HSB 60CB3, HSB T1, 60L69 | 2023-04-18 08:00 | 2023-05-12 15:59 | 8 | Continuous | [6 empty] | N | N | 2023-05-12 15:59
8-00812799 | Completed | QLC T1/T2/1B1/1B2 OOS | QLC 1D1CB3 INSP | 1L115, 1L116, QLC 1B1, QLC 1B2, QLC T1, QLC T2 | 2023-04-18 08:00 | 2023-04-19 13:05 | 2 | Continuous | [6 empty] | N | N | 2023-04-19 13:06
8-00813006 | Approved | WSN 5CB11 OOS | WSN CB PN & POW CN | WSN 5CB11 | 2023-04-19 08:00 | 2023-04-19 16:00 | NR | Continuous | [6 empty] | N | N | 2023-04-18 13:30
8-00813214 | Completed | WBK T1 OOS | NON EL PM | WBK T1 | 2023-04-19 08:00 | 2023-04-19 14:14 | 2 | Continuous | [6 empty] | N | N | 2023-04-19 14:14
8-00833695 | Cancelled | ARN 2CB7 OOS | NERC CPC CB CN PM | ARN 2CB7 | 2023-04-19 08:00 | 2023-04-20 16:00 | 2 | Continuous | [6 empty] | Y | N | 2023-04-18 09:21
8-00764548 | Completed | BSY G4 OOS | Superchlorination (2 days recall time) | BSY T4, BSY G4 | 2023-04-19 08:00 | 2023-04-20 16:00 | 48 | Continuous | [6 empty] | N | N | 2023-04-21 06:21
8-00797133 | Completed | 1L109 HWW 1B5, PVO 1CX1, T3, 1CB2, SWN T1, VIT 1D25 OOS | PVO 1D23, 1D1CB2 | PVO 1CB2, PVO 1CX1, PVO T2, PVO T3, 1L109 | 2023-04-19 08:00 | 2023-04-19 16:08 | NR | Continuous | [6 empty] | N | N | 2023-04-19 16:08
8-00842233 | Completed | CRK 5CX1 Forced OOS | 5BP1 malfunction | CRK 5CX1 | 2023-04-19 16:57 | 2023-06-02 16:16 | NR | Continuous | [6 empty] | N | N | 2023-06-02 16:22
8-00835527 | Denied | ING 5CB9 OOS | Replace control box & Test operation | ING 5CB9 | 2023-04-20 08:00 | 2023-04-21 16:00 | 4 | Continuous | [6 empty] | Y | N | 2023-04-17 09:27
8-00840172 | Completed | MPT 2B6, 2CB1, 2CB6 OOS | SF6 Top Up | MPT 2CB1, MPT 2CB6, MPT 2B6 | 2023-04-20 08:00 | 2023-04-20 16:44 | 1 | Continuous | [6 empty] | N | N | 2023-04-20 16:44
8-00813215 | Completed | WBK T2 OOS | NON EL PM | WBK T2 | 2023-04-20 08:00 | 2023-04-20 13:12 | 2 | Continuous | [6 empty] | N | N | 2023-04-20 13:12
8-00813349 | Completed | CKY 1CB5 OOS | TRIP TESTING | CKY 1CB5 | 2023-04-20 08:00 | 2023-04-20 14:04 | 2 | Continuous | [6 empty] | N | N | 2023-04-20 14:04
8-00813750 | Completed | DMR 5RX6 OOS | DMR 5RX6 NON ELEC | DMR 5RX6 | 2023-04-20 08:00 | 2023-04-20 15:06 | 2 | Continuous | [6 empty] | Y | N | 2023-04-20 20:37
8-00812193 | Completed | JHT 1CB16 OOS | JHT 1CB16 INSP | JHT 1CB16 | 2023-04-20 08:00 | 2023-04-21 11:00 | 2 | Continuous | [6 empty] | N | N | 2023-04-21 13:59
8-00813350 | Cancelled | CKY T4 OOS | NON-ELEC PN | CKY T4 | 2023-04-21 08:00 | 2023-04-21 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-04-12 08:11
8-00833504 | Completed | AMC 5CX2 OOS | Pre-work Inspection | AMC 5CX2 | 2023-04-21 08:00 | 2023-04-21 14:58 | 2 | Continuous | [6 empty] | N | N | 2023-04-21 15:13
8-00785726 | Approved | Revelstok 5MB2/4 OOS | For DS Maintenance | REV 5B11, REV 5MB2, REV 5MB4 | 2023-04-21 22:00 | 2023-04-23 18:00 | 8 | Continuous | [6 empty] | N | N | 2023-04-21 19:56
8-00841005 | Completed | MUR 2B1, T2, T3 OOS | Bus replacement LOA | MUR T2, MUR T3, MUR 2B1 | 2023-04-22 07:00 | 2023-04-23 09:47 | 2 | Continuous | [6 empty] | N | N | 2023-04-23 09:48
8-00833619 | Completed | GMS T14 OOS | GMS Control System Upgrade | GMS T14 | 2023-04-24 08:00 | 2023-04-28 14:13 | 2 | Continuous | [6 empty] | N | N | 2023-04-28 14:32
8-00829556 | Completed | 2L64, KI2 2B4 OOS | Cable jacket repair | 2L64, KI2 2B4 | 2023-04-24 08:00 | 2023-04-27 15:07 | 16 | Continuous | [6 empty] | N | N | 2023-05-13 03:30
8-00813177 | Cancelled | WLT T1, 60VT1 OOS | WLT T1 - NON-ELECTRICALS, ANCHOR INSP, PIPING REPAIR WORK, 60D1 INSP | WLT T1 | 2023-04-24 08:00 | 2023-04-28 16:00 | NR | Continuous | [6 empty] | N | N | 2023-04-06 11:39
8-00793783 | Completed | 1L119, CMX T2, JHT 1B5, OYR T1, BKB T2 OOS | 138KV Disc Inspections at JHT, CBL,OYR,BKB, DMR | CBL 1B1, CBL T1, 1L119, DMR 1CB6, JHT 1B5, OYR 1B1, OYR T1, JHT 1D26, BKB T2, BKB 1B7 | 2023-04-24 08:00 | 2023-04-27 15:27 | 3 | Continuous | [6 empty] | Y | Y | 2023-04-27 15:27
8-00790657 | Cancelled | AMC 5CX1 OOS | AMC P&C Replacement: 5CX1 Deficiency Work | AMC 5CX1 | 2023-04-25 07:00 | 2023-05-05 19:00 | 5 | Continuous | [6 empty] | N | N | 2023-04-21 13:31
8-00805761 | Completed | AMC 5CX1 OOS | Minor Electrical INSP | AMC 5CX1 | 2023-04-25 08:00 | 2023-05-05 11:46 | 4 | Continuous | [6 empty] | N | N | 2023-05-05 11:46
8-00797160 | Completed | 1L122, LDY T1, HWW 1B3, PVO 1CX2, 1CX3, T4, VIT 1B10 OOS | PVO 1D24,1D1CB1, 1DCB27, 1DCB26 INSP, 1CB26 CN, VIT 1D30, 1D2CB10, 1D12CB11 INSP | PVO 1CB1, PVO 1CX2, PVO 1CX3, VIT 1B10, LDY T1, PVO T4, 1L122 | 2023-04-25 08:00 | 2023-04-28 16:51 | 3 | Continuous | [6 empty] | N | N | 2023-04-28 16:52
8-00811695 | Completed | CSQ 2CB1 OOS | CSQ 2CB1 INSP | CSQ 2CB1 | 2023-04-25 08:00 | 2023-04-27 13:19 | 2 | Continuous | [6 empty] | N | N | 2023-04-27 13:19
8-00811698 | Completed | MAN 2CB2 OOS | NERC PM | MAN 2CB2, MAN 2D1CB2, MAN 2D2CB2 | 2023-04-25 08:00 | 2023-04-25 13:29 | 2 | Continuous | [6 empty] | N | N | 2023-04-25 13:30
8-00811309 | Completed | 60L58, ARN T10, 2B11, 60B1 OOS | ARN T10 INSP & Doble | ARN T10, 60L58, ARN 2B11, ARN 60B1 | 2023-04-25 08:00 | 2023-04-28 13:09 | 4 | Continuous | [6 empty] | N | N | 2023-04-28 13:09
8-00810609 | Cancelled | HWD 1CB1 OOS | HWD 1CB1 INSP | HWD 1CB1 | 2023-04-25 08:00 | 2023-04-26 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-04-13 10:18
8-00810321 | Cancelled | 2L263, VNT 2CB2 OOS | CPC CN CA | VNT 2CB2, 2L263 (72L) | 2023-04-25 08:00 | 2023-04-25 16:00 | NR | Continuous | [6 empty] | N | N | 2023-03-23 17:21
8-00810055 | Completed | CBN 2CB5 OOS | CPC Breaker Fail protection testing | CBN 2CB5 | 2023-04-25 08:00 | 2023-04-25 15:27 | 2 | Continuous | [6 empty] | N | N | 2023-04-27 09:13
8-00806524 | Cancelled | 2L11, WLT 2B8 OOS | WLT Stn Insulator Replacement - Make temp bus cut | 2L11, WLT 2B8 | 2023-04-25 08:00 | 2023-04-25 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-01-20 09:19
8-00813180 | Cancelled | MSA T1/5B1 , 5L30 OOS | MSA 5L30 - 5D1CB6, 5D1CB3 INSP, 5SA21 BUTN | MSA T1, 5L30, MSA 5B1 | 2023-04-25 08:00 | 2023-04-29 16:00 | NR | Continuous | [6 empty] | N | N | 2023-02-07 15:23
8-00813182 | Completed | 1L35, MSA 1B4 OOS | MSA 1L35 - 1D1CB4, 1D2CB5 INSP - LOOK AT CVT | 1L35, MSA 1B4 | 2023-04-25 08:00 | 2023-04-27 14:56 | 2 | Continuous | [6 empty] | N | Y | 2023-04-27 14:57
8-00813105 | Completed | 2L40 Out from BSY, BSY 2CB9, 2CB10 OOS | BSY DS INSP | BSY 2CB10, BSY 2CB9, 2L40 | 2023-04-25 08:00 | 2023-04-28 14:05 | 4 | Continuous | [6 empty] | N | N | 2023-04-28 14:06
8-00816161 | Cancelled | 5L81 OOS | Repair on AMC 5BP1 | 5L81, AMC 5CX1 | 2023-04-25 08:00 | 2023-04-27 08:00 | 4 | Continuous | 1950 | 2350 |  |  |  |  | N | N | 2023-04-21 12:13
8-00832800 | Completed | GMS 5B12, T12, T14 outage | GMS DS Repair | GMS 5B12, GMS T12, GMS T14 | 2023-04-25 08:00 | 2023-04-27 16:28 | 2 | Continuous | [6 empty] | Y | N | 2023-04-27 16:28
8-00830701 | Completed | 2L123, SAT 2B4, HWW T1 OOS | Line insulator repl | SAT 2B4, HWW T1, 2L123 | 2023-04-25 08:00 | 2023-04-26 16:43 | 2 | Return Evenings | [6 empty] | N | N | 2023-05-13 03:30
8-00831182 | Completed | ING T7 OOS | Change cable clamps (60KV) | ING T7 | 2023-04-25 08:00 | 2023-04-27 07:56 | 2 | Continuous | [6 empty] | N | N | 2023-04-27 19:06
8-00842393 | Cancelled | AMC 5CX1 OOS | AMC P&C Replacement: 5CX1 Deficiency Work | 5L81, AMC 5CX1 | 2023-04-25 08:00 | 2023-04-27 08:00 | 4 | Continuous | 1950 | 2350 |  |  |  |  | N | N | 2023-04-21 12:45
8-00842791 | Completed | 5L76, NIC 5B14 OOS | Investigate oil leak on NIC 5CVT14 | 5L76, NIC 5B14 | 2023-04-25 08:00 | 2023-05-05 14:16 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-05-05 14:33
8-00837954 | Completed | ING T4, 12RX4 OOS | ING T4 ETM Replacement | ING 12RX4, ING T4 | 2023-04-25 08:00 | 2023-04-28 21:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-04-28 21:00
8-00788149 | Completed | WLT T3, 60B14 OOS | T3 & 60B14 Insulator Deficiency Work | WLT 60B14, WLT 60B9, WLT T3 | 2023-04-26 07:00 | 2023-05-16 14:33 | 3 | Continuous | [6 empty] | N | N | 2023-05-16 15:13
8-00806530 | Cancelled | 2L3, WLT T3, 2B3, 2B4, 2B5 OOS | Stn Insulator Replacement | 2L3, WLT 2D1CB3, WLT 2D1CB6, WLT 2B4, WLT 2B5, WLT 2B3, WLT T3 | 2023-04-26 08:00 | 2023-05-05 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-01-20 09:19
8-00810323 | Cancelled | VNT 2CB3 OOS | CPC CN CA | VNT 2CB3 | 2023-04-26 08:00 | 2023-04-26 16:00 | NR | Continuous | [6 empty] | N | N | 2023-03-23 17:26
8-00811699 | Completed | MAN 2CB3 OOS | NERC PM | MAN 2CB3, MAN 2D1CB3, MAN 2D2CB3 | 2023-04-26 08:00 | 2023-04-26 14:48 | 2 | Continuous | [6 empty] | N | N | 2023-04-26 14:48
8-00842224 | Completed | 2L10 OOS | Insulator Replacement | 2L10 | 2023-04-26 08:00 | 2023-04-27 16:14 | 2 | Continuous | [6 empty] | N | N | 2023-04-27 16:14
8-00813183 | Completed | WLT 2CB4 OOS | WLT 2CB4 CN COND. | WLT 2CB4 | 2023-04-26 08:00 | 2023-04-26 14:45 | NR | Continuous | [6 empty] | N | N | 2023-04-26 14:45
8-00812693 | Completed | SEL 2CB12, 2L289 OOS | Inspection | SEL 2CB11, SEL 2CB12, 2L289 (82L) | 2023-04-26 08:00 | 2023-04-26 16:28 | 2 | Continuous | [6 empty] | N | N | 2023-04-26 16:28
8-00810057 | Denied | CBN 2CB9 OOS | CPC Breaker Fail protection testing | CBN 2CB9 | 2023-04-26 12:00 | 2023-04-27 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-04-24 11:10
8-00839899 | Approved | 5L13 oos | WSN 5D37 trip testing | 5L13, WSN 5D37 (3), WSN 5RX7 | 2023-04-27 07:00 | 2023-04-27 08:00 | 0 | Continuous | [6 empty] | N | N | 2023-04-26 14:27
8-00831186 | Completed | ING T8 OOS | Change cable clamps (60kV) | ING T8 | 2023-04-27 08:00 | 2023-04-28 16:58 | 2 | Continuous | [6 empty] | N | N | 2023-04-28 16:58
8-00819624 | Cancelled | KLY 5CB3 OOS | KLY CB Insp & Doble testing | KLY 5CB3 | 2023-04-27 08:00 | 2023-04-28 16:00 | NR | Continuous | [6 empty] | N | N | 2023-03-07 12:30
8-00815870 | Completed | WSN 5RX7 OOS | WSN 5RX7 Non-EL PN PM | WSN 5RX7 | 2023-04-27 08:00 | 2023-04-27 14:44 | 2 | Continuous | [6 empty] | N | N | 2023-04-27 14:54
8-00811700 | Completed | MAN 2CB6 OOS | NERC PM | MAN 2CB6 | 2023-04-27 08:00 | 2023-04-27 13:09 | 2 | Continuous | [6 empty] | N | Y | 2023-04-27 13:33
8-00798992 | Completed | 2L240 OOS | Replace end of life structures and cross arms | 2L240, SAM T4 | 2023-04-28 08:00 | 2023-04-28 15:13 | 3 | Continuous | [6 empty] | Y | Y | 2023-04-28 15:22
8-00842585 | Completed | ARN 1CB2 OOS | wiring and trip testing | ARN 1CB2, GLS T1 | 2023-04-28 12:00 | 2023-04-28 16:55 | 1 | Continuous | [6 empty] | N | N | 2023-04-28 16:55
8-00833621 | Completed | GMS T13 OOS | GMS Control System Upgrade Project | GMS T13 | 2023-05-01 08:00 | 2023-05-01 15:38 | 2 | Continuous | [6 empty] | N | N | 2023-05-01 15:39
8-00813804 | Approved | DAW 1CB1 OOS | DAW 1CB1 Insp | DAW 1CB1 | 2023-05-01 08:00 | 2023-05-02 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-01 13:58
8-00819633 | Completed | HMH T6 OOS | HMH T6 Insp and Doble testing | HMH T6 | 2023-05-01 08:00 | 2023-05-11 15:45 | 12 | Continuous | [6 empty] | N | Y | 2023-05-11 15:45
8-00816171 | Completed | 5L82 OOS | AMC 5BP2 alarm fix | 5L82 | 2023-05-01 08:00 | 2023-05-19 15:18 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-05-19 15:35
8-00812615 | Completed | WSN T2, T7, 2B4, 12RX1 OOS | WSN DS Insp | WSN 12RX1, WSN T2, WSN T7, WSN 2B4 | 2023-05-01 08:00 | 2023-05-03 13:21 | 2 | Continuous | [6 empty] | N | Y | 2023-05-03 13:22
8-00813185 | Completed | 60L99 out from HCT, HCT T1 OOS | HCT T1 TFR/LTC INSP, ANCHOR INSPECTION, 12CB1 CN. COND. | HCT T1, 60L99 | 2023-05-01 08:00 | 2023-05-11 14:51 | 6 | Continuous | [6 empty] | N | Y | 2023-05-11 14:51
8-00803137 | Completed | 5L82 OOS | Replace EOL spacers | 5L82, AMC 5CX2 | 2023-05-01 08:00 | 2023-05-17 13:04 | 4 | Continuous | 2000 | 2400 | 2500 | 2500 |  |  | N | N | 2023-05-17 13:05
8-00802852 | Completed | 1L115 Out from DMR to LTZ | COB Insulator Replacements | 1L115, PVL T2, QLC T2 | 2023-05-01 08:00 | 2023-05-05 16:49 | 2 | Continuous | [6 empty] | Y | Y | 2023-05-05 16:50
8-00805369 | Cancelled | MDN T3 OOS | CPC non-ele protection testing | MDN T3 | 2023-05-01 08:00 | 2023-05-05 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-02-02 13:23
8-00793712 | Completed | 5L75 OOS | Replace end of life insulators | 5L75 | 2023-05-01 08:00 | 2023-05-05 18:33 | 3 | Continuous | [5 empty] | 1000 | Y | N | 2023-05-05 18:33
8-00810811 | Completed | VIT SC2, T5, T6, 2B2, 1B4 OOS | VIT 1D1CB5,1D2CB4,1D5, 1D6, 2D1CB2, 2D1CB3,2D5, 2D6 INSP, 1CB5 CN | VIT SC2, VIT 1B4, VIT 2B2, VIT T5, VIT T6 | 2023-05-01 08:00 | 2023-05-01 22:12 | 2 | Continuous | [6 empty] | N | N | 2023-05-19 03:30
8-00806523 | Denied | 60L270 Out from KBY to 60D1L270 | Replace Crossarms | 60L270 | 2023-05-01 08:00 | 2023-05-05 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-04-18 10:39
8-00732966 | Completed | 3L2 OOS | UHT 3D31 Repair | BRT 3B1, UHT 3B4, UHT 3RX1, 3L2, SAC T1 | 2023-05-01 10:00 | 2023-05-03 17:33 | 4 | Continuous | [6 empty] | N | N | 2023-05-19 03:30
8-00705994 | Denied | 3L2 OOS | UHT 3D31 Repai | UHT 3D21, UHT 3D31, UHT 3D1CB1, UHT 3D2CB4, 3L2, SAC T1, SAC 3D1 | 2023-05-01 10:00 | 2023-05-08 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-04-26 15:40
8-00712220 | Completed | 3L2, BRT 3B1, 3CB1, 3CB2 | BRT 3D1CB2 INSP, 3D1CB INSP,PN 3CB2 CN, PN 3CB1PN | BRT 3B1, UHT 3B4, UHT 3RX1, 3L2, SAC T1 | 2023-05-01 10:00 | 2023-05-03 17:34 | 2 | Continuous | [6 empty] | N | N | 2023-05-03 17:34
8-00636104 | Completed | 3L2, BRT 3B1 OOS | replace 3CVT1 ABC with new. Note dates are quite flexible | BRT 3B1, UHT 3B4, UHT 3RX1, 3L2, SAC T1 | 2023-05-01 10:00 | 2023-05-03 17:35 | 16 | Continuous | [6 empty] | Y | N | 2023-05-03 17:36
8-00821253 | Cancelled | BRN T2 OOS | BRN T2 Non-EL PN PM | BRN T2 | 2023-05-02 07:00 | 2023-05-02 17:00 | NR | Continuous | [6 empty] | N | N | 2023-04-27 11:18
8-00841044 | Completed | MDN 2CB15, MDN 2RX2 OOS | CPC to operate 2D13 via PNs | MDN 2RX2, MDN 2CB15 | 2023-05-02 08:00 | 2023-05-03 16:07 | 4 | Return Evenings | 2000 | 2400 |  |  |  |  | N | N | 2023-07-17 14:33
8-00819623 | Completed | KLY 5CB7 OOS | KLY CB Insp & Doble testing | KLY 5CB7 | 2023-05-02 08:00 | 2023-05-10 16:22 | NR | Continuous | [6 empty] | N | N | 2023-05-10 16:22
8-00807246 | Completed | 5L75, ACK 5B6 OOS | Replace yard flood lights | ACK 5CB6, ACK 5CB8, 5L75, ACK 5B6 | 2023-05-02 08:00 | 2023-05-02 18:05 | 8 | Continuous | [6 empty] | Y | N | 2023-05-02 18:05
8-00807584 | Cancelled | INV 60CB11, 60CB12, 60CX1 OOS | Replace yard flood lights | INV 60CB11, INV 60CB12, INV 60CX1 | 2023-05-02 08:00 | 2023-05-02 12:00 | NR | Continuous | [6 empty] | N | N | 2023-04-12 13:35
8-00812197 | Completed | JHT 1Cb2 OOS | JHT 1CB2 INSP | JHT 1CB2 | 2023-05-02 08:00 | 2023-05-03 14:32 | 2 | Continuous | [6 empty] | N | N | 2023-05-03 14:32
8-00846996 | Completed | 1L102 Out from CMX | CMX 1CVT2 forced OOS | 1L102, CMX T2 | 2023-05-02 15:42 | 2023-11-24 14:21 | NR | Continuous | [6 empty] | N | N | 2023-12-11 17:29
8-00841740 | Completed | L81-87 oos | Repair damanged conductor | L81-87 | 2023-05-03 07:00 | 2023-05-03 17:02 | NR | Continuous | [6 empty] | N | N | 2023-05-03 17:02
8-00813805 | Completed | DAW 1CB2 OOS | DAW 1CB2 Insp | DAW 1CB2 | 2023-05-03 08:00 | 2023-05-04 14:58 | NR | Continuous | [6 empty] | N | N | 2023-05-04 14:58
8-00806881 | Completed | CBK 5RX4 OOS | ETM & Surge Arrester Replacement | CBK 5RX4 | 2023-05-03 08:00 | 2023-05-19 13:14 | 24 | Continuous | [6 empty] | Y | N | 2023-05-19 13:32
8-00733011 | Completed | 3L2 OOS | Doble Testing of SAC T1, SAC 3CC1 and UHT 3CC1 | 3L2, SAC T1 | 2023-05-03 16:00 | 2023-05-08 19:50 | 6 | Continuous | [6 empty] | Y | N | 2023-05-09 12:20
8-00733390 | Completed | 3L2, BRT 3B1 OOS | Work on BRT 3D1CB2 INSP, 3D1CB INSP,PN 3CB2 CN, PN 3CB1CN | BRT 3CB1, BRT 3CB2, BRT 3B1, 3L2 | 2023-05-03 16:00 | 2023-05-04 12:32 | 2 | Continuous | [6 empty] | Y | Y | 2023-05-04 12:32
8-00847515 | Completed | 1L359 (7L81R) OOS | Forest fire damage | 1L359 (7L81R) | 2023-05-03 20:07 | 2023-10-21 15:23 | NR | Continuous | [6 empty] | N | N | 2023-10-21 15:23
8-00819621 | Cancelled | KLY 5CB4 OOS | KLY CB Insp & Doble testing | KLY 5CB4 | 2023-05-04 08:00 | 2023-05-05 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-05-07 18:00
8-00812607 | Completed | GMS 5B1 OOS | GMS CB, DS Insp & Doble testing | GMS 5B1, GMS 5CB1, GMS 5CB2, GMS 5D1CB1, GMS 5D1CB2 | 2023-05-04 08:00 | 2023-05-09 18:22 | NR | Continuous | [6 empty] | Y | N | 2023-05-09 18:22
8-00812616 | Completed | WSN T2, 5B11, 12RX1 OOS | WSN DS Insp | WSN 12RX1, WSN 2CB6, WSN 5B11, WSN T2 | 2023-05-08 08:00 | 2023-05-12 20:38 | 4 | Continuous | [6 empty] | N | Y | 2023-05-28 03:30
8-00813186 | Completed | MSA 5RX1 OOS | MSA 5RX1 NON-ELECTRICALS NERC, PY/SY PN. - | MSA 5RX1 | 2023-05-08 08:00 | 2023-05-09 15:37 | NR | Return Evenings | [6 empty] | N | N | 2023-05-09 15:37
8-00821251 | Completed | BRN T2 OOS | BRN T2 INSP & Doble testing | BRN T2 | 2023-05-08 08:00 | 2023-05-19 16:21 | 4 | Continuous | [6 empty] | N | N | 2023-05-19 16:22
8-00663796 | Cancelled | 2L50 OOS | Detailed & Oil Sample | 2L50 | 2023-05-08 08:00 | 2023-05-12 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-01-16 11:53
8-00795060 | Cancelled | 5L29 OOS | DMR, TIR CCB, MSA Cable PM | 5L29 | 2023-05-08 08:00 | 2023-05-21 16:00 | NR | Continuous | [6 empty] | N | N | 2023-04-18 07:08
8-00795083 | Completed | 5L29, DMR 5B14, 5MB2 OOS | DMR 5L29 - 5D1&D2CB24, 5CT24 INSP | 5L29, DMR 5RX1, DMR 5RX2, DMR 5RX3, DMR 5RX4, DMR 5MB2, DMR 5B14 | 2023-05-08 08:00 | 2023-05-21 09:56 | 4 | Continuous | [6 empty] | N | N | 2023-06-06 03:30
8-00795086 | Completed | 5L29 OOS | TIR 5RX1,2,3,11,12,13,21,22,23 NETS, RX11 Swagelok | TIR 5RX1, TIR 5RX11, TIR 5RX12, TIR 5RX13, TIR 5RX2, TIR 5RX21, TIR 5RX22, TIR 5RX23, TIR 5RX3, 5L29 | 2023-05-08 08:00 | 2023-05-21 09:56 | 6 | Continuous | [6 empty] | N | N | 2023-05-21 09:59
8-00797192 | Denied | VIT SC2 OOS | SC2 BRUSHGEAR & 4kV | VIT SC2 | 2023-05-08 08:00 | 2023-05-19 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-04 12:43
8-00807592 | Proposed | DUG T1 OOS | ETM Replacement | DUG T1 | 2023-05-08 08:00 | 2023-05-12 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-14 20:04
8-00811833 | Completed | DMR 5RX1 OOS | DMR 5CB51, 5RX1 INSP | DMR 5RX1, DMR 5CB51 | 2023-05-08 08:00 | 2023-05-15 19:09 | 2 | Continuous | [6 empty] | N | N | 2023-05-31 03:30
8-00811835 | Completed | DMR 5RX3 OOS | DMR 5RX3 INSP | DMR 5RX3 | 2023-05-08 08:00 | 2023-05-15 19:09 | 6 | Continuous | [6 empty] | N | N | 2023-05-31 03:30
8-00845935 | Completed | 60L301 Out from HMH, HMH T6, 60B11 OOS | Install drops for 60CB12 replacement | 60L301, HMH 60CB12, HMH T6, HMH 60B11 | 2023-05-08 09:00 | 2023-05-08 17:26 | 1 | Continuous | [6 empty] | N | N | 2023-05-16 07:27
8-00762801 | Cancelled | BSY G3 OOS | BSY G3 Maintenance | BSY T3, BSY G3 | 2023-05-09 01:00 | 2023-05-12 23:00 | 96 | Continuous | [6 empty] | N | N | 2023-03-23 16:20
8-00790666 | Completed | AMC 5CX2 OOS | AMC P&C Replacement: 5CX2 Deficiency Work | 5L82, AMC 5CX2 | 2023-05-09 07:00 | 2023-05-19 15:10 | 7 | Continuous | [6 empty] | N | N | 2023-05-20 15:12
8-00793371 | Completed | 5L29 OOS | Planned maintenance of pumping plants | 5L29 | 2023-05-09 08:00 | 2023-05-21 09:56 | 2 | Continuous | [6 empty] | N | N | 2023-05-21 09:59
8-00806003 | Completed | 2L32, CSQ 2B1 OOS | CSQ DS INSP | 2L32, CSQ 2B1 | 2023-05-09 08:00 | 2023-05-10 14:18 | 2 | Continuous | [6 empty] | N | N | 2023-05-10 14:18
8-00801125 | Cancelled | 2L32 OOS | Detailed Inspection | 2L32 | 2023-05-09 08:00 | 2023-05-12 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-05-03 09:01
8-00810620 | Completed | HWW 1CB12 OOS | HWW 1CB12 CN NERC | HWW 1CB12 | 2023-05-09 08:00 | 2023-05-09 11:49 | 2 | Continuous | [6 empty] | N | N | 2023-05-09 11:49
8-00809127 | Completed | 60L39 Out from BND | VT INSP, Doble Test | BND 60CB3, 60L39, BND 60CB5, BND 60CB4 | 2023-05-09 08:00 | 2023-05-09 15:52 | 4 | Continuous | [6 empty] | N | N | 2023-05-09 15:53
8-00819620 | Cancelled | KLY 5CB17 OOS | KLY CB Insp & Doble testing | KLY 5CB17 | 2023-05-09 08:00 | 2023-05-10 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-05-08 12:46
8-00819048 | Completed | SKA 2RX1 OOS | SKA 2RX1 Insp | SKA 2RX1 | 2023-05-09 08:00 | 2023-05-12 13:04 | NR | Continuous | [6 empty] | N | N | 2023-05-12 13:04
8-00810629 | Completed | HWW 1Cb4 OOS | HWW 1CB4 CN NERC | HWW 1CB4 | 2023-05-09 12:00 | 2023-05-09 13:56 | 2 | Continuous | [6 empty] | N | N | 2023-05-09 13:56
8-00793715 | Completed | 5L77 OOS | Replace end of life insulators | 5L77 | 2023-05-09 20:00 | 2023-05-12 10:18 | 3 | Continuous |  |  |  |  | 850 | 1000 | Y | N | 2023-05-12 10:18
8-00800859 | Completed | 60L40, 60L54 Out from BND | BND DS VT INSP | 60L40, BND 60CB2, BND 60CB3, BND 60CB6, 60L54 | 2023-05-10 08:00 | 2023-05-11 15:00 | 4 | Continuous | [6 empty] | N | N | 2023-05-11 15:00
8-00818862 | Proposed | SKA T2, 12RX2 OOS | SKA 5CB12 PN CN | SKA 12RX2, SKA 5CB12, SKA T2 | 2023-05-10 08:00 | 2023-05-10 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-04 14:53
8-00813212 | Completed | MR2 T1 OOS | CPC NON EL | MR2 T1 | 2023-05-10 08:00 | 2023-05-10 14:10 | NR | Continuous | [6 empty] | N | N | 2023-05-10 14:10
8-00849851 | Completed | SYA 5CX1 Forced OOS | Forced out | SYA 5CX1 | 2023-05-10 12:00 | 2023-05-24 13:59 | NR | Continuous | [6 empty] | Y | N | 2023-05-24 14:02
8-00840539 | Completed | ING T5 and ING 5B10 OOS | ING 5D5 motor replacement | ING T5, ING 5B10, ING 12RX5 | 2023-05-11 08:00 | 2023-05-12 17:17 | 2 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | 2023-05-12 17:17
8-00819619 | Cancelled | KLY 5CB14 OOS | KLY CB Insp & Doble testing | KLY 5CB14 | 2023-05-11 08:00 | 2023-05-12 16:00 | NR | Continuous | [6 empty] | N | N | 2023-03-07 07:56
8-00819614 | Completed | KLY 5CB1 OOS | KLY CB INSP and DOBL | KLY 5CB1 | 2023-05-11 08:00 | 2023-05-12 14:09 | 4 | Continuous | [6 empty] | N | N | 2023-05-12 15:44
8-00805765 | Approved | AMC 5CX2 OOS | Minor Electrical Insp | 5L82, AMC 5CX2 | 2023-05-11 08:00 | 2023-05-19 16:00 | 8 | Continuous | [6 empty] | N | N | 2023-05-10 10:49
8-00706848 | Completed | 1L143 JOR T1 OOS | JOR OSP Step 16 | CLD T2, JOR T1, 1L143, JOR 1B1 | 2023-05-11 08:00 | 2023-07-24 08:24 | 2 | Continuous | [6 empty] | N | N | 2023-07-24 08:25
8-00810636 | Completed | HWW 1CB5 OOS | HWW 1CB5 CN NERC | HWW 1CB5 | 2023-05-11 08:00 | 2023-05-11 11:46 | 2 | Continuous | [6 empty] | N | N | 2023-05-11 11:46
8-00807608 | Proposed | VBY T1 OOS | T1 ETM Replacement | VBY T1 | 2023-05-11 08:00 | 2023-06-22 16:00 | NR | Continuous | [6 empty] | N | Y | 2023-01-14 20:36
8-00806501 | Completed | MUR T5 and MUR 2B5 OOS | PCB Bushing Replacement | MUR T5, MUR 2B5, MUR 2B6 | 2023-05-13 08:00 | 2023-06-26 16:15 | 8 | Continuous | [6 empty] | N | N | 2023-07-12 03:30
8-00806493 | Completed | BND T1 OOS | BND T1 ETM Replacement | BND T1 | 2023-05-15 08:00 | 2023-05-23 15:53 | 4 | Continuous | [6 empty] | N | Y | 2023-05-23 15:57
8-00807463 | Completed | MLS 5CX1 OOS | CX Insp | MLS 5CX1 | 2023-05-15 08:00 | 2023-05-18 18:01 | 4 | Continuous | [6 empty] | N | N | 2023-05-18 18:02
8-00809658 | Completed | ACK T2, 5B2 OOS | T2 INSP and DOBLE | ACK 5B2, ACK 5CB2, ACK 5CB3, ACK T2 | 2023-05-15 08:00 | 2023-05-18 14:17 | 8 | Continuous | [6 empty] | Y | N | 2023-05-18 14:17
8-00797158 | Cancelled | 1L116, LTZ 1B3, 1CVT2, NFD T1 OOS | LTZ 1CVT2 INSP | 1L116, LTZ 1B3, NFD T1 | 2023-05-15 08:00 | 2023-05-15 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-06 11:33
8-00798996 | Completed | 2L255 OOS | Replace end of life structures and cross arms | 2L255 | 2023-05-15 08:00 | 2023-05-17 19:53 | 4 | Continuous | [6 empty] | Y | N | 2023-05-17 19:53
8-00818860 | Approved | SKA T1, 12RX1 OOS with SKA RAS PY/SY OOS OAT | SKA 5CB2 PN CN | SKA 12RX1, SKA 5CB2, SKA T1 | 2023-05-15 08:00 | 2023-05-15 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-11 16:01
8-00818635 | Completed | SKA 12RX1 OOS | SKA 12RX1 Bushing Repl | SKA 12RX1 | 2023-05-15 08:00 | 2023-06-16 13:37 | 120 | Continuous | [6 empty] | N | N | 2023-06-16 13:37
8-00813706 | Completed | CSQ 2CB2, 2B2 OOS | NERC PM | CSQ 2CB2, CSQ 2B2 | 2023-05-15 08:00 | 2023-05-15 15:06 | 2 | Continuous | [6 empty] | N | N | 2023-05-15 17:06
8-00813240 | Completed | HCT T2, 12CB2 OOS | HCT 12CB2 BFPN, HCT T2 Fall arrest anchor inspection | HCT T2, 60L65 | 2023-05-15 08:00 | 2023-05-15 15:36 | NR | Continuous | [6 empty] | N | N | 2023-05-15 15:37
8-00813241 | Completed | MSA 2CB8 OOS | MSA 2CB8 INSP + CN. COND. NERC | MSA 2CB8 | 2023-05-15 08:00 | 2023-05-18 16:59 | NR | Continuous | [6 empty] | N | N | 2023-05-18 16:59
8-00812801 | Cancelled | 60L270, KBY 60CB2, 60D1CB2 OOS | Inspections & doble | 60L270, KBY 60CB2 | 2023-05-15 08:00 | 2023-05-18 16:00 | 6 | Continuous | [6 empty] | N | N | 2023-05-08 08:14
8-00849811 | Completed | VIT SC2 OOS | Inspection | VIT SC2 | 2023-05-15 08:00 | 2023-05-17 16:07 | 1 | Return Evenings | 2000 | 2400 |  |  |  |  | N | N | 2023-05-17 16:07
8-00848366 | Completed | 2L126, SAT 2B2 OOS | DS Maintenance at SAT | 2L126, SAT 2B2 | 2023-05-15 08:00 | 2023-05-16 12:57 | 2 | Continuous | [6 empty] | N | N | 2023-06-01 03:30
8-00807606 | Completed | NAK T2 OOS | PCB Bushing Replacement | NAK T2 | 2023-05-15 10:30 | 2023-06-19 15:04 | 120 | Continuous | [6 empty] | N | N | 2023-06-19 15:04
8-00819058 | Cancelled | SKA 2CB7 OOS with SKA RAS PY/SY OOS OAT | SKA 2CB7 PN CN | SKA 2CB7 | 2023-05-16 07:00 | 2023-05-16 13:00 | 0 | Continuous | [6 empty] | N | N | 2023-05-15 15:35
8-00819275 | Cancelled | KLY 5CB3 OOS | CPC CB NERC PM | KLY 5CB3 | 2023-05-16 08:00 | 2023-05-16 16:00 | NR | Continuous | [6 empty] | N | N | 2023-03-02 14:00
8-00812741 | Completed | 60L290, ELK 60CB4, 60D2CB4 OOS | Inspection | ELK 60CB4, 60L290 | 2023-05-16 08:00 | 2023-05-18 10:34 | 3 | Continuous | [6 empty] | N | N | 2023-05-18 10:34
8-00847170 | Completed | 5L7 OOS | KDY 5CVT13 trouble shooting | 5L7 | 2023-05-16 08:00 | 2023-05-17 11:53 | 4 | Continuous | [6 empty] | Y | N | 2023-05-17 14:34
8-00805895 | Completed | ING 5CB12 OOS | NERC CPC Breaker Fail Testing | ING 5CB12 | 2023-05-16 08:00 | 2023-05-18 15:44 | 2 | Continuous | [6 empty] | Y | N | 2023-05-18 15:44
8-00805382 | Completed | MDN 5CB3 OOS | CPC Control Testing | MDN 5CB2, MDN 5CB3 | 2023-05-16 08:00 | 2023-05-17 15:51 | 2 | Continuous | [6 empty] | N | N | 2023-11-07 20:10
8-00819062 | Cancelled | SKA 2CB8 OOS | SKA 2CB8 PN CN | SKA 2CB8 | 2023-05-16 13:01 | 2023-05-16 19:00 | 0 | Continuous | [6 empty] | N | N | 2023-05-15 14:01
8-00788511 | Completed | WLT 60B1 OOS, 60L92 feeds 60L90 via bypass outside at WLT | Replace 60B1 Insulators | 60L90, WLT 60B1 | 2023-05-17 07:00 | 2023-05-31 09:05 | 3 | Continuous | [6 empty] | N | N | 2023-06-16 03:30
8-00819277 | Cancelled | KLY 5CB1 OOS | KLY CPC CB NERC PM | KLY 5CB1 | 2023-05-17 08:00 | 2023-05-17 16:00 | NR | Continuous | [6 empty] | N | N | 2023-03-02 14:01
8-00847272 | Completed | 60L66 ouit from CAP | Install NEW 69kv Bushings at Capilano | 60L66 | 2023-05-17 08:00 | 2023-05-23 17:17 | 4 | Continuous | [6 empty] | N | N | 2023-05-23 17:17
8-00847748 | Completed | BR1 T3 OOS | Testing on T3 | BR1 T3 | 2023-05-17 12:00 | 2023-05-26 13:15 | 8 | Continuous | [6 empty] | N | N | 2023-05-26 13:15
8-00796929 | Completed | 60L21 Out from SON, 60L20 out from SON | SON CB/DS/IT Replacement (JB) Bypass OSP Rev 3 Step #9 | 60L21, 60L20, SON 60CB21, SON 60CB22, SON T2, SON T3, SON 60B1 | 2023-05-17 19:00 | 2023-05-18 01:02 | 4 | Continuous | [6 empty] | N | N | 2023-05-18 01:02
8-00810781 | Cancelled | MON 1CB1 OOS | NERC PM | MON 1CB1 | 2023-05-18 08:00 | 2023-05-18 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-05-20 18:00
8-00812089 | Completed | CSN 2CB4 OOS | NERC PM | CSN 2CB4 | 2023-05-18 08:00 | 2023-05-18 14:53 | 2 | Continuous | [6 empty] | N | N | 2023-05-18 14:54
8-00848147 | Completed | UHT 3CB3 OOS | Oil top up and engineering to inspect while on site | UHT 3CB3 | 2023-05-18 08:00 | 2023-05-18 16:39 | 2 | Continuous | [6 empty] | N | N | 2023-05-18 16:39
8-00846928 | Completed | UHT 3RX4 OOS | Troubleshoot UHT 3CB34 hydraulic pump cycling | UHT 3CB34, UHT 3RX4 | 2023-05-18 08:00 | 2023-05-18 17:19 | 3 | Continuous | [6 empty] | N | N | 2023-05-19 15:59
8-00815872 | Completed | WSN T5 OOS | WSN T5 Insp and Doble testing | WSN T5 | 2023-05-19 08:00 | 2023-06-02 15:25 | 6 | Continuous | [6 empty] | N | N | 2023-06-02 15:25
8-00810361 | Completed | SVA T1 OOS | TFR and LTC INSP | SVA T1 | 2023-05-19 08:00 | 2023-06-01 12:18 | 4 | Continuous | [6 empty] | N | N | 2023-06-17 03:30
8-00810885 | Denied | VIT T5 OOS | VIT T5 INSP, DOBL & ANCHOR CERT | VIT SC2, VIT T5 | 2023-05-22 08:00 | 2023-05-26 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-05-16 12:06
8-00807607 | Cancelled | RDM T1 OOS | PCB Bushing Replacement | RDM T1 | 2023-05-22 08:00 | 2023-06-30 16:00 | NR | Continuous | [6 empty] | N | Y | 2023-10-23 08:17
8-00793372 | Cancelled | 5L31 OOS | Planned maintenance of pumping plants | 5L31 | 2023-05-22 08:00 | 2023-06-03 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-05-09 11:47
8-00795092 | Cancelled | 5L31 OOS | DMR, TIR CCB, MSA Cable PM | 5L31 | 2023-05-22 08:00 | 2023-06-03 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-03 16:22
8-00795097 | Completed | 5L31 OOS | DMR 5L31 - 5RX7 INSP & NETS | DMR 5RX7 | 2023-05-22 08:00 | 2023-05-26 17:06 | 6 | Continuous | [6 empty] | N | N | 2023-05-26 17:09
8-00819288 | Cancelled | KLY 5CB2 OOS | KLY CB INSP and DOBL | KLY 5CB2 | 2023-05-22 08:00 | 2023-05-23 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-24 11:26
8-00813262 | Completed | MSA 5RX2 OOS | MSA 5RX2 NON-ELECTRICALS NERC, PY/SY PN. - | MSA 5RX2 | 2023-05-22 08:00 | 2023-05-24 16:46 | NR | Return Evenings | [6 empty] | N | N | 2023-06-14 06:20
8-00842947 | Completed | 5L31 OOS | DMR 5D24 BEARING REPLACEMENT/TIR DS INSPs/maintenance of pumping plants | 5L31, DMR 5D24 (3), DMR 5RX5, DMR 5RX6, DMR 5RX8, DMR 5MB1 | 2023-05-22 08:00 | 2023-05-24 08:31 | 6 | Continuous | [6 empty] | N | N | 2023-05-24 08:31
8-00844436 | Completed | 5L42 OOS | CRK 5BP1 repair | 5L42, CRK 5CX1 | 2023-05-23 08:00 | 2023-06-02 16:16 | 3 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-06-02 16:22
8-00805385 | Completed | MDN 5CB5 OOS | CPC Control Testing | MDN 5CB5 | 2023-05-23 08:00 | 2023-05-24 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-05-30 08:43
8-00805942 | Completed | MLN T5, 2B6 OOS | MLN 2D5, 60D5 & 60CVT5 INSPs | MLN T2, MLN 2B6, MLN T5 | 2023-05-23 08:00 | 2023-05-26 14:05 | 2 | Continuous | [6 empty] | N | N | 2023-05-26 14:06
8-00805888 | Completed | ING 5CB4 OOS | NERC CPC Breaker Fail Testing | ING 5CB4 | 2023-05-23 08:00 | 2023-05-25 15:09 | 2 | Continuous | [6 empty] | N | N | 2023-05-25 15:13
8-00801123 | Completed | 2L20 OOS | Detailed inspection | 2L20 | 2023-05-23 08:00 | 2023-05-26 13:58 | 2 | Continuous | [6 empty] | Y | N | 2023-05-26 13:58
8-00800862 | Completed | 60L35 Out from BND | BND DS CB INSP | BND 60CB5, 60L35, BND 60CB10, BND 60CB4 | 2023-05-23 08:00 | 2023-05-24 15:23 | 4 | Continuous | [6 empty] | N | N | 2023-05-24 15:23
8-00798975 | Completed | 5L72 OOS | Replace Circuit End of Llife Spacers and Insulators | 5L72 | 2023-05-23 08:00 | 2023-06-06 14:14 | 4 | Continuous | [6 empty] | N | N | 2023-06-06 14:14
8-00803142 | Completed | 5L42 OOS | Replace EOL insulators | 5L42, CRK 5CX1 | 2023-05-23 08:00 | 2023-06-02 16:16 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-06-02 16:22
8-00807464 | Completed | MLS 5CX2 OOS | CX Insp | MLS 5CX2 | 2023-05-23 08:00 | 2023-06-05 13:38 | 4 | Continuous | [6 empty] | N | N | 2023-06-05 13:38
8-00806538 | Cancelled | 2L11, WLT 2B8 OOS | WLT Stn Insulator Replacement - Make temp bus cut | 2L11, WLT 2B8 | 2023-05-23 08:00 | 2023-05-23 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-01-20 09:18
8-00811231 | Completed | CBL T2 OOS | CBL T2 BUSHING REPLACEMENT | CBL T2 | 2023-05-23 08:00 | 2023-07-10 17:04 | 120 | Continuous | [6 empty] | N | N | 2023-07-26 03:30
8-00812082 | Completed | MUR 2CB1 OOS | MUR 2CB1 Insp | MUR 2CB1 | 2023-05-23 08:00 | 2023-05-25 15:44 | 2 | Continuous | [6 empty] | N | N | 2023-05-25 15:44
8-00810326 | Completed | VNT T4 OOS | NON EL PM | VNT T4 | 2023-05-24 08:00 | 2023-05-24 13:48 | 2 | Continuous | [6 empty] | N | N | 2023-05-24 13:48
8-00809115 | Completed | 60L26 OOS | BND 60D27 Inspection | BND 60CB13, BND 60CB15, 60L26 | 2023-05-24 08:00 | 2023-05-25 14:51 | 4 | Continuous | [6 empty] | N | N | 2023-05-25 14:51
8-00808884 | Completed | 1L348, BMT 1B2 OOS | BMT DS, CVT and SS Insp | BMT 1B2, 1L348 | 2023-05-24 08:00 | 2023-05-24 17:03 | 2 | Continuous | [6 empty] | N | N | 2023-05-24 17:03
8-00795094 | Completed | 5L31 OOS | TIR 5D4,5,6,14,15,16,24,25,26 INSP | 5L31 | 2023-05-24 08:00 | 2023-06-03 14:56 | 4 | Continuous | [6 empty] | N | N | 2023-06-03 14:59
8-00797157 | Cancelled | 1L115 from DMR to LTZ OOS | LTZ 1CB1 BFPN | 1L115, LTZ 1CB1 | 2023-05-24 08:00 | 2023-05-24 12:00 | NR | Continuous | [6 empty] | N | N | 2023-02-07 14:48
8-00706889 | Completed | JOR T1/T2 OOS | JOR OSP Step 18 | JOR T1, JOR T2 | 2023-05-24 08:00 | 2023-10-03 11:47 | NR | Continuous | [6 empty] | Y | N | 2023-10-03 11:47
8-00819628 | Completed | KLY 5RX2 OOS | KLY 5RX2 NERC PM and Leak Repairs | KLY 5RX2 | 2023-05-24 08:00 | 2023-05-26 13:03 | NR | Continuous | [6 empty] | N | N | 2023-05-26 13:04
8-00797177 | Completed | 2L142, GTP 1L12, T14, T11, 1B1 OOS | GTP 1D11 INSP, GTP 1DCB14 INSP, GTP 1D1CB1 INSP, GTP 1CVT1 INSP | 1L12, GTP T11, GTP T14, 2L142 | 2023-05-25 08:00 | 2023-05-26 14:49 | 4 | Continuous | [6 empty] | N | N | 2023-05-26 17:11
8-00808887 | Completed | 1L348, DAW 1B2 OOS | DAW DS, CVT Insp | 1L348, DAW 1B2 | 2023-05-25 08:00 | 2023-05-25 15:29 | 2 | Continuous | [6 empty] | N | N | 2023-05-25 15:29
8-00810327 | Completed | VNT T5 OOS | NON EL PM | VNT T5 | 2023-05-25 08:00 | 2023-05-25 12:54 | 2 | Continuous | [6 empty] | N | N | 2023-05-25 12:54
8-00800861 | Completed | 60L17 Out from BND | VT INSP | BND 60CB12, BND 60CB13, 60L17 | 2023-05-26 08:00 | 2023-05-26 14:45 | 2 | Continuous | [6 empty] | N | N | 2023-05-26 14:45
8-00849333 | Denied | ING 230KV RX Equipment OOS | ING RX/CX Neutral INSP | ING 2RX2, ING 2CX2, ING 2RX1, ING 2CX31, ING 2CX32, ING 2CX11, ING 2RX32, ING 2RX31 | 2023-05-26 08:00 | 2023-05-26 16:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-05-23 10:54
8-00852984 | Completed | PCN 5RX1 oos | Gas top-up | PCN 5RX1 | 2023-05-26 10:00 | 2023-05-26 13:58 | 1 | Continuous | [6 empty] | N | N | 2023-05-26 13:59
8-00802857 | Completed | 1L157, BVC, MRH, RRH OOS | End of Life Structure Replacements | 1L157 | 2023-05-28 07:00 | 2023-05-28 17:52 | NR | Continuous | [6 empty] | N | N | 2023-05-28 18:21
8-00794324 | Completed | 1L157 OOS | KGH 1D2CB6 Repair | 1L125, 1L130, 1L137, KGH 1B1, KGH 1B2, KGH 1B4, JUL T1, 1L141, 1L157, 1L158 | 2023-05-28 07:00 | 2023-05-28 18:23 | 4 | Continuous | [6 empty] | Y | N | 2023-06-13 03:30
8-00794325 | Cancelled | 1L157, 1L130, 1L125, KGH 1B1, KGH 1B2 OOS | Line work | 1L125, 1L130, KGH 1B1, KGH 1B2, 1L157 | 2023-05-29 08:00 | 2023-05-29 18:00 | NR | Continuous | [6 empty] | N | N | 2023-03-21 13:50
8-00797179 | Completed | 2L142, GTP T14, 1CB14 OOS | GTP T14 NON-EL/INSP/DOBL, GTP 1CB14 INSP, GTP 1CVT14 INSP, GTP 2CVT14 INSP, GTP 2DCB14 INSP | GTP T14, 2L142 | 2023-05-29 08:00 | 2023-05-31 18:35 | NR | Continuous | [6 empty] | N | N | 2023-06-16 03:30
8-00802858 | Completed | 1L137 OOS | End of Life Structure Replacements | 1L137, 1L141 | 2023-05-29 08:00 | 2023-06-01 18:23 | 2 | Continuous | [6 empty] | N | N | 2023-06-01 18:24
8-00805841 | Implemented | CHP 5CX1 Forced OOS | Forced outage | CHP 5CX1 | 2023-05-29 08:00 | 2025-12-31 16:00 | 8 | Continuous | [6 empty] | N | N | 2024-04-10 12:21
8-00810889 | Completed | VIT T6 OOS | VIT T6 INSP, DOBL & ANCHOR CERT | VIT T6 | 2023-05-29 08:00 | 2023-06-02 17:20 | 2 | Continuous | [6 empty] | N | N | 2023-06-02 17:20
8-00809117 | Completed | 60L36, 60L1 Out from BND | DS INSP | BND 60CB12, BND 60CX1, 60L36, BND 60CB10, 60L1 | 2023-05-29 08:00 | 2023-05-30 15:50 | 4 | Continuous | [6 empty] | N | N | 2023-05-30 15:50
8-00809662 | Completed | ACK T3 OOS | T3 INSP and DOBLE | ACK T3 | 2023-05-29 08:00 | 2023-06-01 10:30 | 8 | Continuous | [6 empty] | Y | N | 2023-06-01 10:30
8-00833615 | Completed | 2L314, DKW oos | DKT DS Insp | DKT 2B3, 2L314 | 2023-05-29 08:00 | 2023-05-30 16:45 | 2 | Continuous | [6 empty] | Y | N | 2023-05-30 16:45
8-00819091 | Cancelled | 60L390 OOS | Transmission line splices | 60L390 | 2023-05-29 08:00 | 2023-06-02 18:00 | NR | Continuous | [6 empty] | N | N | 2023-05-23 10:32
8-00815873 | Completed | WSN T5, 60CB6, 60CB11, 60CB16 OOS | WSN 60kV DS Insp | WSN 60CB11, WSN 60CB16, WSN 60CB6, WSN T5 | 2023-05-29 08:00 | 2023-06-06 06:07 | 4 | Return Evenings | [6 empty] | N | N | 2023-08-23 17:24
8-00813283 | Completed | 1L35 Out From SEC, SEC 1B3, T1 OOS | SEC T1 - NON-ELECTRICALS, 1CB11 BFPN NERC, 1D11 ROTATING INSULATOR BEARING LEAK | SEC T1, 1L35, SEC 1B3 | 2023-05-29 08:00 | 2023-05-31 15:15 | 2 | Continuous | [6 empty] | N | N | 2023-05-31 15:16
8-00812717 | Completed | CBK 2MB4, T3, T7 OOS | Inspection | CBK T7, CBK 2MB4 | 2023-05-29 08:00 | 2023-06-01 11:50 | 3 | Continuous | [6 empty] | N | N | 2023-06-01 11:51
8-00812459 | Proposed | 2L95 OOS | 2L95 OOS for Structure Repl | 2L95 | 2023-05-29 08:00 | 2023-06-02 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-26 13:39
8-00812464 | Proposed | 2L95 OOS | RBF 2CVT2 Insp | 2L95 | 2023-05-29 08:00 | 2023-05-29 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-23 10:38
8-00855015 | Completed | BQN 2CX1 oos | Capthor Top Up | BQN 2CX1 | 2023-05-29 10:00 | 2023-05-29 16:04 | 2 | Continuous | [6 empty] | Y | N | 2023-05-29 16:04
8-00812775 | Cancelled | 60L270, INV 60CB11, 60CB12 OOS | Disconnect inspections | INV 60CB11, INV 60CB12, 60L270 | 2023-05-30 08:00 | 2023-05-31 16:00 | NR | Continuous | [6 empty] | N | N | 2023-04-11 10:04
8-00807582 | Completed | KHS T2 OOS | Non-Electrcal testing - NERC PM | KHS T2 | 2023-05-30 08:00 | 2023-05-31 08:09 | 3 | Continuous | [6 empty] | N | N | 2023-05-31 08:09
8-00805890 | Completed | ING 5CB7 OOS | NERC CPC Breaker Fail Testing | ING 5CB7 | 2023-05-30 08:00 | 2023-06-01 15:58 | 2 | Continuous | [6 empty] | N | N | 2023-06-01 15:58
8-00805386 | Completed | MDN 5CB6 OOS | CPC Control Testing | MDN 5CB6 | 2023-05-30 08:00 | 2023-05-31 15:42 | 2 | Continuous | [6 empty] | N | N | 2023-11-07 20:06
8-00788513 | Completed | 60L92, WLT 60B3 OOS | WLT OSP Step 18 | 60L92, WLT 60CB1, WLT 60B3 | 2023-05-31 08:00 | 2023-06-15 08:00 | 3 | Continuous | [6 empty] | N | N | 2023-07-01 03:30
8-00806956 | Completed | SEL 5RX3, 5CB43 OOS | BFPN testing and Non-electrical testing(NERC) | SEL 5RX3 | 2023-05-31 08:00 | 2023-06-02 09:59 | 3 | Continuous | [6 empty] | N | N | 2023-06-02 10:03
8-00855619 | Completed | 5L31 and DMR 5MB1 OOS | FLAR JB modification | 5L31, DMR 5RX5, DMR 5RX6, DMR 5RX7, DMR 5RX8, DMR 5MB1 | 2023-05-31 08:00 | 2023-06-02 16:20 | 1 | Return Evenings | [6 empty] | N | N | 2023-06-18 03:30
8-00807263 | Denied | NIC T3 OOS | Pre-Assessment for bushing replacement | NIC T3 | 2023-06-01 07:00 | 2023-06-01 16:00 | 0 | Continuous | [6 empty] | N | N | 2023-05-29 11:44
8-00707771 | Cancelled | VIT SC3 | H2 EXCITER UPGRADES | VIT SC3 | 2023-06-01 08:00 | 2023-12-15 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-01-13 12:33
8-00813282 | Completed | JLN T2 OOS | JLN T2 TFR/LTC INSP, DOBLE, NON-ELECTRICALS | JLN T2 | 2023-06-01 08:00 | 2023-06-02 14:31 | 2 | Continuous | [6 empty] | N | N | 2023-06-02 14:31
8-00805212 | Completed | 2L51 OOS, BND T2 OOS | CPC non-ele PN testing, ele inspection | BND T2 | 2023-06-02 08:00 | 2023-06-20 13:57 | 48 | Continuous | [6 empty] | N | Y | 2023-06-20 13:57
8-00801122 | Completed | 2L31 OOS | Detailed inspection | 2L31 | 2023-06-05 08:00 | 2023-06-08 09:49 | 2 | Continuous | [6 empty] | N | N | 2023-06-08 10:02
8-00659412 | Completed | 5L61 OOS | PGTC - Prince George to Terrace Capacitors | 5L61 | 2023-06-05 08:00 | 2023-06-09 15:50 | 16 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | 2023-06-09 15:50
8-00813173 | Cancelled | 60L92, WLT 60B3 OOS | WLT 60L92 - 60D1CB4, 60D2CB3 INSP | 60L92, WLT 60B3 | 2023-06-05 08:00 | 2023-06-06 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-08 18:00
8-00812723 | Completed | NTL T3 OOS | Tap changer inspections and doble testing | NTL T3 | 2023-06-05 08:00 | 2023-06-15 19:30 | 48 | Continuous | [6 empty] | N | N | 2023-06-22 17:24
8-00812470 | Proposed | 2L352 OOS | Structure Repl | 2L352 | 2023-06-05 08:00 | 2023-06-14 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-26 13:47
8-00812618 | Completed | WSN 5CB15 OOS | CB Insp & Doble testing | WSN 5CB15 | 2023-06-05 08:00 | 2023-06-14 15:06 | 2 | Continuous | [6 empty] | N | N | 2023-06-14 15:06
8-00812608 | Completed | GMS 5B12, T12, T14 oos | GMS DS Insp | GMS 5B12, GMS T12, GMS T14 | 2023-06-05 08:00 | 2023-06-07 14:16 | NR | Continuous | [6 empty] | N | N | 2023-06-07 14:16
8-00812612 | Completed | WSN T4, 12RX2 oos | WSN T4 Insp and install ETM | WSN 12RX2, WSN 2CB7, WSN T4 | 2023-06-05 08:00 | 2023-06-16 14:39 | 4 | Continuous | [6 empty] | N | N | 2023-06-16 14:39
8-00815876 | Denied | SCK 2CB1 OOS | SCK CB PN PM | SCK 2CB1 | 2023-06-05 08:00 | 2023-06-05 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-25 13:59
8-00805384 | Cancelled | MDN 5CB4 OOS | CPC Control Testing | MDN 5CB4 | 2023-06-05 10:00 | 2023-06-07 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-06-09 18:00
8-00819073 | Cancelled | 60L393, OFD T1, T4 OOS | OFD DS, VT Insp & 60D21 Repair | 60L393, OFD T1, OFD T4 | 2023-06-06 06:00 | 2023-06-06 22:00 | NR | Continuous | [6 empty] | N | N | 2023-05-03 11:11
8-00815882 | Completed | BLW 60CX1 OOS | BLW 60kV CB,, RX, CS Insp | BLW 60CB31, BLW 60CX1 | 2023-06-06 08:00 | 2023-06-06 15:06 | NR | Continuous | [6 empty] | N | N | 2023-06-06 15:06
8-00812686 | Completed | SEL 5CB1 OOS | BFPN testing | SEL 5CB1 | 2023-06-06 08:00 | 2023-06-06 15:32 | NR | Continuous | [6 empty] | N | N | 2023-06-06 15:33
8-00812991 | Approved | PCN T2 OOS | PCN PM & 13kV Switchgear PM | PCN T2 | 2023-06-06 08:00 | 2023-06-23 16:00 | NR | Continuous | [6 empty] | Y | N | 2023-06-05 14:01
8-00835840 | Denied | HPN 2CB6 OOS | SF6 moisture check | HPN 2CB6 | 2023-06-06 08:00 | 2023-06-06 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-05-31 14:58
8-00805734 | Completed | MDN 5CB4 OOS | POW commissioning, CN PM | MDN 5CB4 | 2023-06-06 08:00 | 2023-06-07 17:30 | 4 | Continuous | [6 empty] | N | N | 2023-06-08 07:44
8-00805891 | Completed | ING 5CB8 OOS | NERC CPC Breaker Fail Testing | ING 5CB8 | 2023-06-06 08:00 | 2023-06-08 11:36 | 2 | Continuous | [6 empty] | N | N | 2023-06-08 11:37
8-00801127 | Completed | 2L44 OOS | Detailed Inspection | 2L44 | 2023-06-06 08:00 | 2023-06-09 14:09 | 2 | Continuous | [6 empty] | N | N | 2023-06-25 12:16
8-00795834 | Completed | 1L10, GOW 1B2, SHA T2, VIT 1MB1 OOS | SHA 1D22, 25CB2, VIT 1D2CB6, 1D1CB7 | 1L10, GOW 1B2, SHA T2 | 2023-06-06 08:00 | 2023-06-08 15:17 | 4 | Continuous | [6 empty] | N | N | 2023-06-08 15:17
8-00809667 | Completed | ACK 5CB12 OOS | INSP and DOBLE | ACK 5CB12 | 2023-06-06 08:00 | 2023-06-08 15:23 | NR | Continuous | [6 empty] | N | N | 2023-06-08 15:23
8-00806531 | Completed | 1L274 Out from NTL to 1D1L274 | Replace timbers | 1L274 (887L) | 2023-06-07 08:00 | 2023-06-07 12:18 | 3 | Continuous | [6 empty] | N | N | 2023-06-07 12:18
8-00812687 | Cancelled | SEL 5CB2 OOS | BFPN testing | SEL 5CB2 | 2023-06-07 08:00 | 2023-06-07 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-09 18:00
8-00815883 | Proposed | 60L303, BLW 60CB10, 60CB11 OOS | BLW 60VT10 Insp | BLW 60CB10, BLW 60CB11, 60L303 | 2023-06-07 08:00 | 2023-06-08 16:00 | NR | Continuous | [6 empty] | N | N | 2023-02-04 22:11
8-00712317 | Completed | UHT 3D2CB1 | Inspection | UHT 3B1, UHT T1 | 2023-06-07 09:00 | 2023-06-07 14:40 | 2 | Continuous | [6 empty] | N | N | 2023-06-07 14:40
8-00806537 | Completed | 1L274 Out from 1D2L274 to EFT | Replace structures and timbers | 1L274 (887L) | 2023-06-07 12:00 | 2023-06-16 15:24 | 4 | Continuous | [6 empty] | N | N | 2023-06-16 15:24
8-00810769 | Completed | PVO 1CB27 OOS | PVO 1CB27 INSP | PVO 1CB27, PVO 1CX3 | 2023-06-08 08:00 | 2023-06-09 13:06 | 2 | Continuous | [6 empty] | N | N | 2023-06-09 13:06
8-00805736 | Completed | MDN 5CB4, T3 OOS | POW commissioning, CN PM | MDN 12RX31, MDN 12RX32, MDN T3, MDN 2B18, MDN 5MB2 | 2023-06-08 08:00 | 2023-06-08 16:08 | 4 | Continuous | [6 empty] | N | N | 2023-06-08 16:08
8-00819616 | Proposed | KLY 5CB11 OOS | KLY CB PN CA, Insp & Doble testing | KLY 5CB11 | 2023-06-08 08:00 | 2023-06-09 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-24 14:12
8-00821150 | Cancelled | 1L392, HZN OOS | SRS PN PM | 1L392 | 2023-06-08 08:00 | 2023-06-08 18:00 | NR | Continuous | [6 empty] | Y | N | 2023-05-23 14:20
8-00813797 | Cancelled | SBK T12 OOS | SBK T12 Non-EL PN PM | SBK T12 | 2023-06-08 08:00 | 2023-06-08 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-18 13:53
8-00857065 | Completed | 2L112 OOS | BPA Outage | 2L112 | 2023-06-08 08:00 | 2023-06-08 11:48 | NR | Continuous | 2000 | 2000 |  |  | 560 | 600 | N | N | 2023-06-08 11:48
8-00813798 | Cancelled | SBK T11 OOS | SBK T11 Non-EL PN PM | SBK T11 | 2023-06-09 08:00 | 2023-06-09 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-18 13:53
8-00812690 | Completed | SEL 5CB4 OOS | BFPN testing | SEL 5CB4 | 2023-06-09 08:00 | 2023-06-09 14:22 | NR | Continuous |  |  |  |  | 850 | 700 | N | N | 2023-06-10 11:07
8-00813285 | Cancelled | 2L47 OOS | LYHSP - 2CC1 B DOBLE | 2L47 | 2023-06-09 08:00 | 2023-06-09 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-17 08:40
8-00816707 | Completed | GMS 5B7 oos | CPC PM | GMS 5B7, GMS 5CB7, GMS 5CB8 | 2023-06-09 12:00 | 2023-06-11 16:05 | 2 | Continuous | [6 empty] | Y | N | 2023-06-15 16:41
8-00841975 | Completed | GMS 5B7 oos | DS Repl and CT Inspection | GMS 5B7, GMS 5CB7, GMS 5CB8 | 2023-06-09 16:00 | 2023-06-11 13:56 | 48 | Continuous | [6 empty] | Y | N | 2023-06-11 16:30
8-00819090 | Cancelled | 60L390 OOS | RUP 60CC8 Doble testing | 60L390 | 2023-06-12 07:00 | 2023-06-12 17:00 | NR | Continuous | [6 empty] | N | N | 2023-05-18 15:20
8-00819626 | Denied | 5L13, KLY 5B11 OOS | KLY 500kV DS Insp | KLY 5B11, KLY 5CB1, KLY 5CB3, KLY 5D1, KLY 5D1CB1, KLY 5D1CB2, KLY 5D1CB21 (3), KLY 5D1CB3, KLY 5D1CB4, KLY 5D1CB5, 5L13, KLY T1 | 2023-06-12 08:00 | 2023-06-16 16:00 | NR | Continuous | [6 empty] | Y | N | 2023-05-28 21:23
8-00815874 | Cancelled | WSN 2CB3 OOS | WSN CB Insp | WSN 2CB3 | 2023-06-12 08:00 | 2023-06-16 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-06-07 11:32
8-00814417 | Completed | CRK 5CX1 OOS | Minor Insp | 5L42, CRK 5CX1 | 2023-06-12 08:00 | 2023-06-16 17:15 | 4 | Continuous | [6 empty] | N | N | 2023-06-16 17:16
8-00812598 | Cancelled | GMS 5B9 OOS | GMS DS Insp | GMS 5B9, GMS 5D1CB10, GMS 5D1CB9, GMS 5D9 | 2023-06-12 08:00 | 2023-06-15 16:00 | NR | Continuous | [6 empty] | Y | N | 2023-06-07 11:12
8-00842005 | Completed | GMS 5B9 oos | Fix phase lock on DS | GMS 5B9, GMS 5CB10, GMS 5CB9 | 2023-06-12 08:00 | 2023-06-20 15:23 | 48 | Continuous | [6 empty] | Y | N | 2023-06-20 15:23
8-00849523 | Completed | 2L22 OOS | Structure Replacements | 2L22 | 2023-06-12 08:00 | 2023-06-15 16:31 | 2 | Continuous | [6 empty] | Y | N | 2023-06-15 16:38
8-00801129 | Completed | 2L56 OOS | Detailed Inspection | CAM T3, CAM T4, 2L56 | 2023-06-12 08:00 | 2023-06-13 15:55 | 2 | Continuous | [6 empty] | N | N | 2023-06-13 15:56
8-00795112 | Cancelled | 1L101, CMX T1, OYR T2, BKB T1 OOS | 1L101, BKB T1, 1B1, DMR 1CB7, CMX T1, 1B1, JHT 1B11, OYR T2, 1B2 | CMX T1, 1L101, OYR T2, BKB T1 | 2023-06-12 08:00 | 2023-06-13 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-16 15:32
8-00810675 | Completed | LTZ T2 OOS | LTZ T2 & LTC INSP, DOBLE & ANCHOR PLATE CERT, PN MET | LTZ T2 | 2023-06-12 08:00 | 2023-06-30 14:56 | 2 | Continuous | [6 empty] | N | N | 2023-06-30 14:57
8-00810313 | Completed | VAS 5CB12 OOS | CPC CN CA | VAS 5CB12 | 2023-06-12 08:00 | 2023-06-12 16:48 | NR | Continuous | [6 empty] | N | N | 2023-06-12 16:48
8-00810333 | Cancelled | VNT 1B11 OOS | VNT 1D2, 1D2CB15, 1D2CB11, 1D1CB10 and 1D5 INSP | VNT 1B11 | 2023-06-12 08:00 | 2023-06-16 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-13 11:39
8-00812021 | Completed | JHT 1B1 OOS | JHT 1D1CB1, 1D1CB16 INSP | JHT 1B1 | 2023-06-12 08:00 | 2023-06-13 12:11 | 2 | Continuous | [6 empty] | N | N | 2023-06-13 12:11
8-00811337 | Completed | ING T7 OOS | DS Insp & animal mitigation | ING 60D7, ING T7 | 2023-06-12 08:00 | 2023-06-26 09:19 | 2 | Continuous | [6 empty] | N | N | 2023-06-26 09:19
8-00806901 | Cancelled | CBK T2 OOS | Non-Electrcal testing - NERC PM | CBK T2 | 2023-06-12 08:00 | 2023-06-16 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-29 07:48
8-00806414 | Completed | 5L42 OOS | Replace EOL insulators | 5L42, CRK 5CX1 | 2023-06-12 08:00 | 2023-06-16 17:15 | 4 | Continuous | 2000 | 2400 | 2500 | 2500 |  |  | N | N | 2023-06-16 17:16
8-00806959 | Completed | SEL 5CB5 OOS | BFPN testing (NERC) | SEL 5CB5 | 2023-06-12 08:00 | 2023-06-12 16:49 | NR | Continuous | [6 empty] | N | N | 2023-06-12 16:49
8-00807197 | Completed | 5L76, ACK 5B5 OOS | Replace yard flood lights | 5L76, ACK 5B5 | 2023-06-12 08:00 | 2023-06-12 16:52 | NR | Continuous | [6 empty] | N | N | 2023-06-12 16:52
8-00807593 | Completed | MON T1 OOS | PCB Bushing Replacement | MON T1 | 2023-06-12 08:00 | 2023-07-20 15:31 | 120 | Continuous | [6 empty] | N | N | 2023-07-20 15:31
8-00807684 | Completed | MLS 5CX3 OOS | CX INSP | MLS 5CX3 | 2023-06-12 08:00 | 2023-06-15 14:35 | 4 | Continuous | [6 empty] | N | N | 2023-06-15 14:35
8-00798234 | Completed | 5L76 OOS | Replace End of Life Insulators | 5L76 | 2023-06-12 16:00 | 2023-06-13 16:33 | 4 | Continuous | 2000 | 2400 |  |  | 850 | 1000 | N | N | 2023-06-13 16:33
8-00805893 | Completed | ING 5CB11 OOS | NERC CPC Breaker Fail Testing | ING 5CB11 | 2023-06-13 08:00 | 2023-06-16 15:31 | 2 | Continuous | [6 empty] | N | N | 2023-06-16 15:41
8-00810314 | Completed | VAS 5CB13 OOS | CPC CN CA | VAS 5CB13 | 2023-06-13 08:00 | 2023-06-13 18:02 | NR | Continuous | [6 empty] | N | N | 2023-06-13 18:03
8-00810332 | Recalled | VNT T2, T5, 1B11 OOS | NON EL, INSP and DOBLE | VNT 1CB10, VNT 1CB11, VNT T2, VNT T5 | 2023-06-13 08:00 | 2023-06-13 15:16 | 6 | Continuous | [6 empty] | Y | N | 2023-06-13 17:14
8-00813284 | Completed | LYN T2 OOS | LYN T2 TFR/LTC INSP, DOBLE, NON-ELECTRICALS | LYN T2 | 2023-06-13 08:00 | 2023-06-22 12:49 | 8 | Continuous | [6 empty] | N | N | 2023-06-22 12:50
8-00798238 | Completed | 5L79 OOS | Replace End of Life Insulators | 5L79 | 2023-06-13 16:00 | 2023-06-20 15:10 | 3 | Return Weekends | 2000 | 2400 |  |  | 850 | 1000 | N | N | 2023-06-20 15:11
8-00861463 | Completed | 1L359 (7L81R) Out from RBL to FNC | ATCO line repair | 1L359 (7L81R) | 2023-06-13 20:00 | 2023-10-16 14:56 | 2 | Continuous | [6 empty] | N | N | 2023-10-16 14:56
8-00813799 | Cancelled | SBK T21 OOS | SBK T21 Non-EL PN PM | SBK T21 | 2023-06-14 08:00 | 2023-06-14 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-18 13:54
8-00810315 | Approved | VAS 5CB14 OOS | CPC CN CA | VAS 5CB14 | 2023-06-14 08:00 | 2023-06-15 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-06-15 16:59
8-00821149 | Completed | SRS T3 OOS | SRS T2 Non-EL PN PM | SRS T3 | 2023-06-15 07:00 | 2023-06-15 15:29 | NR | Continuous | [6 empty] | N | N | 2023-06-15 15:29
8-00813800 | Cancelled | SBK T22 OOS | SBK T22 Non-EL PN PM | SBK T22 | 2023-06-15 08:00 | 2023-06-15 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-18 13:54
8-00810316 | Approved | VAS 5CB22 OOS | CPC CN CA | VAS 5CB22 | 2023-06-15 08:00 | 2023-06-16 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-06-16 12:01
8-00809320 | Cancelled | NIC 5DCBB43, 5B13, 5L72 OOS | 5DCB43 DS PM | 5L72, NIC 5B13, NIC 5DCB43 | 2023-06-15 08:00 | 2023-06-15 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-10 09:23
8-00788518 | Completed | 60L90 out from WLT, WLT 60B1 OOS | Close Temp Bus Cut #5 | 60L90, WLT 60B1 | 2023-06-15 08:00 | 2023-06-15 15:41 | 3 | Continuous | [6 empty] | N | N | 2023-06-15 15:42
8-00812726 | Completed | NTL T4 OOS | Tap changer inspections and doble testing | NTL T4 | 2023-06-16 07:00 | 2023-07-07 17:16 | 48 | Continuous | [6 empty] | N | N | 2023-07-07 17:16
8-00810755 | Cancelled | PVO 1CB25 OOS | PVO 1CB25 CN | PVO 1CX1 | 2023-06-16 08:00 | 2023-06-16 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-06-16 08:33
8-00818718 | Completed | SKA 12RX2 OOS | SKA 12RX2 Bushing Repl | SKA 12RX2 | 2023-06-16 14:00 | 2023-07-13 18:08 | 120 | Continuous | [6 empty] | N | N | 2023-07-13 18:08
8-00859721 | Completed | VIT SC2 OOS | To extend the brush life until VIT SC4 is RTS | VIT SC2 | 2023-06-17 06:00 | 2023-07-11 17:18 | 1 | Return Evenings | 2000 | 2400 |  |  |  |  | N | N | 2023-09-22 18:00
8-00797141 | Completed | 1L112, HWD T1, HMC, NEX | HWD 1D1, JPT 1CVT21 INSP | 1L112, HWD T1 | 2023-06-18 07:00 | 2023-06-18 20:06 | 1 | Continuous | [6 empty] | N | N | 2023-06-18 20:13
8-00793167 | Completed | 60L91, 60L61 OLLP/ANR | WLT OSP Step 20 | 60L62, WLT 60B9, WLT 60B10 | 2023-06-19 07:00 | 2023-06-21 11:33 | 3 | Continuous | [6 empty] | N | N | 2023-06-21 11:33
8-00805749 | Cancelled | BSY 2MB1, 2MB2 OOS | BSY 2D33, BSY 2CT2 INSP | BSY 2CB1, BSY 2CB16, BSY 2CB8, BSY 2CB9, BSY 2MB2, BSY 2MB1 | 2023-06-19 08:00 | 2023-06-30 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-05-30 10:32
8-00807462 | Cancelled | 5L1 oos | Spacer Repl | 5L1 | 2023-06-19 08:00 | 2023-06-28 16:00 | NR | Continuous | [6 empty] | Y | N | 2023-09-05 10:48
8-00855600 | Completed | ING T5, 12RX5 OOS | PCB Bushing and oil leak repairs. | ING T5, ING 12RX5 | 2023-06-19 08:00 | 2023-08-01 21:42 | 120 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-08-01 21:42
8-00815879 | Completed | BLW T3, 2B5 OOS | BLW DS Insp | BLW T3, BLW 2B5 | 2023-06-19 08:00 | 2023-06-20 16:06 | 2 | Continuous | [6 empty] | N | N | 2023-07-06 03:30
8-00815880 | Cancelled | BLW T3 oos | BLW T3 Insp and Doble testing | BLW T3 | 2023-06-19 08:00 | 2023-06-23 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-08 11:59
8-00818866 | Cancelled | SKA T2 OOS | SKA T2 Non-EL PN PM | SKA 5CB12, SKA T2 | 2023-06-19 08:00 | 2023-06-23 16:00 | NR | Continuous | [6 empty] | N | N | 2023-07-05 06:38
8-00812784 | Completed | PVL T1 OOS | PVL T1, 25VTT1 INSP, ANCHOR PLATE INSP | PVL T1 | 2023-06-19 08:00 | 2023-07-07 08:37 | 8 | Continuous | [6 empty] | N | N | 2023-07-07 08:37
8-00812797 | Completed | INV T11 OOS | Work on tap changer | INV T11 | 2023-06-19 08:00 | 2023-06-29 14:12 | 48 | Continuous | [6 empty] | N | N | 2023-06-30 06:12
8-00812592 | Cancelled | GMS 5RX1 OOS | GMS 5RX1 Non-EL NERC PM | GMS 5RX1 | 2023-06-19 08:00 | 2023-06-20 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-06 10:28
8-00813276 | Completed | MSA T2, 12RX2 OOS | MSA T2 NON-ELECTRICALS, | MSA 12RX2, MSA SS4, MSA T2 | 2023-06-19 08:00 | 2023-06-30 15:24 | 4 | Continuous | [6 empty] | N | N | 2023-06-30 15:36
8-00857416 | Completed | 3L13, and BRT 3B7 OOS | VEG Mangement | 3L13, BRT 3B7 | 2023-06-19 11:00 | 2023-06-29 09:50 | 5 | Continuous | [6 empty] | Y | N | 2023-06-29 09:50
8-00812525 | Completed | 2L86 OOS | Structure Repl | 2L86 | 2023-06-19 12:00 | 2023-06-30 10:51 | 2 | Continuous | [6 empty] | N | N | 2023-06-30 11:02
8-00797134 | Completed | 1L11, GOW 1B4, KSH T3, VIT 1B3 OOS | KSH 1D1CB6, 1D3, 25CB3, VIT 1D23, 1D2CB3 | 1L11, VIT 1B3, KSH T3 | 2023-06-20 07:00 | 2023-06-23 15:17 | NR | Continuous | [6 empty] | N | N | 2023-06-23 15:17
8-00659414 | Completed | 5L62 OOS | PGTC - Prince George to Terrace Capacitors | 5L62 | 2023-06-20 08:00 | 2023-06-22 19:57 | 16 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | 2023-06-23 02:38
8-00805843 | Completed | 5L83, RYC 5CX1 OOS | RYC 5D1 & 5D2 Insp | 5L83, RYC 5CX1 | 2023-06-20 08:00 | 2023-06-27 14:46 | 8 | Continuous | [6 empty] | N | N | 2023-06-27 15:02
8-00801128 | Completed | 2L39 OOS | Detailed Inspection | 2L39 | 2023-06-20 08:00 | 2023-06-23 10:50 | 2 | Continuous | [6 empty] | N | Y | 2023-06-23 11:00
8-00807465 | Completed | KDY 5CX1 oos | KDY 5CX1 INSP, MNRI, DOBL | KDY 5CX1 | 2023-06-20 08:00 | 2023-07-10 11:07 | 4 | Continuous | [6 empty] | N | N | 2023-07-10 11:07
8-00808890 | Completed | 1L350, BMT 1B8 OOS | BMT DS and CVT Insp | 1L350, BMT 1B8 | 2023-06-20 08:00 | 2023-06-20 16:32 | NR | Continuous | [6 empty] | N | N | 2023-06-20 16:32
8-00809671 | Completed | MDN 2CB5 OOS | CPC Breaker Fail Testing | MDN 2CB5 | 2023-06-20 08:00 | 2023-06-20 13:53 | 2 | Continuous | [6 empty] | N | N | 2023-06-20 13:53
8-00810317 | Completed | VAS 5RX1 OOS | INSP and DOBLE | VAS 5RX1 | 2023-06-20 08:00 | 2023-06-22 18:00 | 6 | Continuous | [6 empty] | N | N | 2023-06-24 21:54
8-00811344 | Completed | ING 2CB19 OOS | CB Inspection | ING 2CB19 | 2023-06-20 08:00 | 2023-06-22 11:55 | 2 | Continuous | [6 empty] | N | N | 2023-06-22 11:55
8-00811396 | Completed | ING 2CB1 OOS | CPC Control Testing | ING 2CB1 | 2023-06-20 08:00 | 2023-06-22 10:57 | 2 | Continuous | [6 empty] | N | N | 2023-06-22 10:57
8-00812258 | Cancelled | CSN 2CB2 OOS | NERC PM | CSN 2CB2 | 2023-06-20 08:00 | 2023-06-21 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-06-23 18:00
8-00812705 | Completed | KCL 2CB2 OOS | PM Inpsection | KCL 2CB2 | 2023-06-20 08:00 | 2023-06-23 12:12 | NR | Continuous | [6 empty] | N | N | 2023-06-23 12:12
8-00818578 | Cancelled | TKW 5CB13 OOS | TKW CB POW PM | TKW 5CB13 | 2023-06-20 08:00 | 2023-06-20 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-06 15:58
8-00813355 | Completed | FCN T2, 25CB2 OOS | PM INSPECTION of FCN 25CB2 | FCN T2 | 2023-06-20 08:00 | 2023-06-23 14:06 | 8 | Continuous | [6 empty] | N | N | 2023-06-23 14:06
8-00842062 | Completed | MDN 2CB14, 2CX1, 2CX2, 2RX1 OOS | MDN 2CB14 Replacement | MDN 2RX1, MDN 2CB14, MDN 2CX2, MDN 2CX1 | 2023-06-20 08:00 | 2023-07-14 10:08 | 0 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-07-30 03:30
8-00815881 | Completed | BLW T3, 60CB9, 60CB10, 60CX1 OOS | BLW DS Insp and VT Doble testing | BLW 60CB10, BLW 60CB9, BLW 60CX1, BLW T3 | 2023-06-20 16:00 | 2023-06-22 16:06 | 2 | Continuous | [6 empty] | N | N | 2023-06-22 16:06
8-00819630 | Denied | KLY 5RX1 OOS | KLY 5RX1 CPC Non-EL PM, NERC PM, Leak Repair | KLY 5RX1 | 2023-06-21 08:00 | 2023-06-23 16:00 | NR | Return Evenings | [6 empty] | N | N | 2023-06-20 19:08
8-00812995 | Proposed | KDS 5CB3 OOS | CB CN | KDS 5CB3 | 2023-06-21 08:00 | 2023-06-21 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-14 09:45
8-00809674 | Completed | MDN 2CB6 OOS | CPC Breaker Fail Testing | MDN 2CB6 | 2023-06-21 08:00 | 2023-06-21 14:33 | 2 | Continuous | [6 empty] | N | N | 2023-06-21 14:34
8-00808892 | Completed | 1L350, DAW 1B4 OOS | DAW DS, CVT Insp | DAW 1B4, 1L350 | 2023-06-21 08:00 | 2023-06-21 16:01 | NR | Continuous | [6 empty] | N | N | 2023-06-21 16:11
8-00805957 | Completed | 2L27 OOS | WHY 2CVT3 INSP | 2L27 | 2023-06-21 08:00 | 2023-06-21 15:42 | 2 | Continuous | [6 empty] | N | Y | 2023-06-21 15:52
8-00788520 | Completed | 60L62 Out from WLT, WLT 60B10/11/12 OOS, 60L91 fed from 60L62 | Replace WLT 60B10 & 60B12 Insulators | 60L62, WLT 60B10, WLT 60B12, WLT 60B11 | 2023-06-21 08:00 | 2023-07-07 09:48 | 3 | Continuous | [6 empty] | N | N | 2023-07-07 09:48
8-00811348 | Completed | ING 2CB20 OOS | CB Inspection | ING 2CB20 | 2023-06-22 08:00 | 2023-06-23 14:39 | 2 | Continuous | [6 empty] | N | N | 2023-06-23 14:44
8-00812997 | Cancelled | KDS 5CB1 OOS | CB CN | KDS 5CB1 | 2023-06-22 08:00 | 2023-06-22 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-24 18:00
8-00813811 | Proposed | 1L390 OOS | Structure Repl | 1L390 | 2023-06-25 08:00 | 2023-06-25 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-30 23:02
8-00797183 | Completed | 1L122 Out from PVO 1D22 to HWW 1D24, 60L128, PVO T1, T2, 1CX2, 1CX3, T4, LDY T1, LCW T1, T2 OOS | PVO 1D2CB1, 60D1, 60D1CB3, 60D2CB3, 60BP3 | 60L128, PVO 1CX2, PVO 1CX3, LCW T1, LCW T2, LDY T1, PVO T1, PVO T2, PVO T4, 1L122 | 2023-06-26 07:00 | 2023-06-27 07:07 | 2 | Continuous | [6 empty] | N | N | 2023-06-27 07:07
8-00803296 | Completed | 1L14 OOS | End of Life Structure Replacements | 1L14, KSH T2, SHA T1 | 2023-06-26 08:00 | 2023-06-29 12:26 | NR | Continuous | [6 empty] | N | N | 2023-06-29 12:26
8-00800860 | Completed | 60L11 Out from BND | BND 60VT5 INSP | BND 60CB15, BND 60CB6, BND 60CB5, 60L11 | 2023-06-26 08:00 | 2023-06-26 15:19 | 2 | Continuous | [6 empty] | N | N | 2023-07-12 03:30
8-00801132 | Completed | 2L33 OOS | Detailed Inspection | 2L33 | 2023-06-26 08:00 | 2023-06-30 16:06 | 2 | Continuous | [6 empty] | Y | N | 2023-06-30 16:06
8-00801134 | Completed | 2L45 OOS | Detailed Inspection | 2L45 | 2023-06-26 08:00 | 2023-06-28 16:37 | 2 | Continuous | [6 empty] | N | Y | 2023-06-28 16:37
8-00806963 | Approved | SEL 5CB11 OOS | BFPN testing (NERC) | SEL 5CB11 | 2023-06-26 08:00 | 2023-06-26 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-22 17:04
8-00821248 | Completed | TAC T2, SS2 OOS | TAC T2, SS2 Doble testing | TAC T2 | 2023-06-26 08:00 | 2023-07-04 15:39 | NR | Continuous | [6 empty] | N | N | 2023-07-10 02:33
8-00821250 | Completed | TAC T5 OOS | TAC T5 Doble testing | TAC T5 | 2023-06-26 08:00 | 2023-07-04 16:09 | 4 | Continuous | [6 empty] | N | N | 2023-07-10 02:32
8-00812568 | Cancelled | 2L86 oos | HMH DS Insp | 2L86, HMH 2D21 | 2023-06-26 08:00 | 2023-06-26 16:00 | NR | Continuous | [6 empty] | N | N | 2023-07-04 10:53
8-00813286 | Denied | 60L62, WLT 60B9/10/11 OOS | WLT 60L62 - 60D1CB10, 60D1CB11, 60D1CB12, 60D2CB10, 60D1CB9 INSP, 60CB9 BFPN. COND. | 60L62, WLT 60B10, WLT 60B11 | 2023-06-26 08:00 | 2023-06-30 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-26 14:02
8-00813354 | Completed | FCN T1, 25CB1 OOS | PM INSPECTION of FCN 25CB1 | FCN T1 | 2023-06-26 08:00 | 2023-06-29 13:05 | 8 | Continuous | [6 empty] | N | N | 2023-06-29 13:05
8-00794311 | Completed | 1L117, JHT 1B14 OOS | 1L117, JHT 1B14, LDR 1B1 - 138KV Disc INSP | 1L117, JHT 1CB13, JHT 1CB14, JHT 1B14 | 2023-06-26 16:00 | 2023-06-28 14:31 | 2 | Continuous | [6 empty] | N | N | 2023-06-28 14:31
8-00859019 | Completed | AMC 5CX1 OOS | Troubleshoot and fix B phase SY LDM GFOI Fail | AMC 5CX1 | 2023-06-27 07:00 | 2023-06-28 15:07 | 5 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-06-28 15:07
8-00812689 | Completed | SEL 5CB3 OOS | BFPN testing | SEL 5CB3 | 2023-06-27 08:00 | 2023-06-27 14:25 | NR | Continuous | [6 empty] | N | N | 2023-06-27 14:26
8-00809675 | Completed | ACK 5CX1, 5RX7, 5MB1 OOS | BUTN to fix set screw in mech cabinet. | ACK 5CB1, ACK 5CB10, ACK 5CB5, ACK 5RX7, ACK 5CX1, ACK 5CB49, ACK 5MB1 | 2023-06-27 08:00 | 2023-06-28 14:00 | 6 | Continuous | [6 empty] | N | N | 2023-06-28 14:01
8-00809676 | Completed | MDN 2CB7 OOS | CPC Breaker Fail Testing | MDN 2CB7 | 2023-06-27 08:00 | 2023-06-27 15:47 | 2 | Continuous | [6 empty] | N | N | 2023-06-27 15:48
8-00811341 | Completed | ING T9 OOS | Tap Changer Major Insp & Animal Mitigation | ING T9 | 2023-06-27 08:00 | 2023-06-28 16:33 | 2 | Continuous | [6 empty] | N | N | 2023-06-28 16:33
8-00810331 | Approved | VNT 1CB11 OOS | BFPN PM | VNT 1CB11 | 2023-06-28 08:00 | 2023-06-28 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-06-27 14:33
8-00809678 | Completed | MDN 2CB8 OOS | CPC Breaker Fail Testing | MDN 2CB8 | 2023-06-28 08:00 | 2023-06-28 15:27 | 2 | Continuous | [6 empty] | N | N | 2023-06-28 15:27
8-00807580 | Approved | NLY 2CB4 OOS | NERC PM | NLY 2CB4 | 2023-06-28 08:00 | 2023-06-28 12:00 | NR | Continuous | [6 empty] | N | N | 2023-06-27 14:32
8-00812731 | Approved | 1L275, NTL 1CB2 OOS | BFPN testing | NTL 1CB2, 1L275 (786L) | 2023-06-28 08:00 | 2023-06-28 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-06-27 14:34
8-00819631 | Completed | KLY 5RX6 OOS | KLY 5RX6 CPC Non-EL PM & KLY 5CB36 Repairs | KLY 5RX6, KLY 5CB36 | 2023-06-28 08:00 | 2023-06-29 16:48 | NR | Return Evenings | [6 empty] | N | N | 2023-06-30 11:02
8-00812754 | Completed | 2l294 out from NLY to AAL | Inspection and doble of 2SSVT1 | 2L294, NLY 2CB3, NLY 2CB4 | 2023-06-28 11:00 | 2023-06-28 19:08 | NR | Continuous |  |  |  |  | 850 | 500 | N | N | 2023-06-28 19:09
8-00807579 | Approved | NLY 2CB3 OOS | NERC PM | NLY 2CB3 | 2023-06-28 12:00 | 2023-06-28 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-27 14:37
8-00812064 | Completed | JHT 1B13 OOS | JHT 1D2CB13, 1D2CB4 INSP | JHT 1B4, JHT 1B13 | 2023-06-29 07:00 | 2023-06-30 09:25 | 2 | Continuous | [6 empty] | Y | N | 2023-06-30 09:26
8-00810329 | Completed | VNT T6 OOS | NON EL PM | VNT T6 | 2023-06-29 08:00 | 2023-07-05 18:17 | 2 | Continuous | [6 empty] | N | N | 2023-07-05 18:17
8-00807578 | Completed | NLY 2CB2 OOS | NERC PM | NLY 2CB2 | 2023-06-29 08:00 | 2023-06-29 12:18 | NR | Continuous | [6 empty] | N | N | 2023-06-29 12:18
8-00809670 | Completed | ACK 5RX7 OOS | BUTN to fix set screw in mech cabinet. | ACK 5RX7, ACK 5CB47 | 2023-06-29 08:00 | 2023-06-29 11:54 | 2 | Continuous | [6 empty] | N | N | 2023-06-29 11:55
8-00812478 | Proposed | 2L353 OOS | Structure Repl | 2L353 | 2023-06-29 08:00 | 2023-06-29 16:00 | NR | Continuous | [6 empty] | N | Y | 2023-02-04 22:18
8-00807581 | Completed | NLY 2CB6 OOS | NERC PM | NLY 2CB6 | 2023-06-29 12:00 | 2023-06-29 14:05 | NR | Continuous | [6 empty] | N | N | 2023-06-29 16:34
8-00815885 | Completed | 60L344, 60L359, FM2 OOS | TAC & FM2 DS, VT Insp | 60L344, 60L359 | 2023-06-29 23:00 | 2023-06-30 04:06 | 2 | Continuous | [6 empty] | N | N | 2023-06-30 04:06
8-00821262 | Cancelled | 1L384 out from TPY | TPY 1CVT11 Insp | 1L384 | 2023-06-30 08:00 | 2023-06-30 18:00 | NR | Continuous | [6 empty] | N | N | 2023-05-19 08:18
8-00806964 | Completed | SEL 2CB3 OOS | BFPN testing (NERC) | SEL 2CB3 | 2023-06-30 08:00 | 2023-06-30 13:19 | NR | Continuous | [6 empty] | N | N | 2023-06-30 13:19
8-00679786 | Completed | 5L71 & 5L72 OOS | MCA Black start testing with G3 & G4 | 5L71, 5L72, 60L223, NIC 5CB13, NIC 5CB3 | 2023-07-02 10:00 | 2023-07-02 15:07 | 1 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | 2023-07-02 15:08
8-00803307 | Proposed | 60L22 OOS | Replace emergent structures | 60L22 | 2023-07-03 08:00 | 2023-07-16 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-09 14:55
8-00807577 | Cancelled | NLY T1 OOS | Environmental Remediation | NLY T1 | 2023-07-03 08:00 | 2023-07-05 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-15 09:24
8-00809463 | Proposed | 1L364 out from GMS to 1D1L364 | Install tap for new ATT TVC | 1L364 | 2023-07-03 08:00 | 2023-07-10 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-19 12:21
8-00810881 | Cancelled | ELK 60B1 OOS | Replace 60VT1 for PCB Phase Out | ELK 60B1 | 2023-07-03 08:00 | 2023-07-14 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-01 13:40
8-00813203 | Cancelled | FMT T1 OOS, 60L270 Switching | Environmental Remediation | FMT T1 | 2023-07-03 08:00 | 2023-07-05 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-20 12:45
8-00813007 | Denied | DMR 5RX8, 5CB58 OOS | DMR 5CB58, 5RX8 INSP, CN , NETS | DMR 5RX8, DMR 5CB58 | 2023-07-04 08:00 | 2023-07-07 16:00 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-06-22 09:04
8-00812701 | Cancelled | SEL 2CB4 OOS | Inspection | SEL 2CB4 | 2023-07-04 08:00 | 2023-07-04 16:00 | NR | Continuous | [6 empty] | N | N | 2023-02-15 11:28
8-00812729 | Completed | NTL 2CB2, 2D4, T4 OOS | Breaker Inspection and disconnect repair | NTL 2CB2, NTL T4 | 2023-07-04 08:00 | 2023-07-07 17:17 | 6 | Continuous | [6 empty] | N | N | 2023-07-07 17:17
8-00821239 | Cancelled | GLN T2 OOS | GLN 2VR2 Insp | GLN T2 | 2023-07-04 08:00 | 2023-07-05 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-09 08:46
8-00813592 | Completed | MAN 2B5, 2CB4, 2CB5 OOS | INSP, NERC PM | MAN 2CB4, MAN 2CB5, MAN 2B5 | 2023-07-04 08:00 | 2023-07-12 15:00 | 2 | Continuous | [6 empty] | N | N | 2023-07-12 15:01
8-00809687 | Completed | MDN 2CB9 OOS | CPC Breaker Fail Testing | MDN 2CB9 | 2023-07-04 08:00 | 2023-07-04 14:57 | 2 | Continuous | [6 empty] | N | N | 2023-07-04 15:39
8-00806961 | Completed | SEL 5CB8 OOS | BFPN testing (NERC) | SEL 5CB8 | 2023-07-04 08:00 | 2023-07-04 15:25 | NR | Continuous | [6 empty] | N | N | 2023-07-04 15:25
8-00807466 | Denied | 5L2 OOS | Spacer Repl | 5L2, GMS 5D22, GMS 5RX2, KDY 5D22 (3), GMS 5B4 | 2023-07-04 08:00 | 2023-07-14 16:00 | 2 | Continuous | [6 empty] | Y | N | 2023-06-27 09:30
8-00807467 | Denied | KDY 5CX2 OOS | CX INSP | KDY 5CX2 | 2023-07-04 08:00 | 2023-07-21 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-27 09:31
8-00803309 | Cancelled | 60L301 out from CRQ | Replace EOL structures | 60L301 | 2023-07-04 08:00 | 2023-07-20 16:00 | 4 | Return Weekends | [6 empty] | N | N | 2023-06-28 10:31
8-00805846 | Completed | RYC 5CX1 OOS | Minor Electrical Insp, PY/SY protection INSP | RYC 5CX1 | 2023-07-04 08:00 | 2023-07-12 09:40 | 8 | Continuous | [6 empty] | N | N | 2023-07-28 03:30
8-00805876 | Completed | 2L74 OOS | FLW DS CB CVT INSP | 2L74, FLW 2MB1, FLW 2B1, FLW 2B5 | 2023-07-04 08:00 | 2023-07-06 15:36 | 4 | Continuous | [6 empty] | Y | Y | 2023-07-06 15:36
8-00675410 | Cancelled | 5L2 OOS | Install GMS 5GD22 | 5L2, GMS 5RX2 | 2023-07-04 08:00 | 2023-07-15 16:00 | NR | Continuous | [6 empty] | Y | N | 2023-06-30 09:41
8-00785871 | Completed | REV T7, T9, SST1 OOS | Transformer and DS Maintenance | REV T7 | 2023-07-04 10:00 | 2023-07-21 17:58 | 4 | Continuous | [6 empty] | N | N | 2023-07-21 17:58
8-00868109 | Completed | DAW T1 oos | PCB Bushing Repl | DAW T1 | 2023-07-04 16:00 | 2023-08-11 11:19 | 120 | Continuous | [6 empty] | N | N | 2023-08-11 11:20
8-00861437 | Completed | SEL 5CB2 OOS | BFPN testing | SEL 5CB2 | 2023-07-05 08:00 | 2023-07-05 12:57 | 1 | Continuous | [5 empty] | 700 | N | N | 2023-07-05 12:57
8-00812740 | Cancelled | 60L294, ELK 60CB3, 60D2CB3 OOS | Inspection | ELK 60CB3, ELK 60D2CB3, 60L294 | 2023-07-05 08:00 | 2023-07-06 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-19 07:34
8-00813359 | Completed | 2L2 out from RBW, RBW T2 OOS | ETM REPLACMENT, NON-ELEC PN, COOLER INSPECTION | RBW T2, 2L2 | 2023-07-05 08:00 | 2023-07-14 14:59 | 48 | Continuous | [6 empty] | N | N | 2023-07-14 14:59
8-00794312 | Cancelled | 1L118 JHT 1B16 LDR 1CB4 OOS | 1L118, JHT 1B16, LDR 1CB4 - 138KV Disc INSP | 1L118, JHT 1CB4, LDR 1CB4, JHT 1B16 | 2023-07-05 08:00 | 2023-07-07 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-07-05 09:22
8-00809692 | Completed | MDN 2CB11 OOS | CPC Control Testing | MDN 2CB11 | 2023-07-05 08:00 | 2023-07-05 15:50 | 2 | Continuous | [6 empty] | N | N | 2023-07-05 15:50
8-00809337 | Completed | NIC 5RX3, 5CB43 | 5DCB43 DS PM | NIC 5RX3, NIC 5CB43 | 2023-07-05 08:00 | 2023-07-07 12:07 | NR | Continuous | 2000 | 2400 |  |  |  |  | Y | N | 2023-07-07 12:07
8-00811305 | Completed | DMR 1CB4 OOS | DMR 1CB4 & 1CVT4 INSP & CN | DMR 1CB4 | 2023-07-05 08:00 | 2023-07-05 09:51 | 2 | Continuous | [6 empty] | N | N | 2023-07-21 03:30
8-00811399 | Completed | ING 2CB3 OOS | CPC Control Testing | ING 2CB3 | 2023-07-06 08:00 | 2023-07-06 14:46 | 2 | Continuous | [6 empty] | N | N | 2023-07-06 14:46
8-00797164 | Cancelled | 1L14, GTP 1B3, T13, SS13 OOS | GTP T13 NON-EL, GTP 25CB11 BFPN, GTP 25CB12 BFPN, GTP 1D2CB2 INSP | 1L14, GTP 1B3, GTP T13 | 2023-07-07 08:00 | 2023-07-07 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-07-06 15:30
8-00812610 | Denied | 5L2, WSN 5B2, 5RX4 OOS | WSN DS Insp | 5L2, WSN 5B2, WSN 5D1CB4, WSN 5DCB34, WSN 5RX4 | 2023-07-07 08:00 | 2023-07-07 16:00 | NR | Continuous | [6 empty] | Y | N | 2023-06-27 14:09
8-00867660 | Completed | 5L1 OOS | Spacer Repl | 5L1 | 2023-07-07 08:00 | 2023-07-10 15:16 | 4 | Continuous | [6 empty] | Y | N | 2023-07-10 15:21
8-00812128 | Completed | 60L62 out from WLT 60D27 to 60D3L62, WLT 60B9/B10 OOS | WLT OSP Step 23--Temp Bypass connecting 60L91 and WLT 60D26 just outside WLT sub. | 60L62, WLT 60B9, WLT 60B10 | 2023-07-07 11:00 | 2023-07-07 13:41 | 3 | Continuous | [6 empty] | N | N | 2023-07-07 13:41
8-00818634 | Cancelled | STW T3, 1D21 | STW 1D21 DS PM | STW 1D21, STW T3 | 2023-07-08 06:00 | 2023-07-08 12:00 | NR | Continuous | [6 empty] | N | N | 2023-07-06 13:04
8-00814861 | Completed | MCA 5RX4 OOS | Deficiency work | MCA 5RX4 | 2023-07-09 11:30 | 2023-08-08 12:26 | 24 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | 2023-08-08 12:26
8-00819092 | Completed | 60L393, RUP 60CB10, 60CB15 OOS | RUP 60kV DS, VT Insp | 60L393, OFD T1, OFD T4, RUP 60CB16, RUP 60CB9 | 2023-07-10 08:00 | 2023-07-10 16:29 | 4 | Continuous | [6 empty] | N | N | 2023-07-10 16:29
8-00812743 | Cancelled | 60L287, ELK 60CB5, 60D1, 60D21, 60D1CB2 OOS | Inspection | ELK 60CB5, ELK 60D1, ELK 60D1CB2, ELK 60D21, 60L287 | 2023-07-10 08:00 | 2023-07-14 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-19 07:36
8-00813204 | Cancelled | FMT T2 OOS, 60L270 Switching | Environmental Remediation | FMT T2 | 2023-07-10 08:00 | 2023-07-12 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-20 12:45
8-00867294 | Completed | 5L2 oos | Spacer Repl | 5L2 | 2023-07-10 08:00 | 2023-07-14 16:40 | 2 | Continuous | [6 empty] | Y | N | 2023-07-14 16:40
8-00869323 | Completed | KDY 5CX2 oos | Series Cap Insp | KDY 5CX2 | 2023-07-10 08:00 | 2023-07-21 09:39 | NR | Continuous | [6 empty] | N | N | 2023-07-21 09:39
8-00861922 | Approved | BRT 3B2 and 3L14 OOS | commissioning testing | 3L14, BRT 3B2 | 2023-07-10 12:00 | 2023-07-17 16:00 | 2 | Continuous | [6 empty] | Y | N | 2023-07-06 15:09
8-00868520 | Approved | L81-87 oos | Hotspot Repair | L81-87 | 2023-07-11 07:00 | 2023-07-11 18:00 | NR | Continuous | [6 empty] | N | N | 2023-07-10 16:14
8-00819093 | Completed | 60L391 out from RUP, 60CB10 & 60CB11 OOS | RUP 60kV DS, VT Insp | 60L391, RUP 60CB10, RUP 60CB11 | 2023-07-11 07:00 | 2023-07-11 13:22 | 4 | Continuous | [6 empty] | N | N | 2023-07-11 13:23
8-00813281 | Completed | 1L37, MSA 1B5 OOS | MSA 1L37 - 1D22 REPLACE B PHASE CRANK ARM | MSA 1B5, 1L37 | 2023-07-11 08:00 | 2023-07-13 12:42 | NR | Continuous | [6 empty] | Y | N | 2023-07-13 12:42
8-00812621 | Completed | WSN 5CB4 OOS | CB Insp & Doble testing | WSN 5CB4 | 2023-07-11 08:00 | 2023-07-13 18:09 | NR | Continuous | [6 empty] | N | N | 2023-07-13 18:09
8-00812703 | Completed | SEL T4, 2CB10, 2CB11 OOS | Disconnect Inspection | SEL 2CB10, SEL 2CB11 | 2023-07-11 08:00 | 2023-07-11 15:34 | 2 | Continuous | [6 empty] | N | N | 2023-07-11 15:34
8-00809693 | Completed | MDN 2CB12 OOS | CPC Control Testing | MDN 2CB12 | 2023-07-11 08:00 | 2023-07-11 15:15 | 2 | Continuous | [6 empty] | N | N | 2023-07-11 15:15
8-00712754 | Cancelled | MSA 1L37, 1B5, 1CB6, 1CB5 | MSA 1D1CB5, 1D2CB6 inspection, 1D22 crank arm repair + 1CVT5 foam removal | MSA 1CB5, MSA 1CB6, 1L37 | 2023-07-11 08:00 | 2023-07-14 16:00 | 2 | Continuous | [6 empty] | Y | N | 2023-07-05 09:54
8-00819094 | Completed | RUP T2, 60CB9, 60D1CB14 OOS | RUP 60D2 Repair, 12CLSS2 Insp | RUP 60D2, RUP T2 | 2023-07-12 07:00 | 2023-07-12 13:36 | 4 | Continuous | [6 empty] | Y | N | 2023-07-12 13:36
8-00869711 | Completed | 5L83 OOS | Urgent repair - Replace bent operating arms on disconnects. | 5L83, RYC 5CX1, RYC 5CB1 | 2023-07-12 08:00 | 2023-07-14 14:20 | 5 | Continuous | [6 empty] | N | N | 2023-07-14 14:20
8-00864749 | Completed | FLW 2CB2 OOS | 2CB2 INSP | FLW 2CB2 | 2023-07-12 08:00 | 2023-07-13 14:29 | 2 | Continuous | [6 empty] | N | N | 2023-07-13 14:29
8-00809892 | Completed | MDN 2CB17 OOS | CPC Breaker Fail Testing | MDN 2CB17 | 2023-07-12 08:00 | 2023-07-12 13:33 | 2 | Continuous | [6 empty] | N | N | 2023-07-12 13:33
8-00809669 | Completed | ACK 5CB3 OOS | INSP and DOBLE | ACK 5CB3 | 2023-07-12 08:00 | 2023-07-14 12:09 | 2 | Continuous | [6 empty] | N | N | 2023-07-14 12:09
8-00806905 | Completed | CBK 5CB13 OOS | Breaker Fail testing NERC PM | CBK 5CB13 | 2023-07-12 08:00 | 2023-07-13 18:13 | 3 | Continuous | [6 empty] | N | N | 2023-07-13 18:13
8-00868521 | Completed | L82-88 OOS | Hotspot Repair | L82-88 | 2023-07-13 07:00 | 2023-07-13 18:00 | NR | Continuous | [6 empty] | N | N | 2023-07-23 06:42
8-00810405 | Cancelled | 1L364, FOX OOS | FOX DS, CVT Insp | 1L364 | 2023-07-13 08:00 | 2023-07-13 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-09 13:55
8-00819064 | Denied | 2L102 OOS | BQN RX PN PM | SKA 2RX2, 2L102, BQN 2RX22, BQN 2RX25, BQN 2RX231, 2L374, BQN 2RX232 | 2023-07-13 09:00 | 2023-07-13 19:00 | NR | Continuous | [6 empty] | Y | N | 2023-06-27 11:19
8-00819087 | Completed | 60L392 out from RUP | RUP CVT Insp and Doble testing | 60L392 | 2023-07-13 10:00 | 2023-07-13 12:04 | 4 | Continuous | [6 empty] | N | N | 2023-07-13 12:04
8-00750916 | Cancelled | VIT T9, SC4 OOS | VIT SC4 Eplan Placeholder | VIT SC4, VIT T9 | 2023-07-14 16:00 | 2023-07-14 17:00 | 1 | Continuous | [6 empty] | N | N | 2023-05-30 10:20
8-00827294 | Cancelled | 1L387 OOS | Transmission line splicing | 1L387 | 2023-07-15 08:00 | 2023-07-15 16:00 | 2 | Continuous | [6 empty] | Y | N | 2023-06-26 14:15
8-00821146 | Completed | TKW T2, T4, 12RX2, 5MB1 OOS | TKW DS Insp and T2 Doble testing | TKW 5MB1, TKW T2, TKW T4, TKW 1B11, TKW 12RX2 | 2023-07-17 08:00 | 2023-07-20 21:04 | 4 | Continuous | [6 empty] | N | N | 2023-07-20 21:04
8-00818764 | Completed | SKA 60CB1 OOS | SKA 60CB1 Insp | SKA 60CB1 | 2023-07-17 08:00 | 2023-07-19 14:17 | 2 | Continuous | [6 empty] | N | N | 2023-07-19 14:17
8-00812706 | Completed | 2L295, KCL 2CB5, 2CB6, 2D26 OOS | PM Inspection | 2L295, KCL 2CB5, KCL 2CB6 | 2023-07-17 08:00 | 2023-07-21 13:17 | 4 | Continuous | [6 empty] | N | N | 2023-07-21 17:26
8-00813207 | Proposed | SPL T1 OOS | Environmental Remediation | SPL T1 | 2023-07-17 08:00 | 2023-07-19 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-27 12:49
8-00803294 | Completed | 1L138 OOS | End of Life Structure Replacements | LDY T2, 1L138 | 2023-07-17 08:00 | 2023-07-21 14:39 | 2 | Continuous | [6 empty] | N | N | 2023-07-21 14:40
8-00810407 | Cancelled | 2L309, DKT 2B2 OOS | DKT SSVT OYSR | DKT 2B2, 2L309 | 2023-07-17 08:00 | 2023-07-17 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-27 14:13
8-00811377 | Completed | DMR 5CB15 OOS | DMR 5CB15, 5CT15 INSP & CN | DMR 5CB15 | 2023-07-17 08:00 | 2023-07-19 16:08 | 2 | Continuous | [6 empty] | N | N | 2023-07-19 16:08
8-00806037 | Completed | 2L39, NEL 2B2, 2CB2, 2CB3 OOS | NERC PM, INSP | 2L39, NEL 2B2 | 2023-07-17 08:00 | 2023-07-21 11:33 | 2 | Continuous | [6 empty] | N | N | 2023-07-21 11:34
8-00807680 | Completed | 5L7 OOS | Insulator Repl | 5L7 | 2023-07-17 08:00 | 2023-07-21 14:16 | 4 | Continuous | [6 empty] | Y | N | 2023-07-21 14:16
8-00807552 | Completed | 60L223 OOS | Replace end of life structures and crossarms | 60L223 | 2023-07-17 14:00 | 2023-07-28 16:05 | 4 | Continuous | [6 empty] | N | Y | 2023-07-31 07:06
8-00869744 | Completed | CYP T2 OOS, 2L13 Switching OOS | to determine the difference in noise level with the transformer online versus offline | CYP T2 | 2023-07-18 05:45 | 2023-07-18 06:27 | 0 | Continuous | [6 empty] | Y | N | 2023-07-18 06:27
8-00812732 | Completed | NTL T2, 60CB2 OOS | Breaker inspection | NTL 60CB2, NTL T2 | 2023-07-18 06:00 | 2023-07-18 15:59 | 2 | Continuous | [6 empty] | N | N | 2023-07-18 15:59
8-00819075 | Proposed | 60L391 out from OFD, OFD T2, T3 OOS | OFD DS, VT Insp | OFD 60D1CB5, OFD 60D22, OFD 60D2CB4, 60L391, OFD T2, OFD T3 | 2023-07-18 06:00 | 2023-07-18 22:00 | NR | Continuous | [6 empty] | N | N | 2023-06-28 08:59
8-00868188 | Completed | SYA 5CX1 OOS | SYA 5CX1 Cap Thor Low Air | SYA 5CX1 | 2023-07-18 08:00 | 2023-07-19 11:41 | 5 | Continuous | [6 empty] | N | N | 2023-07-19 11:41
8-00809898 | Completed | MDN 2CB18 OOS | CPC Control Testing | MDN 2CB18 | 2023-07-18 08:00 | 2023-07-18 15:24 | 2 | Continuous | [6 empty] | N | N | 2023-07-18 15:24
8-00809900 | Completed | MDN 2CB19 OOS | CPC Breaker Fail Testing | MDN 2CB19 | 2023-07-19 08:00 | 2023-07-19 15:49 | 2 | Continuous | [6 empty] | N | N | 2023-07-19 15:49
8-00810347 | Completed | VVW 1CB8 OOS | Inspection | VVW 1CB8 | 2023-07-19 08:00 | 2023-07-20 13:48 | 4 | Continuous | [6 empty] | N | N | 2023-07-20 13:48
8-00818766 | Completed | SKA 60CB2 OOS | SKA 60CB2 Insp | SKA 60CB2 | 2023-07-19 12:01 | 2023-07-19 14:44 | 2 | Continuous | [6 empty] | N | N | 2023-07-19 14:44
8-00875811 | Completed | CRK 5CX1 Forced OOS | Capacitor damage | CRK 5CX1 | 2023-07-21 18:34 | 2023-08-18 17:19 | NR | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-08-18 21:27
8-00807588 | Proposed | AFT T1 OOS | ETM Replacement | AFT T1 | 2023-07-23 08:00 | 2023-08-30 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-31 12:03
8-00807681 | Completed | 5L12 oos | Insulator Repl | 5L12 | 2023-07-24 08:00 | 2023-07-28 14:57 | 4 | Continuous | [6 empty] | N | N | 2023-07-28 14:57
8-00868398 | Cancelled | 3L5 OOS | Complete Tower Painting between 00/02 and 01/04 | 3L5 | 2023-07-24 08:00 | 2023-08-02 16:00 | 5 | Continuous | [6 empty] | Y | N | 2023-07-24 08:36
8-00821147 | Cancelled | TKW T3 & T5 OOS | TKW T3 & T5 Non-EL PN PM | TKW 12RX3, TKW T3, TKW T5 | 2023-07-24 08:00 | 2023-07-25 16:00 | NR | Continuous | [6 empty] | N | N | 2023-07-06 14:39
8-00812758 | Completed | 2L293 out from NLY 2B2 OOS | Inspection | 2L293, NLY 2CB2, NLY 2CB3, NLY 2B2 | 2023-07-24 08:00 | 2023-07-25 15:16 | 2 | Continuous |  |  |  |  | 560 | 600 | N | N | 2023-07-25 15:17
8-00812694 | Completed | 2L293 OOS and SEL 2MB2 OOS | Inspection | 2L293, SEL 2CB13, SEL 2CB5, SEL 2CB3, SEL 2MB2 | 2023-07-24 08:00 | 2023-07-28 14:10 | 2 | Continuous |  |  |  |  | 560 | 600 | Y | N | 2023-07-28 14:10
8-00813208 | Proposed | SPL T2 OOS | Environmental Remediation | SPL T2 | 2023-07-24 08:00 | 2023-07-26 16:00 | NR | Continuous | [6 empty] | N | N | 2023-07-19 07:30
8-00806529 | Completed | 2L293 OOS | Replace timbers | 2L293 | 2023-07-24 10:00 | 2023-08-11 11:40 | 6 | Continuous |  |  |  |  | 560 | 600 | Y | N | 2023-08-11 12:24
8-00812151 | Cancelled | 60L21 out from BR1, BR1 T30 OOS | BR1 60CB1 INSP, BR1 60D2CB1 INSP, BR1 60CB30 INSP, BR1 60DCB30 INSP | 60L21, BR1 T30, BR1 60B2 | 2023-07-24 12:30 | 2023-07-27 16:00 | 4 | Continuous | [6 empty] | Y | N | 2023-07-24 14:28
8-00811770 | Completed | DMR 5CB24 OOS | DMR 5CB24, 5CT24 INSP | DMR 5CB24 | 2023-07-25 08:00 | 2023-07-26 16:18 | 2 | Continuous | [6 empty] | N | N | 2023-07-26 16:22
8-00810411 | Completed | 1L349, SLS T1 OOS | SLS DS, CVT Insp | SLS T1, 1L349 | 2023-07-25 08:00 | 2023-07-25 15:29 | NR | Continuous | [6 empty] | N | N | 2023-07-25 15:42
8-00806977 | Proposed | SEL 2PT13 OOS | Replace yard flood lights | 2L293, SEL 2MB2 | 2023-07-25 08:00 | 2023-07-26 16:00 | NR | Continuous | [6 empty] | N | N | 2023-07-20 08:03
8-00809901 | Completed | MDN 2CB20 OOS | CPC Breaker Fail Testing | MDN 2CB20 | 2023-07-25 08:00 | 2023-07-25 14:21 | 2 | Continuous | [6 empty] | N | N | 2023-07-25 14:21
8-00801135 | Completed | 60L17 Out from NWR | Detailed Inspection | 60L17 | 2023-07-25 08:00 | 2023-07-28 16:18 | 2 | Continuous | [6 empty] | N | N | 2023-07-28 16:18
8-00812696 | Cancelled | SEL 2CB5 OOS | Breaker Inspection | SEL 2CB5 | 2023-07-25 08:00 | 2023-07-27 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-07-21 11:13
8-00813802 | Cancelled | 1L349, SLS T1 OOS | SLS T1 Non-EL PN PM | SLS T1, 1L349 | 2023-07-25 08:00 | 2023-07-25 16:00 | NR | Continuous | [6 empty] | N | N | 2023-04-06 11:25
8-00823319 | Cancelled | 60L390 out from 60D1L390 to 60D2L390 | Transmission line splices | 60L390 | 2023-07-25 08:00 | 2023-08-04 18:00 | NR | Continuous | [6 empty] | N | N | 2023-05-29 16:22
8-00807569 | Completed | KCL T5, 60CB5 OOS, 25L Closed | Replace 60CB5 | KCL 60CB5, KCL T5 | 2023-07-25 09:00 | 2023-08-18 16:42 | 120 | Continuous | [6 empty] | N | N | 2023-08-18 22:41
8-00875222 | Completed | BQN 2CX1 OOS | Captohor top-up | BQN 2CX1 | 2023-07-25 11:00 | 2023-07-25 15:45 | 3 | Continuous | [6 empty] | Y | N | 2023-07-25 15:52
8-00813595 | Completed | HPN 2CB7 OOS | NERC PM | HPN 2CB7 | 2023-07-26 08:00 | 2023-07-26 15:33 | 2 | Continuous | [6 empty] | N | N | 2023-07-26 15:34
8-00809484 | Completed | COK 2CB1 OOS | CPC Control Testing | COK 2CB1 | 2023-07-26 08:00 | 2023-07-26 15:13 | 2 | Continuous | [6 empty] | N | N | 2023-07-26 15:14
8-00807598 | Completed | MON T4 OOS | PCB Bushing Replacement | MON T3, MON T4 | 2023-07-26 08:00 | 2023-09-13 10:00 | NR | Continuous | [6 empty] | N | N | 2023-10-24 15:20
8-00810638 | Proposed | AVO T1 OOS | PCB Env Remediation T1 | AVO T1 | 2023-07-27 08:00 | 2023-07-29 16:00 | NR | Continuous | [6 empty] | N | N | 2023-07-05 09:16
8-00810639 | Cancelled | AVO T1 OOS | Inspection | AVO T1 | 2023-07-27 08:00 | 2023-07-28 16:00 | NR | Continuous | [6 empty] | N | N | 2023-07-17 09:47
8-00811823 | Completed | DMR 5CB4 OOS | DMR 5CB4, 5CT4 INSP & CN | DMR 5CB4 | 2023-07-27 08:00 | 2023-07-28 16:10 | 2 | Continuous | [6 empty] | N | N | 2023-07-28 16:10
8-00810410 | Completed | 2L342, SLS 2B22 OOS | SLS VT Insp and DOBL | 2L342, SLS 2B22 | 2023-07-28 08:00 | 2023-07-28 14:09 | NR | Continuous | [6 empty] | N | N | 2023-07-28 14:09
8-00659441 | Completed | 5L63 OOS | Telkwa Relocation Project | 5L63 | 2023-07-30 05:00 | 2023-08-04 21:50 | 96 | Continuous | [6 empty] | Y | N | 2023-08-04 22:30
8-00814159 | Completed | 5L63, TKW 5RX1 OOS | TKW 5RX1 Life Extension | 5L63, TKW 5B12, TKW 5B2, TKW 5RX1 | 2023-07-30 05:00 | 2023-08-04 21:50 | 8 | Continuous | [6 empty] | N | N | 2023-08-04 22:18
8-00856644 | Completed | 60L390 out from 60D1L390 | Automatic splice replacement | 60L390 | 2023-07-30 08:00 | 2023-08-01 16:03 | 24 | Continuous | [6 empty] | Y | N | 2023-08-08 09:32
8-00854417 | Completed | 5L63 OOS | Flar work on 5L63 | 5L63, SKA 5CB12, SKA 5CB2 | 2023-07-30 08:00 | 2023-08-01 16:33 | 2 | Continuous | [6 empty] | N | N | 2023-08-01 16:33
8-00812733 | Completed | NTL 60CB12, 60VT4 OOS | Inspection, doble and BFPN testing | 60L281 | 2023-07-31 06:30 | 2023-08-03 17:01 | 4 | Continuous | [6 empty] | N | N | 2023-08-03 17:01
8-00812923 | Completed | DMR 1CB2 OOS | DMR 1CB2 CN | DMR 1CB2 | 2023-07-31 08:00 | 2023-07-31 16:03 | 2 | Continuous | [6 empty] | N | N | 2023-07-31 16:03
8-00812697 | Cancelled | SEL 2CB13 OOS | Breaker Inspection | SEL 2CB13 | 2023-07-31 08:00 | 2023-08-02 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-07-21 11:13
8-00813206 | Cancelled | HLD T2 OOS | Environmental Remediation | HLD T2 | 2023-07-31 08:00 | 2023-08-02 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-04 13:31
8-00813602 | Completed | MUR T8, 2B7 OOS | INSP, PN PM | MUR 2B7, MUR T8 | 2023-07-31 08:00 | 2023-08-02 14:09 | 2 | Continuous | [6 empty] | N | N | 2023-08-02 14:09
8-00813759 | Completed | GMS T14 OOS | GMS T14 Insp, DOBL, Non-EL PN PM | GMS T14 | 2023-07-31 08:00 | 2023-08-04 18:30 | 3 | Continuous | [6 empty] | N | N | 2023-08-05 20:27
8-00818580 | Cancelled | 5L63, TKW 5RX1 OOS | TKW 5RX1 NON-ELE PN PM | 5L63, TKW 5RX1 | 2023-07-31 08:00 | 2023-08-01 16:00 | NR | Continuous | [6 empty] | N | N | 2023-07-24 10:41
8-00795924 | Completed | 2L128, DMR 2B13 OOS | DMR 2D1CB23, 2D2CB13 INSP | DMR 2B13, HWW T2, 2L128 | 2023-07-31 08:00 | 2023-08-01 16:16 | 2 | Continuous | [6 empty] | Y | N | 2023-08-01 16:22
8-00801136 | Completed | 2L51 OOS | Detailed Inspection | BND T2, 2L51 | 2023-07-31 08:00 | 2023-08-04 13:49 | 2 | Continuous | [6 empty] | Y | N | 2023-08-04 14:02
8-00802859 | Completed | 2L154 OOS | End of Life Structure Replacements | 2L154 | 2023-07-31 08:00 | 2023-08-04 15:02 | 2 | Continuous | [6 empty] | Y | N | 2023-08-04 15:02
8-00805740 | Completed | MDN 5CB6 OOS | POW commissioning | MDN 5CB6 | 2023-07-31 08:00 | 2023-07-31 15:39 | 4 | Continuous | [6 empty] | N | N | 2023-07-31 15:39
8-00810354 | Completed | 1L209 Out from VVW 1D24, VVW 1B4 OOS | DS PM 1D1CB1, 1D1CB4 | 1L209, VVW 1CB1, VVW 1CB4, VVW 1B4 | 2023-07-31 08:00 | 2023-08-01 13:35 | 4 | Continuous | [6 empty] | N | N | 2023-08-01 13:35
8-00807683 | Completed | 5L13 OOS | Insulator Repl | 5L13 | 2023-07-31 08:00 | 2023-08-04 15:10 | 4 | Continuous | [6 empty] | N | N | 2023-08-04 15:11
8-00785736 | Completed | REV T8 OOS | 500 kV Disconnect Maintenance | REV T8 | 2023-07-31 22:00 | 2023-08-11 15:46 | 4 | Continuous | [6 empty] | N | N | 2023-08-11 15:46
8-00807596 | Cancelled | MON T3 OOS | PCB Bushing Replacement | MON T3 | 2023-08-01 08:00 | 2023-09-01 16:00 | NR | Continuous | [6 empty] | N | N | 2023-02-24 10:48
8-00809494 | Completed | COK 2CB2 OOS | CPC Control Testing | COK 2CB2 | 2023-08-01 08:00 | 2023-08-01 14:40 | 2 | Continuous | [6 empty] | N | N | 2023-08-01 14:40
8-00807548 | Cancelled | VNT T11 OOS | Replace yard flood lights | VNT T11 | 2023-08-01 08:00 | 2023-08-01 12:00 | NR | Continuous | [6 empty] | N | N | 2023-07-11 15:52
8-00810412 | Cancelled | 2L322, BLM TVC oos | Pole Repl | 2L322 | 2023-08-01 08:00 | 2023-08-03 16:00 | NR | Continuous | [6 empty] | N | Y | 2023-07-25 14:58
8-00812924 | Completed | DMR 1CB3 OOS | DMR 1CB3 CN | DMR 1CB3 | 2023-08-01 08:00 | 2023-08-01 14:36 | 2 | Continuous | [6 empty] | N | N | 2023-08-01 14:47
8-00810406 | Completed | 1L364 out from FJN to 1D2L364 | FJN DS, CVT Insp | 1L364, FJN 1B4 | 2023-08-02 08:00 | 2023-08-05 09:10 | NR | Continuous | [6 empty] | N | N | 2023-08-05 09:11
8-00810355 | Completed | 1L242 Out from VVW 1D23, VVW 1B9 OOS | DS PM 1D2CB9, 1D2CB5 | 1L242, VVW 1CB8, VVW 1CB5, VVW 1B9 | 2023-08-02 08:00 | 2023-08-02 14:18 | 4 | Continuous | [6 empty] | N | N | 2023-08-21 03:30
8-00809505 | Completed | COK 2CB5 OOS | CPC Control Testing | COK 2CB5 | 2023-08-02 08:00 | 2023-08-02 14:25 | 2 | Continuous | [6 empty] | N | N | 2023-08-02 14:25
8-00721888 | Completed | 60L20 By-pass (Out from CRQ) | CRQ replacement project | 60L20 | 2023-08-02 08:00 | 2023-08-04 08:52 | 3 | Continuous | [6 empty] | Y | N | 2023-08-04 08:52
8-00795122 | Completed | 2L154, GLD T1, GLD T4, DMR 2B3 OOS | 2L154, DMR 2D22, 2B3, GLD T1, T4, 1B1 - INSP | 2L154, DMR 2B3 | 2023-08-02 08:00 | 2023-08-04 15:04 | 2 | Continuous | [6 empty] | N | N | 2023-08-04 15:04
8-00794308 | Completed | 2L154, GLD T1, T4 OOS | 54, DMR 2D22, 2B3, GLD T1, T4, 1B1 - INSP | 2L154, GLD 1B1, GLD T1, GLD T4 | 2023-08-02 08:00 | 2023-08-03 15:16 | 2 | Continuous | [6 empty] | N | N | 2023-08-19 03:30
8-00806008 | Cancelled | HPN T3 OOS | HPN T3 NON-ELE PN PM | HPN T3 | 2023-08-03 08:00 | 2023-08-04 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-02-06 13:31
8-00813818 | Cancelled | KDS T3 OOS | KDS T3 Non-EL PN PM | KDS T3 | 2023-08-03 08:00 | 2023-08-03 16:00 | NR | Continuous | [6 empty] | N | N | 2023-07-13 15:15
8-00721962 | Completed | 60L20, 60L29, 60L301 all out from CRQ | CRQ replacement project | 60L20, 60L29, 60L301 | 2023-08-04 07:00 | 2023-08-04 14:09 | 3 | Continuous | [6 empty] | Y | N | 2023-08-20 03:30
8-00813813 | Proposed | 1L373 OOS | Structure Repl | 1L373 | 2023-08-04 08:00 | 2023-08-04 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-30 23:36
8-00813817 | Proposed | 1L373, 1L366, 1L368 OOS | MFE DS Insp and T1 Non-EL PN PM | 1L366, 1L368, 1L373, MFE T1 | 2023-08-04 08:00 | 2023-08-04 16:00 | NR | Continuous | [6 empty] | N | Y | 2023-07-07 09:15
8-00731734 | Completed | 60L301 Out from CRQ | CRQ replacement project | CRQ 60CB1, CRQ 60CB2, CRQ 60CB3, 60L20, 60L29, 60L301, CRQ 60B1 | 2023-08-04 12:00 | 2023-09-05 | 720 | Continuous | [6 empty] | Y | N | 2023-09-05 01:44
8-00813205 | Cancelled | HLD T1 OOS, 1L205 Switching | Environmental Remediation | HLD T1 | 2023-08-07 08:00 | 2023-08-09 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-04 13:31
8-00818842 | Cancelled | SKA T2, 5CB12 OOS | SKA 5CT12 Insp | SKA 5CB12, SKA T2 | 2023-08-08 08:00 | 2023-08-08 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-08-17 09:19
8-00819634 | Cancelled | HMH T5 OOS | HMH T5 Insp and Doble testing | HMH T5 | 2023-08-08 08:00 | 2023-08-18 16:00 | 12 | Continuous | [6 empty] | N | N | 2023-08-02 14:24
8-00689978 | Cancelled | 1L201 OOS | End of Life Structure and Cross Arm Replacement | 1L201 | 2023-08-08 08:00 | 2023-08-17 16:00 | NR | Continuous | [6 empty] | N | Y | 2022-02-03 14:41
8-00797185 | Completed | 60L83, SNY T1, 60D23, SS1 OOS | SNY T1 NON-EL, SNY 25CB1 BFPN, SNY 60D21 INSP, SNY 60D1 INSP, SNY 60D23 INSP | SNY T1, 60L83 | 2023-08-08 08:00 | 2023-08-09 16:42 | 2 | Continuous | [6 empty] | N | N | 2023-08-09 16:42
8-00805746 | Cancelled | 5L83, MDN 5CB6 OOS | POW commissioning | 5L83 | 2023-08-08 08:00 | 2023-08-09 16:00 | 0 | Return Evenings | [6 empty] | N | N | 2023-08-08 11:05
8-00803293 | Completed | 1L119 OOS | End of Life Structure Replacements | CBL T1, 1L119 | 2023-08-08 08:00 | 2023-08-11 11:57 | 2 | Continuous | [6 empty] | N | N | 2023-08-11 12:26
8-00801137 | Completed | 2L55 OOS | Detailed Inspection | 2L55 | 2023-08-08 08:00 | 2023-08-14 14:55 | 8 | Continuous | [6 empty] | N | N | 2023-08-14 14:55
8-00809508 | Completed | COK 2CB7 OOS | CPC Control Testing | COK 2CB7 | 2023-08-08 08:00 | 2023-08-08 14:48 | 2 | Continuous | [6 empty] | N | N | 2023-08-08 14:49
8-00810800 | Completed | ARM T1 OOS | Inspection | ARM T1 | 2023-08-08 08:00 | 2023-08-10 13:29 | 8 | Continuous | [6 empty] | N | N | 2023-08-10 13:29
8-00818726 | Completed | SKA T4 OOS | SKA T4 bushing Repl | SKA T4 | 2023-08-09 08:00 | 2023-09-18 17:29 | 120 | Continuous | [6 empty] | N | N | 2023-09-18 17:29
8-00813603 | Completed | HPN 2CB8 OOS | NERC PM | HPN 2CB8 | 2023-08-09 08:00 | 2023-08-09 16:11 | 2 | Continuous | [6 empty] | Y | N | 2023-08-09 16:11
8-00813330 | Cancelled | CKY 2CB8 OOS | PM INSPECTION of CKY 2CB8 | CKY 2CB8 | 2023-08-09 08:00 | 2023-08-11 16:00 | 8 | Continuous | [6 empty] | N | N | 2023-07-20 09:27
8-00812808 | Cancelled | 60L281 SPD60CVT21 OOS | Inspections | 60L281 | 2023-08-10 08:00 | 2023-08-10 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-07-26 10:11
8-00813751 | Approved | DMR T4 OOS | DMR T4 NON ELEC & 2CB26 CN | DMR 2CB26, DMR T4 | 2023-08-10 08:00 | 2023-08-11 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-08-10 17:58
8-00805747 | Cancelled | MDN 5CB6, T3 OOS | POW (Point on Wave) Commissioning | MDN T3, MDN 5MB2, MDN 5CB6 | 2023-08-10 08:00 | 2023-08-11 16:00 | 0 | Return Evenings | [6 empty] | N | N | 2023-08-08 10:31
8-00785679 | Completed | Illecillewaet T1 OOS | Preventative Maintenance work | ILL T1 | 2023-08-13 06:00 | 2023-08-18 14:01 | 8 | Continuous | [6 empty] | N | N | 2023-08-18 14:01
8-00818624 | Cancelled | 1L387 OOS | 1L387 Splices | 1L381, 1L387, 1L403, 1L402 | 2023-08-13 06:00 | 2023-08-13 14:00 | 2 | Continuous | [6 empty] | N | N | 2023-08-04 08:15
8-00798984 | Completed | 2L253 OOS | Replace EOL Structures and Cross Arms | 2L253 | 2023-08-13 07:00 | 2023-08-20 06:16 | 3 | Continuous | [6 empty] | Y | Y | 2023-08-20 06:16
8-00803295 | Completed | 1L102 OOS | End of Life Structure Replacements | 1L102, CMX T2, CBL T3 | 2023-08-14 08:00 | 2023-08-18 16:11 | 2 | Continuous | [6 empty] | N | N | 2023-08-18 16:12
8-00801139 | Completed | 2L50 OOS | Detailed Inspection | 2L50 | 2023-08-14 08:00 | 2023-08-18 13:58 | 2 | Continuous | [6 empty] | N | Y | 2023-08-18 13:58
8-00805310 | Completed | CK5 5MB1 OOS | Replace bus protection relays | CK5 5CB1, CK5 5CB2, CK5 5MB1, CK5 5CB3 | 2023-08-14 08:00 | 2023-08-17 17:26 | 4 | Continuous | [6 empty] | N | N | 2023-08-17 17:26
8-00810852 | Completed | VIT 2CB1, 2CB5, 2CB7, 2MB1 OOS | VIT 2CB1, 2D1CB1, 2CVTMB1 INSP | VIT 2CB1, VIT 2CB7, VIT 2CB5, VIT 2MB1 | 2023-08-14 08:00 | 2023-08-18 14:27 | 2 | Continuous | [6 empty] | N | N | 2023-08-18 14:27
8-00813756 | Cancelled | 1L364 out from GMS | GMS DS Insp | 1L364, GMS 1B4 | 2023-08-14 08:00 | 2023-08-18 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-30 17:20
8-00813789 | Completed | BMT T3, 1B1 OOS | BMT DS, CVT, SS Insp and T3 Doble Testing | BMT 1B1, BMT T3, BMT 1CX1 | 2023-08-14 08:00 | 2023-08-15 18:20 | 3 | Continuous | [6 empty] | N | N | 2023-08-31 03:30
8-00813819 | Completed | KDS T4 OOS | KDS Transf PM and Doble testing | KDS T4, KDS 1B5 | 2023-08-14 08:00 | 2023-08-28 15:14 | 12 | Continuous | [6 empty] | N | N | 2023-08-28 15:14
8-00815877 | Proposed | SCK 2CB2 | SCK CB PN PM | SCK 2CB2 | 2023-08-14 08:00 | 2023-08-14 16:00 | NR | Continuous | [6 empty] | N | N | 2023-02-04 21:15
8-00812477 | Proposed | 2L94 OOS | Structure Repl | 2L94 | 2023-08-14 08:00 | 2023-08-17 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-26 13:57
8-00870191 | Completed | BSY G3 OOS | Inspection & Maintenance | BSY T3, BSY G3 | 2023-08-14 08:00 | 2023-08-17 20:33 | 96 | Continuous | [6 empty] | N | N | 2023-08-17 20:33
8-00881028 | Completed | RYC 5CX1 OOS | Troubleshoot RYC bank issue | RYC 5CX1 | 2023-08-14 08:00 | 2023-08-18 11:53 | 4 | Continuous | [6 empty] | N | N | 2023-08-18 11:53
8-00821495 | Completed | GMS T12 OOS | GMS RTU Cutover | GMS T12 | 2023-08-14 08:00 | 2023-09-01 16:40 | 8 | Continuous | [6 empty] | N | N | 2023-09-01 16:41
8-00812933 | Cancelled | DMR T7 OOS | DMR 2CB7, T7, 1CB14 INSP CN , NETS, 2SA7 REPL | DMR T7 | 2023-08-15 08:00 | 2023-08-23 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-08-10 08:44
8-00821238 | Completed | GLN T2, T5, 2B2 OOS | GLN 2D2 Insp | GLN 2B2, GLN 5MB2, GLN T2, GLN T5 | 2023-08-15 08:00 | 2023-08-17 13:19 | 4 | Continuous | [6 empty] | N | N | 2023-08-17 13:19
8-00807570 | Cancelled | KCL T5 OOS | Environmental Remediation | KCL T5 | 2023-08-15 08:00 | 2023-08-17 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-11 13:59
8-00797187 | Completed | 60L87, SNY T2, 60D23, SS2 | SNY T2 NON-EL, SNY 25CB2 BFPN, SNY 60D22 INSP, SNY 60D2 INSP, SNY INSTALL 60D23 BUS CUT | SNY T2, SNY 60D23, 60L87 | 2023-08-15 08:00 | 2023-08-16 14:26 | 4 | Continuous | [6 empty] | N | Y | 2023-08-16 14:26
8-00718695 | Completed | DAW T2 OOS | Bushing Repl | DAW T2 | 2023-08-15 14:00 | 2023-09-13 12:20 | 120 | Continuous | [6 empty] | N | N | 2023-09-13 12:20
8-00882053 | Completed | BMT T3, 2MB3, 2B21 OOS | BMT T3, DS, CVT, SS inspections | BMT T3, BMT 2B21, BMT 2MB3 | 2023-08-15 16:00 | 2023-08-16 17:21 | 3 | Continuous | [6 empty] | N | N | 2023-08-16 17:21
8-00812041 | Completed | JHT 1B10 OOS | JHT 1D1CB9, 1D2CB10 INSP | JHT 1CB9, JHT 1CB10, JHT 1B10 | 2023-08-16 07:00 | 2023-08-17 17:29 | 2 | Continuous | [6 empty] | N | N | 2023-08-17 17:29
8-00812266 | Completed | MUR 2CB9 OOS | NERC PM | MUR 2CB9 | 2023-08-17 08:00 | 2023-08-17 16:42 | 2 | Continuous | [6 empty] | N | N | 2023-08-17 18:09
8-00797190 | Completed | 60L87, SNY T2, 60D23, SS2 OOS | SNY Restore 60D23 BUS CUT LINK | SNY T1, SNY 60B1, KTG 60B2, KTG 60D23, 60L83 | 2023-08-17 08:00 | 2023-08-17 15:24 | NR | Continuous | [6 empty] | N | N | 2023-08-17 15:25
8-00882217 | Completed | CRK 5CX1 OOS | To replace A phase failed capacitors (forced out) | CRK 5CX1 | 2023-08-17 08:00 | 2023-08-18 17:23 | 3 | Continuous | [6 empty] | N | N | 2023-08-18 21:27
8-00814419 | Cancelled | CK5 5CB1 OOS | Trip Testing | CK5 5CB1 | 2023-08-17 08:00 | 2023-08-17 16:00 | 1 | Continuous | [6 empty] | N | N | 2023-08-19 18:00
8-00884458 | Completed | 5L41 OOS | Forced out due to wildfire | 5L41 | 2023-08-17 19:50 | 2023-08-23 21:04 | NR | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-10-22 17:53
8-00884467 | Completed | 5L72 Forced OOS | Forced out due to wildfire | 5L72 | 2023-08-17 20:48 | 2023-08-18 12:07 | NR | Continuous | [6 empty] | N | N | 2023-08-18 12:07
8-00814421 | Cancelled | CK5 5CB3 OOS | Trip testing | CK5 5CB3 | 2023-08-18 08:00 | 2023-08-18 16:00 | 1 | Continuous | [6 empty] | N | N | 2023-08-20 18:00
8-00712732 | Cancelled | MSA 2L48, 2B2, 2CB3, 2CB2 | MSA 2D22, 2D2CB2, 2D1CB3 Inspection + SCADA testing | MSA 2CB2, MSA 2CB3, MSA 2B2, 2L48 | 2023-08-18 08:00 | 2023-08-20 16:00 | 2 | Continuous | [6 empty] | N | N | 2022-04-10 17:12
8-00785704 | Completed | Illecillewaet T2 OOS | Inspection & Doble Testing | ILL T2 | 2023-08-21 08:00 | 2023-09-05 08:06 | 8 | Continuous | [6 empty] | N | Y | 2023-09-05 08:06
8-00805311 | Completed | CK5 5MB1 OOS | Replace bus protection relays | CK5 5CB1, CK5 5CB2, CK5 5MB1, CK5 5CB3 | 2023-08-21 08:00 | 2023-08-24 14:10 | 4 | Continuous | [6 empty] | N | N | 2023-08-24 14:10
8-00801140 | Completed | 60L35 Out from NWR | Detailed Inspection | 60L35 | 2023-08-22 08:00 | 2023-08-23 14:10 | 2 | Continuous | [6 empty] | N | N | 2023-08-23 14:10
8-00802853 | Completed | 1L115 OOS | COB Insulator Replacements | 1L115, PVL T2 | 2023-08-22 08:00 | 2023-08-25 16:10 | 2 | Continuous | [6 empty] | Y | Y | 2023-08-25 16:10
8-00775659 | Cancelled | LAJ 60D SS1 OOS | Replace SS1 | LAJ 60D1 | 2023-08-22 08:00 | 2023-09-21 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-08 13:48
8-00775661 | Cancelled | LAJ 60D1 OOS | To replace LAJ 480V Station Service | LAJ 60D1 | 2023-08-22 08:00 | 2023-09-21 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-08 13:47
8-00797180 | Completed | 2L142, HSY 2B4 OOS | 2L142 Cable Outage, HSY 2CB4 INSP, HSY 2CB3 INSP | GTP T14, 2L142, HSY 2B4, HSY 2D24 | 2023-08-22 08:00 | 2023-08-25 11:40 | NR | Continuous | [6 empty] | N | N | 2023-08-25 11:52
8-00812148 | Cancelled | 60L22, LAJ 60B1, 60L55 LAJ 12F51 OOS | LAJ 60D22 INSP, LAJ 60D23 INSP, | 60L22, LAJ 60B1, 60L55 | 2023-08-22 08:00 | 2023-08-22 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-08 13:46
8-00811704 | Completed | NEL 2CB1 OOS | BFPN - NERC PM | NEL 2CB1 | 2023-08-22 08:00 | 2023-08-22 15:25 | 2 | Continuous | [6 empty] | N | N | 2023-08-22 15:25
8-00806903 | Completed | CBK 5CB11 OOS | Breaker Fail testing NERC PM | CBK 5CB11 | 2023-08-22 08:00 | 2023-08-25 06:03 | 3 | Continuous | [6 empty] | N | N | 2023-08-25 06:03
8-00806886 | Cancelled | 5L92, CBK 5RX4 OOS | Non-Electrcal testing - NERC PM | 5L92, CBK 5RX4 | 2023-08-22 08:00 | 2023-08-24 16:00 | 4 | Continuous |  |  |  |  | 110 | 300 | N | N | 2023-03-15 13:16
8-00812150 | Cancelled | 60L22, LAJ G1, LAJ 60B1, 60L55, LAJ 12F51 OOS | LAJ D2Y 60D1 PM, LAJ D2Y 60DCB1 PM | LAJ 60B1 | 2023-08-22 08:00 | 2023-08-22 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-08 13:45
8-00812700 | Completed | 5L92, SEL 5CB3, 5CB4 OOS | Inspection | 5L92, SEL 5CB3, SEL 5CB4 | 2023-08-22 08:00 | 2023-08-22 15:33 | 2 | Continuous |  |  |  |  | 30 | 300 | N | N | 2023-08-22 16:28
8-00883954 | Completed | 60L99 OOS | To replace r.o.w. structures | HCT T1, 60L99 | 2023-08-22 08:00 | 2023-08-29 10:52 | 4 | Continuous | [6 empty] | N | N | 2023-08-29 10:53
8-00805337 | Cancelled | 2L90 OOS | Replace Emergent Structures | 2L90 | 2023-08-22 10:00 | 2023-08-25 16:00 | 6 | Continuous | [6 empty] | N | N | 2023-08-16 14:17
8-00811852 | Denied | NEL 2CB6 OOS | BFPN - NERC PM | NEL 2CB6 | 2023-08-23 08:00 | 2023-08-23 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-08-21 12:44
8-00818827 | Completed | SKA T4, 2MB1A, 60CB1, 60CB2 OOS | SKA 230kV and 60kV DS Insp | SKA 2D4, SKA T4, SKA 2MB1A | 2023-08-24 08:00 | 2023-08-25 11:55 | 3 | Continuous | [6 empty] | N | N | 2023-08-25 11:56
8-00886064 | Completed | BQN 2CX1 OOS | Urgent Capthor top-up | BQN 2CX1 | 2023-08-26 11:00 | 2023-08-26 15:01 | 2 | Continuous | [6 empty] | Y | N | 2023-08-26 15:01
8-00884070 | Cancelled | L82-88 OOS | RioTinto work: CT Replacement | L82-88 | 2023-08-28 07:00 | 2023-08-31 17:00 | NR | Continuous | [6 empty] | N | N | 2023-08-22 09:07
8-00797182 | Completed | 2L143, HSY 2B9 OOS | 2L143 Cable Outage, HSY 2CB9 INSP, HSY 2CB10 INSP | 2L143, HSY 2B9 | 2023-08-28 07:00 | 2023-08-31 17:02 | 4 | Continuous | [6 empty] | N | N | 2023-09-16 03:30
8-00775975 | Cancelled | Illecillewaet T4 OOS & 60L218/219 OOS | For Tap Changer Inspectiong and Maintenance. | 60L218, ILL T4, 60L219 | 2023-08-28 08:00 | 2023-09-01 16:00 | 72 | Continuous | [6 empty] | Y | Y | 2023-08-15 09:30
8-00775981 | Cancelled | WHN T7 OOS | Station transformer maintenance | WHN T7 | 2023-08-28 08:00 | 2023-09-01 16:00 | 4 | Continuous | [6 empty] | Y | N | 2023-08-21 10:32
8-00805314 | Denied | CK5 5MB2 OOS | Replace bus protection relays | CK5 5CB21, CK5 5CB22, CK5 5CB23, CK5 5MB2 | 2023-08-28 08:00 | 2023-09-01 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-08-24 11:24
8-00802854 | Completed | 1L116 OOS | COB Insulator Replacements | 1L116, PVL T1, QLC T1 | 2023-08-28 08:00 | 2023-09-01 16:14 | 2 | Continuous | [6 empty] | Y | N | 2023-09-01 16:14
8-00810868 | Completed | VIT 2MB3 2CB3/4/10/11 OOS | VIT 2CB3, 2CB4, 2D2CB3, 2D2CB4 INSP, 2CB10, 2CB11 CN | VIT 2MB3 | 2023-08-28 08:00 | 2023-08-31 14:49 | 2 | Continuous | [6 empty] | N | N | 2023-08-31 14:49
8-00810414 | Denied | 1L364 out from GMS to PPS to 1D1L364 | GMS DS Insp | 1L364, PPS T1, GMS 1B4 | 2023-08-28 08:00 | 2023-09-01 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-24 09:12
8-00806027 | Completed | 2L49, HPN 2CB6 OOS | NERC PM, INSP | 2L49, HPN 2B5 | 2023-08-28 08:00 | 2023-08-31 12:13 | 2 | Continuous | [6 empty] | N | N | 2023-08-31 12:35
8-00807565 | Cancelled | 60L218 OOS | Replace end of life structures and crossarms | 60L218 | 2023-08-28 08:00 | 2023-09-06 16:00 | NR | Return Weekends | [6 empty] | Y | N | 2023-06-26 14:20
8-00819066 | Completed | SKA 2RX2 OOS | SKA RX and CT Insp and Doble testing | SKA 2RX2 | 2023-08-28 08:00 | 2023-08-30 09:16 | 3 | Continuous | [6 empty] | N | N | 2023-08-30 09:16
8-00813755 | Cancelled | DMR T6 OOS | DMR T6 NETS & 2SA6 REPL | DMR T6 | 2023-08-28 08:00 | 2023-08-28 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-07-20 15:17
8-00812713 | Completed | CBK 5CB21 OOS | POW Testing | CBK 5CB21 | 2023-08-28 08:00 | 2023-08-28 10:29 | 2 | Continuous | [6 empty] | N | N | 2023-08-28 10:29
8-00813287 | Cancelled | WLT T3 OOS | NON-ELECTRICALS, ANCHOR INSPECTION, PIPING REPAIR WORK | WLT T3 | 2023-08-28 08:00 | 2023-09-01 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-03 09:21
8-00813665 | Completed | 2L41 OOS | end of life insulator replacement | 2L41 | 2023-08-28 10:00 | 2023-08-31 14:59 | 2 | Continuous | [6 empty] | N | N | 2023-08-31 14:59
8-00813812 | Completed | 1L365 Partial Outage | Structure Repl | 1L365 | 2023-08-28 16:00 | 2023-09-01 12:45 | 4 | Continuous | [6 empty] | N | N | 2023-09-01 14:57
8-00806499 | Completed | MUR T3 OOS | PCB Bushing Replacement | MUR T3 | 2023-08-28 16:00 | 2023-10-10 21:27 | 120 | Continuous | [6 empty] | N | N | 2023-10-26 03:30
8-00888064 | Recalled | 5L92 OOS | Replace defective insulators & spacer | 5L92 | 2023-08-29 06:00 | 2023-08-29 15:01 | 2 | Continuous |  |  |  |  | 30 | 300 | N | N | 2023-08-29 15:01
8-00813280 | Completed | MSA T1, 12RX1 OOS | MSA T1 NON-ELECTRICALS., 5CB1 BUTN, T1 PY/SY PN. NERC, 12RX1 PY/SY PN. NERC | MSA 12RX1, MSA T1 | 2023-08-29 08:00 | 2023-09-01 12:33 | 4 | Continuous | [6 empty] | N | N | 2023-09-01 12:34
8-00812707 | Completed | KCL 2CB10, 2CB11, 2CT10 OOS | BREAKER FAIL PN | KCL 2CB10, KCL 2CB11 | 2023-08-29 08:00 | 2023-09-13 19:10 | NR | Continuous | [6 empty] | Y | N | 2023-09-13 22:35
8-00806520 | Recalled | 5L92 OOS | Replace defective insulators & spacers | 5L92 | 2023-08-29 08:00 | 2023-08-30 16:42 | 6 | Continuous |  |  |  |  | 30 | 300 | N | N | 2023-08-29 05:52
8-00809688 | Completed | 5L76, ACK 5B5 OOS | 5D2CB5 INSP | 5L76, ACK 5B5 | 2023-08-29 08:00 | 2023-08-29 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-09-06 05:29
8-00807585 | Cancelled | INV 60CB11, 60CB11, T4 OOS | Replace yard flood lights | INV 60CB1, INV 60CB11, INV T4 | 2023-08-29 08:00 | 2023-08-29 16:00 | NR | Continuous | [6 empty] | N | N | 2023-04-11 09:53
8-00811417 | Completed | MLN 2CB9 OOS | CPC Control Testing | MLN 2CB9 | 2023-08-29 08:00 | 2023-08-30 14:50 | 2 | Continuous | [6 empty] | N | N | 2023-08-30 14:50
8-00690017 | Cancelled | 2L253 OOS | End of Life Structure and Cross Arm Replacement | 2L253 | 2023-08-29 08:00 | 2023-09-02 16:00 | NR | Continuous | [6 empty] | N | Y | 2022-02-03 14:48
8-00797169 | Completed | 1L18, SAL 1D21, T1 OOS | SAL 1D12 BUS CUT FOR SAL 1D12 INSP | 1L18, SAL T1, SAL 1D21 | 2023-08-29 08:00 | 2023-08-29 14:51 | 2 | Continuous | [6 empty] | N | N | 2023-08-29 14:51
8-00797170 | Completed | 1L18, SAL 1D22, T2 OOS | SAL 1D12 BUS CUT FOR SAL 1D12 INSP | 1L18, SAL T2, SAL 1D12, SAL 1D22 | 2023-08-29 12:00 | 2023-08-30 16:10 | 6 | Continuous | [6 empty] | N | N | 2023-08-31 07:52
8-00806293 | Cancelled | SPG T12 OOS | SPG GIS Feeder Section 5 Addition | SPG T12 | 2023-08-30 08:00 | 2023-11-07 16:00 | 6 | Continuous | [6 empty] | N | Y | 2023-08-28 14:58
8-00805693 | Denied | MDN 2CB30, 2CX3 OOS | CPC Control Testing & RXCX Insp | MDN 2CX3, MDN 2CB30 | 2023-08-30 08:00 | 2023-08-30 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-08-25 18:21
8-00812714 | Cancelled | CBK 5CB23 OOS | POW Testing | CBK 5CB23 | 2023-08-30 08:00 | 2023-08-31 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-14 06:33
8-00813358 | Completed | 2L1 out from RBW, RBW T1 OOS | ETM REPLACMENT, NON-ELEC PN, COOLER INSPECTION | RBW T1, 2L1 | 2023-08-30 08:00 | 2023-08-31 16:13 | 4 | Continuous | [6 empty] | N | N | 2023-08-31 16:13
8-00888865 | Completed | NIC 5RX4 Forced OOS | Equipment damage | NIC 5RX4 | 2023-08-30 14:04 | 2023-11-03 12:33 | NR | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-11-03 12:36
8-00888422 | Cancelled | 5L92 OOS | Replace defective insulators & spacer | 5L92 | 2023-08-31 07:00 | 2023-08-31 13:00 | 2 | Continuous |  |  |  |  | 30 | 300 | N | N | 2023-09-05 15:21
8-00818743 | Completed | SKA T4 OOS | SKA T4 Insp & Doble testing | SKA 60CB1, SKA 60CB2, SKA T4 | 2023-08-31 08:00 | 2023-09-01 13:37 | 3 | Continuous | [6 empty] | N | Y | 2023-09-01 14:52
8-00811419 | Completed | MLN 2CB10 OOS | CPC Control Testing | MLN 2CB10 | 2023-08-31 08:00 | 2023-08-31 14:42 | 2 | Continuous | [6 empty] | N | N | 2023-08-31 17:04
8-00793370 | Completed | 1L18, SAL 1D21, 1D12 OOS | SAL 1D12 RESTORE BUS CUT LINK | 1L18, SAL T1, SAL 1D21 | 2023-08-31 08:00 | 2023-08-31 10:59 | 6 | Continuous | [6 empty] | N | N | 2023-08-31 10:59
8-00805691 | Cancelled | MDN 2CB29, 2CX4 OOS | CPC Control Testing & RXCX Insp | MDN 2CX4 | 2023-09-01 08:00 | 2023-09-01 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-12-28 13:34
8-00814448 | Cancelled | CK5 5CB21 OOS | Trip testing | CK5 5CB21 | 2023-09-01 08:00 | 2023-09-01 16:00 | 1 | Continuous | [6 empty] | N | N | 2023-08-28 15:47
8-00824345 | Completed | GMS T11 OOS | GMS RTU cutover | GMS T11 | 2023-09-01 12:00 | 2023-10-05 11:55 | 8 | Continuous | [6 empty] | N | N | 2023-10-05 11:55
8-00813199 | Cancelled | BKL T1 OOS, 1L220 Switching | Environmental Remediation | BKL T1 | 2023-09-04 08:00 | 2023-09-06 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-11 14:00
8-00813339 | Completed | 60L68/60L69 OOS from SQH, SQH T1/T2 OOS | 60L68 OOS, 60L69 Out from SQH, SQH 60B1, SQH 60B2, SQH 60DCB4, SQH 60CB1, SQH 60CB2, SQH 60CB3, SQH T1, SQH T2 | SQH T1, SQH T2, 60L69, 60L68 | 2023-09-05 08:00 | 2023-09-09 21:13 | 4 | Continuous | [6 empty] | Y | N | 2023-09-09 21:14
8-00815875 | Completed | SCK T2 OOS, 2L352 out for switching | SCK T2 Insp and Doble testing | SCK T2 | 2023-09-05 08:00 | 2023-09-15 15:05 | 6 | Continuous | [6 empty] | N | N | 2023-09-15 15:05
8-00813786 | Completed | BMT T1, 2MB1 OOS | BMT DS, CVT & SS Insp and T1 Doble Testing | BMT T1, BMT 2MB1 | 2023-09-05 08:00 | 2023-09-06 16:10 | NR | Continuous | [6 empty] | N | N | 2023-09-06 16:11
8-00813677 | Completed | SPG 2CB4 OOS | NERC PM | SPG 2CB4 | 2023-09-05 08:00 | 2023-09-05 13:14 | 2 | Continuous | [6 empty] | N | N | 2023-09-05 13:14
8-00880334 | Cancelled | 1L214 OOS | Clearance to replace structures | 1L214 | 2023-09-05 08:00 | 2023-09-08 16:00 | 3 | Continuous | [6 empty] | N | N | 2023-09-01 13:39
8-00874276 | Completed | DMR T2 OOS | To remove and replace DMR 2SA2 | DMR T2 | 2023-09-05 08:00 | 2023-09-13 14:03 | 4 | Continuous | [6 empty] | N | N | 2023-09-14 00:28
8-00806018 | Completed | 2L33, HPN 2CB4, 2CB5 OOS | HPN DS INSP | HPN 2CB4, HPN 2CB5, 2L33 | 2023-09-05 08:00 | 2023-09-08 09:52 | 2 | Continuous | [6 empty] | N | N | 2023-09-08 09:52
8-00805207 | Completed | BND T1 OOS | CPC non-ele PN testing | BND T1 | 2023-09-05 08:00 | 2023-09-06 16:17 | 2 | Continuous | [6 empty] | N | N | 2023-09-06 16:17
8-00798245 | Completed | 5L98, VAS 5RX1, 5B11 OOS | Replace end of life insulators | 5L98, VAS 5RX1, VAS 5B11 | 2023-09-05 08:00 | 2023-09-07 12:22 | 3 | Continuous |  |  |  |  | 560 | 450 | N | N | 2023-09-07 12:22
8-00799372 | Completed | SAL T2 OOS, SAL T1 supplied from VIT | SAL T2 INSP/DOBL | 1L18, SAL T2 | 2023-09-05 08:00 | 2023-09-08 15:27 | 6 | Continuous | [6 empty] | N | N | 2023-09-08 15:28
8-00793381 | Completed | 2L142 OOS | detailed inspection | 2L142 | 2023-09-05 08:00 | 2023-09-08 13:45 | 2 | Continuous | [6 empty] | N | N | 2023-09-08 13:45
8-00797137 | Completed | 1L110, NFD 1B1, 1B2, T1, T2 | NFD 1D21, 1D2CB4, 1CVT1, 1D1, JPT 1D1CB2 | 1L110, NFD T1, NFD 1B1 | 2023-09-05 08:00 | 2023-09-07 15:59 | 2 | Continuous | [6 empty] | N | N | 2023-09-07 15:59
8-00810833 | Cancelled | VIT 2CB2 OOS | VIT 2CB2 INSP | VIT 2CB2 | 2023-09-05 08:00 | 2023-09-06 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-09-01 09:53
8-00807258 | Completed | NIC T3 OOS | PCB Bushing Replacement for NIC T3A | NIC T3 | 2023-09-05 08:00 | 2023-09-11 19:22 | 120 | Continuous | [6 empty] | N | N | 2023-09-27 03:30
8-00812152 | Cancelled | BRT T4, 2L19, BRT 2B4 OOS | BRT T4C NON ELEC PN, BRT 2D4 INSP | 2L19, BRT T4, BRT 2B4 | 2023-09-06 08:00 | 2023-09-06 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-21 09:29
8-00795110 | Cancelled | 2L48 OOS | 2L48 MSA & Say DS Inspections, | MSA 2CB2, MSA 2CB3, SAY 2B4, 2L48 | 2023-09-06 08:00 | 2023-09-06 18:00 | 3 | Continuous | [6 empty] | N | N | 2023-08-30 15:17
8-00803308 | Proposed | 2L19 OOS | Repalce emergent strucutres | 2L19 | 2023-09-06 08:00 | 2023-09-12 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-09 15:08
8-00879672 | Completed | 5L75 OOS | Inspection of ACK 5D2CB6 | 5L75, ACK 5B6 | 2023-09-06 08:00 | 2023-09-06 16:31 | 2 | Continuous | [6 empty] | N | N | 2023-09-06 16:31
8-00806454 | Cancelled | 2L19 OOS | Transmission Structure replacements | 2L19 | 2023-09-06 09:00 | 2023-09-12 16:00 | 3 | Continuous | [6 empty] | N | N | 2023-08-22 09:35
8-00810844 | Cancelled | VIT 2CB3 OOS | VIT 2CB3 INSP | VIT 2CB3 | 2023-09-07 08:00 | 2023-09-08 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-09-01 12:17
8-00869334 | Completed | 5L2, 5B3, 5B13, 5RX4 OOS | WSN DS Insp | 5L2, WSN 5B13, WSN 5B3, WSN 5RX4 | 2023-09-07 08:00 | 2023-09-07 18:23 | 4 | Continuous | [6 empty] | Y | N | 2023-09-08 00:27
8-00813290 | Completed | SEC 1CB5 OOS | SEC 1CB5 COND. NERC, REPAIR BUSHING TEAR | SEC 1CB5 | 2023-09-07 08:00 | 2023-09-07 16:00 | NR | Continuous | [6 empty] | N | N | 2023-09-07 16:00
8-00776891 | Cancelled | Illecillewaet Station Outage | For Station Disconnect work | 2L253, 60L218, 60L219 | 2023-09-10 00:01 | 2023-09-10 09:00 | 1 | Continuous | [6 empty] | N | N | 2023-06-19 12:57
8-00795925 | Completed | 1L131, TSV T1, T2, GLD 1B2 OOS | GLD and TSV 138KV Disc INSP | 1L131, GLD 1B2, TSV T1, TSV T2 | 2023-09-10 08:00 | 2023-09-10 17:57 | 3 | Continuous | [6 empty] | N | N | 2023-09-10 17:58
8-00884072 | Cancelled | L81-87 OOS | RioTinto work: CT Repl | L81-87 | 2023-09-11 07:00 | 2023-09-14 17:00 | NR | Continuous | [6 empty] | N | N | 2023-08-22 09:15
8-00889537 | Cancelled | NIC 5CB8, 5B18, 5L71 OOS | LOA to the crane | 5L71, NIC 5B18, NIC 5CB8 | 2023-09-11 08:00 | 2023-09-14 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-09-23 10:37
8-00813318 | Completed | 60L97 out from JLN , JLN T2 and 60CB1 OOS | JLN 60L97 - 60D1CB1, 60GD2 INSP, 60VT1 A,B,C INSP + DOBLE | JLN 60CB1, JLN T2, 60L97 | 2023-09-11 08:00 | 2023-09-15 12:48 | 2 | Continuous | [6 empty] | N | N | 2023-09-15 12:48
8-00813360 | Cancelled | SQH T1 OOS | ETM REPLACEMENT, SQH 25CB1 BFPN | SQH T1 | 2023-09-11 08:00 | 2023-09-15 16:00 | 8 | Continuous | [6 empty] | N | N | 2023-09-13 18:00
8-00813200 | Cancelled | BKL T3 OOS, 1L241 Switching | Environmental Remediation | BKL T3 | 2023-09-11 08:00 | 2023-09-13 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-11 14:00
8-00812594 | Completed | 5L1, WSN 5B2, 5RX2 OOS | WSN DS INSP | 5L1, WSN 5B2, WSN 5RX2 | 2023-09-11 08:00 | 2023-09-11 16:14 | 2 | Continuous | [6 empty] | Y | N | 2023-09-11 16:26
8-00793384 | Cancelled | 2L143 OOS | detailed inspection | 2L143 | 2023-09-11 08:00 | 2023-09-13 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-05-25 11:12
8-00804247 | Cancelled | 5L71 OOS | Replace Marker balls on 5L71 | 5L71 | 2023-09-11 08:00 | 2023-09-14 16:00 | NR | Continuous | [6 empty] | Y | N | 2023-09-06 22:13
8-00805318 | Completed | CK5 5MB2 OOS | Replace bus protection relays | CK5 5MB2 | 2023-09-11 08:00 | 2023-09-14 12:23 | 4 | Continuous | [6 empty] | N | N | 2023-09-14 12:23
8-00801138 | Completed | 2L40 out from NEL to BND | Detailed Inspection | 2L40, NEL 2CB4 | 2023-09-11 08:00 | 2023-09-15 14:06 | 2 | Continuous | [6 empty] | N | N | 2023-09-15 14:07
8-00801142 | Completed | 60L73 OOS | Detailed Inspection | 60L73 | 2023-09-11 08:00 | 2023-09-12 15:51 | 2 | Continuous | [6 empty] | N | N | 2023-09-12 15:51
8-00810791 | Cancelled | SAM T6, 60D21 OOS | Inspection | SAM 60D21, SAM T6 | 2023-09-11 08:00 | 2023-09-11 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-25 09:59
8-00810793 | Cancelled | SAM T6 OOS | Inspection & doble | SAM T6 | 2023-09-11 08:00 | 2023-09-15 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-25 09:52
8-00810404 | Completed | 2L308 OOS | Pole Repl | 2L308 | 2023-09-11 08:00 | 2023-09-13 12:18 | 4 | Continuous | [6 empty] | N | N | 2023-09-13 12:19
8-00810338 | Completed | VNT 1CB2 OOS | CPC CN CA | VNT 1CB2 | 2023-09-11 08:00 | 2023-09-11 13:46 | NR | Continuous | [6 empty] | N | N | 2023-09-11 13:47
8-00809367 | Denied | 2L129, TBY 2RX1 OOS | TBY 2RX1 Non-EL and Bushing Replacement | 2L129, TBY 2RX1 | 2023-09-11 08:00 | 2023-09-22 16:00 | 16 | Continuous | [6 empty] | N | N | 2023-08-23 08:27
8-00809410 | Completed | HSY T1, 2CB10, 2CB11 OOS | HSY 2CB10 INSP, HSY 2CB11 INSP | HSY T1, HSY 2B10 | 2023-09-11 08:00 | 2023-09-11 17:05 | 4 | Continuous | [6 empty] | N | N | 2023-09-11 17:05
8-00807611 | Completed | RDM T1 OOS | PCB Bushing Replacement | RDM T1 | 2023-09-11 08:00 | 2023-11-03 12:04 | NR | Continuous | [6 empty] | N | N | 2023-11-19 03:30
8-00877527 | Completed | 5L71 OOS | MCA Roof Project | 5L71 | 2023-09-11 09:00 | 2023-09-14 17:06 | 8 | Continuous | [6 empty] | Y | N | 2023-09-14 17:06
8-00806025 | Completed | 2L32, HPN 2B8, 2CB1 OOS | NERC PM, INSP | 2L32, HPN 2B8 | 2023-09-11 12:00 | 2023-09-15 14:40 | 4 | Continuous | [6 empty] | N | N | 2023-09-15 14:40
8-00800887 | Completed | KI2 T4 OOS | Oil sample piping, CPC non-ele PN testing | KI2 T4 | 2023-09-12 08:00 | 2023-09-15 14:04 | 4 | Continuous | [6 empty] | N | N | 2023-09-15 14:04
8-00810334 | Completed | VNT 1CB12 OOS | INSP and DOBLE | VNT 1CB12 | 2023-09-12 08:00 | 2023-09-13 17:27 | 2 | Continuous | [6 empty] | N | N | 2023-09-13 17:27
8-00813361 | Cancelled | SQH T1, 25B1, 25VT1 OOS | PM INSPECTIONS of SQH 25VT1, SS1 | SQH T1 | 2023-09-12 08:00 | 2023-09-12 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-09-06 15:26
8-00882500 | Completed | NIC 5CB18 OOS | Gas gauge replacement | NIC 5CB18 | 2023-09-13 08:00 | 2023-09-13 16:50 | 1 | Continuous | [6 empty] | N | N | 2023-09-20 07:50
8-00810339 | Proposed | VNT 1CB4 OOS | CPC CN CA | VNT 1CB4 | 2023-09-13 08:00 | 2023-09-13 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-31 10:34
8-00807686 | Completed | 5L3, PCN 5B1, 5RX1 OOS | PCN 5RX1 INSP, DOBL | 5L3, PCN 5B1, PCN 5RX1 | 2023-09-13 16:00 | 2023-09-22 16:00 | 6 | Continuous | [6 empty] | Y | N | 2023-09-26 04:01
8-00799042 | Completed | 5L3 oos | Connect new KDY 5SSCVT | 5L3 | 2023-09-13 16:00 | 2023-09-22 16:46 | 4 | Continuous | [6 empty] | Y | N | 2023-09-22 16:46
8-00811524 | Completed | CKY T6 2CB9/2CB10 OOS | CKY 230kv DS replacement project | CKY T6, CKY 2B9 | 2023-09-14 08:00 | 2023-09-27 13:05 | 4 | Continuous | [6 empty] | N | N | 2023-09-27 13:05
8-00671829 | Completed | 5L72 OOS | Safety fencing on the switchgear roof | 5L72 | 2023-09-14 15:00 | 2023-09-23 13:10 | 6 | Continuous | [6 empty] | Y | N | 2023-09-23 13:10
8-00810857 | Proposed | MON T5, 1D2CB2, 1D1CB5, 60D21, 60D22 OOS | Piggyback 8-807603 | MON 1D1CB5, MON 1D2CB2, MON 60D21, MON 60D22, MON T5 | 2023-09-15 08:00 | 2023-09-15 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-31 10:34
8-00807602 | Completed | MON T5 OOS | PCB Bushing Replacement | MON T2, MON T5 | 2023-09-15 08:00 | 2023-11-07 20:30 | NR | Continuous | [6 empty] | N | Y | 2023-11-07 20:30
8-00807603 | Proposed | MON T5 OOS | Surge Arrester Replacement Program , ETM Replacement Program | MON T5 | 2023-09-15 08:00 | 2023-10-21 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-31 10:34
8-00853014 | Completed | 170L OOS, Coleman supplied via 1L275 | AltaLink outage - Replace insulators | NTL 60CB12, NTL 60CB3, 170L (632s Russell - 799s Coleman) | 2023-09-18 06:00 | 2023-09-18 16:43 | 4 | Continuous | [6 empty] | N | N | 2023-09-18 16:44
8-00813362 | Completed | SQH T2, SS2 OOS | ETM REPLACEMENT, PM INSPECTION of SQH SS2, SQH 25CB2 BFPN | SQH T2 | 2023-09-18 08:00 | 2023-09-22 15:09 | 4 | Continuous | [6 empty] | N | N | 2023-09-22 15:09
8-00813202 | Cancelled | BLU T1 OOS, 1L211 Switching | Environmental Remediation | BLU T1 | 2023-09-18 08:00 | 2023-09-20 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-11 14:01
8-00813794 | Approved | CWD T2 OOS | CWD T2 Insp and Doble Testing | CWD T2 | 2023-09-18 08:00 | 2023-09-29 16:00 | 8 | Continuous | [6 empty] | N | N | 2023-09-15 09:02
8-00806544 | Proposed | CSN T2 OOS | Refurbish sound enclosure | CSN T2 | 2023-09-18 08:00 | 2023-10-06 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-09-13 08:08
8-00797163 | Cancelled | 1L14 GTP T13 OOS | GTP 1D1CB1 INSP, GTP 1DCB14 INSP, 1L14 line crew work | 1L14, GTP T13 | 2023-09-18 08:00 | 2023-09-19 16:00 | NR | Continuous | [6 empty] | N | N | 2023-02-15 11:46
8-00801141 | Completed | 2L64 OOS | Detailed Inspection | 2L64 | 2023-09-18 08:00 | 2023-09-25 10:43 | 2 | Continuous | [6 empty] | Y | N | 2023-09-25 10:43
8-00793429 | Completed | 2L145 OOS | detailed inspection | 2L145 | 2023-09-19 06:30 | 2023-09-22 07:31 | 4 | Continuous | [6 empty] | N | N | 2023-09-22 07:32
8-00890447 | Completed | SKA 12RX2 OOS | RX Insp and Doble | SKA 12RX2 | 2023-09-19 07:00 | 2023-09-22 16:00 | 3 | Continuous | [6 empty] | Y | N | 2023-10-12 03:30
8-00813288 | Cancelled | CYP T2 OOS | CYP T2 - NON ELECTRICALS | CYP T2 | 2023-09-19 08:00 | 2023-09-21 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-09-12 13:44
8-00793782 | Completed | 1L102. CMX T2, JHT 1B9 OOS | 1L102 , JHT, CBL, CMX, PUN Disc INSP | 1L102, CMX T2, JHT 1B9 | 2023-09-19 08:00 | 2023-09-22 14:34 | 3 | Continuous | [6 empty] | Y | N | 2023-09-22 14:35
8-00806010 | Completed | 2L3, HPN 2CB2, 2CB3 OOS | NERC PM, INSP | 2L3, HPN 2B2 | 2023-09-19 08:00 | 2023-09-22 15:28 | 2 | Continuous | [6 empty] | N | N | 2023-09-22 15:29
8-00807259 | Cancelled | NIC T3 OOS | PCB Bushing Replacement for NIC T3B | NIC T3 | 2023-09-19 08:00 | 2023-10-27 16:00 | NR | Continuous | [6 empty] | N | N | 2023-02-22 08:36
8-00810415 | Cancelled | 2L312 OOS | Pole Repl | 2L312 | 2023-09-19 08:00 | 2023-09-22 16:00 | NR | Continuous | [6 empty] | N | N | 2023-09-05 10:21
8-00812149 | Cancelled | 60L22, LAJ 60B1, 60L55, LAJ 12F51 OOS | LAJ T2 Doble,LAJ 60CVT21 INSP/Doble | LAJ 60B1, LAJ T2 | 2023-09-19 08:00 | 2023-09-19 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-08 14:06
8-00811361 | Cancelled | DMR 5CB14 OOS | DMR 5CB14, 5CT14 INSP | DMR 5CB14 | 2023-09-19 08:00 | 2023-09-20 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-09-18 11:00
8-00889652 | Completed | VNT 1CB5 OOS | VNT 1CB5 CN PM | VNT 1CB5 | 2023-09-19 10:00 | 2023-09-19 12:59 | 2 | Continuous | [6 empty] | N | N | 2023-09-19 12:59
8-00887874 | Completed | 5L75 OOS | LOA for REV SWGR roof work | 5L75 | 2023-09-19 15:00 | 2023-09-20 16:57 | 2 | Continuous | [6 empty] | Y | N | 2023-09-20 16:57
8-00889002 | Cancelled | 2L293, 2L222 OOS | SEL PCB lighting replacement | 2L222, 2L293 | 2023-09-20 08:00 | 2023-09-20 16:00 | 2 | Continuous |  |  |  |  | 560 | 600 | N | N | 2023-09-13 15:07
8-00891825 | Cancelled | SKA 12RX2 OOS | RX Insp and Doble | SKA 12RX2 | 2023-09-20 08:00 | 2023-09-22 16:00 | 3 | Continuous | [6 empty] | N | N | 2023-09-13 15:31
8-00893741 | Completed | SYA 5CX1 OOS | Inspection | SYA 5CX1 | 2023-09-20 08:00 | 2023-09-20 16:21 | 2 | Continuous | [6 empty] | N | N | 2023-09-20 16:21
8-00826210 | Completed | 5L12, KLY 5B3, 5RX3 oos | LOA for KLY CB Replacement | 5L12, KLY 5B3, KLY 5RX3, KLY 5CB33 | 2023-09-20 08:00 | 2023-09-22 22:36 | 3 | Continuous | [6 empty] | N | N | 2023-09-22 22:37
8-00821243 | Cancelled | GLN T11 OOS | GLN T11 Non-EL PN PM | GLN T11 | 2023-09-20 08:00 | 2023-09-20 16:00 | NR | Continuous | [6 empty] | N | N | 2023-09-08 09:46
8-00887890 | Completed | 5L77 OOS | LOA for REV SWGR Roof Work | 5L77 | 2023-09-20 15:00 | 2023-09-21 14:58 | 2 | Continuous | [6 empty] | N | N | 2023-09-21 14:59
8-00888816 | Completed | 2L293, 2L286 (84L), SEL 2MB2, 2MB1, 2D25 OOS | PCB light replacement | 2L293, SEL 2MB1, SEL 2MB2, SEL T1, 2L286 (84L) | 2023-09-21 08:00 | 2023-09-21 19:35 | 2 | Continuous |  |  |  |  | 560 | 600 | Y | N | 2023-10-07 03:30
8-00813344 | Approved | CKY 2CB10 OOS | TRIP TESTING | CKY 2CB10 | 2023-09-21 08:00 | 2023-09-21 16:00 | NR | Continuous | [6 empty] | N | N | 2023-09-20 15:05
8-00731740 | Cancelled | 60L20, 60L29 and 60L301 out from CRQ | CRQ replacement prject | 60L20, 60L29, 60L301 | 2023-09-22 12:00 | 2023-09-22 16:00 | 3 | Continuous | [6 empty] | N | N | 2023-08-15 13:40
8-00785820 | Cancelled | REV 5MB2 OOS | 5CB4 Doble Test | REV 5MB2 | 2023-09-23 07:00 | 2023-09-24 16:00 | 4 | Continuous | [6 empty] | Y | N | 2023-09-26 18:00
8-00877622 | Completed | MCA 5B5, LS3, 5CB6/11 OOS | DS PM | MCA 5CB11, MCA 5CB6, MCA LS3, MCA 5B5 | 2023-09-23 16:00 | 2023-10-04 20:33 | 4 | Continuous | [6 empty] | N | N | 2023-10-04 20:33
8-00793435 | Completed | 2L146 OOS | detailed inspection | 2L146 | 2023-09-25 06:30 | 2023-09-28 16:32 | 4 | Continuous | [6 empty] | N | N | 2023-09-28 16:32
8-00885541 | Completed | SEL T3 OOS | 12PT3 Replacement | SEL T3 | 2023-09-25 07:00 | 2023-10-11 18:18 | 2 | Continuous | [6 empty] | N | N | 2023-10-11 18:18
8-00884204 | Completed | 2L293 OOS | Replace end of life timbers | 2L293 | 2023-09-25 08:00 | 2023-09-29 15:46 | 4 | Continuous |  |  |  |  | 560 | 600 | Y | N | 2023-09-29 15:47
8-00879998 | Completed | VNT T2 OOS | VNT T2 INSP | VNT T2 | 2023-09-25 08:00 | 2023-09-29 13:58 | 12 | Continuous | [6 empty] | N | N | 2023-09-29 13:59
8-00824379 | Cancelled | GMS T13 OOS | GMS RTU cutover | GMS 2CB1, GMS T13 | 2023-09-25 08:00 | 2023-09-30 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-21 08:12
8-00889845 | Completed | 43L OOS. 18 MW added to 1L251 (PRI, BCG, HED) | FBC Outage. 43L maintenance | 43L | 2023-09-25 08:00 | 2023-09-29 18:29 | NR | Continuous | [6 empty] | N | N | 2023-09-29 23:30
8-00813289 | Completed | 60L99 out from CYP | CYP 60L99 - 60D1CB8 GEAR BOX BROKEN CB | CYP 60CB9, 60L99, CYP 60CB7 | 2023-09-25 08:00 | 2023-09-26 14:27 | 2 | Continuous | [6 empty] | N | N | 2023-09-26 14:30
8-00813326 | Denied | 1L44 out from SEC | SEC 1L44 - 1D25 REPLACE GEAR BOX | SEC 1D25, 1L44 | 2023-09-25 08:00 | 2023-09-26 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-09-08 17:13
8-00803304 | Cancelled | 60L22 OOS | Replace emergent structures | 60L22 | 2023-09-25 08:00 | 2023-10-07 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-16 10:18
8-00811436 | Completed | KI2 T1, T4, 2B1 OOS | Insp & Doble | KI2 12RX1, KI2 T1, KI2 2B1, KI2 T4 | 2023-09-25 08:00 | 2023-10-06 16:37 | 4 | Continuous | [6 empty] | N | N | 2023-10-22 03:30
8-00810416 | Cancelled | 1L349 OOS | Pole Repl | 1L349 | 2023-09-25 08:00 | 2023-09-26 16:00 | NR | Continuous | [6 empty] | N | N | 2023-09-05 10:23
8-00807571 | Cancelled | KCL T7 OOS | Environmental Remediation | KCL T7 | 2023-09-25 08:00 | 2023-09-27 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-11 14:02
8-00809068 | Completed | NTL T4, 2CB2 OOS | NTL 2CT2 Replacement | NTL 2CB2, NTL T4 | 2023-09-25 08:00 | 2023-11-09 23:49 | 8 | Continuous | [6 empty] | N | N | 2023-11-09 23:49
8-00809697 | Completed | 2L255, ACK 2B11 OOS | Inspection | ACK 2B11, 2L255 | 2023-09-25 08:00 | 2023-09-27 15:06 | 3 | Continuous | [6 empty] | N | N | 2023-09-27 15:06
8-00806479 | Cancelled | 60L22 OOS | Transmission structure replacements | 60L22 | 2023-09-25 09:00 | 2023-10-07 16:00 | 4 | Continuous | [6 empty] | Y | N | 2023-09-18 14:34
8-00813321 | Completed | COM 1L44, 1L45, 1MK1 OOS | COM 1CB2 COND - NERC + 1D1CB1 INSP - Requires IPP Coordination | 1L45, COM 1MK1, COM 1CB2 | 2023-09-25 09:00 | 2023-09-25 14:46 | 4 | Continuous | [6 empty] | Y | N | 2023-09-25 15:04
8-00803260 | Completed | 1L140 OOS | End of Life Structure Replacements | 1L140 | 2023-09-25 10:00 | 2023-10-03 11:10 | 2 | Continuous | [6 empty] | N | N | 2023-10-03 11:10
8-00891004 | Completed | KDY 5CX2 OOS | LOA outage to set new concrete cable vault | KDY 5CX2 | 2023-09-25 11:00 | 2023-09-25 15:19 | 1 | Continuous | [6 empty] | N | N | 2023-09-25 15:19
8-00891112 | Cancelled | MCA 5CB6 OOS | NERC Upgrades | MCA 5CB6 | 2023-09-25 13:00 | 2023-09-26 17:00 | 1 | Return Evenings | [6 empty] | N | N | 2023-09-28 18:00
8-00897422 | Approved | KIT SC2 OOS | Series Cap maintenance and card repl | KIT SC2 | 2023-09-26 07:00 | 2023-09-28 16:00 | NR | Continuous | [6 empty] | N | N | 2023-09-25 10:37
8-00826216 | Completed | 5L12, KLY 5B3, 5RX3 OOS | LOA for KLY CB Replacement | 5L12, KLY 5B3, KLY 5RX3, KLY 5CB33 | 2023-09-26 08:00 | 2023-09-28 16:56 | 3 | Continuous | [6 empty] | N | N | 2023-09-28 21:46
8-00877378 | Denied | 2L113, NTL T3, T4, T2, 60B2 OOS | Inpection, doble and repair | 2L113, NTL T2, NTL T3, NTL T4, NTL 60B2 | 2023-09-26 08:00 | 2023-09-26 16:00 | 2 | Continuous |  |  |  |  | 850 | 700 | N | N | 2023-09-21 14:41
8-00813671 | Completed | 60L39 Out from HPN | DS Insp | 60L39, LOH T3, HPN 60B6, LOH 60B3 | 2023-09-26 08:00 | 2023-09-28 14:24 | 2 | Continuous | [6 empty] | Y | N | 2023-09-28 14:25
8-00812221 | Completed | JHT 1MB1 OOS | JHT 1D1CB3, 1D1CB8, 1D2CB2, 1D2CB7 INSP | JHT 1CB4, JHT 1CB2, JHT 1CB7, JHT 1CB8, JHT 1MB1 | 2023-09-26 08:00 | 2023-09-27 11:02 | 2 | Continuous | [6 empty] | Y | N | 2023-09-27 11:02
8-00890814 | Completed | 2L277 (71L) OOS | FBC Outage. Maintenance | NLY 2CB3, 2L277 (71L) | 2023-09-26 08:30 | 2023-09-28 14:24 | NR | Continuous | [6 empty] | Y | N | 2023-09-28 14:24
8-00898161 | Completed | CBK 5RX5 Forced OOS | Forced out | CBK 5RX5 | 2023-09-26 14:37 | 2023-10-10 15:21 | NR | Continuous | [6 empty] | N | N | 2023-10-26 03:30
8-00810058 | Completed | 60L10 OOS, HOP 60B2 OOS | Relocate 60D22 and 60L10, Install new 60D24 | 60L10, HOP T12, HOP 60B2 | 2023-09-27 08:00 | 2023-10-11 07:24 | 6 | Continuous | [6 empty] | N | N | 2023-10-27 03:30
8-00805930 | Completed | ING 2CX2, 2RX2 OOS | ING CX DS INSP | ING 2D30, ING 2RX2, ING 2D26, ING 2CX2 | 2023-09-27 08:00 | 2023-09-28 15:47 | 2 | Continuous | [6 empty] | N | N | 2023-09-28 15:47
8-00879224 | Submitted | MCA 5B5, LS3, SS3, SS2, 60L223 OOS | Switching outage | 60L223, MCA LS3, MCA 5B5 | 2023-09-27 20:00 | 2023-09-27 20:30 | 0 | Continuous | [6 empty] | N | N | 2023-09-25 15:07
8-00891114 | Cancelled | MCA 5CB7 OOS | NERC Upgrades | MCA 5CB7 | 2023-09-28 07:00 | 2023-09-28 20:00 | 1 | Continuous | [6 empty] | Y | N | 2023-10-18 14:06
8-00877386 | Completed | NTL T1, 60B1 OOS | NTL 60VT1, T1, DS PM and Inspection | NTL T1, NTL 60B1 | 2023-09-28 08:00 | 2023-09-28 16:59 | 2 | Continuous | [6 empty] | N | N | 2023-09-28 16:59
8-00813578 | Completed | 2L2 out from CKY to RBW, CKY 2B4 OOS | Replace 2D25 -- CKY DS replacement stage #2 | RBW T2, CKY 2B4, 2L2 | 2023-09-28 08:00 | 2023-10-18 10:18 | 10 | Continuous | [6 empty] | Y | N | 2023-10-18 10:18
8-00899070 | Completed | CBN 5CB8 Forced OOS | Defective. Awaiting replacement parts | CBN 5CB8 | 2023-09-28 16:00 | 2024-02-01 08:36 | NR | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2024-02-01 08:36
8-00891125 | Approved | MCA 5CB10 OOS | NERC Upgrades | MCA 5CB10 | 2023-09-29 07:00 | 2023-09-29 20:00 | 1 | Continuous | [6 empty] | N | N | 2023-09-28 11:27
8-00897987 | Approved | 5L71, NIC 5B18 OOS | NIC 5CB8 Energization | 5L71, NIC 5B18 | 2023-09-29 08:00 | 2023-09-29 12:00 | 2 | Continuous | [6 empty] | N | N | 2023-09-28 09:22
8-00895478 | Completed | 1L359 (7L81R), FNC OOS | Fire damage repair on BC side of 1L359 | 1L359 (7L81R) | 2023-09-29 08:00 | 2023-10-21 15:35 | 2 | Continuous | [6 empty] | N | N | 2023-10-21 15:35
8-00795830 | Completed | 1L48, GPT T1, FVW T1 OOS | 138kv DISC, SAY,FVW,GPT INSP and FVW DS replacement | FVW T1, GPT T1, SAY T3, SAY 1B4, 1L48, SAY 1B3 | 2023-10-02 07:00 | 2023-10-03 16:52 | 4 | Continuous | [6 empty] | N | N | 2023-10-03 16:52
8-00809838 | Cancelled | 5L94 OOS | AltaLink outage for repairing | 5L94 / 1201L, NTL 60CB12, 1L274 (887L), 1L275 (786L) | 2023-10-02 08:00 | 2023-10-07 17:00 | 4 | Continuous |  |  |  |  | 50 | 100 | N | N | 2023-09-26 10:47
8-00806029 | Cancelled | 2L31, MUR 2CB5 OOS | NERC PM, INSP | 2L31, MUR 2B2 | 2023-10-02 08:00 | 2023-10-06 16:00 | 2 | Continuous | [6 empty] | Y | N | 2023-09-28 15:08
8-00806548 | Cancelled | ING 2CX2 OOS | PCB Replacement | ING 2CX2 | 2023-10-02 08:00 | 2023-10-12 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-09-15 08:53
8-00807610 | Cancelled | AFT T1 OOS | PCB Bushing Replacement | AFT T1 | 2023-10-02 08:00 | 2023-11-08 16:00 | NR | Continuous | [6 empty] | N | Y | 2023-09-11 09:08
8-00894286 | Completed | 5L94 (1201L) OOS | AltaLink Outage. Maintenance at 1201L, 520s | 5L94 / 1201L, NTL 60CB12, 1L274 (887L), 1L275 (786L) | 2023-10-02 08:00 | 2023-10-07 17:37 | NR | Continuous | [6 empty] | N | N | 2023-10-07 17:38
8-00812572 | Completed | 2L354 OOS | Structure Repl | 2L354 | 2023-10-02 08:00 | 2023-10-05 20:12 | 4 | Continuous | [6 empty] | N | N | 2023-10-05 20:13
8-00813788 | Cancelled | BMT T2 OOS | BMT T2 Non-EL PN PM | BMT T2 | 2023-10-03 08:00 | 2023-10-03 16:00 | NR | Continuous | [6 empty] | N | N | 2023-09-14 14:55
8-00890269 | Completed | AMC 5CX1 OOS | Replace AMC 5CVT1 (Long Recall) | AMC 5CX1 | 2023-10-03 08:00 | 2023-10-13 12:01 | 96 | Continuous | [6 empty] | N | N | 2023-10-29 03:30
8-00842521 | Completed | 2L256, VNT 1B1, 2B1, T1 OOS | Flood light replacement | 2L256, VNT T1, VNT 2B1, VNT 1B1 | 2023-10-03 08:00 | 2023-10-03 15:59 | 2 | Continuous | [6 empty] | N | N | 2023-10-03 15:59
8-00809694 | Completed | 2L256, ACK 2B9 OOS | Inspection | ACK 2B9, 2L256 | 2023-10-03 08:00 | 2023-10-05 10:59 | 4 | Continuous | [6 empty] | N | N | 2023-10-05 10:59
8-00806895 | Completed | 5L94, CBK 5RX5 OOS | Non-Electrcal testing - NERC PM | 5L94 / 1201L, CBK 5RX5, NTL 60CB12, 1L274 (887L), 1L275 (786L) | 2023-10-03 08:00 | 2023-10-06 13:51 | 4 | Continuous | [6 empty] | N | N | 2023-10-06 14:07
8-00807257 | Completed | NIC 5RX3 OOS | PCB Bushing Replacement | NIC 5RX3, NIC 5NR3 | 2023-10-03 08:00 | 2023-10-30 14:36 | NR | Continuous | 2000 | 2400 |  |  |  |  | Y | N | 2023-10-30 14:36
8-00811407 | Cancelled | KI2 2CB3 OOS | CPC Breaker Fail Testing | KI2 2CB3 | 2023-10-03 08:00 | 2023-10-04 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-10-06 18:00
8-00797165 | Completed | 1L152, NFD T2, T3 OOS | NFD 1D23,1D1CB5, 1D3,1D2, JPT 1D1CB2 INSP | NFD T2, NFD T3, 1L152, NFD 1B3, NFD 1B2 | 2023-10-03 08:00 | 2023-10-05 16:49 | 3 | Continuous | [6 empty] | N | N | 2023-10-05 17:01
8-00818755 | Cancelled | SKA T5 OOS | SKA DS Insp and VT Doble testing | SKA 60CB3, SKA T5, SKA 60CB4 | 2023-10-04 08:00 | 2023-10-16 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-09 14:07
8-00818632 | Cancelled | SKA T5 OOS | SKA T5 LTC, Insp & Doble testing | SKA T5 | 2023-10-04 08:00 | 2023-10-16 16:00 | NR | Continuous | [6 empty] | N | N | 2023-07-25 14:48
8-00795113 | Denied | DMR SVC OOS | Inspection | DMR SVC | 2023-10-05 08:00 | 2023-10-06 16:00 | 2 | Return Evenings | 2000 | 2400 |  |  |  |  | N | N | 2023-09-05 08:40
8-00899000 | Completed | 2L31 OOS | MUR 2VT3 INSP/DOBLE | 2L31 | 2023-10-06 08:00 | 2023-10-06 15:40 | 2 | Continuous | [6 empty] | N | N | 2023-10-06 15:44
8-00814164 | Proposed | SEA T1 OOS | ETM replacement | SEA T1 | 2023-10-08 08:00 | 2023-10-12 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-01-31 14:46
8-00819095 | Cancelled | MIN T2 OOS | MIN T2 Insp | MIN T2 | 2023-10-09 08:00 | 2023-10-13 16:00 | NR | Continuous | [6 empty] | N | N | 2023-09-28 09:23
8-00653904 | Cancelled | 5L72 OOS | Control System Upgrade | 5L72 | 2023-10-09 08:00 | 2023-10-13 16:00 | 48 | Continuous | [6 empty] | N | N | 2023-01-16 15:16
8-00896300 | Completed | 2L277 (71L) OOS | FBC Outage. 71L Maintenance | 2L277 (71L) | 2023-10-10 07:00 | 2023-10-19 21:23 | 48 | Continuous | [6 empty] | Y | N | 2023-10-19 21:23
8-00894735 | Completed | 1L359 (7L81R) OOS from FNC | FNC to repair fire-damaged structures on their portion of 1L359 | 1L359 (7L81R) | 2023-10-10 08:00 | 2023-10-21 15:21 | 2 | Continuous | [6 empty] | N | N | 2023-10-21 15:22
8-00894902 | Approved | CHP 5CX1 OOS | NERC device hardening | CHP 5CX1 | 2023-10-10 08:00 | 2023-10-12 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-10-05 23:10
8-00901463 | Cancelled | 1L359 (7L81R) OOS | Fire damage repair on BC side of 1L359 | 1L359 (7L81R) | 2023-10-10 08:00 | 2023-10-31 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-10-10 11:37
8-00896711 | Approved | 2L277 (71L) OOS | FBC Outage. WHS 71CB Mtce | 2L277 (71L), WHS CB71, WHS 71-T2, WHS 71-T1 | 2023-10-10 08:00 | 2023-10-13 17:00 | NR | Continuous | [6 empty] | N | N | 2023-10-05 23:09
8-00824360 | Cancelled | 1L361, GMS 1B1, 1B7, 1B8 OOS | GMS RTU cutover | 1L361, GMS 1B1, GMS 1B7, GMS 1B8 | 2023-10-10 08:00 | 2023-10-18 16:00 | 8 | Continuous | [6 empty] | N | Y | 2023-10-05 13:53
8-00871885 | Completed | 2L22 OOS | Structure replacements | BSY 2CB8, 2L22 | 2023-10-10 08:00 | 2023-10-19 16:49 | 4 | Return Weekends | 1500 | 1500 |  |  |  |  | N | N | 2023-10-19 16:49
8-00813793 | Cancelled | CWD T1 OOS | CWD Transf Insp and Doble Testing | CWD T1 | 2023-10-10 08:00 | 2023-10-21 16:00 | NR | Continuous | [6 empty] | N | N | 2023-10-04 11:35
8-00813687 | Completed | MUR T2, T3 OOS | MUR 2D3, 2D2CB2, 2D2CB1, 2D2, 12NRXT3 Insepctions | MUR T2, MUR T3, MUR 2B1, MUR 60B11, MUR 60B13 | 2023-10-10 08:00 | 2023-10-13 13:47 | 4 | Continuous | [6 empty] | N | N | 2023-10-13 13:47
8-00812575 | Proposed | 2L96 OOS | Structure Repl | 2L96 | 2023-10-10 08:00 | 2023-10-13 16:00 | NR | Continuous | [6 empty] | N | N | 2023-10-05 08:02
8-00812577 | Proposed | WSN 2RX10 OOS | WSN 2RX10 Non-EL PM | WSN 2RX10 | 2023-10-10 08:00 | 2023-10-10 16:00 | NR | Continuous | [6 empty] | N | N | 2023-01-26 16:18
8-00812578 | Completed | 2L352 OOS | 2L352 Structure Repl | 2L352, CRQ 60CB1 | 2023-10-10 08:00 | 2023-10-15 20:30 | 3 | Continuous | [6 empty] | N | N | 2023-10-15 20:55
8-00805881 | Denied | 5L51 OOS | ING CT INSP | ING 5MB1, ING 5D2CB4 (3), 5L51 | 2023-10-10 08:00 | 2023-10-11 16:00 | 2 | Continuous |  |  | 1500 | 1700 |  |  | N | N | 2023-09-28 14:16
8-00811438 | Cancelled | KI2 T3 OOS | CPC Non-ele Protection Testing | KI2 T3 | 2023-10-10 08:00 | 2023-10-12 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-09-15 14:35
8-00811413 | Completed | KI2 2CB5 OOS | CPC Control Testing | KI2 2CB5 | 2023-10-10 08:00 | 2023-10-11 11:43 | 2 | Continuous | [6 empty] | N | N | 2023-10-11 11:43
8-00839758 | Completed | 5L51 OOS | BPA Outage (Maintenance at Custer) | 5L51 | 2023-10-11 07:30 | 2023-10-11 17:02 | NR | Continuous |  |  | 1500 | 1700 |  |  | N | N | 2023-10-11 17:02
8-00898570 | Completed | 1L214 OOS | Replace structures - Thermal uprating project | 1L214 | 2023-10-11 08:00 | 2023-10-26 15:38 | 3 | Continuous | [6 empty] | N | N | 2023-10-26 15:38
8-00813343 | Cancelled | CKY 2CB4 OOS | PM INSPECTION of CKY 2CB4 | CKY 2CB4 | 2023-10-11 08:00 | 2023-10-13 16:00 | 8 | Continuous | [6 empty] | N | N | 2023-10-05 08:16
8-00807261 | Cancelled | NIC T3 OOS | PCB Bushing Replacement for NIC T3C | NIC T3 | 2023-10-11 08:00 | 2023-11-18 16:00 | NR | Continuous | [6 empty] | N | N | 2023-02-22 08:35
8-00809437 | Completed | HSY 2B3, T2 OOS | HSY 2CB3 INSP, HSY 2CB2 INSP | HSY T2, HSY 2B3 | 2023-10-11 08:00 | 2023-10-11 16:42 | 4 | Continuous | [6 empty] | N | N | 2023-10-11 16:42
8-00809369 | Completed | 5L79, NIC 5B16, ACK 5B1 OOS | DS INSP | ACK 5CB1, ACK 5CB2, 5L79, NIC 5CB16, NIC 5CB6 | 2023-10-11 08:00 | 2023-10-13 15:33 | 4 | Continuous | [6 empty] | N | N | 2023-10-13 15:33
8-00809376 | Cancelled | 5L79 ACK 5CB1, 5CB2 OOS | ACK 5D21, 5D2CB1, 5D1CB2 INSP's | ACK 5CB1, ACK 5CB2, 5L79 | 2023-10-11 08:00 | 2023-10-13 16:00 | NR | Continuous | [6 empty] | N | N | 2023-09-25 10:35
8-00811409 | Completed | KI2 2CB6 OOS | CPC Breaker Fail Testing | KI2 2CB6 | 2023-10-12 08:00 | 2023-10-13 08:19 | 2 | Continuous | [6 empty] | N | N | 2023-10-13 08:20
8-00812248 | Completed | KGH 1CB6 OOS | KGH 1CB6 INSP | KGH 1CB6 | 2023-10-12 08:00 | 2023-10-13 10:18 | 2 | Continuous | [6 empty] | N | N | 2023-10-13 10:18
8-00812250 | Cancelled | KGH 1CB8 OOS | KGH 1CB8 PLUG INSTALLATION (CB) | KGH 1CB8 | 2023-10-12 08:00 | 2023-10-13 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-09-22 08:12
8-00805884 | Denied | 5L52 OOS | ING CT INSP | 5L52 | 2023-10-12 08:00 | 2023-10-13 16:00 | 2 | Continuous |  |  | 1500 | 1700 |  |  | N | N | 2023-09-28 08:34
8-00818734 | Completed | SKA T5 OOS | SKA T5 Bushing Repl | SKA T5 | 2023-10-12 08:00 | 2023-11-16 08:00 | 120 | Continuous | [6 empty] | N | N | 2023-11-25 05:45
8-00899541 | Completed | 5L3 OOS | PCN 5LT3 Oil Samples | 5L3 | 2023-10-14 08:00 | 2023-10-15 16:00 | 5 | Continuous | [6 empty] | Y | N | 2023-10-16 13:14
8-00814166 | Proposed | SEA T2 OOS | ETM replacement | SEA T2 | 2023-10-15 08:00 | 2023-10-19 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-01-31 14:46
8-00815471 | Completed | 60L282 OOS, 60L294 Out from ELK, WIN & CFE supplied from ABN | VT Replacement | ELK 60B1, 60L294, 60L282 | 2023-10-15 13:00 | 2023-10-29 16:14 | 4 | Continuous | [6 empty] | N | Y | 2023-10-29 16:14
8-00813691 | Completed | MUR 2B6, 2CB6, 2CB7 OOS | NERC PM, Inspections | MUR 2B6 | 2023-10-16 08:00 | 2023-10-20 11:27 | 2 | Continuous | [6 empty] | N | N | 2023-10-20 11:27
8-00812762 | Completed | 2L112, NLY 2B4, T2 OOS | NLY T2 Inspections and Doble | 2L112, NLY 2B4, NLY T2 | 2023-10-16 08:00 | 2023-10-27 15:06 | 120 | Continuous | 2000 | 2000 | 2500 | 2500 | 560 | 600 | N | N | 2023-10-27 15:12
8-00902510 | Completed | 1L359 (7L81R) OOS | Restore temporary line cuts on STR 370 | 1L359 (7L81R) | 2023-10-16 08:00 | 2023-10-26 12:30 | 2 | Continuous | [6 empty] | N | N | 2023-10-27 13:00
8-00892891 | Completed | 2L51 Out from HPN 2D24 to BND 2D24 OOS | cable crossing LOA outage | 2L51 | 2023-10-16 08:00 | 2023-10-17 10:33 | 6 | Continuous | 1200 | 1200 |  |  |  |  | N | N | 2023-10-17 10:33
8-00898024 | Approved | RYC 5CX1 OOS | CPC NERC device hardening | RYC 5CX1 | 2023-10-16 08:00 | 2023-10-18 16:00 | 4 | Return Evenings | [6 empty] | N | N | 2023-10-13 14:32
8-00860426 | Completed | CBN T1, T1 PY/SY PN OOS | CPC NON-ELE PM | CBN T1, UHT 3RX4 | 2023-10-16 08:00 | 2023-10-18 11:22 | 4 | Continuous | [6 empty] | N | N | 2023-10-18 11:22
8-00805855 | Completed | CBN T6, T7 OOS, 60L12, 60L14 Out From CBN | Disconnect High Contact Resistance CO WO's | 60L14, 60L12, CBN T6, CBN 60B2, CBN 60B3, CBN 60B5, CBN 60B6, CBN T7 | 2023-10-16 08:00 | 2023-11-17 15:29 | 6 | Continuous | [6 empty] | Y | N | 2023-11-17 15:29
8-00805955 | Completed | 2L63, SYH T3 OOS | SYH T3 Insp & Doble, DS SS2 INSP | SYH 2D23, SYH 2D3, SYH T3, 2L63 | 2023-10-16 08:00 | 2023-10-20 11:47 | 2 | Continuous | [6 empty] | N | N | 2023-11-05 02:30
8-00803305 | Cancelled | 60L22 OOS | Replace emergent structures | 60L22 | 2023-10-16 08:00 | 2023-10-28 16:00 | NR | Continuous | [6 empty] | N | N | 2023-05-16 10:19
8-00802860 | Completed | 2L154 OOS | End of Life Structure Replacements | 2L154, GLD T1 | 2023-10-16 08:00 | 2023-10-20 15:34 | 3 | Continuous | [6 empty] | Y | N | 2023-10-20 15:35
8-00799776 | Completed | 5L72, MCA 5RX3 OOS | Controls Modernization Project | 5L72, MCA 5RX3 | 2023-10-16 08:00 | 2023-10-22 08:24 | 2 | Continuous | [6 empty] | Y | N | 2023-10-22 08:24
8-00800553 | Completed | MDN 5CB5 OOS | POW commissioning | MDN 5CB5 | 2023-10-16 08:00 | 2023-10-16 16:18 | 4 | Continuous | [6 empty] | N | N | 2023-10-16 16:18
8-00797193 | Completed | VIT SC2 OOS | SC2 BRUSHGEAR, ST2 INSP | VIT SC2 | 2023-10-16 08:00 | 2023-12-08 19:15 | 120 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-12-08 20:16
8-00797194 | Cancelled | VIT SC3 OOS | VIT SC3 BRUSHGEAR | VIT SC3 | 2023-10-16 08:00 | 2023-11-03 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-03 09:59
8-00797195 | Cancelled | VIT SC4 OOS | VIT SC4 BRUSHGEAR | VIT SC2, VIT SC4 | 2023-10-16 08:00 | 2023-10-25 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-22 10:33
8-00811403 | Completed | KI2 2CB4 OOS | CPC Control Testing | KI2 2CB4 | 2023-10-16 08:00 | 2023-10-16 14:22 | 2 | Continuous | [6 empty] | N | N | 2023-10-16 14:22
8-00811300 | Completed | DMR 1CB15 OOS | DMR 1CB15 INSP | DMR 1CB15 | 2023-10-16 08:00 | 2023-10-16 16:44 | 2 | Continuous | [6 empty] | N | N | 2023-10-16 16:44
8-00806480 | Cancelled | 60L22 OOS | Transmission structure replacements | 60L22 | 2023-10-16 09:00 | 2023-10-28 15:00 | 4 | Continuous | [6 empty] | N | N | 2023-10-10 11:20
8-00897447 | Completed | 42L Out from OLI. PRI 15 MW load added to 1L251 | FBC Outage | 42L, OLI 42-1 | 2023-10-16 09:00 | 2023-11-04 10:51 | NR | Continuous | [6 empty] | N | N | 2023-11-04 10:52
8-00899510 | Approved | WHS 71-T2 OOS, 2L277 (71L) Derated to 200 MVA | FBC Outage | WHS 71-T2 | 2023-10-16 09:00 | 2023-10-20 17:00 | NR | Continuous | [6 empty] | N | N | 2023-10-13 09:19
8-00903488 | Approved | SYA 5CX2 OOS | Inspect control cards for NERC C2FM project | SYA 5CX2 | 2023-10-16 12:00 | 2023-10-19 16:00 | 1 | Return Evenings and Weekends | [6 empty] | N | N | 2023-10-14 11:22
8-00812570 | Proposed | 2L94 OOS | Structure Repl | 2L94 | 2023-10-16 12:00 | 2023-10-20 12:00 | 3 | Continuous | [6 empty] | N | N | 2023-10-11 12:02
8-00856428 | Completed | 5L4 oos | Oil Sampling | 5L4 | 2023-10-17 07:00 | 2023-10-19 14:23 | 4 | Continuous | [6 empty] | Y | N | 2023-10-19 14:24
8-00835012 | Completed | MCA 5CB6 OOS | Disconnect switch 125VDC power supply upgrade | MCA 5CB6 | 2023-10-17 07:00 | 2023-10-17 22:12 | 4 | Continuous | [6 empty] | Y | N | 2023-10-17 22:13
8-00879616 | Completed | 60L285, NTL 60CB11 OOS. SPD transferred to 60L281 | 60CB11/60VT3 Inspection/doble | NTL 60CB11, 60L285 | 2023-10-17 08:00 | 2023-11-07 09:16 | 4 | Continuous | [6 empty] | N | N | 2023-11-23 03:30
8-00904238 | Completed | 2L51 OOS | Cable crossing, LOA | BND T2, 2L51 | 2023-10-17 08:00 | 2023-10-20 16:38 | 6 | Continuous | 1200 | 1200 |  |  |  |  | N | N | 2023-10-20 16:38
8-00811310 | Completed | DMR 1CB5 OOS | DMR 1CB5 INSP | DMR 1CB5, DMR 1B2, DMR 1B4 | 2023-10-17 08:00 | 2023-10-18 15:17 | 2 | Continuous | [6 empty] | N | N | 2023-10-18 15:17
8-00689997 | Cancelled | 1L214 OOS | End of Life Structure and Cross Arm Replacement | 1L214 | 2023-10-17 08:00 | 2023-10-26 16:00 | NR | Return Weekends | [6 empty] | N | N | 2022-02-03 14:52
8-00800558 | Approved | 5L83, MDN 5CB5 OOS | POW Commissioning | MDN 5CB5, 5L83 | 2023-10-17 08:00 | 2023-10-18 16:00 | 4 | Return Evenings | [6 empty] | N | N | 2023-10-16 16:02
8-00809700 | Completed | ACK 2MB2 OOS | Inspection | ACK 2MB2 | 2023-10-18 08:00 | 2023-10-20 13:30 | NR | Continuous | [6 empty] | N | N | 2023-10-20 13:37
8-00903641 | Denied | CBK 5RX5 OOS | 5RX5 B Gas relay piping install (emergency) | CBK 5RX5 | 2023-10-18 08:00 | 2023-10-18 16:00 | 3 | Continuous | [6 empty] | N | N | 2023-10-16 15:22
8-00860427 | Completed | CBN T2 OOS | CPC NON-ELE PM | CBN T2, UHT 3RX4 | 2023-10-18 12:00 | 2023-10-20 13:54 | 4 | Continuous | [6 empty] | N | N | 2023-10-20 13:55
8-00879663 | Completed | 60L270 Open between D1 and D2. CRS Islanded | INSP/MTCE at SKU | 60L270 | 2023-10-19 08:00 | 2023-10-19 16:12 | 3 | Continuous | [6 empty] | N | N | 2023-10-19 16:12
8-00824361 | Cancelled | 1L364 out from GMS to 1D1L364 to PPS T1, GMS 1B4 & LR2 OOS | GMS RTU cutover | 1L364, PPS T1, GMS 1B4 | 2023-10-19 08:00 | 2023-10-30 08:00 | 8 | Continuous | [6 empty] | N | Y | 2023-10-18 09:11
8-00800750 | Completed | MDN 5CB5, T2 OOS | POW Commissioning | MDN 5CB5 | 2023-10-19 08:00 | 2023-10-19 11:51 | 4 | Continuous | [6 empty] | N | N | 2023-10-19 11:51
8-00902413 | Completed | 5L72, MCA 5B7, 5CB7/9 OOS | To facilitate testing of MCA 5D23/33 after control upgrade | 5L72, MCA 5B7, MCA 5CB7, MCA 5CB9 | 2023-10-20 14:00 | 2023-10-22 08:24 | 0 | Continuous | [6 empty] | Y | N | 2023-10-22 08:24
8-00842329 | Completed | 2L13 OOS | end of life wood structure | 2L13, CKY 2B20 | 2023-10-23 08:00 | 2023-10-29 12:32 | 4 | Continuous | [6 empty] | Y | N | 2023-10-29 12:33
8-00813198 | Proposed | 1L205, HLD T1 OOS | Replacement of 1L205 Wood pole Structure | 1L205, HLD T1 | 2023-10-23 08:00 | 2023-10-28 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-04 13:55
8-00797175 | Completed | 2L129, VIT 2B1 OOS | VIT 2D2CB1, 2D2CB2 | VIT 2B1, 2L129 | 2023-10-23 08:00 | 2023-10-23 15:54 | 2 | Continuous | [6 empty] | N | N | 2023-10-23 15:54
8-00903676 | Approved | WHS T1 OOS, 2L277 (71L) restricted to 200 MVA | FBC Outage | WHS 71-T1 | 2023-10-23 09:00 | 2023-10-27 17:00 | NR | Continuous | [6 empty] | N | N | 2023-10-20 13:59
8-00873644 | Completed | BQN 2CX1 OOS | Cap Thor Replacement | BQN 2CX1 | 2023-10-23 12:00 | 2023-10-27 14:25 | 2 | Continuous | [6 empty] | Y | N | 2023-10-27 14:25
8-00813588 | Completed | 2L13 and CKY 2B10/2B20 OOS | Replace 2D27 | 2L13, CKY 2B20 | 2023-10-23 12:00 | 2023-11-09 16:39 | 8 | Continuous | [6 empty] | Y | N | 2023-11-25 03:30
8-00835018 | Completed | MCA 5CB9 OOS | Disconnect switch 125VDC power supply upgrade | MCA 5CB9 | 2023-10-24 07:00 | 2024-01-19 13:40 | 4 | Continuous | [6 empty] | Y | N | 2024-01-19 13:40
8-00894234 | Completed | AMC 5CX2 OOS | AMC 5CX2 CT testing/mtce | AMC 5CX2 | 2023-10-24 08:00 | 2023-10-27 10:51 | 4 | Continuous | [6 empty] | N | N | 2023-10-27 10:51
8-00813695 | Completed | MUR 2CB8 OOS | NERC PM, INSP | MUR 2CB8 | 2023-10-24 08:00 | 2023-10-27 14:24 | 2 | Continuous | [6 empty] | N | N | 2023-10-27 14:24
8-00819067 | Cancelled | BQN 2CX1 OOS | CX PM | BQN 2CX1 | 2023-10-24 08:00 | 2023-10-26 18:00 | NR | Continuous | [6 empty] | Y | N | 2023-10-17 15:02
8-00812480 | Completed | PAL T11 OOS | PAL 1D11 INSP | PAL T11 | 2023-10-24 08:00 | 2023-10-24 17:46 | 2 | Continuous | [6 empty] | N | N | 2023-10-24 17:46
8-00793700 | Cancelled | 5L91 OOS | Replace end of life spacers and insulators | 5L91 | 2023-10-24 08:00 | 2023-11-03 16:00 | 5 | Continuous |  |  |  |  | 560 | 500 | N | N | 2023-09-27 15:02
8-00809701 | Completed | ACK T2, 2B8 OOS | Inspection | ACK 2B8, ACK T2 | 2023-10-24 08:00 | 2023-10-25 11:19 | 4 | Continuous | [6 empty] | N | N | 2023-10-25 11:20
8-00809418 | Completed | HSY T12, 2Cb4/9 OOS | HSY 2CB9 INSP, HSY 2CB4 INSP | HSY T12, HSY 2B5/8 | 2023-10-24 08:00 | 2023-10-25 10:24 | 4 | Continuous | [6 empty] | N | N | 2023-10-25 10:24
8-00907679 | Completed | MDN 2RX1 Forced OOS | Low Oil (Known Leak Issue) | MDN 2RX1 | 2023-10-24 16:51 | 2023-11-17 14:23 | NR | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-11-17 14:23
8-00907740 | Completed | 5L72 Forced OOS | Disconnect gassing | 5L72 | 2023-10-24 18:01 | 2023-12-12 12:15 | NR | Continuous | 2000 | 2400 |  |  |  |  | Y | N | 2023-12-12 12:22
8-00907746 | Implemented | MCA 5D1CB9 Forced OOS, MCA 5B7 Bus Cut | Equipment Failure | MCA 5D1CB9 | 2023-10-24 18:01 | 2024-12-31 16:00 | NR | Continuous | [6 empty] | Y | N | 2024-02-06 17:07
8-00902073 | Cancelled | 5L72 OOS | Install Marker balls | 5L72 | 2023-10-25 07:00 | 2023-10-27 15:00 | 2 | Continuous | 2000 | 2000 |  |  |  |  | N | N | 2023-10-25 14:24
8-00835019 | Submitted | MCA 5CB10 OOS | Disconnect switch 125VDC power supply upgrade | MCA 5CB10 | 2023-10-25 07:00 | 2023-10-25 20:00 | 4 | Continuous | [6 empty] | Y | N | 2023-10-25 09:52
8-00906169 | Denied | 5L1 OOS | Replace based of Str 151-1 due to damange | 5L1 | 2023-10-25 08:00 | 2023-10-25 16:00 | 3 | Continuous | [6 empty] | Y | N | 2023-10-23 10:43
8-00813699 | Completed | MUR T7 OOS | PN PM | MUR T7 | 2023-10-25 08:00 | 2023-10-26 15:38 | 2 | Continuous | [6 empty] | N | N | 2023-10-26 15:38
8-00805961 | Completed | 2L22 OOS | WHY 2CVT2 INSP | BSY 2CB8, 2L22, WHY T2, WHY 2B2 | 2023-10-26 08:00 | 2023-10-27 12:44 | 2 | Continuous | [6 empty] | N | N | 2023-10-27 12:44
8-00907479 | Completed | MONROE-CUSTER NO 2 OOS | BPA Outage - Proximity for DS Replacement | MONROE-CUSTER NO 2 500KV LINE_ | 2023-10-26 19:00 | 2023-10-27 01:00 | NR | Continuous | [6 empty] | N | N | 2023-10-27 02:33
8-00906338 | Completed | MON 1CB5, 1CB2, T5 OOS | DS INSP | MON 1CB2, MON 1CB5, MON T5 | 2023-10-27 08:00 | 2023-11-04 10:57 | 2 | Continuous | [6 empty] | N | N | 2023-11-04 10:58
8-00898511 | Cancelled | 5L81 OOS | Test energization of AMC 5CVT1 | 5L81 | 2023-10-27 08:00 | 2023-10-27 16:00 | 2 | Continuous | 1000 | 1000 | 2000 | 2000 |  |  | N | N | 2023-10-13 14:52
8-00904826 | Completed | 2L263 (72L) OOS | FBC Outage | 2L263 (72L) | 2023-10-28 08:00 | 2023-10-28 15:41 | NR | Continuous | [6 empty] | N | N | 2023-10-28 15:41
8-00904729 | Completed | L82-88 OOS | Customer Request: CT Repl | L82-88 | 2023-10-30 07:00 | 2023-11-09 13:20 | NR | Continuous | [6 empty] | N | N | 2023-11-09 13:20
8-00903699 | Completed | 11EL OOS. WTS-VAS Path Open | FBC Outage | 11EL | 2023-10-30 07:00 | 2023-11-03 10:20 | NR | Continuous | [6 empty] | N | N | 2023-11-03 13:47
8-00824383 | Cancelled | GMS T14 OOS | GMS RTU cutover | GMS 2CB3, GMS T14 | 2023-10-30 08:00 | 2023-11-02 16:00 | NR | Continuous | [6 empty] | N | N | 2023-06-21 08:13
8-00813242 | Denied | MSA 2CB9 OOS | MSA 2CB9 - PVRP, LOCH, CN. COND. NERC | MSA 2CB9 | 2023-10-30 08:00 | 2023-11-01 16:00 | NR | Continuous | [6 empty] | N | N | 2023-10-19 11:43
8-00813334 | Completed | 60L68, CKY 60CB2/CB3 OOS | PM INSPECTIONS of CKY 60D1CB2, 60D1CB3, 60D22, 60CVT2, SQH 60CB1, 60VT1, TEST SQH 60CB1 CN | 60L68, CKY 60B2 | 2023-10-30 08:00 | 2023-11-04 16:25 | 4 | Continuous | [6 empty] | N | N | 2023-11-04 16:25
8-00805873 | Cancelled | 2L129 OOS | ARN DS VT CB Insp/Mtce | ARN 2CB6, ARN 2CB7, 2L129 | 2023-10-30 08:00 | 2023-11-03 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-10-10 08:38
8-00798271 | Cancelled | 1L281 Part Out | Replace end of life structures and cros sarms between ARM and RJ1 switch | 1L218 | 2023-10-30 08:00 | 2023-11-02 16:00 | 0 | Continuous | [6 empty] | N | N | 2023-10-10 08:26
8-00803259 | Proposed | CBN T3 OOS | ETM Replacement | CBN T3 | 2023-10-30 08:00 | 2023-11-03 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-01-31 14:41
8-00801143 | Cancelled | 2L20 OOS | Overview Inspection | CSQ 2B7, 2L20 | 2023-10-30 08:00 | 2023-11-02 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-10-26 09:16
8-00793191 | Cancelled | 2L129 OOS | Planned maintenance of pumping plants | 2L129 | 2023-10-30 08:00 | 2023-11-06 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-02-16 09:40
8-00811324 | Completed | DMR 2CB23 OOS | DMR 2CB23 INSP & CN | DMR 2CB23 | 2023-10-30 08:00 | 2023-11-01 15:31 | 2 | Continuous | [6 empty] | Y | N | 2023-11-01 15:31
8-00811345 | Cancelled | DMR 2CB4 OOS | COMPRESSOR REPLACEMENT | DMR 2CB4 | 2023-10-30 08:00 | 2023-11-02 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-10-06 12:26
8-00824358 | Completed | 2L308 OOS | GMS RTU cutover | GMS T13, GMS T14, 2L308 | 2023-10-30 08:01 | 2023-11-08 11:38 | 8 | Continuous | [6 empty] | N | N | 2023-11-08 11:38
8-00903701 | Completed | WTS T2 OOS. 77L Restricted to 238 MVA | FBC Outage | WTS T2, WTS CB1, WTS CB3 | 2023-10-30 09:00 | 2023-11-03 13:11 | NR | Continuous | [6 empty] | Y | N | 2023-11-03 13:44
8-00903349 | Approved | 30 MW load (total) added to 1L251 (PRI, BCG, HED, KER) | FBC Outage | 42L | 2023-10-30 09:00 | 2023-11-03 15:00 | NR | Continuous | [6 empty] | N | N | 2023-10-27 14:13
8-00835016 | Cancelled | MCA 5CB7 OOS | Disconnect switch 125VDC power supply upgrade | MCA 5CB7 | 2023-10-31 07:00 | 2023-10-31 20:00 | 4 | Continuous | [6 empty] | Y | N | 2023-10-25 15:05
8-00901306 | Denied | 2L293, SEL 2MB2, 2L221 OOS | PCB lighting removal LOA | 2L221, 2L293, SEL 2MB2 | 2023-10-31 08:00 | 2023-10-31 16:00 | 2 | Continuous |  |  |  |  | 560 | 600 | N | N | 2023-10-26 15:38
8-00896521 | Cancelled | NIC 5RX11 OOS | Oil Leak Repair | NIC 5RX11 | 2023-10-31 08:00 | 2023-10-31 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-11-08 23:00
8-00908851 | Completed | 2L221 OOS | Work being done in proximity of the Line | 2L221 | 2023-10-31 08:00 | 2023-10-31 14:45 | 2 | Continuous | [6 empty] | Y | N | 2023-11-08 23:05
8-00813703 | Completed | MUR T2, 12RX32 OOS | PN PM, Doble test | MUR T2, MUR 60B11, MUR 60B13 | 2023-10-31 08:00 | 2023-11-02 14:43 | 2 | Continuous | [6 empty] | N | N | 2023-11-02 14:43
8-00888876 | Completed | 1L275 OOS | ALTALINK OUTAGE | 1L275 (786L) | 2023-11-01 06:00 | 2023-11-05 20:47 | 96 | Continuous | [6 empty] | N | N | 2023-11-05 20:52
8-00812704 | Completed | KCL T7 OOS | KCL T7 oiling and 2D7 Disconnect PM | KCL T7 | 2023-11-01 08:00 | 2023-11-22 13:04 | 24 | Continuous | [6 empty] | N | N | 2023-11-22 13:04
8-00811295 | Completed | DMR 1CB1 OOS | DMR 1CB1 INSP | DMR 1CB1 | 2023-11-02 08:00 | 2023-11-03 15:08 | 2 | Continuous | [6 empty] | N | N | 2023-11-03 15:08
8-00810779 | Completed | BKL STATCOM OOS | INSP, MJ05 and NON EL | BKL STATCOM | 2023-11-02 08:00 | 2023-11-03 15:02 | 6 | Continuous | [6 empty] | N | N | 2023-11-03 15:11
8-00810795 | Denied | 1L218 Out from SAM, SAM T1, 1B1 OOS | SAM 1D1 Inspection | 1L218, SAM T1, SAM 1B1 | 2023-11-03 08:00 | 2023-11-03 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-10-31 09:02
8-00910264 | Completed | CBK 5RX5 OOS | Gas accummulation (emergency) | CBK 5CB23, CBK 5RX5 | 2023-11-03 08:00 | 2023-11-03 10:34 | 1 | Continuous | [6 empty] | N | N | 2023-11-03 10:42
8-00911237 | Completed | BQN 2CX1 OOS | Troubleshoot alarm cause | BQN 2CX1 | 2023-11-04 10:00 | 2023-11-04 15:32 | 2 | Continuous | [6 empty] | Y | N | 2023-11-04 15:32
8-00881445 | Completed | 1L244, NIC 1CB15, 1CB16 OOS | DS PM | 1L244, NIC 1CB15, NIC 1CB16, WBK T1, WBK T2, WBK T3 | 2023-11-05 22:30 | 2023-11-06 04:40 | 1 | Continuous | [6 empty] | N | N | 2023-11-14 08:45
8-00899530 | Approved | 170L OOS, 1L275 radial feeding Coleman (10 MW) | AltaLink Outage | 170L (632s Russell - 799s Coleman) | 2023-11-06 06:30 | 2023-11-06 08:00 | NR | Continuous | [6 empty] | N | N | 2023-11-02 15:12
8-00909550 | Completed | 1L274 Out From 1D4L274 to BCK 1D21 | Line maintenance | 1L274 (887L) | 2023-11-06 08:00 | 2023-11-06 21:04 | 15000 | Continuous | [6 empty] | N | N | 2023-11-06 21:04
8-00833627 | Cancelled | GMS T11 OOS | GMS Control System Upgrade | GMS T11 | 2023-11-06 08:00 | 2023-11-11 16:00 | 24 | Continuous | [6 empty] | N | N | 2023-06-21 13:45
8-00910609 | Completed | L81-87 OOS | Customer outage: Disconnect repair | L81-87 | 2023-11-07 07:00 | 2023-11-09 13:41 | NR | Continuous | [6 empty] | N | N | 2023-11-09 13:41
8-00906238 | Approved | LEE CB3 OOS | FBC Outage | LEE CB3 | 2023-11-07 07:00 | 2023-11-07 17:00 | NR | Continuous | [6 empty] | N | N | 2023-11-06 15:19
8-00903708 | Completed | 60L277 (12L) OOS, 25L Closed | FBC Outage | 60L227 (12L) | 2023-11-07 08:00 | 2023-11-08 11:22 | NR | Continuous | [6 empty] | N | N | 2023-11-08 11:22
8-00909733 | Completed | 2L240 OOS | End of life crossarms replacement | 2L240 | 2023-11-07 08:00 | 2023-11-07 16:15 | 2 | Continuous | [6 empty] | N | N | 2023-11-07 16:21
8-00911697 | Completed | KCL 2B10 OOS | KCL 2D2 motor replacement | KCL 2B10, KCL 2CB10, KCL 2CB11 | 2023-11-07 08:00 | 2023-11-15 18:10 | 3 | Continuous | [6 empty] | N | N | 2023-11-14 13:36
8-00883348 | Cancelled | 5L83, MDN 5CB6 OOS | POW commissioning | 5L83 | 2023-11-07 08:00 | 2023-11-08 16:00 | 0 | Return Evenings | 2000 | 2400 |  |  |  |  | N | N | 2023-10-30 13:46
8-00812617 | Completed | WSN 5CB3 oos | CB Insp & Doble testing | WSN 5CB3 | 2023-11-07 08:00 | 2023-11-17 15:15 | 4 | Continuous | [6 empty] | N | N | 2023-11-17 15:15
8-00812481 | Completed | PAL 1CB7 OOS | PAL 1CB7 PCB BUSHING OIL SAMPLES | PAL 1CB7, PAL T3 | 2023-11-07 08:00 | 2023-11-07 13:19 | 2 | Continuous | [6 empty] | N | N | 2023-11-07 13:20
8-00812473 | Completed | PAL 1CB6 OOS | PAL 1CB6 PCB BUSHING OIL SAMPLES | PAL 1CB6 | 2023-11-07 08:00 | 2023-11-07 14:39 | 2 | Continuous | [6 empty] | N | N | 2023-11-07 14:40
8-00813239 | Cancelled | 1L31 Out from GIB, GIB T2, 1B3 OOS | GIB 1L31 - 1D2 COND, 1D2CB3 INSP, 1D22 A PHASE ALIGNMENT ISSUE CO | GIB T2, 1L31, GIB 1B3 | 2023-11-07 08:00 | 2023-11-08 16:00 | 2 | Continuous | [6 empty] | Y | N | 2023-11-02 08:12
8-00810649 | Completed | AVO 1CB1 OOS | Inspection | AVO 1CB1 | 2023-11-07 08:00 | 2023-11-08 13:47 | 4 | Continuous | [6 empty] | N | N | 2023-11-08 13:47
8-00809702 | Completed | 2L240, ACK 2B13 OOS | Inspection | ACK 2B13, 2L240, SAM 1CB2 | 2023-11-07 08:00 | 2023-11-07 16:15 | 2 | Continuous | [6 empty] | N | N | 2023-11-07 16:20
8-00809495 | Completed | PIK 2RX2 OOS | PIK 2CB22 INSP, CN PM | PIK 2CB22, PIK 2RX2 | 2023-11-07 08:00 | 2023-11-07 15:16 | 4 | Continuous | [6 empty] | N | N | 2023-11-08 14:22
8-00801144 | Completed | 2L31 OOS | Overview Inspection | 2L31 | 2023-11-07 08:00 | 2023-11-10 11:15 | 2 | Continuous | [6 empty] | N | N | 2023-11-10 11:15
8-00804248 | Completed | 1L241 OOS | Replace EOL structures | 1L241 | 2023-11-07 08:00 | 2023-11-10 15:13 | 2 | Continuous | [6 empty] | N | N | 2023-11-10 15:13
8-00810803 | Denied | 1L218 Open between ARM-RVG | ARM 1D22, 1D2CB1 INSP | ARM T2, 1L218, SAM 1CB1, ARM 1B2 | 2023-11-08 08:00 | 2023-11-10 16:00 | 6 | Continuous | [6 empty] | N | N | 2023-11-06 14:08
8-00870571 | Completed | JOE 60CX1, 60CX2 OOS | JOE Station Upgrade (60D31 and 60CT1 removed) | JOE 60CX1, JOE 60CX2, JOE 60D31 | 2023-11-08 08:00 | 2024-02-09 11:06 | 6 | Continuous | [6 empty] | N | N | 2024-03-01 03:30
8-00910984 | Completed | 2L263 (72L) OOS | FBC Outage | 2L263 (72L) | 2023-11-08 08:00 | 2023-11-08 22:08 | NR | Continuous | [6 empty] | N | N | 2023-11-08 22:08
8-00904605 | Cancelled | 2L293, NLY 2B2 OOS | NLY 2D22 Mtce | 2L293, NLY 2B2 | 2023-11-08 08:00 | 2023-11-08 16:00 | 2 | Continuous |  |  |  |  | 560 | 600 | N | N | 2023-10-27 13:23
8-00902918 | Completed | 60L284 Out from CBK. CBK 60CB7/8 OOS | Inspection | CBK 60CB7, CBK 60CB8, 60L284 | 2023-11-08 08:00 | 2023-11-08 22:43 | 2 | Continuous | [6 empty] | N | N | 2023-11-08 22:43
8-00912900 | Completed | ACK 5RX8, 5CB48 OOS | Low SF6 Alarm | ACK 5RX8, ACK 5CB48 | 2023-11-08 12:30 | 2023-11-08 15:22 | 2 | Continuous | [6 empty] | N | N | 2023-11-08 15:22
8-00807551 | Completed | 60L208, 1L214 OOS | Replace end of life structures and crossarms | 1L214, 60L208 | 2023-11-08 14:00 | 2023-12-07 12:46 | 6 | Continuous | [6 empty] | N | Y | 2023-12-07 12:46
8-00809501 | Denied | PIK 2CB15 OOS | PIK 2CB15 BFPN | PIK 2CB15 | 2023-11-09 08:00 | 2023-11-09 16:00 | 1 | Continuous | [6 empty] | N | N | 2023-11-06 09:07
8-00810712 | Cancelled | 1L219, DUG 1B6 OOS | Repair DS & PM | 1L219, DUG 1B6 | 2023-11-09 08:00 | 2023-11-10 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-10-23 10:47
8-00884764 | Completed | 60L289 Out from CBK, CBK 60CB3/5 OOS | Inspection | 60L289, CBK 60CB3, CBK 60CB5 | 2023-11-09 08:00 | 2023-11-10 00:10 | 2 | Continuous | [6 empty] | N | N | 2023-11-10 00:10
8-00912885 | Completed | ACK 5CX2, 5CB50 OOS | Low SF6 Alarm | ACK 5CX2 | 2023-11-09 09:30 | 2023-11-09 23:48 | 2 | Continuous | [6 empty] | N | N | 2023-11-09 23:48
8-00813746 | Completed | GMS 1B7 OOS | GMS 1CT7 INSP | GMS 1CB7, GMS 1B7 | 2023-11-12 08:00 | 2023-11-12 12:33 | NR | Continuous | [6 empty] | N | N | 2023-11-12 12:33
8-00814122 | Cancelled | GLN T2, T5 OOS | GLN 230kV Load Interconnection (Blackwater) | GLN 2MB1, GLN T2, GLN T5 | 2023-11-13 08:00 | 2023-12-08 16:00 | NR | Return Weekends | [6 empty] | N | N | 2023-12-01 14:33
8-00813356 | Completed | PEM T1 OOS | ETM REPLACMENT, NON-ELEC PN, COOLER INSPECTION | PEM T1 | 2023-11-14 08:00 | 2023-11-17 14:47 | 4 | Continuous | [6 empty] | N | N | 2023-11-17 14:47
8-00813314 | Completed | DCV T1, 12CB1 OOS | DCV T1 NON-ELECTRICALS, 12CB1 BFPN COND. | 60L90, DCV T1 | 2023-11-14 08:00 | 2023-11-21 12:48 | 6 | Continuous | [6 empty] | N | N | 2023-11-21 12:48
8-00833633 | Cancelled | GMS T12 oos | GMS Control System Upgrade | GMS T12 | 2023-11-14 08:00 | 2023-11-20 16:00 | 24 | Continuous | [6 empty] | N | N | 2023-06-21 13:45
8-00810344 | Completed | VVW 1CB1 OOS | VVW 1CB1 INSP | VVW 1CB1 | 2023-11-14 08:00 | 2023-11-17 11:26 | 4 | Continuous | [6 empty] | N | N | 2023-11-17 11:26
8-00805348 | Completed | COK T2 OOS | Non-EL Protection Testing | COK T2 | 2023-11-14 08:00 | 2023-11-16 15:57 | 4 | Continuous | [6 empty] | N | N | 2023-11-16 15:57
8-00801145 | Completed | 2L32 OOS | Overview Inspection | CSQ 2CB1, 2L32 | 2023-11-14 08:00 | 2023-11-17 14:33 | 2 | Continuous | [6 empty] | N | N | 2023-11-17 14:33
8-00798241 | Denied | 5L96 OOS | Replace end of life insulators | 5L96 | 2023-11-14 08:00 | 2023-11-17 16:00 | 3 | Continuous |  |  |  |  | 560 | 450 | N | N | 2023-11-03 12:30
8-00877647 | Approved | 1L275 radially supply Coleman | AltaLink Outage (Line repair) | 170L (632s Russell - 799s Coleman) | 2023-11-15 07:00 | 2023-11-20 16:00 | NR | Continuous | [6 empty] | N | N | 2023-11-17 08:37
8-00898439 | Cancelled | NIC 5CB12 OOS | Dashpot replacement | NIC 5CB12 | 2023-11-15 08:00 | 2023-11-17 16:00 | NR | Continuous | [6 empty] | N | N | 2023-11-20 18:00
8-00901294 | Completed | 2L293, SEL 2MB2, 2L222 OOS | PCB lighting removal LOA | 2L222, 2L293, SEL 2MB2 | 2023-11-16 08:00 | 2023-11-16 15:40 | 2 | Continuous |  |  |  |  | 560 | 600 | Y | N | 2023-11-16 15:44
8-00809443 | Completed | PIK 2CB13 OOS | PIK 2CB13 INSP, AFCH, CN PM, DOBL | PIK 2CB13 | 2023-11-16 08:00 | 2023-11-17 15:08 | 4 | Continuous | [6 empty] | N | N | 2023-11-17 15:08
8-00809447 | Completed | PIK 2CB17 OOS | PIK 2CB17 INSP, AFCH, CN PM, DOBL | PIK 2CB17 | 2023-11-20 08:00 | 2023-11-21 15:43 | 4 | Continuous | [6 empty] | N | N | 2023-11-21 15:43
8-00811460 | Completed | FLW 2B2, 2CB2, 2CB3 OOS | Insp & Doble | FLW 2B2, FLW T1 | 2023-11-20 08:00 | 2023-12-15 13:56 | 4 | Continuous | [6 empty] | N | N | 2023-12-15 13:56
8-00801146 | Completed | 2L33 OOS | Overview Inspection | 2L33 | 2023-11-20 08:00 | 2023-11-24 12:59 | 2 | Continuous | [6 empty] | N | N | 2023-11-24 13:00
8-00803297 | Completed | 1L14 OOS | End of Life Structure Replacements | 1L14, KSH T2, SHA T1 | 2023-11-20 08:00 | 2023-11-24 16:14 | 2 | Continuous | [6 empty] | N | N | 2023-11-24 16:14
8-00911021 | Completed | BTS CB7 OOS | FBC Outage | BTS CB7 | 2023-11-20 08:00 | 2023-11-23 14:00 | NR | Continuous | [6 empty] | N | N | 2023-11-23 17:25
8-00813357 | Completed | PEM T2 OOS | ETM REPLACMENT, NON-ELEC PN, COOLER INSPECTION | PEM T2 | 2023-11-20 08:00 | 2023-11-23 14:15 | 4 | Continuous | [6 empty] | Y | N | 2023-11-23 14:15
8-00813581 | Completed | 2L9 , CKY 2B8 OOS | Replace 2D24 | CKY T6, 2L9, CKY 2B8 | 2023-11-20 08:00 | 2023-11-25 08:01 | 6 | Continuous | [6 empty] | Y | N | 2023-12-13 03:30
8-00813363 | Cancelled | UHT 3CB5 OOS | TRIP TESTING | UHT 3CB5 | 2023-11-21 08:00 | 2023-11-21 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-10-18 11:56
8-00917914 | Completed | MCA 5B7, 5L72 OOS | MCA 5B7 SF6 gas work, disassembly, hi-pot set up, and Hi-Pot | 5L72, MCA 5B7 | 2023-11-21 08:00 | 2023-12-12 12:14 | NR | Continuous | [6 empty] | N | N | 2023-12-12 12:22
8-00902531 | Completed | SYA 5CX2 OOS | Inspection | SYA 5CX2 | 2023-11-21 08:00 | 2023-11-23 09:48 | 6 | Continuous | [6 empty] | N | N | 2023-12-09 03:30
8-00902946 | Completed | 60L295 Out from SPL, SPL T1 OOS | SPL 60VT3 oil samples | 60L295, SPL T1 | 2023-11-21 08:00 | 2023-11-21 12:28 | 2 | Continuous | [6 empty] | N | N | 2023-11-21 12:28
8-00918605 | Completed | TKW 12RX2 Forced out | Forced outage | TKW 12RX2 | 2023-11-22 07:40 | 2023-11-24 16:47 | NR | Continuous | [6 empty] | N | N | 2023-11-24 16:47
8-00916442 | Completed | SEL 5CB9, 5CB8 OOS | SEL 5CB9 BFPN | SEL 5CB8, SEL 5CB9 | 2023-11-22 08:00 | 2023-11-22 14:11 | 0 | Continuous | [6 empty] | N | N | 2023-11-22 14:11
8-00864051 | Completed | 60L219, SCB, PIN OOS | WHN 60CB1 annual PM work, BF Trip Testing | WHN 60CB1, 60L219 | 2023-11-22 08:00 | 2023-11-22 14:55 | 1 | Continuous | [6 empty] | N | N | 2023-11-22 14:55
8-00809452 | Completed | PIK 2CB 18 OOS | PIK 2CB18 INSP, AFCH, CN PM, DOBL | PIK 2CB18 | 2023-11-22 08:00 | 2023-11-23 17:04 | 4 | Continuous | [6 empty] | N | N | 2023-11-23 17:09
8-00911568 | Completed | 60L225 (13L), KCL T5 OOS | KCL T5 PCB soil remediation LOA | 60L225 (13L), KCL T5 | 2023-11-23 08:00 | 2023-11-28 15:12 | 3 | Continuous | [6 empty] | N | N | 2023-11-28 15:15
8-00916176 | Completed | 1L275 OOS | Emergent hot spot repairs on 1CT22, and 1D22 | 1L275 (786L) | 2023-11-24 07:00 | 2023-11-24 14:44 | 2 | Continuous | [6 empty] | N | N | 2023-11-24 14:44
8-00813364 | Completed | UHT 3RX4 OOS | NON-ELEC PN | UHT 3CB34, UHT 3RX4 | 2023-11-24 08:00 | 2023-11-24 14:43 | NR | Continuous | [6 empty] | N | N | 2023-11-24 14:43
8-00818633 | Cancelled | SKA T6 oos | SKA T6 Insp & Doble testing | SKA T6 | 2023-11-24 08:00 | 2023-12-08 16:00 | NR | Continuous | [6 empty] | N | N | 2023-09-15 11:11
8-00813329 | Cancelled | CKY T5, 2B6 OOS | PM INSPECTIONS of CKY 2D2CB6, 2D2CB8 | CKY 2CB6, CKY 2CB8, CKY T5, CKY 2B6 | 2023-11-27 08:00 | 2023-11-29 16:00 | 8 | Continuous | [6 empty] | N | Y | 2023-11-08 09:11
8-00824355 | Cancelled | 1L363, 1B2 OOS | GMS RTU cutover | PPS T2, GMS 1B2, 1L363 | 2023-11-27 08:00 | 2023-11-27 18:00 | 2 | Continuous | [6 empty] | N | N | 2023-11-29 18:00
8-00810343 | Cancelled | VVW T2 OOS | transformer and LTC INSP, DOBLE | VVW T2 | 2023-11-27 08:00 | 2023-12-01 16:00 | NR | Continuous | [6 empty] | N | N | 2023-08-09 12:47
8-00916230 | Completed | 5L1 OOS | Base of Str. 151-1 Replacement | 5L1 | 2023-11-28 05:00 | 2023-11-28 17:29 | 8 | Continuous | [6 empty] | Y | N | 2023-11-28 17:29
8-00913994 | Completed | NIC 5RX11 OOS | Oil leak repair | NIC 5RX11 | 2023-11-28 08:00 | 2023-11-28 13:54 | 2 | Continuous | [6 empty] | N | N | 2023-11-28 13:54
8-00813317 | Completed | DCV T3, 12CB3 OOS | DCV T3 NON-ELECTRICALS, 12CB3 BFPN COND., 60D3 Inspection | DCV T3 | 2023-11-28 08:00 | 2023-11-28 14:44 | 3 | Continuous | [6 empty] | N | N | 2023-11-28 14:45
8-00812474 | Completed | PAL 1CB9 OOS | PAL 1CB9 PCB BUSHING OIL SAMPLES | PAL 1CB9, PAL T11 | 2023-11-28 08:00 | 2023-11-28 16:37 | 2 | Continuous | [6 empty] | N | N | 2023-11-28 16:37
8-00810348 | Completed | VVW 1CX1 OOS | VVW 1CX1 and 1CBCX1 INSP | VVW 1CX1, VVW 1CBCX1 | 2023-11-28 08:00 | 2023-11-30 16:48 | 2 | Continuous | [6 empty] | N | N | 2023-11-30 16:48
8-00811319 | Cancelled | DMR 2Cb13 OOS | DMR 2CB13 INSP & CN | DMR 2CB13 | 2023-11-28 08:00 | 2023-11-28 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-11-30 18:00
8-00809490 | Completed | PIK 2CB8 OOS | PIK 2CB8 INSP, AFCH, DOBL | PIK 2CB8 | 2023-11-28 08:00 | 2023-11-29 14:25 | 4 | Continuous | [6 empty] | N | N | 2023-11-29 14:25
8-00806038 | Completed | 2L45, SPG 2B5, 2CB4 OOS | NERC PM, INSP | 2L45, SPG 2B5 | 2023-11-28 08:00 | 2023-12-01 15:00 | 2 | Continuous | [6 empty] | N | N | 2023-12-01 15:00
8-00801147 | Completed | 2L45 OOS | Overview Inspection | 2L45, SPG 2B5 | 2023-11-28 08:00 | 2023-11-30 12:55 | 2 | Continuous | [6 empty] | N | N | 2023-12-07 21:15
8-00804249 | Completed | 2L265 OOS | Structure replacement | 2L265, NIC 2CB11, NIC 2CB12, VVW 1CB7, VVW 1CB8, VVW T3, VVW T2, WKA 1CB4, WKA T1 | 2023-11-29 08:00 | 2023-12-08 12:39 | 4 | Continuous | [6 empty] | Y | N | 2023-12-08 12:39
8-00810340 | Denied | 2L265, VVW 2B7, NIC 2CB11, 2CB12 OOS | DS PM at VVW and NIC on 2L265 | 2L265, NIC 2CB11, NIC 2CB12, VVW 2B7 | 2023-11-29 08:00 | 2023-12-06 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-11-17 13:23
8-00917101 | Completed | 2L265, NIC 2CB11/12, VVW 2B7, 1B7 OOS | DS PM at VVW and NIC | 2L265, NIC 2CB11, NIC 2CB12, VVW T3, VVW 1B7, VVW T2, VVW 2B7 | 2023-11-29 08:00 | 2023-12-05 12:03 | 4 | Continuous | [6 empty] | N | N | 2023-12-21 03:30
8-00919548 | Completed | CBK 5RX5 OOS | Emergency maintenance | CBK 5CB23, CBK 5RX5 | 2023-11-29 08:00 | 2023-11-29 12:19 | 1 | Continuous | [6 empty] | N | N | 2023-11-29 12:19
8-00913292 | Completed | NTL T4, 12CX3 OOS | PCB soil remediation around NTL SS4 | NTL T4 | 2023-11-29 11:00 | 2023-11-30 14:13 | 1 | Continuous | [6 empty] | N | N | 2023-11-30 14:13
8-00826541 | Completed | 60L298, JOE 60CX1/2 OOS | JOE Station Upgrade | JOE 60CB6, JOE 60CX1, JOE 60CX2, 60L298, JOE 60B6, JOE 60CB1, JOE T11, JOE 60B1 | 2023-11-30 07:00 | 2023-12-18 23:04 | 8 | Continuous | [6 empty] | N | N | 2023-12-18 23:04
8-00905622 | Cancelled | CBK T6, 12RX6, 12CX2 OOS | PM, inspection, hot spot repair | CBK 12CX2, CBK 12RX6, CBK 60CB8, CBK T6 | 2023-11-30 08:00 | 2023-12-01 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-12-06 11:11
8-00809454 | Completed | PIK 2CB7 OOS | PIK 2CB7 INSP, AFCH, DOBL | PIK 2CB7 | 2023-11-30 08:00 | 2023-12-01 14:45 | 4 | Continuous | [6 empty] | N | N | 2023-12-01 14:45
8-00919600 | Completed | KCL 2CB11 OOS | Relay Repair | KCL 2CB11 | 2023-12-01 10:00 | 2023-12-01 11:09 | 1 | Continuous | [6 empty] | N | N | 2023-12-01 11:12
8-00893165 | Completed | DMR SVC OOS | Inspection | DMR 1B8, DMR SVC | 2023-12-04 07:00 | 2023-12-04 17:49 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2023-12-04 17:49
8-00813327 | Completed | PHR T1, 1B2 OOS | PHR T1, 1D21 INSP + DOBL | PHR T1, PHR 1B1 | 2023-12-04 08:00 | 2023-12-08 15:54 | NR | Continuous | [6 empty] | N | N | 2023-12-08 15:54
8-00813348 | Cancelled | CKY 2CB9 OOS | TRIP TESTING | CKY 2CB9 | 2023-12-04 08:00 | 2023-12-04 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-12-06 18:00
8-00810645 | Completed | AVO STATCOM 2 OOS | INSP, MJ05 and NON EL | AVO STATCOM UNIT 2 | 2023-12-04 08:00 | 2023-12-05 14:38 | 6 | Continuous | [6 empty] | N | N | 2023-12-05 14:38
8-00801150 | Completed | 2L40, BND T1 OOS | Overview Inspection | 2L40, NEL 2CB4 | 2023-12-04 08:00 | 2023-12-08 16:34 | 2 | Continuous | [6 empty] | N | N | 2023-12-08 16:34
8-00813347 | Cancelled | CKy 2CB8 OOS | TRIP TESTING | CKY 2CB8 | 2023-12-05 08:00 | 2023-12-05 16:00 | NR | Continuous | [6 empty] | N | N | 2023-12-07 18:00
8-00917124 | Completed | AMC 5CX1 OOS | NERC Security Patching | AMC 5CX1 | 2023-12-05 08:00 | 2023-12-05 16:44 | 4 | Continuous | [6 empty] | N | N | 2023-12-05 16:44
8-00917126 | Completed | AMC 5CX2 OOS | NERC Security Patching | AMC 5CX2 | 2023-12-06 08:00 | 2023-12-06 13:07 | 4 | Continuous | [6 empty] | N | N | 2023-12-22 03:30
8-00811335 | Completed | DMR 2CB3 OOS | DMR 2CB3, 2CT3 INSP & CN | DMR 2CB3 | 2023-12-06 08:00 | 2023-12-06 13:46 | 2 | Continuous | [6 empty] | N | N | 2023-12-06 13:46
8-00810643 | Completed | AVO STATCOM 1 OOS | INSP, MJ05 and NON EL | AVO STATCOM UNIT 1 | 2023-12-06 12:00 | 2023-12-07 15:47 | 6 | Continuous | [6 empty] | N | N | 2023-12-07 15:47
8-00919620 | Completed | ACK 5RX7 OOS | Investigation of prior tripping | ACK 5RX7 | 2023-12-07 08:00 | 2023-12-07 14:17 | 4 | Continuous | [6 empty] | N | N | 2023-12-07 14:17
8-00922761 | Completed | 1L214 OOS. 60L208 RTS | 1L214 Structures Replacement | 1L214 | 2023-12-07 12:00 | 2023-12-21 15:23 | 5 | Continuous | [6 empty] | N | N | 2023-12-21 15:23
8-00923583 | Completed | MCA 5B6, LS2 OOS | MCA 5B7 Testing | MCA 5B6, MCA 5B7, MCA LS2 | 2023-12-10 07:00 | 2023-12-10 19:00 | 4 | Continuous | [6 empty] | N | N | 2023-12-11 09:46
8-00924033 | Completed | SYA 5CX1 OOS | Cap Thor low air alarm | SYA 5CX1 | 2023-12-12 08:00 | 2023-12-14 11:40 | 6 | Continuous | [6 empty] | Y | N | 2023-12-14 11:40
8-00809358 | Completed | NIC 2CB12 OOS | NERC PM 2CB12 Inspection | NIC 2CB12 | 2023-12-12 08:00 | 2023-12-13 13:33 | 4 | Continuous | [6 empty] | N | N | 2023-12-13 13:33
8-00801154 | Completed | 2L44 OOS | Overview Inspection | 2L44 | 2023-12-12 08:00 | 2023-12-14 15:41 | 2 | Continuous | [6 empty] | N | N | 2023-12-14 15:41
8-00926328 | Completed | 5L72, MCA 5B6, LS2 OOS | MCA 5CB6 & 5CB7 NERC CN Trip Testing | 5L72, MCA 5B6, MCA LS2 | 2023-12-13 07:00 | 2023-12-13 18:12 | 1 | Continuous | [6 empty] | Y | N | 2023-12-13 18:13
8-00813328 | Completed | SEC T2, 1CB12 OOS | SEC T2 NON-ELECTRICALS, FOLLOW UP TO PM CO | SEC 1CB12, SEC T2 | 2023-12-13 08:00 | 2023-12-13 14:40 | NR | Continuous | [6 empty] | N | N | 2023-12-13 14:40
8-00811457 | Completed | ING T8 OOS | Insp & Animal Mitigation | ING 60CB4, ING T8 | 2023-12-13 08:00 | 2023-12-29 11:30 | 4 | Continuous | [6 empty] | N | N | 2023-12-29 11:30
8-00917721 | Completed | CBK 60CB7 OOS | BFPN | CBK 60CB7 | 2023-12-14 08:00 | 2023-12-14 14:04 | 2 | Continuous | [6 empty] | N | N | 2023-12-14 14:04
8-00928186 | Cancelled | SEL 5CB2 OOS | SF6 gas topup | SEL 5CB1, SEL 5CB2 | 2023-12-18 08:00 | 2023-12-18 16:00 | 1 | Continuous |  |  |  |  | 850 | 700 | N | N | 2023-12-20 18:00
8-00887017 | Completed | NIC 5RX4 OOS | Maintenance on NIC 5CB44 | NIC 5RX4, NIC 5CB44 | 2023-12-18 08:00 | 2023-12-18 11:32 | 2 | Continuous | [6 empty] | N | N | 2023-12-18 11:32
8-00811330 | Completed | DMR 2CB25 OOS | DMR 2CB25 INSP | DMR 2CB25 | 2023-12-18 08:00 | 2023-12-19 14:08 | 2 | Continuous | [6 empty] | N | N | 2023-12-19 14:08
8-00801155 | Completed | 2L39 OOS | Overview Inspection | BSY 2CB8, 2L39 | 2023-12-18 08:00 | 2023-12-22 11:15 | 2 | Continuous | [6 empty] | N | Y | 2023-12-22 11:30
8-00805923 | Completed | ING 2CX11, 2RX1 OOS | ING CX RX DS CB INSP | ING 2CX11 | 2023-12-18 08:00 | 2023-12-22 11:49 | 2 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2024-01-10 11:18
8-00908279 | Completed | NIC 5RX11 OOS | Maintenance on NIC 5CB51 | NIC 5RX11, NIC 5CB51 | 2023-12-18 12:00 | 2023-12-18 14:26 | 2 | Continuous | [6 empty] | N | N | 2023-12-18 14:26
8-00923502 | Completed | CBK T6 OOS | NERC PM, hot spot repair | CBK 12CX2, CBK 12RX6, CBK 60CB5, CBK T6 | 2023-12-19 08:00 | 2023-12-20 13:50 | 2 | Continuous | [6 empty] | N | N | 2023-12-20 13:50
8-00887020 | Completed | NIC 5RX3 OOS | Maintenance on NIC 5CB43 | NIC 5RX3, NIC 5CB43 | 2023-12-19 08:00 | 2023-12-19 11:35 | 2 | Continuous | [6 empty] | N | N | 2023-12-19 11:35
8-00887025 | Completed | NIC 5CB11 OOS | Breaker Maintenance | NIC 5CB11 | 2023-12-19 12:00 | 2023-12-19 14:03 | 2 | Continuous | [6 empty] | N | N | 2023-12-19 14:03
8-00925580 | Completed | NTL T1, 13CX1 OOS | Oil level gauge replacement | NTL T1 | 2023-12-20 08:00 | 2023-12-20 16:46 | 2 | Continuous | [6 empty] | N | N | 2023-12-20 16:46
8-00921454 | Completed | NIC 5CB18 OOS | Troubleshooting | NIC 5CB18 | 2023-12-20 08:00 | 2023-12-20 16:53 | 4 | Continuous | [6 empty] | N | N | 2023-12-20 16:53
8-00929458 | Completed | 5L98 Forced OOS | Forced OOS (End time is subject to change) | 5L98 | 2023-12-21 04:43 | 2023-12-23 14:56 | NR | Continuous |  |  |  |  | 560 | 450 | N | N | 2023-12-23 14:56
8-00801156 | Completed | 60L58 OOS | Detailed Inspection | 60L58 | 2024-01-01 08:00 | 2024-01-01 14:48 | 2 | Continuous | [6 empty] | N | N | 2024-01-01 14:48
8-00813210 | Cancelled | NAK T1 OOS (No isolation required) | Pre-Assessment for bushing replacement | NAK T1 | 2024-01-02 08:00 | 2024-01-03 16:00 | NR | Continuous | [6 empty] | N | N | 2023-02-20 13:30
8-00799002 | Completed | 1L214 OOS | Replace end of life structures and crossarms | 1L214 | 2024-01-02 09:00 | 2024-02-02 15:02 | 4 | Return Weekends | [6 empty] | N | Y | 2024-02-02 15:24
8-00695478 | Recalled | 60L39 Out from BND | Insulator Replacement (TY-0963)) | BND 60CB3, 60L39, BND 60CB4 | 2024-01-03 08:00 | 2024-01-03 14:43 | 8 | Continuous | [6 empty] | N | N | 2024-04-09 09:31
8-00810345 | Completed | VVW 1CB5 OOS | Inspection | VVW 1CB5, VVW 1CX1 | 2024-01-03 08:00 | 2024-01-04 12:54 | 4 | Continuous | [6 empty] | N | N | 2024-01-04 12:54
8-00826560 | Completed | 60L295 Out from JOE | Replace JOE 60CB5 | 60L295, JOE T13, JOE 60B4 | 2024-01-03 08:00 | 2024-01-10 15:40 | 3 | Continuous | [6 empty] | N | Y | 2024-01-11 00:42
8-00813211 | Cancelled | NAK T2 OOS (No isolation required) | Pre-Assessment for bushing replacement | NAK T2 | 2024-01-04 08:00 | 2024-01-05 16:00 | NR | Continuous | [6 empty] | N | N | 2023-02-20 13:37
8-00931842 | Completed | 1L206, WKA 1B1 OOS | Urgent Hot Spot Repair | WKA 1D21, 1L206, WKA 1B1 | 2024-01-05 08:00 | 2024-01-05 13:44 | 2 | Continuous | [6 empty] | N | N | 2024-01-05 13:44
8-00813254 | Completed | MSA 5CB3 OOS | MSA 5CB3 - BUTN | MSA 5CB3 | 2024-01-08 08:00 | 2024-01-08 15:31 | NR | Continuous | [6 empty] | N | N | 2024-01-08 15:31
8-00814173 | Cancelled | WRK T12 OOS | 60SA2 replacement | WRK T12 | 2024-01-08 08:00 | 2024-01-12 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-12-13 09:36
8-00813590 | Completed | CKY T5 and CKY 2B6 OOS | Replace 2D5 | CKY 2CB6, CKY 2CB8, CKY 60CB2, CKY T5, CKY 2B6 | 2024-01-08 08:00 | 2024-01-25 16:40 | 6 | Continuous | [6 empty] | Y | N | 2024-01-25 16:40
8-00807567 | Completed | SVA T3 OOS | ETM Replacement | SVA T3 | 2024-01-08 08:00 | 2024-02-02 14:49 | 6 | Continuous | [6 empty] | N | N | 2024-02-02 15:19
8-00929760 | Completed | SYA 5CX2 OOS | 5CX2 OSU card replacement | SYA 5CX2 | 2024-01-09 08:00 | 2024-01-10 17:39 | 4 | Continuous | [6 empty] | N | N | 2024-01-10 17:39
8-00930811 | Completed | KI2 60CB2 OOS | CPC BFPN PM | KI2 60CB2 | 2024-01-09 08:00 | 2024-01-09 15:20 | 2 | Continuous | [6 empty] | N | N | 2024-01-09 15:20
8-00924491 | Completed | 60L227 (12L) OOS. 25L Closed | KCL T6 PM | KCL T6, 60L227 (12L) | 2024-01-09 08:00 | 2024-01-11 00:45 | 4 | Continuous | [6 empty] | N | N | 2024-01-11 00:45
8-00917719 | Completed | CBK 60CB5 OOS | BFPN | CBK 60CB5 | 2024-01-09 08:00 | 2024-01-09 13:49 | 2 | Continuous | [6 empty] | N | N | 2024-01-09 13:49
8-00929300 | Completed | CBK 12CX3 OOS | Replace blown fuse | CBK 12CX3 | 2024-01-10 08:00 | 2024-01-10 13:14 | 2 | Continuous | [6 empty] | N | N | 2024-01-10 13:14
8-00931347 | Completed | SEL 5CB2 OOS | Investigation on 5CT2 cables | SEL 5CB2 | 2024-01-10 08:00 | 2024-01-10 15:20 | 2 | Continuous | [5 empty] | 700 | N | N | 2024-01-10 15:20
8-00900519 | Cancelled | 60L299, JOE 60CB5/6 OOS | Replace JOE 60CB5 | 60L299, JOE 60CB5, JOE 60CB6, 60L298 | 2024-01-10 08:00 | 2024-01-12 08:00 | 4 | Continuous | [6 empty] | N | Y | 2024-01-08 14:32
8-00813256 | Completed | MSA 5CB5 OOS | MSA 5CB5 - BUTN | MSA 5CB5 | 2024-01-11 08:00 | 2024-01-11 14:10 | NR | Continuous | [6 empty] | Y | N | 2024-01-11 14:10
8-00695484 | Denied | 60L40 Out from BND | Insulator Replacement | 60L40, BND 60CB2, BND 60CB6, BND 60D21 | 2024-01-12 08:00 | 2024-01-22 16:00 | 8 | Continuous | [6 empty] | N | N | 2024-01-08 09:34
8-00932513 | Completed | NEL T4 OOS | NEL 2SA4 Emergency Replacement | 60L2, NEL T4, 60L3, 60L18 | 2024-01-15 07:00 | 2024-01-18 15:11 | 2 | Continuous | [6 empty] | Y | N | 2024-01-18 15:12
8-00814172 | Cancelled | WRK T11 OOS | 60SA1 replacement | WRK T11 | 2024-01-15 08:00 | 2024-01-19 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-12-20 09:07
8-00926187 | Completed | 60L294 OOS | Replace defective structures | 60L294 | 2024-01-16 08:00 | 2024-01-19 22:20 | 4 | Continuous | [6 empty] | N | N | 2024-01-19 22:20
8-00811431 | Completed | ING 2CB7 OOS | CB Inspection | ING 2CB7 | 2024-01-16 08:00 | 2024-01-18 16:28 | 4 | Continuous | [6 empty] | N | N | 2024-01-18 16:28
8-00932444 | Approved | SEL 5CB9 OOS | PN PM | SEL 5CB8, SEL 5CB9 | 2024-01-18 08:00 | 2024-01-18 16:00 | 1 | Continuous | [6 empty] | N | N | 2024-01-17 11:31
8-00929770 | Completed | SYA 5CX1 OOS | Rreplace all OSU cards | SYA 5CX1 | 2024-01-22 08:00 | 2024-01-24 08:47 | 4 | Continuous | [6 empty] | N | N | 2024-01-24 08:47
8-00924809 | Completed | 60L289 OOS | Replacing damaged structures | 60L289 | 2024-01-22 08:00 | 2024-02-02 11:43 | 6 | Continuous | [6 empty] | N | N | 2024-02-02 12:09
8-00813257 | Completed | MSA 5CB6 OOS | MSA 5CB6 INSP, DOBLE, BUTN, 5CT6 A,B,C INSP | MSA 5CB6 | 2024-01-22 08:00 | 2024-01-26 15:14 | NR | Continuous | [6 empty] | Y | N | 2024-01-26 15:14
8-00801157 | Completed | 2L51 OOS | Overview Inspection | BND T2, 2L51 | 2024-01-22 08:00 | 2024-01-26 16:24 | 4 | Continuous | [6 empty] | N | N | 2024-01-26 16:24
8-00695486 | Denied | 60L54 Out from BND | Insulator Replacement (TY-0963)) | BND 60CB2, BND 60CB3, BND 60D22, 60L54 | 2024-01-23 08:00 | 2024-01-29 16:00 | 8 | Continuous | [6 empty] | N | N | 2024-01-08 14:17
8-00937183 | Completed | REV 5B9, T8 OOS | SF6 Top Up | REV 2CB2, REV 5B9, REV T8 | 2024-01-23 20:00 | 2024-02-02 20:01 | 4 | Continuous | [6 empty] | N | N | 2024-02-02 20:01
8-00826554 | Completed | 60L299, JOE 60CB5, 60CB6, T11 OOS | JOE 60CB6 & disconnects replacement | 60L299, JOE 60CB5, JOE 60CB6 | 2024-01-24 08:00 | 2024-03-12 11:42 | 8 | Continuous | [6 empty] | N | Y | 2024-03-12 11:42
8-00939778 | Implemented | CBK 12RX32 Forced OOS | CBK 12CB32 - Defective Equipment | CBK 12RX32 | 2024-01-24 09:07 | 2024-05-10 16:00 | NR | Continuous | [6 empty] | N | N | 2024-03-26 12:06
8-00927848 | Completed | 1L201 Out from VNT 1D27 to TIL 1D1 to 1D1L201, TIL, TIL 1D1 OOS | Energization for TIL T1 | 1L201, TIL 1D1 | 2024-01-25 12:00 | 2024-01-25 16:04 | 2 | Continuous | [6 empty] | N | N | 2024-01-25 16:04
8-00924862 | Completed | KCL T7, 2MB4, 2CB16, 1CB11 OOS | KCL 2D7 Inspection | KCL 2CB11, KCL 2CB16, KCL 2MB4, KCL T7 | 2024-01-30 08:00 | 2024-02-02 13:40 | 4 | Continuous | [6 empty] | N | N | 2024-02-02 13:53
8-00695487 | Denied | 60L11 Out from BND | Insulator Replacement (TY-0963)) | BND 60CB15, BND 60CB6, BND 60DCB15, BND 60DCB5, BND 60DCB6, BND 60D24, BND 60CB5, 60L11 | 2024-01-30 08:00 | 2024-02-07 16:00 | 8 | Continuous | [6 empty] | N | N | 2024-01-08 10:01
8-00801158 | Completed | 2L55 OOS | Overview Inspection | 2L55 | 2024-01-30 08:00 | 2024-02-02 16:07 | 2 | Continuous | [6 empty] | N | N | 2024-02-02 16:07
8-00811445 | Completed | ARN 2CB3 OOS | CB Inspection | ARN 2CB3 | 2024-01-30 08:00 | 2024-01-31 16:21 | 2 | Continuous | [6 empty] | N | N | 2024-01-31 16:21
8-00937516 | Completed | ACK T2 OOS | Qualitrol Wiring Issue | ACK T2 | 2024-01-30 08:00 | 2024-01-31 14:15 | 4 | Continuous | [6 empty] | N | N | 2024-01-31 14:15
8-00937563 | Completed | ING 2B6, T2, T7 OOS | 2D1CB6 improper lean back repair | ING T2, ING T7, ING 2B6 | 2024-01-30 08:00 | 2024-01-30 16:30 | 2 | Continuous | [6 empty] | N | N | 2024-01-30 16:30
8-00933740 | Completed | 60L270 Out rom 60D4L270 to 60D5L270 | Changing structure 44-10 | 60L270 | 2024-01-30 09:30 | 2024-01-30 12:51 | 1 | Continuous | [6 empty] | N | N | 2024-01-30 12:52
8-00937135 | Completed | 5L75 OOS, REV 5B7, ACK 5B6 Switching OOS | REV 5CT21 Repair | 5L75 | 2024-01-30 10:00 | 2024-01-30 14:30 | 1 | Continuous | [5 empty] | 1000 | Y | N | 2024-01-30 14:30
8-00922331 | Implemented | CBN 5CB8 OOS | Breaker Replacement | CBN 5CB8 | 2024-02-01 08:00 | 2024-05-13 14:00 | 4 | Continuous | [6 empty] | N | N | 2024-04-11 13:58
8-00811429 | Cancelled | ING 2CB6 OOS | CB Inspection | ING 2CB6 | 2024-02-01 08:00 | 2024-02-02 16:00 | 2 | Continuous | [6 empty] | N | N | 2024-01-25 11:52
8-00930812 | Completed | NIC T2 OOS | INFR Scan of T3 | NIC T2 | 2024-02-03 08:00 | 2024-02-04 13:40 | 1 | Continuous | [6 empty] | N | N | 2024-02-04 13:40
8-00883039 | Completed | SVA T1, 1B4, 1CB4, 1CB5 OOS | SAV 1D1CB4 Live parts replacement and gear box | SVA T1, SVA 1B4 | 2024-02-05 08:00 | 2024-02-09 12:33 | 4 | Continuous | [6 empty] | N | N | 2024-02-09 12:33
8-00813810 | Completed | 1L384 Partial Outage | 1L384 Structure Repl | 1L384 | 2024-02-05 08:00 | 2024-02-11 12:10 | 2 | Continuous | [6 empty] | N | N | 2024-02-27 03:30
8-00813371 | Cancelled | 2L12. CKY 2B10 OOS | Replace 2D29, 2D2CB20, 2D1CB10 | 2L12, CKY 2B10 | 2024-02-05 08:00 | 2024-02-29 16:00 | NR | Continuous | [6 empty] | N | N | 2024-01-29 08:17
8-00811449 | Completed | ING 2CB17 OOS | CB Inspection | ING 2CB17 | 2024-02-05 08:00 | 2024-02-06 14:38 | 2 | Continuous | [6 empty] | N | N | 2024-02-06 14:38
8-00806518 | Cancelled | 2L294 Out from CBK to AAL | Replace structures and lacing | 2L294 | 2024-02-05 08:00 | 2024-02-09 16:00 | NR | Continuous |  |  |  |  | 850 | 500 | N | N | 2024-01-15 07:34
8-00801160 | Completed | 2L56 OOS | Overview Inspection | MPT 2CB3, CAM T3, CAM T4, 2L56, MPT 2D2, MPT T2 | 2024-02-05 08:00 | 2024-02-09 16:45 | 4 | Continuous | 1500 | 1900 |  |  |  |  | N | N | 2024-02-09 16:48
8-00798266 | Completed | 1L218 Out between VNT-RVS | Replace end of life structures and cross arms | 1L218, SAM 1CB1, SAM T3 | 2024-02-05 08:00 | 2024-02-09 11:19 | 6 | Continuous | [6 empty] | Y | N | 2024-02-09 11:19
8-00805752 | Cancelled | BSY 2MB3, 2MB4 OOS | BSY 2D44, BSY 2CT4 Inspection | BSY 2CB4, BSY 2CB5, BSY 2D2CB4, BSY 2D2CB5, BSY 2MB3 | 2024-02-05 08:00 | 2024-02-09 16:00 | 4 | Continuous | [6 empty] | N | N | 2024-01-03 10:42
8-00944503 | Completed | MDN 12RX32 Forced OOS | hotspot found during infrared testing | MDN 12RX32 | 2024-02-05 11:56 | 2024-03-07 07:28 | NR | Continuous | [6 empty] | N | N | 2024-03-07 07:28
8-00801159 | Cancelled | 2L50 OOS | Overview Inspection | 2L50 | 2024-02-06 08:00 | 2024-02-09 16:00 | 2 | Continuous | [6 empty] | N | N | 2024-01-31 09:19
8-00813353 | Cancelled | 2L12. CMS plant, 25F51 OOS | PM INSPECTION of CMS 2CVT1 | 2L12 | 2024-02-06 08:00 | 2024-02-06 16:00 | 4 | Continuous | [6 empty] | N | N | 2024-01-18 11:40
8-00935399 | Completed | NTL T4 OOS | Repair lean back on NTL 12D4 | NTL 60CB4, NTL T4 | 2024-02-07 07:00 | 2024-02-08 13:00 | 4 | Continuous | [6 empty] | N | N | 2024-02-08 13:00
8-00923066 | Completed | MDN 2CB14 | Raise CB cabinet platform | MDN 2RX1, MDN 2CB14, MDN 2CX2, MDN 2CX1 | 2024-02-07 08:00 | 2024-02-21 13:49 | 4 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2024-02-21 13:49
8-00806343 | Completed | 60L50 OOS | Manhole work (Creative Energy project) | DGR T2, 60L50 | 2024-02-07 08:00 | 2024-02-21 12:28 | 4 | Continuous | [6 empty] | N | N | 2024-02-21 12:28
8-00939915 | Completed | 5L72, NIC 5CB43, 5B13 OOS | NIC 5CB43 SF6 top up | 5L72, MCA 5B7, NIC 5B13, NIC 5RX3, NIC 5CB43 | 2024-02-07 08:00 | 2024-02-07 16:14 | 4 | Continuous | [5 empty] | 1000 | Y | N | 2024-02-23 03:30
8-00939916 | Completed | NIC 5RX3, 5CB43 OOS | NIC 5CB43 SF6 leak investigation | NIC 5RX3, NIC 5CB43 | 2024-02-07 16:00 | 2024-02-09 14:06 | 4 | Continuous | [6 empty] | N | N | 2024-02-09 14:08
8-00937375 | Completed | NTL T2 OOS | Replace oil level gauge | NTL T2 | 2024-02-09 07:00 | 2024-02-09 13:16 | 1 | Continuous | [6 empty] | N | N | 2024-02-09 13:16
8-00807549 | Cancelled | VNT T1 OOS | Replace yard flood lights | VNT T1 | 2024-02-12 08:00 | 2024-02-12 16:00 | NR | Continuous | [6 empty] | N | N | 2024-01-22 10:05
8-00807547 | Cancelled | VNT T1 OOS | PCB Bushing Replacement | VNT T1 | 2024-02-12 08:00 | 2024-03-21 16:00 | NR | Continuous | [6 empty] | N | N | 2024-01-10 16:08
8-00801162 | Completed | 2L64 OOS | Overview Inspection | 2L64 | 2024-02-12 08:00 | 2024-02-16 07:52 | 2 | Continuous | [6 empty] | N | N | 2024-02-16 07:52
8-00925211 | Completed | VIT SC3 OOS | VIT SC3 UPGRADE PROJ | VIT SC3 | 2024-02-12 08:00 | 2024-02-29 08:19 | NR | Continuous | [6 empty] | N | N | 2024-02-29 15:04
8-00815554 | Cancelled | VIT SC3 OOS | SC3 EXCITER/P&C/H2 UPGRADES | VIT SC3 | 2024-02-12 08:00 | 2024-11-30 16:00 | NR | Continuous | [6 empty] | N | N | 2024-01-15 09:18
8-00807564 | Cancelled | 1L209 out from SAM | Replace end of life structures and crossarms | 1L209 | 2024-02-13 08:00 | 2024-03-01 16:00 | NR | Continuous | [6 empty] | N | N | 2024-02-06 16:21
8-00939353 | Completed | 1L203, SVA 1B5 OOS | SVA 1D25 maintenance | 1L203, SVA 1B5 | 2024-02-13 08:00 | 2024-02-14 15:33 | 2 | Continuous | [6 empty] | N | N | 2024-02-14 15:33
8-00940967 | Completed | 2L256, ACK 2B9 OOS | SF6 Gas Top Up | ACK 2B9, 2L256 | 2024-02-13 08:00 | 2024-02-13 13:13 | 2 | Continuous | [6 empty] | N | N | 2024-02-13 13:13
8-00939827 | Cancelled | MCA 5CB11 OOS | POW NERC Firmware Upgrade | MCA 5CB11 | 2024-02-13 10:00 | 2024-02-13 16:00 | 1 | Continuous | [6 empty] | Y | N | 2024-02-15 18:00
8-00943901 | Completed | ACK 5CX1 OOS | Low Gas Pressure checkup | ACK 5CX1, ACK 5CB49 | 2024-02-14 08:00 | 2024-02-14 11:51 | 2 | Continuous | [6 empty] | N | N | 2024-02-14 11:51
8-00806313 | Cancelled | 60L50 OOS | Underground duct work (Creative Energy project) | DGR T2, 60L50 | 2024-02-14 08:00 | 2024-02-20 16:00 | 4 | Continuous | [6 empty] | N | N | 2024-02-07 10:04
8-00940817 | Completed | 73L Out from RGA 73-1, 42L Out from OLI 42-1 (VAS-VNT Open) | FBC Outage | 73L, 42L, RGA 73-1 | 2024-02-14 11:00 | 2024-02-14 14:18 | 1 | Continuous | [6 empty] | N | N | 2024-02-14 14:18
8-00948213 | Completed | 5L72, SYA 5CX2 OOS | SYA 5CX2 repair, 5BP2 snow clean-up | 5L72, SYA 5CX2 | 2024-02-15 08:00 | 2024-02-15 16:07 | 2 | Continuous | [6 empty] | Y | N | 2024-02-15 16:07
8-00798247 | Completed | 1L201 Out from MON to LU2 | Replace end of life structures and crossarms | 1L201 | 2024-02-15 08:00 | 2024-02-16 14:04 | 3 | Continuous | [6 empty] | N | N | 2024-02-16 14:05
8-00813741 | Proposed | MUR 60B11, 60CB12 OOS | New 60L34 cable termination | MUR 60CB12, MUR 60B11 | 2024-02-19 08:00 | 2024-03-01 16:00 | 4 | Continuous | [6 empty] | N | N | 2023-01-31 09:55
8-00813711 | Completed | 1L364 out from GMS-PPS-1D1L364 | Pole Repl | 1L364, PPS T1 | 2024-02-20 07:00 | 2024-02-23 09:55 | 4 | Continuous | [6 empty] | N | N | 2024-02-23 09:55
8-00793374 | Completed | 2L142 OOS | overview inspection | 2L142 | 2024-02-20 07:00 | 2024-02-23 11:58 | 2 | Continuous | [6 empty] | N | N | 2024-02-23 11:59
8-00803306 | Cancelled | 60L21 OOS | Replace emergent structures | 60L21 | 2024-02-20 08:00 | 2024-02-22 16:00 | NR | Continuous | [6 empty] | N | N | 2024-02-12 08:21
8-00813258 | Completed | MSA 5CB4 OOS | MSA 5CB4 BUTN, 5CT4 A,B,C INSP | MSA 5CB4 | 2024-02-20 08:00 | 2024-02-21 16:26 | 2 | Continuous | [6 empty] | N | N | 2024-02-21 16:26
8-00943880 | Completed | 1L214 OOS | FAC008 deficient structures | 1L214 | 2024-02-20 08:00 | 2024-02-29 16:06 | 4 | Continuous | [6 empty] | N | N | 2024-02-29 16:06
8-00939857 | Completed | 1L204 Out from 1D3L204, DUG 1B4 OOS | SF6 hose replacement | 1L204, DUG 1B4 | 2024-02-20 08:00 | 2024-02-22 16:04 | 4 | Continuous | [6 empty] | N | N | 2024-02-22 16:04
8-00806476 | Cancelled | 60L21 out from BR1 | 60L21 BR1 to SON | 60L21 | 2024-02-20 09:00 | 2024-02-22 15:00 | NR | Continuous | [6 empty] | N | N | 2024-01-31 10:14
8-00813340 | Completed | 60L69 out from SQH to 60D2L69, SQH T2 OOS | PM INSPECTIONS of SQH 60CB2, 60DCB2, 60VT2, TEST 60CB2 CN. | SQH T2, 60L69, SQH 60B2 | 2024-02-21 08:00 | 2024-02-24 15:56 | 4 | Continuous | [6 empty] | Y | N | 2024-02-24 15:56
8-00949343 | Completed | 5L72, SYA 5CX2 OOS | SYA 5CX2 repair, 5PVT2 gas top-up | 5L72, SYA 5CX2 | 2024-02-21 08:00 | 2024-02-23 12:19 | 6 | Continuous | [5 empty] | 1000 | Y | N | 2024-02-23 12:19
8-00948418 | Completed | VAS CB3 OOS | FBC Outage - MRS Testing | VAS CB3 | 2024-02-22 07:00 | 2024-02-22 14:18 | NR | Continuous | [6 empty] | N | N | 2024-02-22 14:18
8-00948428 | Completed | 76L, VAS CB6, CB1 OOS | FBC Outage | VAS CB1, VAS CB6, 76L | 2024-02-22 07:00 | 2024-02-22 16:55 | NR | Continuous | [6 empty] | N | N | 2024-02-22 16:55
8-00898771 | Completed | REV T7, 5MB5, 5B12, 2B5 OOS | REV SWGR PM | REV 2B5, REV 5B12, REV 5MB5, REV T7 | 2024-02-25 20:00 | 2024-03-02 01:59 | 4 | Continuous | [6 empty] | N | N | 2024-03-02 02:00
8-00813713 | Completed | 1L360 OOS | Pole Repl | 1L360 | 2024-02-26 07:00 | 2024-02-27 16:40 | 4 | Continuous | [6 empty] | Y | N | 2024-02-27 16:40
8-00793383 | Completed | 2L143 OOS | overview inspection | 2L143 | 2024-02-26 07:00 | 2024-02-29 14:56 | 2 | Continuous | [6 empty] | N | Y | 2024-02-29 14:57
8-00794313 | Cancelled | 1L101, JHT 1CB10 OOS | 1L101, JHT 1CB10 138KV Disc INSP | 1L101, JHT 1CB10 | 2024-02-26 08:00 | 2024-03-11 16:00 | 120 | Continuous | [6 empty] | N | N | 2023-11-29 14:43
8-00805283 | Proposed | CK5 5RX1 OOS | AutoVAR Installation | CK5 5RX1 | 2024-02-26 08:00 | 2024-02-26 16:00 | 2 | Continuous | [6 empty] | N | N | 2023-01-17 17:15
8-00805938 | Cancelled | 2L76 OOS | MLN 2D24 & 2D1CB11 INSPs | MLN 2B7, 2L76 | 2024-02-26 08:00 | 2024-02-28 16:00 | 2 | Continuous | [6 empty] | Y | N | 2024-02-14 10:22
8-00800933 | Completed | KI2 T5 OOS | Oil sample piping, CPC non-ele PN testing | KI2 T5 | 2024-02-26 08:00 | 2024-02-29 14:35 | 4 | Continuous | [6 empty] | N | N | 2024-02-29 14:35
8-00813372 | Cancelled | 2L12, CKY 2B10 OOS | Replace 2D29, 2D2CB20, 2D1CB10 | 2L12, CKY 2B10 | 2024-02-26 08:00 | 2024-03-15 16:00 | NR | Continuous | [6 empty] | N | N | 2024-01-29 09:22
8-00813342 | Completed | 60L69 out from PTO to 60D9L69, PTO T1, PTO 25F51 | OSYR, FEEDER PN | PTO T1, 60L69 | 2024-02-27 08:00 | 2024-02-27 14:55 | 4 | Continuous | [6 empty] | N | Y | 2024-02-27 14:56
8-00923981 | Completed | 5L72 OOS | Install marker balls | 5L72 | 2024-02-27 08:00 | 2024-02-29 13:34 | 3 | Continuous | 2000 | 2400 |  |  |  | 1000 | Y | N | 2024-02-29 13:34
8-00810319 | Completed | VAS T2, 5B12 OOS | VAS 5D1CB13 INSP | VAS 5CB13, VAS T2, VAS 5CB12, VAS 5B12 | 2024-02-27 08:00 | 2024-02-27 16:27 | 2 | Continuous | [6 empty] | N | N | 2024-02-27 16:27
8-00949969 | Completed | SEL T1 OOS | LOA for inspection | SEL T1 | 2024-02-28 09:00 | 2024-02-28 15:10 | 2 | Continuous | [6 empty] | N | N | 2024-02-28 15:10
8-00887021 | Completed | NIC 5CB6 OOS | Breaker maintenance | NIC 5CB6 | 2024-02-29 08:00 | 2024-02-29 12:00 | 2 | Continuous | [6 empty] | N | N | 2024-03-06 08:55
8-00818759 | Completed | 60L389, SKA 60CB4 & 60CB7 OOS | SKA 60kV DS and CVT Insp | SKA 60CB7, SKA 60CB4, 60L389 | 2024-02-29 08:00 | 2024-03-01 15:59 | NR | Continuous | [6 empty] | Y | N | 2024-03-01 15:59
8-00887022 | Completed | NIC 5CB16 OOS | Breaker maintenance | NIC 5CB16 | 2024-02-29 12:00 | 2024-02-29 14:35 | 2 | Continuous | [6 empty] | N | N | 2024-02-29 14:35
8-00928647 | Implemented | NIC T2 OOS | Replace PCB bushings and Leak Repair | NIC T2 | 2024-03-01 08:00 | 2024-06-17 16:00 | 120 | Continuous | [6 empty] | Y | Y | 2024-04-09 07:27
8-00761027 | Completed | 5L71, 5L72 OOS | MCA Blackstart Testing | 5L71, 5L72, 60L223 | 2024-03-03 10:00 | 2024-03-03 16:16 | 1 | Continuous | [6 empty] | N | N | 2024-03-03 16:16
8-00898781 | Completed | REV T8, 5MB6, 5B9, 2B2 OOS | SWGR PM | REV 2B2, REV 5B9, REV 5MB6, REV T8 | 2024-03-03 20:00 | 2024-03-09 21:13 | 4 | Continuous | [6 empty] | N | N | 2024-03-09 21:14
8-00948439 | Completed | 34L OOS. 42L Open at OLI. VAS-WTS path open | FBC Outage | 34L, ASM CB11E, ASM T1, ASM T2 | 2024-03-04 07:00 | 2024-03-06 13:46 | NR | Continuous | [6 empty] | N | N | 2024-03-06 13:57
8-00948455 | Completed | 34L, WTS CB12, CB13 OOS. 42L Open at OLI. VAS-WTS path open | FBC Outage | 34L, WTS CB13, WTS CB12 | 2024-03-04 07:00 | 2024-03-06 13:46 | NR | Return Evenings | [6 empty] | N | N | 2024-03-06 13:59
8-00927101 | Denied | WSN T5, 2B2 OOS | WSN 2D5 repl. | WSN T5, WSN 2B2 | 2024-03-04 08:00 | 2024-03-15 15:00 | 6 | Continuous | [6 empty] | N | Y | 2024-02-29 11:02
8-00813335 | Completed | 60L70, CKY 60CB1/CB6 OOS | Disconnect PM and Breaker INSPs | CKY 60CB1, CKY 60CB6, SQH 60CB3, 60L70, SQH 60CB6, SQH T3 | 2024-03-04 08:00 | 2024-03-15 16:08 | 10 | Continuous | [6 empty] | N | Y | 2024-03-15 16:08
8-00793431 | Completed | 2L146 OOS | overview inspection | 2L146 | 2024-03-05 07:00 | 2024-03-08 20:28 | 2 | Continuous | [6 empty] | Y | Y | 2024-03-08 20:28
8-00813688 | Completed | 2L86 OOS | Structure Repl | 2L86, CRQ 60CB1 | 2024-03-05 09:00 | 2024-03-08 20:25 | 3 | Continuous | [6 empty] | N | N | 2024-03-08 20:25
8-00953140 | Completed | NTL T1, 60B1 OOS. EV1 supplied from NTL 60CB13 | NTL 60CB11 Energization | NTL 60CB11, 60L285, NTL 60B1 | 2024-03-05 16:00 | 2024-03-05 16:50 | 120 | Continuous | [6 empty] | N | N | 2024-03-05 16:51
8-00947273 | Completed | WTS T2 OOS | FBC Outage | WTS T2 | 2024-03-07 07:00 | 2024-03-07 11:35 | NR | Continuous | [6 empty] | Y | N | 2024-03-07 11:35
8-00953006 | Completed | ACK 5CB10 OOS | Personnel training | ACK 5CB10 | 2024-03-07 08:00 | 2024-03-07 14:32 | 2 | Continuous | [6 empty] | N | N | 2024-03-07 14:32
8-00918429 | Completed | 5L83, MDN 5CB5, 5CB6, NIC 5CB12, 5CB22 OOS | MDN 5CB6 POW commissioning | NIC 5CB12, NIC 5CB22, MDN 5CB5, MDN 5CB6, 5L83 | 2024-03-07 08:00 | 2024-03-07 16:55 | 0 | Continuous | 2000 | 2400 |  |  |  |  | N | N | 2024-03-08 05:55
8-00952655 | Cancelled | 5L2, GMS 5RX2 OOS | Disconnect NEMA pad repair | 5L2, GMS 5B4 | 2024-03-08 07:00 | 2024-03-08 18:00 | 10 | Continuous | [6 empty] | Y | N | 2024-03-05 16:22
8-00918424 | Completed | MDN 5MB2, T3 OOS | MDN 5CB6 POW commissioning | MDN 12RX31, MDN 12RX32, MDN T3, MDN 5MB2 | 2024-03-08 08:00 | 2024-03-08 11:42 | 0 | Continuous | [6 empty] | N | N | 2024-03-08 11:42
8-00793428 | Completed | 2L145 OOS | overview inspection | 2L145 | 2024-03-11 07:00 | 2024-03-15 11:28 | 4 | Continuous | [6 empty] | Y | N | 2024-03-15 11:28
8-00800770 | Completed | MDN 5CB8 OOS | MDN 5CB8 POW commissioning | MDN 5CB8 | 2024-03-11 08:00 | 2024-03-11 15:18 | 4 | Continuous | [6 empty] | N | N | 2024-03-11 15:18
8-00914316 | Completed | 5L96 OOS | Replace end of life insulators | 5L96 | 2024-03-11 08:00 | 2024-03-13 14:38 | 3 | Continuous |  |  |  |  | 560 | 450 | N | N | 2024-03-13 16:52
8-00813275 | Cancelled | MSA t5, 2B9, 1B6 OOS | MSA T5 - T5 NON-ELECTRICALS, PY/SY PN. NERC, 2D1CB9, 1D1CB1, 1D1CB6 INSP, 2D1CB9 C PHASE OUT OF ALIGNMENT, 1CB6 CN. COND. | MSA T5, MSA 2B9, MSA 1B6 | 2024-03-11 08:00 | 2024-03-15 16:00 | 4 | Continuous | [6 empty] | N | N | 2024-03-04 13:26
8-00953701 | Completed | 1L204 Out from DUG, DUG 1B4 OOS | DUG 1D23 Whip Install | 1L204, DUG 1B4 | 2024-03-11 08:00 | 2024-03-12 14:30 | 3 | Continuous | [6 empty] | N | N | 2024-03-12 14:30
8-00951017 | Completed | JOE 60CB5 OOS | Repair and commission | JOE 60CB5 | 2024-03-12 08:00 | 2024-03-20 13:15 | 4 | Continuous | [6 empty] | N | N | 2024-03-20 13:15
8-00812802 | Completed | QLC T1, 1CB1 OOS | QLC 1CB1 INSP & CN | QLC 1CB1, QLC T1 | 2024-03-12 08:00 | 2024-03-12 08:15 | 2 | Continuous | [6 empty] | N | N | 2024-03-12 08:15
8-00800772 | Approved | 5L82, MDN 5CB8 OOS | MDN 5CB8 POW commissioning | 5L82, MDN 5CB7, MDN 5CB8 | 2024-03-12 08:00 | 2024-03-13 16:00 | 1 | Return Evenings | 2000 | 2400 |  |  |  |  | N | N | 2024-03-12 15:08
8-00951443 | Approved | 1L275 OOS | Move 1CT22 metering panel at NTL | 1L275 (786L) | 2024-03-13 07:00 | 2024-03-14 00:53 | 3 | Continuous | [6 empty] | N | N | 2024-03-13 17:09
8-00926465 | Completed | 2L9 OOS | LYN 2D1 Inspection, T1 Non-Electricals, T1 PY/SY PN, 2D1CB2 Repairs | LYN 2CB2, LYN T1, 2L9 | 2024-03-13 08:00 | 2024-03-14 12:54 | 4 | Continuous | [6 empty] | Y | Y | 2024-03-14 12:54
8-00936384 | Denied | 5L52 OOS | Transmission line insulator maintenance | 5L52 | 2024-03-14 08:00 | 2024-03-15 16:00 | 4 | Continuous | 2000 | 2400 | 1000 | 1200 |  |  | N | N | 2024-02-23 13:03
8-00800775 | Approved | MDN 5MB1, T2 OOS | POW commissioning | MDN 5MB1, MDN T2 | 2024-03-14 08:00 | 2024-03-15 16:00 | 1 | Return Evenings | 1200 | 1600 |  |  |  |  | N | Y | 2024-03-14 13:51
8-00940503 | Completed | VIT SC2, T5 and T6 OOS | Disconnect Switch Inspections | VIT SC2, VIT 1B4, VIT 2B2, VIT T5, VIT T6 | 2024-03-16 07:00 | 2024-03-17 14:28 | 4 | Continuous | 2000 | 2400 |  |  |  |  | Y | N | 2024-03-17 15:45
8-00793777 | Completed | 1L101, CMX T1, OYR T2, BKB T1 OOS | 138KV Disc Inspections at JHT,OYR, CMX, DMR, BKB | CMX T1, 1L101, JHT 1CB10, JHT 1CB11, OYR T2, BKB T1 | 2024-03-17 08:00 | 2024-03-19 18:07 | 5 | Continuous | [6 empty] | Y | Y | 2024-03-19 18:07
8-00947280 | Completed | 62L OOS | FBC Outage | 62L | 2024-03-18 07:00 | 2024-03-18 11:40 | NR | Continuous | [6 empty] | Y | N | 2024-03-18 11:45
8-00950344 | Cancelled | 2L112 OOS | BCH to BPA for REPLACE STRUCTURES AT VARIOUS LOCATIONS | 2L112 | 2024-03-18 08:00 | 2024-03-25 08:00 | 2 | Continuous | 2000 | 2000 | 2500 | 2500 | 560 | 600 | N | N | 2024-03-12 09:55
8-00943352 | Cancelled | 3L5 OOS | 3CVT2,3D22, 3D1CB3, 3D1CB2 INSP | ROS 3D2CB4, ROS 3B2, 3L5, ROS 3D2CB3 | 2024-03-18 08:00 | 2024-03-21 16:00 | 3 | Continuous | [6 empty] | N | N | 2024-03-01 10:03
8-00937927 | Completed | 2L112 OOS | Repair NLY T2 oil leak | 2L112, NLY T2 | 2024-03-18 08:00 | 2024-03-25 09:20 | 60 | Continuous | 2000 | 2000 | 2500 | 2500 | 560 | 600 | N | N | 2024-04-10 03:30
8-00798131 | Completed | 60L66 OOS | reterminate 60L66 to new CAP 60D21 & terminate Temp 60kV o/h line | CAP 60CB1, CAP T2, 60L66, CAP T3, CAP T4 | 2024-03-18 08:00 | 2024-03-23 12:08 | 12 | Continuous | [6 empty] | N | Y | 2024-03-23 12:08
8-00812804 | Cancelled | 5L29 OOS | TIR 5RX13 PAINT | TIR 5RX13, 5L29 | 2024-03-18 08:00 | 2024-03-24 16:00 | 2 | Continuous | [6 empty] | N | N | 2024-03-01 15:59
8-00813366 | Cancelled | 2L5, FCN 2B1, T1 OOS | REPAIR FCN 2D21, 2DCB1, 2D1CB3 | FCN 2B1, FCN T1, 2L5 | 2024-03-18 08:00 | 2024-03-21 16:00 | 4 | Continuous | [6 empty] | N | N | 2024-02-15 11:32
8-00936396 | Completed | 5L44 OOS | Replace end of life insulators | 5L44 | 2024-03-19 08:00 | 2024-03-20 16:10 | 3 | Return Evenings | 1200 | 1200 | 2500 | 2500 |  |  | N | N | 2024-03-20 16:10
8-00801185 | Completed | 60L52 OOS | Detailed Inspection | 60L52, DGR T3 | 2024-03-19 08:00 | 2024-03-22 13:55 | 2 | Continuous | [6 empty] | N | N | 2024-03-22 13:55
8-00961005 | Completed | SYA 5CX1 OOS | Forced OOS | SYA 5CX1 | 2024-03-19 15:55 | 2024-03-26 16:06 | NR | Continuous | [6 empty] | N | N | 2024-03-26 16:06
8-00924372 | Completed | CHS OOS. 1L209 Out from CHS 1D21 to 1D22 | T2 ETM, animal mitigation, shield wire re-string, mobile connection | 1L209, CHS T2 | 2024-03-19 20:00 | 2024-03-20 06:36 | 10 | Continuous | [6 empty] | N | N | 2024-03-20 06:36
8-00953825 | Approved | 48L OOS. 42L Open at OLI. VAS-WTS Path Open | FBC Outage. MRS testing | 48L | 2024-03-20 07:00 | 2024-03-20 15:00 | NR | Continuous | [6 empty] | N | N | 2024-03-19 15:42
8-00953826 | Approved | 11WL OOS. 42L Open at OLI. VAS-WTS Path Open | FBC Outage. MRS testing | 11WL | 2024-03-20 07:00 | 2024-03-20 15:00 | NR | Continuous | [6 empty] | N | N | 2024-03-19 15:43
8-00959138 | Completed | 1L274 Open between GRH and FRO | Urgent cross-arm replacement | 1L274 (887L) | 2024-03-20 08:00 | 2024-03-20 18:11 | 3 | Continuous | [6 empty] | N | N | 2024-03-20 18:11
8-00945314 | Completed | 1L209 Out from SAM | Replace end of life structures and crossarms | 1L209 | 2024-03-20 08:00 | 2024-03-22 17:10 | 8 | Continuous | [6 empty] | N | N | 2024-03-22 17:10
8-00950952 | Completed | 60L299, JOE 60B5 OOS | JOE 60CB5 energization | 60L299, JOE 60CB5, 60L298, JOE 60B5 | 2024-03-20 08:00 | 2024-03-20 16:31 | 1 | Continuous | [6 empty] | N | N | 2024-03-20 16:31
8-00812710 | Completed | KCL 2CB14, 2CB15 OOS | BREAKER FAIL PN | KCL 2CB14, KCL 2CB15 | 2024-03-20 08:00 | 2024-03-28 13:21 | 24 | Continuous | [6 empty] | Y | N | 2024-03-28 13:21
8-00800810 | Completed | MDN 5CB7 OOS | POW commissioning | MDN 5CB7 | 2024-03-20 08:00 | 2024-03-20 16:42 | 1 | Continuous | [6 empty] | N | N | 2024-03-20 16:42
8-00800811 | Completed | 5L82, MDN 5CB7 OOS | POW commissioning | 5L82, AMC 5CX2, MDN 5CB7 | 2024-03-21 08:00 | 2024-03-21 14:32 | 1 | Continuous | [6 empty] | Y | N | 2024-03-21 15:56
8-00958406 | Cancelled | 60L284 OOS | Replace defective structure | 60L284 | 2024-03-21 08:00 | 2024-03-21 16:00 | 2 | Continuous | [6 empty] | N | N | 2024-03-20 10:28
8-00800814 | Completed | MDN 5MB2, T3 OOS | POW commissioning | MDN 12RX31, MDN 12RX32, MDN T3, MDN 5MB2 | 2024-03-22 08:00 | 2024-03-22 14:01 | 1 | Continuous | [6 empty] | N | N | 2024-03-24 20:33
8-00788577 | Completed | 2L14/WLT 2B5 OOS | WLT OSP Step 24 | 2L14, WLT 2B5, WLT 2B6 | 2024-03-22 08:00 | 2024-04-12 11:36 | 3 | Continuous | [6 empty] | Y | N | 2024-04-12 11:36
8-00914382 | Completed | SKA T2 OOS | Install ETM on T2 | SKA T2 | 2024-03-22 12:00 | 2024-03-28 13:39 | 6 | Continuous | [6 empty] | N | N | 2024-03-28 13:39
8-00957226 | Completed | VAS T1 OOS | FBC Outage. Mtce & MRS testing | VAS T1 | 2024-03-25 07:00 | 2024-03-28 10:50 | NR | Continuous | [6 empty] | N | N | 2024-03-28 10:50
8-00950353 | Completed | 2L112 OOS | BPA Outage. Structure replacement | 2L112, NLY T2 | 2024-03-25 08:00 | 2024-04-06 05:49 | 2 | Continuous | [6 empty] | N | N | 2024-04-06 05:50
8-00950647 | Completed | 2L112 OOS | Repair NLY T2 | 2L112, NLY T2 | 2024-03-25 08:00 | 2024-04-03 09:55 | 60 | Continuous | 2000 | 2000 | 2500 | 2500 | 560 | 600 | N | N | 2024-04-03 09:55
8-00800818 | Completed | MDN 5CB3 OOS | POW commissioning | MDN 5CB3 | 2024-03-25 08:00 | 2024-03-25 16:00 | 1 | Continuous | 1000 | 1000 |  |  |  |  | N | N | 2024-03-27 11:43
8-00801187 | Completed | 60L53 OOS | Detailed Inspection | DGR T1, 60L53 | 2024-03-25 08:00 | 2024-03-26 11:09 | 4 | Continuous | [6 empty] | N | N | 2024-03-26 11:09
8-00801189 | Cancelled | 60L100 OOS | Detailed Inspection | 60L100 | 2024-03-25 08:00 | 2024-03-26 16:00 | 2 | Continuous | [6 empty] | N | N | 2024-03-04 08:33
8-00923976 | Completed | 1L214 OOS | Replace end of life structures | 1L214 | 2024-03-25 09:00 | 2024-04-05 16:44 | 2 | Continuous | [6 empty] | N | N | 2024-04-05 16:46
8-00956063 | Completed | 5L72 OOS | Install Marker balls | 5L72 | 2024-03-25 09:00 | 2024-03-27 14:31 | 3 | Continuous | 2000 | 2400 |  |  |  | 1000 | Y | N | 2024-03-27 14:45
8-00963024 | Implemented | SEL 5CB1 | Forced OOS | SEL 5CB1 | 2024-03-25 12:44 | 2024-04-30 16:00 | NR | Continuous |  |  |  |  | 850 | 700 | N | N | 2024-04-11 13:55
8-00957664 | Completed | 5L2, GMS 5RX2 OOS | Disconnect NEMA pad repair | 5L2, GMS 5RX2, GMS 5B4 | 2024-03-26 07:30 | 2024-03-26 18:01 | 10 | Continuous | [6 empty] | Y | N | 2024-03-26 18:01
8-00961570 | Completed | SYA 5CX1 OOS | OSU Card replacement | SYA 5CX1 | 2024-03-26 08:00 | 2024-03-26 16:06 | 4 | Continuous | [6 empty] | Y | N | 2024-03-26 16:06
8-00800829 | Completed | 5L45, MDN 5CB3 OOS | POW commissioning | 5L45, MDN 5CB3 | 2024-03-26 08:00 | 2024-03-27 16:35 | 1 | Return Evenings | [6 empty] | Y | N | 2024-03-27 16:36
8-00957227 | Approved | WTS T1 OOS | FBC Outage. MRS testing | WTS T1 | 2024-03-27 07:00 | 2024-03-28 15:00 | NR | Return Evenings | [6 empty] | Y | N | 2024-03-26 16:49
8-00959533 | Cancelled | 60L51 OOS | oil sampling | DGR T4, 60L51 | 2024-03-28 07:00 | 2024-03-29 16:00 | 2 | Continuous | [6 empty] | N | N | 2024-03-28 06:36
8-00800830 | Completed | MDN 5CB3, T1 OOS | POW commissioning | MDN 5CB3, MDN T1 | 2024-03-28 08:00 | 2024-03-28 11:28 | 1 | Continuous | [6 empty] | N | N | 2024-03-28 11:28